G2022149 | 0 | 23 | 01E07V01 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT3 Kandea |  | 65 | 0 | 0 | Preparing | 2022-07-14 | 2022-08-22 | [5 empty] | 86112281 | 22876775 | 108989056 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 12 | 01E07V01 | 007 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BANTAENG |  | R7 MKS BTN PT3 LAMALAKA NIPA-NIPA (1) |  | 65 | 0 | 0 | Preparing | 2022-07-14 | 2022-08-24 | [5 empty] | 163421685 | 36248846 | 199670531 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 13 | 01E07V01 | 007 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BANTAENG |  | R7 MKS BTN PT3 LAMALAKA NIPA-NIPA (2) |  | 65 | 0 | 0 | Preparing | 2022-07-14 | 2022-08-24 | [5 empty] | 87188620 | 23735351 | 110923971 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 21 | 01E07V01 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK PT3 Haji Kalla & DIRGANTARA |  | 65 | 0 | 0 | Preparing | 2022-07-14 | 2022-08-25 | [5 empty] | 351951737 | 76847636 | 428799373 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 19 | 01E07V01 | 007 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SINJAI |  | R7 MKS SIN PT3 DS-SINJAI INNER 1 |  | 55 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-31 | [5 empty] | 941824511 | 187326807 | 1129151318 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 11 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT3 LIMBUNG (Macini Baji) |  | 65 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-22 | [5 empty] | 391629292 | 84661698 | 476290990 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 20 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT3 PASAR LIMBUNG & MONCOBALANG |  | 60 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-25 | [5 empty] | 655657744 | 114320045 | 769977789 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 14 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT3 ZIGMA ROYAL PARK, MAPALA |  | 55 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-30 | [5 empty] | 338232527 | 60539359 | 398771886 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 15 | 01E07V01 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA PT3 NEW DS ODC-TMA-FAV |  | 55 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-31 | [5 empty] | 959292254 | 179102376 | 1138394630 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022150 | 1 | 7 | 01E07P02 | 007 | 72040187 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004686/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan HEM 1 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-12 | HEM | PARE-PARE | WONOMULYO |  | R7 PRE WON PT2 PLUS RSUD WONOMULYO |  | 88 | 100 | 100 | BAST-1 | 2022-07-14 | 2022-08-02 | 2022-07-21 | TEL.284/LG.320/R7W-7D100000/2022 | 2022-07-22 | TEL.0002/LG.320/R7W-7D1G0000/2022 | 2022-07-22 | 43479234 | 9665337 | 53144571 | 53144571 | 4500470580 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-07-29
G2022151 | 0 | 11 | 01E07P02 | 007 | 72040044 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | CANGADI |  | R7 PRE CGI HEM KTR BANK SULSELBAR |  | 85 | 90 | 0 | Siap UT | 2022-07-17 | 2022-08-27 | 2022-07-17 | TEL.329/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 129483144 | 31797351 | 161280495 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022151 | 0 | 12 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KTR KEJAKSAAN MAMUJU |  | 88 | 90 | 0 | Siap UT | 2022-07-14 | 2022-08-23 | 2022-07-14 | TEL.330/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 44159560 | 7962124 | 52121684 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022151 | 0 | 13 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM POLDA MAMUJU |  | 88 | 90 | 0 | Siap UT | 2022-07-14 | 2022-08-23 | 2022-07-14 | TEL.331/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 74702583 | 24777004 | 99479587 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022151 | 0 | 8 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM MASJID AL-MARKAZ |  | 88 | 90 | 0 | Siap UT | 2022-07-15 | 2022-08-25 | 2022-07-15 | TEL.333/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 2684206 | 365115 | 3049321 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022151 | 0 | 7 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM MASJID AS-SYAKUR BCR |  | 88 | 90 | 0 | Siap UT | 2022-07-15 | 2022-08-25 | 2022-07-15 | TEL.332/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 3468768 | 837331 | 4306099 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022151 | 0 | 10 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM MESJID NUR JANNAH KODIM |  | 88 | 90 | 0 | Siap UT | 2022-07-15 | 2022-08-26 | 2022-07-15 | TEL.334/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 8197680 | 2065894 | 10263574 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022151 | 0 | 9 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004688/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 7 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | POLEWALI |  | R7 PRE PLW HEM KOMINFO KTR. DAMKAR |  | 88 | 90 | 0 | Siap UT | 2022-07-14 | 2022-08-24 | 2022-07-14 | TEL.335/LG.320/R7W-7D320000/2022 | 2022-08-01 |  |  | 2121966 | 305196 | 2427162 | 0 | 4500470760 |  |  |  |  | MAPPADECENG JAYA LESTARI
G2022152 | 0 | 29 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | BARRU |  | R7 PRE BAR HEM POLRES BARRU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 3964477 | 531135 | 4495612 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 10 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | BARRU |  | R7 PRE BAR HEM DPRD_DAMKAR BARRU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 27753660 | 5752335 | 33505995 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 8 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | BARRU |  | R7 PRE BAR HEM RSUD BARRU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 9 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | BARRU |  | R7 PRE BAR HEM BPKAD BARRU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 2248486 | 291547 | 2540033 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 18 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | ENREKANG |  | R7 PRE ENR HEM KPU ENREKANG |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 301811 | 2017802 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 20 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAJENE |  | R7 PRE MAJ HEM SPN POLDA SULBAR |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 65763234 | 11127732 | 76890966 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 19 | 01E07P02 | 007 | 72040082 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MALILI |  | R7 PRE MLL HEM DINAS KOMINFO MLL |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 43104193 | 8810604 | 51914797 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 28 | 01E07P02 | 007 | 72040086 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAMASA |  | R7 PRE MMS HEM LPSE MAMASA |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 2248486 | 291547 | 2540033 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 22 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KOMINFO MAMUJU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 11723051 | 3059418 | 14782469 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 7 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM DINAS ESDM PROV SULBAR |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 13013794 | 3613468 | 16627262 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 27 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KTR PUPR SULBAR |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 14 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PALOPO |  | R7 PRE PLP HEM HSI ODP-PLP-FAZ/115 |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 2248486 | 291547 | 2540033 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 15 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PALOPO |  | R7 PRE PLP HEM HSI ODP-PLP-FQ/078 |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 11 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM HSI ODP-PRE-FBA/054 |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 21 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM RSUD ANDI MAKKASAU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 16 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM HSI ODP-PRE-FBC/074-075 |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 3431982 | 479176 | 3911158 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 12 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM HIS ODP-PRE-FBB/093 |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 13 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKU HEM HSI ODP-PKA-FC/121 |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 301811 | 2017802 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 30 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKU HEM RSUD PASANGKAYU |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 17 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKU HEM KTR BUPATI (PEMERINTAHAN) |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 301811 | 2017802 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 23 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PINRANG |  | R7 PRE PIN HEM BALAI KB PIN MATIRO SOMPE |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 364034 | 2080025 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 24 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PINRANG |  | R7 PRE PIN HEM BALAI KB TIROANG |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 25 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PINRANG |  | R7 PRE PIN HEM BALAI KB WATANG SAWITTO |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-27 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
G2022152 | 0 | 26 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004689/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan HEM 24 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-14 | 2022-08-27 | HEM | PARE-PARE | PINRANG |  | R7 PRE PIN HEM BALAI KB LEMBANG |  | 100 | 0 | 0 | Preparing | 2022-07-14 | 2022-07-26 | [5 empty] | 1715991 | 239588 | 1955579 | 0 | 4500470776 |  |  |  |  | TELKOM AKSES
12022174 | 0 | 11 | 01C11B01 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004692/HK.810/SSP-10400000/2022 | Surat Pesanan-5 (SP#5) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-07-14 | 2022-11-10 | Ekspan PCEF Sandvine | UJUNGPANDANG | MATTOANGIN |  |  |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 4500469469 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
G2022153 | 0 | 10 | 01E07V01 | 007 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004771/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 2 LoP Area Witel Makassar | 2022-07-15 | 2022-09-12 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | KIMA |  | R7 MKS KIM PT3 TALLASA CITY BLOK A3&B |  | 65 | 85 | 0 | Instalasi | 2022-07-15 | 2022-08-22 | 2022-07-22 |  |  |  |  | 145541356 | 86318064 | 231859420 | 0 | 4500470700 |  |  |  |  | SIPAKALEBBI 2
G2022153 | 0 | 9 | 01E07V01 | 007 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004771/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 2 LoP Area Witel Makassar | 2022-07-15 | 2022-09-12 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | KIMA |  | R7 MKS KIM PT3 TALLASA CITY BLOK D |  | 60 | 85 | 0 | Instalasi | 2022-07-15 | 2022-09-07 | 2022-07-22 |  |  |  |  | 255319666 | 128871725 | 384191391 | 0 | 4500470700 |  |  |  |  | SIPAKALEBBI 2
G2022154 | 0 | 10 | 01E07L12 | 007 | 74050005 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004780/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LoP Area Witel Papua | 2022-07-18 | 2022-10-15 | FIMO NODE-B 2022 | MERAUKE | BADE |  | R7 JYP BAD KEP064 Obaa_Kepi |  | 0 | 0 | 0 | Preparing | [7 empty] | 15339982 | 4427270 | 19767252 | 0 | 4500471187 |  |  |  |  | TELKOM AKSES
G2022154 | 0 | 7 | 01E07L12 | 007 | 74050005 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004780/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LoP Area Witel Papua | 2022-07-18 | 2022-10-15 | FIMO NODE-B 2022 | MERAUKE | BADE |  | R7 JYP BAD KEP005 |  | 0 | 0 | 0 | Preparing | [7 empty] | 4351755 | 2443195 | 6794950 | 0 | 4500471187 |  |  |  |  | TELKOM AKSES
G2022154 | 0 | 9 | 01E07L12 | 007 | 74050005 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004780/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LoP Area Witel Papua | 2022-07-18 | 2022-10-15 | FIMO NODE-B 2022 | MERAUKE | BADE |  | R7 JYP BAD KEP029 TBG OBAA |  | 0 | 0 | 0 | Preparing | [7 empty] | 5465397 | 2432751 | 7898148 | 0 | 4500471187 |  |  |  |  | TELKOM AKSES
G2022154 | 0 | 11 | 01E07L12 | 007 | 74050005 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004780/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LoP Area Witel Papua | 2022-07-18 | 2022-10-15 | FIMO NODE-B 2022 | MERAUKE | BADE |  | R7 JYP BAD KEP065 Obaa_Kepi 2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 22571032 | 5668918 | 28239950 | 0 | 4500471187 |  |  |  |  | TELKOM AKSES
G2022154 | 0 | 8 | 01E07L12 | 007 | 74050005 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004780/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LoP Area Witel Papua | 2022-07-18 | 2022-10-15 | FIMO NODE-B 2022 | MERAUKE | BADE |  | R7 JYP BAD KEP016 Tbg Nambi Oman Bapai |  | 0 | 0 | 0 | Preparing | [7 empty] | 6228170 | 2174758 | 8402928 | 0 | 4500471187 |  |  |  |  | TELKOM AKSES
T2022028 | 1 | 71 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 24 Port AC PoE |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 134769327 | 0 | 134769327 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 70 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 24 Port AC Non PoE |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 12251757 | 0 | 12251757 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 72 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 24 Port DC |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 103175064 | 0 | 103175064 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 73 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 8 Port DC |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 73195416 | 0 | 73195416 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 74 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch AC Support 10 G NON POE 24 Port SFP |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 226795096 | 0 | 226795096 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 75 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch AC Support 10 G POE 24 Port RJ45 |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 28581543 | 0 | 28581543 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 77 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch DC Support 10 G NON POE 24 Port SFP |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 1077039180 | 0 | 1077039180 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
T2022028 | 1 | 76 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004782/HK.810/TSC-B0200000/2022 | Surat Pesanan-1 (SP#1) Pengadaan L2 Switch | 2022-07-18 | 2022-12-31 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch DC Support 10 G NON POE 24 Port Combo |  | 20 |  |  |  | 2022-07-26 | 2023-01-01 | [5 empty] | 444091238 | 0 | 444091238 | 0 | 4500470666 |  |  |  |  | PINS INDONESIA
G2022155 | 0 | 7 | 01E07V06 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004785/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 2 LoP Area Witel Gorontalo | 2022-07-18 | 2022-08-31 | FIMO NODE-B 2022 | GORONTALO | ISIMU |  | R7 GTO ISM BOA006 DULUPI |  | 0 | 0 | 0 | Preparing | [7 empty] | 172418179 | 34975632 | 207393811 | 0 | 4500471196 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022155 | 0 | 6 | 01E07V06 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004785/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 2 LoP Area Witel Gorontalo | 2022-07-18 | 2022-08-31 | FIMO NODE-B 2022 | GORONTALO | ISIMU |  | R7 GTO ISM ISM034 MOHIYOLO |  | 0 | 0 | 0 | Preparing | [7 empty] | 11526052 | 2683625 | 14209677 | 0 | 4500471196 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022156 | 0 | 8 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-31 | [5 empty] | 16727874 | 3484543 | 20212417 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 9 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-27 | [5 empty] | 76678805 | 15623092 | 92301897 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 10 | 01E07J04 | 007 | 72080054 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | JENEPONTO |  | R7 MKS JNP PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-27 | [5 empty] | 8639217 | 1945237 | 10584454 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 11 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-29 | [5 empty] | 46265204 | 9810167 | 56075371 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 12 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-28 | [5 empty] | 28573533 | 5193214 | 33766747 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 13 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-28 | [5 empty] | 13820507 | 3224777 | 17045284 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 14 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-31 | [5 empty] | 11096460 | 2700690 | 13797150 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 15 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | TAKALAR |  | R7 MKS TKA PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-30 | [5 empty] | 5086770 | 1194500 | 6281270 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 16 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-28 | [5 empty] | 7292992 | 1809356 | 9102348 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022156 | 0 | 17 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004786/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 10 LOP Periode Februari-Maret 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-07-18 | 2022-09-15 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP PT2 FEB-MAR 2022 (10 LOP) |  | 100 | 0 | 0 | Preparing | 2022-07-18 | 2022-07-30 | [5 empty] | 13027663 | 2518532 | 15546195 | 0 | 4500470219 |  |  |  |  | TELKOM AKSES
G2022157 | 0 | 11 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004865/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP Area Witel Papua | 2022-07-20 | 2022-09-17 | FIMO NODE-B 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE JAP459 DMTPERTIGAANKOYATIMUR |  | 20 | 0 | 0 | Preparing | 2022-07-20 | 2022-09-17 | [5 empty] | 27411307 | 9630236 | 37041543 | 0 | 4500471729 |  |  |  |  | TRANSDATA SATKOMINDO
G2022157 | 0 | 9 | 01E07L12 | 007 | 74030043 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004865/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP Area Witel Papua | 2022-07-20 | 2022-09-17 | FIMO NODE-B 2022 | JAYAPURA | KUALA KENCANA |  | R7 JYP KUK COK008 Combat Batalyon 754 |  | 20 | 0 | 0 | Preparing | 2022-07-20 | 2022-09-17 | [5 empty] | 18393414 | 5225109 | 23618523 | 0 | 4500471729 |  |  |  |  | TRANSDATA SATKOMINDO
G2022157 | 0 | 8 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004865/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP Area Witel Papua | 2022-07-20 | 2022-09-17 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM102 KANTORBUPATITIMIKA |  | 20 | 0 | 0 | Preparing | 2022-07-20 | 2022-09-17 | [5 empty] | 15376792 | 4361552 | 19738344 | 0 | 4500471729 |  |  |  |  | TRANSDATA SATKOMINDO
G2022157 | 0 | 7 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004865/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP Area Witel Papua | 2022-07-20 | 2022-09-17 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM189 TBGJALURSDTIMIKAMW |  | 20 | 0 | 0 | Preparing | 2022-07-20 | 2022-09-17 | [5 empty] | 18738686 | 6385797 | 25124483 | 0 | 4500471729 |  |  |  |  | TRANSDATA SATKOMINDO
G2022157 | 0 | 12 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004865/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP Area Witel Papua | 2022-07-20 | 2022-09-17 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK MRK245 TBG SIDOMULYO |  | 20 | 0 | 0 | Preparing | 2022-07-20 | 2022-09-17 | [5 empty] | 6488485 | 2471991 | 8960476 | 0 | 4500471729 |  |  |  |  | TRANSDATA SATKOMINDO
G2022157 | 0 | 10 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004865/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP Area Witel Papua | 2022-07-20 | 2022-09-17 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK MRK094 DMT TRANS WASUR |  | 20 | 0 | 0 | Preparing | 2022-07-20 | 2022-09-17 | [5 empty] | 9370924 | 3438341 | 12809265 | 0 | 4500471729 |  |  |  |  | TRANSDATA SATKOMINDO
G2022158 | 0 | 14 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | GORONTALO |  | LOP07 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 15 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | GORONTALO |  | LOP09 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 13 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | GORONTALO |  | LOP05 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 17 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | ISIMU |  | LOP08 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 16 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | ISIMU |  | LOP06 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 2310752 | 322083 | 2632835 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 8 | 01E07V01 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | KWANDANG |  | LOP03 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 7 | 01E07V01 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | KWANDANG |  | LOP02 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 2310752 | 322083 | 2632835 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 6 | 01E07V01 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | KWANDANG |  | LOP01 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 9 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | LOP04 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 10 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | LOP10 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 11 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | LOP11 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 2310752 | 322083 | 2632835 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022158 | 0 | 12 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 12 LoP Area Witel Gorontalo | 2022-07-20 | 2022-08-18 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | LOP12 |  | 50 | 0 | 0 | Preparing | 2022-07-20 | 2022-08-18 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500471644 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022159 | 0 | 8 | 01E07P02 | 007 | 72040082 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004911/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-21 | 2022-10-18 | FIMO NODE-B 2022 | PARE-PARE | MALILI |  | R7 PRE MLL MLI040 |  | 20 |  | 0 |  | 2022-07-21 | 2022-10-16 | [5 empty] | 162869387 | 47069940 | 209939327 | 0 | 4500471881 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022159 | 0 | 9 | 01E07P02 | 007 | 72040082 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004911/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-21 | 2022-10-18 | FIMO NODE-B 2022 | PARE-PARE | MALILI |  | R7 PRE MLL MLI037 |  | 20 |  | 0 |  | 2022-07-21 | 2022-10-11 | [5 empty] | 6347373 | 2264142 | 8611515 | 0 | 4500471881 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022159 | 0 | 10 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004911/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-21 | 2022-10-18 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MLI099 |  | 20 |  | 0 |  | 2022-07-21 | 2022-10-16 | [5 empty] | 20732871 | 4397948 | 25130819 | 0 | 4500471881 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022159 | 0 | 12 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004911/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-21 | 2022-10-18 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MLI096 |  | 20 |  | 0 |  | 2022-07-21 | 2022-10-16 | [5 empty] | 12987135 | 3255865 | 16243000 | 0 | 4500471881 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022159 | 0 | 11 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004911/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-21 | 2022-10-18 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MLI014 |  | 20 |  | 0 |  | 2022-07-21 | 2022-10-15 | [5 empty] | 306667063 | 76031253 | 382698316 | 0 | 4500471881 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022159 | 0 | 7 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004911/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-21 | 2022-10-18 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MLI095 |  | 20 |  | 0 |  | 2022-07-21 | 2022-10-16 | [5 empty] | 244036317 | 66680280 | 310716597 | 0 | 4500471881 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022160 | 0 | 11 | 01E07V04 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004912/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Palapa Ring 6 LOP Area Witel Sultra | 2022-07-21 | 2022-11-17 | PALAPA RING | KENDARI | BAU-BAU |  | R7 KDI BBU PRTENG NOC LAKUDO |  | 30 | 0 | 0 | Preparing | 2022-07-22 | 2022-11-17 | [5 empty] | 111781090 | 611163355 | 722944445 | 0 | 4500471883 |  |  |  |  | INNANDA INDAH
G2022160 | 0 | 12 | 01E07V04 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004912/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Palapa Ring 6 LOP Area Witel Sultra | 2022-07-21 | 2022-11-17 | PALAPA RING | KENDARI | BAU-BAU |  | R7 KDI BBU PRTENG NOC BURANGA |  | 30 | 0 | 0 | Preparing | 2022-07-21 | 2022-11-17 | [5 empty] | 100105694 | 370333725 | 470439419 | 0 | 4500471883 |  |  |  |  | INNANDA INDAH
G2022160 | 0 | 9 | 01E07V04 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004912/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Palapa Ring 6 LOP Area Witel Sultra | 2022-07-21 | 2022-11-17 | PALAPA RING | KENDARI | KENDARI |  | R7 KDI KDR PRTENG NOC KENDARI |  | 30 | 0 | 0 | Preparing | 2022-07-21 | 2022-11-17 | [5 empty] | 260293854 | 251589378 | 511883232 | 0 | 4500471883 |  |  |  |  | INNANDA INDAH
G2022160 | 0 | 10 | 01E07V04 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004912/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Palapa Ring 6 LOP Area Witel Sultra | 2022-07-21 | 2022-11-17 | PALAPA RING | KENDARI | KENDARI |  | R7 KDI KDR PRTENG NOC WAWONI |  | 30 | 0 | 0 | Preparing | 2022-07-22 | 2022-11-17 | [5 empty] | 145068095 | 131094187 | 276162282 | 0 | 4500471883 |  |  |  |  | INNANDA INDAH
G2022160 | 0 | 13 | 01E07V04 | 007 | 72050057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004912/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Palapa Ring 6 LOP Area Witel Sultra | 2022-07-21 | 2022-11-17 | PALAPA RING | KENDARI | RAHA |  | R7 KDI RAH PRTENG NOC RAHA |  | 30 | 0 | 0 | Preparing | 2022-07-21 | 2022-11-17 | [5 empty] | 103358598 | 371721281 | 475079879 | 0 | 4500471883 |  |  |  |  | INNANDA INDAH
G2022160 | 0 | 8 | 01E07V04 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004912/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Palapa Ring 6 LOP Area Witel Sultra | 2022-07-21 | 2022-11-17 | PALAPA RING | KENDARI | UNAAHA |  | R7 KDI UNH PRTENG NOC WANGGUDU |  | 30 | 0 | 0 | Preparing | 2022-07-21 | 2022-11-17 | [5 empty] | 100025110 | 128859121 | 228884231 | 0 | 4500471883 |  |  |  |  | INNANDA INDAH
G2022161 | 0 | 8 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004913/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 Tahap 2 2 LOP Area Witel Sultra | 2022-07-21 | 2022-10-18 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 BELAKANG RS BHAYANGKARA |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-18 | [5 empty] | 226468552 | 49278730 | 275747282 | 0 | 4500471880 |  |  |  |  | INNANDA INDAH
G2022161 | 0 | 9 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004913/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 Tahap 2 2 LOP Area Witel Sultra | 2022-07-21 | 2022-10-18 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 DIST 2 THE VILLAS |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-18 | [5 empty] | 162837754 | 50967092 | 213804846 | 0 | 4500471880 |  |  |  |  | INNANDA INDAH
G2022162 | 0 | 13 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | GORONTALO |  | PT2 KUA TAPA |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 11 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | GORONTALO |  | PT2+ Gorontalo Molosipat U Kec. Sipatana Kota Gorontalo |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 10926440 | 3051491 | 13977931 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 12 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | GORONTALO |  | PT2+ KUA DUNGINGI |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 14566365 | 4239613 | 18805978 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 8 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | GORONTALO |  | PT2 Jl. Taman Wisata Lombongo Kecamatan Suwawa Tengah Kabupaten Bone Bolango |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 10 | 01E07V06 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | ISIMU |  | PT2 Padengo Kec. Limboto Bar. Kabupaten Gorontalo |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 2310752 | 322083 | 2632835 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 7 | 01E07V06 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | ISIMU |  | GOMEDS HEM PT3 Harapan Kec. Wonosari Kabupaten Boalemo |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 207698763 | 54696826 | 262395589 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 9 | 01E07V06 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | KWANDANG |  | PT2 Jl. Buol - Ilangata Kec. Anggrek Kabupaten Gorontalo Utara |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022162 | 0 | 14 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004934/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS Juni Tahun 2022 Area Witel Gorontalo | 2022-07-21 | 2022-09-08 | HEM | GORONTALO | MARISA |  | HEM PT2 INDOMARETT RANDANGAN |  | 50 | 0 | 0 | Preparing | 2022-07-21 | 2022-09-08 | [5 empty] | 1722832 | 250972 | 1973804 | 0 | 4500472026 |  |  |  |  | TELKOM AKSES
G2022163 | 0 | 8 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004935/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 2 LoP Area Witel Makassar | 2022-07-21 | 2022-09-03 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT3 MANNURUKI |  | 65 | 0 | 0 | Preparing | 2022-07-21 | 2022-08-22 | [5 empty] | 47730906 | 11917840 | 59648746 | 0 | 4500472101 |  |  |  |  | PRASETIA DWIDHARMA
G2022163 | 0 | 9 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004935/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 2 LoP Area Witel Makassar | 2022-07-21 | 2022-09-03 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT3 MANNURUKI (2) |  | 65 |  | 0 |  | 2022-07-21 | 2022-08-22 | [5 empty] | 90202262 | 22716442 | 112918704 | 0 | 4500472101 |  |  |  |  | PRASETIA DWIDHARMA
G2022164 | 0 | 13 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004936/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 Tahap 2 5 LoP Area Witel Papua Barat | 2022-07-21 | 2022-10-03 | OSP FO FTTH PT3 2022 | SORONG | BIAK |  | R7 SON BIA PT3 JL RAYA SORIDO |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-03 | [5 empty] | 331805808 | 85492896 | 417298704 | 0 | 4500472102 |  |  |  |  | TRANSDATA SATKOMINDO
G2022164 | 0 | 14 | 01E07V01 | 007 | 74060039 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004936/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 Tahap 2 5 LoP Area Witel Papua Barat | 2022-07-21 | 2022-10-03 | OSP FO FTTH PT3 2022 | SORONG | MANOKWARI |  | R7 SON MWR PT3 KAMPUNG RABU CERIA |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-03 | [5 empty] | 355446218 | 75588085 | 431034303 | 0 | 4500472102 |  |  |  |  | TRANSDATA SATKOMINDO
G2022164 | 0 | 9 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004936/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 Tahap 2 5 LoP Area Witel Papua Barat | 2022-07-21 | 2022-10-03 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 ALUN ALUN AIMAS |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-03 | [5 empty] | 748315811 | 190963325 | 939279136 | 0 | 4500472102 |  |  |  |  | TRANSDATA SATKOMINDO
G2022164 | 0 | 10 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004936/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 Tahap 2 5 LoP Area Witel Papua Barat | 2022-07-21 | 2022-10-03 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 KAMPUNG INGGRIS |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-03 | [5 empty] | 222618993 | 48172135 | 270791128 | 0 | 4500472102 |  |  |  |  | TRANSDATA SATKOMINDO
G2022164 | 0 | 12 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004936/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 Tahap 2 5 LoP Area Witel Papua Barat | 2022-07-21 | 2022-10-03 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 JL. WORTEL AIMAS |  | 20 | 0 | 0 | Preparing | 2022-07-21 | 2022-10-03 | [5 empty] | 615683440 | 154292632 | 769976072 | 0 | 4500472102 |  |  |  |  | TRANSDATA SATKOMINDO
G2022165 | 0 | 7 | 01E07V01 | 007 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004943/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 1 LoP Area Witel Makassar | 2022-07-22 | 2022-09-04 | FEEDER BRANCHING 2022 | UJUNGPANDANG | JENEPONTO |  | R7 MKS JNP FE TOGO-TOGO |  | 64 |  | 0 |  | 2022-07-22 | 2022-09-02 | [5 empty] | 265949924 | 67025546 | 332975470 | 0 | 4500472141 |  |  |  |  | MANDOR KAWAT
G2022166 | 0 | 8 | 01E07V04 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004984/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP-FO NIQE 1 LoP Area Witel Makassar | 2022-07-25 | 2022-10-22 | OSP-FO NIQE | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP NIQE BSC BONE |  | 0 | 0 | 0 | Preparing | [7 empty] | 479299371 | 96101078 | 575400449 | 0 | 4500472304 |  |  |  |  | MANDOR KAWAT
G2022167 | 0 | 14 | 01E07V04 | 007 | 73020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004985/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Palapa Ring 3 LoP Area Witel Sulut Malut | 2022-07-25 | 2022-11-21 | PALAPA RING | TERNATE | MOROTAI |  | R7 MDO MTA PRTENG NOC MOROTAI |  | 20 | 0 | 0 | Preparing | 2022-07-25 | 2022-11-21 | [5 empty] | 124930917 | 27939091 | 152870008 | 0 | 4500472177 |  |  |  |  | PERKONSUMA
G2022167 | 0 | 11 | 01E07V04 | 007 | 73020044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004985/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Palapa Ring 3 LoP Area Witel Sulut Malut | 2022-07-25 | 2022-11-21 | PALAPA RING | TERNATE | TOBELO |  | R7 MDO TOB PRTENG TSEL MALIFUT-DARU |  | 20 | 0 | 0 | Preparing | 2022-07-25 | 2022-11-21 | [5 empty] | 2170369211 | 3140752407 | 5311121618 | 0 | 4500472177 |  |  |  |  | PERKONSUMA
G2022167 | 0 | 13 | 01E07V04 | 007 | 73020044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.004985/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Palapa Ring 3 LoP Area Witel Sulut Malut | 2022-07-25 | 2022-11-21 | PALAPA RING | TERNATE | TOBELO |  | R7 MDO TOB PRTENG NOC TOBELO |  | 20 | 0 | 0 | Preparing | 2022-07-25 | 2022-11-21 | [5 empty] | 33679487 | 32129596 | 65809083 | 0 | 4500472177 |  |  |  |  | PERKONSUMA
G2022168 | 0 | 12 | 01E07Q02 | 007 | 73010104 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | AMBON |  | R7 AMB ABO PT2 LATUHALAT |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-31 | [5 empty] | 39219426 | 7459919 | 46679345 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 9 | 01E07Q02 | 007 | 73010104 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | AMBON |  | R7 AMB ABO PT2 HATALAI |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-31 | [5 empty] | 11728841 | 2368839 | 14097680 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 8 | 01E07Q02 | 007 | 73010104 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | AMBON |  | R7 AMB ABO PT2 GUNUNG NONA |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-31 | [5 empty] | 22736566 | 5892525 | 28629091 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 13 | 01E07Q02 | 007 | 73010042 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | MASOHI |  | R7 AMB MSH PT2 GEREJA SUNGAI YORDAN |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-31 | [5 empty] | 15225044 | 4069803 | 19294847 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 15 | 01E07Q02 | 007 | 73010042 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | MASOHI |  | R7 AMB MSH PT2 TOKO BISMA |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-31 | [5 empty] | 11146453 | 2842449 | 13988902 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 14 | 01E07Q02 | 007 | 73010042 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | MASOHI |  | R7 AMB MSH PT2 ODC-MSH-FAD |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-31 | [5 empty] | 22923887 | 4296205 | 27220092 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 10 | 01E07Q02 | 007 | 73010119 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | AMBON | TUAL |  | R7 AMB TUA PT2 KEI KECIL |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 21538046 | 4063515 | 25601561 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
G2022168 | 0 | 11 | 01E07Q02 | 007 | 73030018 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004992/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan PT2 8 LOP Tahun 2022 Area Witel Maluku | 2022-07-25 | 2022-09-07 | OSP FO FTTH PT2 2022 | TUAL | TUAL |  | R7 AMB TUA PT2 JL KE DULAH |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 9091992 | 2511887 | 11603879 | 0 | 4500472530 |  |  |  |  | TELKOM AKSES
12022182 | 0 | 59 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | KENDARI | KENDARI |  | r7.ken.pe-mobile.2 ex sr-mlg.2 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 60 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | KENDARI | KENDARI |  | r7.ken.pe-mobile.2 ex sr-sukoharjo.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 58 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | KENDARI | KENDARI |  | r7.ken.pe-mobile.1 ex sr-sukoharjo.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 57 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | KENDARI | KENDARI |  | r7.ken.pe-mobile.1 ex sr-mlg.1 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 111 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | PALU | PALU |  | r7.plu.pe-mobile.1 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 55 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | PALU | PALU |  | r7.plu.pe-mobile.2 ex sr-gayungan.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 54 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | PALU | PALU |  | r7.plu.pe-mobile.1 ex sr-gombel.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 112 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | PALU | PALU |  | r7.plu.pe-mobile.2 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 53 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | PALU | PALU |  | r7.plu.pe-mobile.1 ex sr-gayungan.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 56 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | PALU | PALU |  | r7.plu.pe-mobile.2 ex sr-gombel.2new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 52 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | TERNATE | TERNATE |  | r7.tnt.pe-mobile.2 ex r7.pnk.pe-mobile.2 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 109 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | TERNATE | TERNATE |  | r7.tnt.pe-mobile.1 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 110 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | TERNATE | TERNATE |  | r7.tnt.pe-mobile.2 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 51 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | TERNATE | TERNATE |  | r7.tnt.pe-mobile.1 ex r7.pnk.pe-mobile.1 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 22 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | BALAIKOTA |  | r7.bal.asbr-tsel.1 ex R1.PBR.ASBR-TSEL.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 60000000 | 347913200 | 407913200 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 8 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | BALAIKOTA |  | r7.bal.rr-tsel.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 696484900 | 352466900 | 1048951800 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 25 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | BALAIKOTA |  | r7.bal.asbr-tsel.1 ex sr-kenanga.1-new |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 415652400 | 415652400 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 67 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.2 ex sr-gayungan.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 115 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.2 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 68 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.2 ex sr-palu.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 114 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.1 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 63 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.1 ex sr-gayungan.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 62 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.1 ex sr-sorong.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 65 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.2 ex sr-ternate.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 64 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.1 ex sr-palu.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 66 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.2 ex sr-sorong.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 6 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.rr-tsel.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 696484900 | 352466900 | 1048951800 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 21 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.asbr-tsel.1 ex R1.DRI.ASBR-TSEL.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 60000000 | 347913200 | 407913200 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 23 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.asbr-tsel.1 ex sr-kenanga.1-new |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 410981000 | 410981000 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 61 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PENGAYOMAN |  | r7.pgy.pe-mobile.1 ex sr-ternate.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 9 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PETTARANI |  | r7.ptr.rr-tsel.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 696484900 | 352466900 | 1048951800 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 28 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PETTARANI |  | r7.ptr.asbr-tsel.1 ex R1.BLN.ASBR-TSEL.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 60000000 | 347913200 | 407913200 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 30 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | PETTARANI |  | r7.ptr.asbr-tsel.1 ex sr-kenanga.2-new |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 415652400 | 415652400 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 73 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.1 ex sr-sorong.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 113 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.1 | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 69 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.1 ex sr-pattimura.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 7 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.rr-tsel.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 696484900 | 352466900 | 1048951800 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 24 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.asbr-tsel.1 ex R1.MRP.ASBR-TSEL.1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 60000000 | 347913200 | 407913200 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 27 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.asbr-tsel.1 ex sr-kenanga.2-new |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 410981000 | 410981000 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 76 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.2 ex sr-timika.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 75 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.2 ex sr-gayungan.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 74 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.2 ex sr-pattimura.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 71 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.1 ex sr-timika.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 72 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.1 ex sr-kendari.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 70 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.1 ex sr-gayungan.1-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 78 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.2 ex sr-sorong.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
12022182 | 0 | 77 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004994/HK.810/SSP-10000000/2022 | Surat Pesanan-10 (SP#10) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2022-07-25 | 2023-01-20 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | r7.sud.pe-mobile.2 ex sr-kendari.2-new | [12 empty] | 0 | 0 | 0 | 0 | 4500471335 |  |  |  |  | SISINDOKOM LINTASBUANA
G2022169 | 0 | 10 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 3755860 | 0 | 3755860 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 11 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 9389650 | 0 | 9389650 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 12 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | KIMA |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 18603610 | 8371540 | 26975150 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 13 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | MAROS |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 1877930 | 0 | 1877930 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 14 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 22781120 | 24619220 | 47400340 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 15 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 26291020 | 0 | 26291020 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 16 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 14207730 | 1399230 | 15606960 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 17 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 13145510 | 0 | 13145510 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022169 | 0 | 18 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005060/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE RELOKASI UTILITAS 9 LOP Area Witel Makassar | 2022-07-26 | 2022-09-08 | QE RELOKASI | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-26 | 2022-07-31 | [5 empty] | 13907660 | 4066200 | 17973860 | 0 | 4500472756 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 17 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | AMBON | AMBON |  | PEKERJAAN QE RELOKASI PERIODE FEB, MARET, MEI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-05 | [5 empty] | 73593900 | 22528560 | 96122460 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 18 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | AMBON | PASSO |  | PEKERJAAN QE RELOKASI PERIODE FEB, MARET, MEI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-05 | [5 empty] | 19092310 | 4689690 | 23782000 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 16 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | GORONTALO | GORONTALO |  | PEKERJAAN QE RELOKASI PERIODE JUNI 2022 |  | 50 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-30 | [5 empty] | 3386190 | 574300 | 3960490 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 20 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE RELOKASI PERIODE MEI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-13 | [5 empty] | 35317860 | 32888190 | 68206050 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 19 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | JAYAPURA | TIMIKA |  | PEKERJAAN QE RELOKASI PERIODE MEI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-13 | [5 empty] | 29388600 | 31682790 | 61071390 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 26 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | KENDARI | KENDARI |  | PEKERJAAN QE RELOKASI PERIODE MARET, MEI 2022 |  | 70 | 0 | 0 | Preparing | 2022-07-26 | 2022-09-08 | [5 empty] | 140090840 | 45826900 | 185917740 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 27 | 01E07Y05 | 007 | 72050057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | KENDARI | RAHA |  | PEKERJAAN QE RELOKASI PERIODE MARET, MEI 2022 |  | 70 | 0 | 0 | Preparing | 2022-07-26 | 2022-09-08 | [5 empty] | 32276070 | 95348940 | 127625010 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 23 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | PALU | PALU B |  | PEKERJAAN QE RELOKASI PERIODE FEBRUARI, APRIL 2022 |  | 95 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-02 | [5 empty] | 106544410 | 80096930 | 186641340 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 24 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | PALU | TAWAELI |  | PEKERJAAN QE RELOKASI PERIODE FEBRUARI, APRIL 2022 |  | 95 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-02 | [5 empty] | 3663000 | 4973160 | 8636160 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 25 | 01E07Y05 | 007 | 72030139 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | PALU | TENTENA |  | PEKERJAAN QE RELOKASI PERIODE FEBRUARI, APRIL 2022 |  | 95 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-02 | [5 empty] | 3266120 | 4567580 | 7833700 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 22 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | PARE-PARE | MAKALE |  | PEKERJAAN QE RELOKASI PERIODE MARET 2022 |  | 95 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-02 | [5 empty] | 4101270 | 1859370 | 5960640 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022170 | 0 | 21 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005061/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 12 Lop Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-07-26 | 2022-09-08 | QE RELOKASI | SORONG | SORONG |  | PEKERJAAN QE RELOKASI PERIODE APR-MEI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-26 | 2022-08-04 | [5 empty] | 8453200 | 2242610 | 10695810 | 0 | 4500472776 |  |  |  |  | TELKOM AKSES
G2022171 | 0 | 7 | 01E07T02 | 007 | 74040016 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005066/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN LASTMILE NODE B 2 LOP AREA WITEL PAPUA BARAT | 2022-07-26 | 2022-09-23 | FIMO NODE-B 2022 | MANOKWARI | WARMARE |  | R7 SON WMMR MWR188 |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-09-23 | [5 empty] | 447355993 | 123158491 | 570514484 | 0 | 4500472773 |  |  |  |  | TRANSDATA SATKOMINDO
G2022171 | 0 | 8 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005066/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN LASTMILE NODE B 2 LOP AREA WITEL PAPUA BARAT | 2022-07-26 | 2022-09-23 | FIMO NODE-B 2022 | SORONG | NABIRE |  | R7 SON NAB NAB143 DMT Mamoribo Nabarua |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-09-23 | [5 empty] | 38482905 | 9643893 | 48126798 | 0 | 4500472773 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 11 | 01E07R03 | 007 | 72010004 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | AMURANG |  | R7 MDO AMR AMR018 Karowa |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 205909247 | 44251018 | 250160265 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 14 | 01E07R03 | 007 | 72010012 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | BOROKO |  | R7 MDO BOR KTG038 Mokoditek |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 1061910648 | 192762795 | 1254673443 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 13 | 01E07R03 | 007 | 72010052 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG KTG906 Combat Dumoga |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 8813707 | 2410138 | 11223845 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 12 | 01E07R03 | 007 | 72010052 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG KTG204 MC Adampe Dolot |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 57813586 | 27523238 | 85336824 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 9 | 01E07R03 | 007 | 72010064 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | MANADO BAHU |  | R7 MDO BAH MDO314 MC Citraland |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 30869355 | 24155952 | 55025307 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 7 | 01E07R03 | 007 | 72010248 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | TAGULANDANG |  | R7 MDO TAG THN079 MCR Tagulandang |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 10941504 | 2492666 | 13434170 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022172 | 0 | 10 | 01E07R03 | 007 | 72010112 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005089/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 7 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-26 | 2022-10-23 | FIMO NODE-B 2022 | MANADO | TONDANO |  | R7 MDO TDN TDO278 API MCP Kembuan Tondano |  | 20 | 0 | 0 | Preparing | 2022-07-26 | 2022-10-23 | [5 empty] | 27654331 | 5979549 | 33633880 | 0 | 4500472719 |  |  |  |  | TRANSDATA SATKOMINDO
G2022173 | 0 | 10 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-15 | [5 empty] | 8593070 | 4568570 | 13161640 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 11 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-11 | [5 empty] | 83570 | 0 | 83570 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 12 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-10 | [5 empty] | 418720 | 0 | 418720 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 13 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | KIMA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 10301280 | 4204740 | 14506020 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 14 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | MAROS |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-15 | [5 empty] | 30810 | 0 | 30810 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 15 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-10 | [5 empty] | 6033000 | 3127070 | 9160070 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 16 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 0 | 0 | 0 | Preparing | 2022-08-02 | 2022-08-10 | [5 empty] | 14132710 | 8556390 | 22689100 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 17 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-12 | [5 empty] | 7638460 | 4304430 | 11942890 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 18 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-15 | [5 empty] | 369320 | 0 | 369320 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 19 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 0 | 0 | 0 | Preparing | 2022-08-02 | 2022-08-15 | [5 empty] | 5868660 | 4191610 | 10060270 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 20 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 0 | 0 | 0 | Preparing | 2022-08-02 | 2022-08-11 | [5 empty] | 8882540 | 5128190 | 14010730 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 21 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 0 | 0 | 0 | Preparing | 2022-08-02 | 2022-08-12 | [5 empty] | 278890 | 0 | 278890 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 22 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 0 | 0 | 0 | Preparing | 2022-08-02 | 2022-08-11 | [5 empty] | 3675950 | 2339960 | 6015910 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022173 | 0 | 23 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005122/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 14 LoP Area Witel Makassar | 2022-07-27 | 2022-09-09 | QE WIBS | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 20 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-15 | [5 empty] | 51830 | 0 | 51830 | 0 | 4500473088 |  |  |  |  | TELKOM AKSES
G2022174 | 0 | 12 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005137/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Papua | 2022-07-28 | 2022-09-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM209 |  | 20 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-25 | [5 empty] | 5617545 | 2661101 | 8278646 | 0 | 4500473260 |  |  |  |  | TRANSDATA SATKOMINDO
G2022174 | 0 | 11 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005137/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Papua | 2022-07-28 | 2022-09-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM190 |  | 20 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-25 | [5 empty] | 8858764 | 3676435 | 12535199 | 0 | 4500473260 |  |  |  |  | TRANSDATA SATKOMINDO
G2022174 | 0 | 10 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005137/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Papua | 2022-07-28 | 2022-09-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM161 |  | 20 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-25 | [5 empty] | 3052229 | 1686435 | 4738664 | 0 | 4500473260 |  |  |  |  | TRANSDATA SATKOMINDO
G2022174 | 0 | 8 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005137/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Papua | 2022-07-28 | 2022-09-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM126 |  | 20 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-25 | [5 empty] | 13185256 | 3771100 | 16956356 | 0 | 4500473260 |  |  |  |  | TRANSDATA SATKOMINDO
G2022174 | 0 | 9 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005137/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Papua | 2022-07-28 | 2022-09-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM135 |  | 20 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-25 | [5 empty] | 14524441 | 5334447 | 19858888 | 0 | 4500473260 |  |  |  |  | TRANSDATA SATKOMINDO
G2022174 | 0 | 7 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005137/HK.810/R7W-7B1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 6 LOP Tahun 2022 Area Witel Papua | 2022-07-28 | 2022-09-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM142 |  | 20 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-25 | [5 empty] | 47267874 | 14706366 | 61974240 | 0 | 4500473260 |  |  |  |  | TRANSDATA SATKOMINDO
G2022175 | 0 | 7 | 01E07V01 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005165/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 2 LoP Area Witel Makassar | 2022-07-28 | 2022-09-25 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT3 ILMA D MANSION |  | 70 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-31 | [5 empty] | 77894694 | 18036639 | 95931333 | 0 | 4500473107 |  |  |  |  | RATI UTAMA KARYA
G2022175 | 0 | 8 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005165/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH-2 2 LoP Area Witel Makassar | 2022-07-28 | 2022-09-25 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT3 GRIYA HARAPAN BAJIMINASA |  | 55 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-31 | [5 empty] | 40086173 | 8493867 | 48580040 | 0 | 4500473107 |  |  |  |  | RATI UTAMA KARYA
G2022176 | 0 | 14 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | JAYAPURA | ABEPURA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-15 | [5 empty] | 16430 | 0 | 16430 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 15 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-15 | [5 empty] | 707880 | 0 | 707880 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 16 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-15 | [5 empty] | 1900 | 0 | 1900 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 18 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | JAYAPURA | SENTANI |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-15 | [5 empty] | 1900 | 0 | 1900 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 19 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | JAYAPURA | TIMIKA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-15 | [5 empty] | 12630 | 0 | 12630 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 37 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | KENDARI | KENDARI |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 50 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-10 | [5 empty] | 24656210 | 0 | 24656210 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 38 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | KENDARI | MANDONGA |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 50 | 0 | 0 | Preparing | 2022-07-28 | 2022-09-10 | [5 empty] | 751700 | 0 | 751700 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 40 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | MANADO | BITUNG |  | PEKERJAAN QE WIBS JANUARI-FEBRUARI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2780100 | 0 | 2780100 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 39 | 01E07Y05 | 007 | 72010267 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | MANADO | HULU SIAU |  | PEKERJAAN QE WIBS JANUARI-FEBRUARI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2745600 | 3585540 | 6331140 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 41 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | MANADO | KOTAMOBAGU |  | PEKERJAAN QE WIBS JANUARI-FEBRUARI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 398700 | 0 | 398700 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 42 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | MANADO | MANADO |  | PEKERJAAN QE WIBS JANUARI-FEBRUARI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 18670880 | 3639880 | 22310760 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 17 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | MERAUKE | MERAUKE |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-15 | [5 empty] | 832000 | 0 | 832000 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 33 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | BARRU |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 13050 | 0 | 13050 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 36 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | ENREKANG |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 6110 | 0 | 6110 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 26 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | MAKALE |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 830 | 0 | 830 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 28 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | MALILI |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 16600 | 0 | 16600 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 24 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | MAMUJU |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 724280 | 780440 | 1504720 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 25 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | MASAMBA |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 3532150 | 2195890 | 5728040 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 29 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | PALOPO |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 356300 | 0 | 356300 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 30 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | PARE-PARE |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 41370 | 0 | 41370 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 31 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | PINRANG |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 33200 | 0 | 33200 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 32 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | SENGKANG |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 9130 | 0 | 9130 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 34 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | SIDRAP |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 20250 | 0 | 20250 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 35 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | PARE-PARE | SOROWAKO |  | PEKERJAAN QE WIBS JANUARI - MARET 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-09 | [5 empty] | 830 | 0 | 830 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 23 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | SORONG | BIAK |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 100 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-05 | [5 empty] | 1955220 | 0 | 1955220 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 21 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | SORONG | FAKFAK |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-05 | [5 empty] | 414540 | 0 | 414540 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 22 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | SORONG | MANOKWARI |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-05 | [5 empty] | 3144830 | 0 | 3144830 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 20 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | SORONG | SORONG |  | PEKERJAAN QE WIBS JANUARI 2022 |  | 90 | 0 | 0 | Preparing | 2022-07-28 | 2022-08-05 | [5 empty] | 3133880 | 0 | 3133880 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022176 | 0 | 43 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005168/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE WIBS 29 LOP Area Witel Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-07-28 | 2022-09-10 | QE WIBS | TERNATE | TERNATE |  | PEKERJAAN QE WIBS JANUARI-FEBRUARI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 411660 | 0 | 411660 | 0 | 4500473380 |  |  |  |  | TELKOM AKSES
G2022177 | 0 | 7 | 01E07O02 | 007 | 72030088 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.005174/HK.810/R7W-7C100000/2022 | LASTMILE HEM 1 LOP WITEL SULTENG | 2022-07-29 | 2022-08-27 | HEM | PALU | TAWAELI |  | R7 PAL TWL HEM PT CONCH CEMENT INDONESIA |  | 0 | 0 | 0 | Preparing | [7 empty] | 286550749 | 78351391 | 364902140 | 0 | 4500473318 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022178 | 0 | 8 | 01E07R03 | 007 | 72010002 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD TDO084 DMT Kuala Batu |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 257970072 | 46633103 | 304603175 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 15 | 01E07R03 | 007 | 72010004 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | AMURANG |  | R7 MDO AMR AMR110 |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 301207051 | 52849872 | 354056923 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 10 | 01E07R03 | 007 | 72010004 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | AMURANG |  | R7 MDO AMR AMR062 TBG Tenga Pakuweru |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 45845316 | 9036829 | 54882145 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 11 | 01E07R03 | 007 | 72010008 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | BITUNG |  | R7 MDO BIT BIT068 b.Prot Pimpin Tanjungmerah |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 241298258 | 43741587 | 285039845 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 12 | 01E07R03 | 007 | 72010008 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | BITUNG |  | R7 MDO BIT BIT104 MCR Manembonembo |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 4229736 | 1822759 | 6052495 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 7 | 01E07R03 | 007 | 72010052 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG KTG099 DMT Toraut |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 496946855 | 88862274 | 585809129 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 9 | 01E07R03 | 007 | 72010127 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | LANGOWAN |  | R7 MDO LAN AMR057 TBG Silian Minahasa |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 5193277 | 2107488 | 7300765 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 13 | 01E07R03 | 007 | 72010104 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | TAHUNA |  | R7 MDO THN THN110 |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 4229736 | 1822759 | 6052495 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022178 | 0 | 14 | 01E07R03 | 007 | 72010283 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005179/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP 2022 WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-07-29 | 2022-10-26 | FIMO NODE-B 2022 | MANADO | TUTUYAN |  | R7 MDO TUT RTN001 |  | 20 | 0 | 0 | Preparing | 2022-07-29 | 2022-10-26 | [5 empty] | 2450441 | 1428822 | 3879263 | 0 | 4500473261 |  |  |  |  | TRANSDATA SATKOMINDO
G2022179 | 0 | 7 | 01E07Q02 | 007 | 73010057 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.005306/HK.810/R7W-7E1H0000/2022 | Pengadaan Pekerjaan Lastmile Node-B 1 LOP Tahun 2022 Area Witel Maluku | 2022-08-02 | 2022-09-05 | FIMO NODE-B 2022 | AMBON | PASSO |  | R7 AMB PAO AMB182 DMT Suli Salahutu 2 |  | 20 | 0 | 0 | Preparing | 2022-08-02 | 2022-09-05 | [5 empty] | 13772131 | 4060439 | 17832570 | 0 | 4500473966 |  |  |  |  | TRANSDATA SATKOMINDO
G2022180 | 0 | 9 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005332/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 3 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-08-02 | 2022-08-31 | FIMO NODE-B 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK BLK085 Protelindo Tanah Harapan |  | 0 | 0 | 0 | Preparing | [7 empty] | 10290361 | 3949858 | 14240219 | 0 | 4500474082 |  |  |  |  | SIPAKALEBBI 2
G2022180 | 0 | 8 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005332/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 3 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-08-02 | 2022-08-31 | FIMO NODE-B 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK BLK125 |  | 0 | 0 | 0 | Preparing | [7 empty] | 4551960 | 2220460 | 6772420 | 0 | 4500474082 |  |  |  |  | SIPAKALEBBI 2
G2022180 | 0 | 7 | 01E07J04 | 007 | 72080054 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005332/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 3 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-08-02 | 2022-08-31 | FIMO NODE-B 2022 | UJUNGPANDANG | JENEPONTO |  | R7 MKS JNP JNP064 DMT Isat Jeneponto |  | 0 | 0 | 0 | Preparing | [7 empty] | 9779006 | 3546523 | 13325529 | 0 | 4500474082 |  |  |  |  | SIPAKALEBBI 2
T2022042 | 0 | 26 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005336/HK.810/TSC-B0000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Platform Allot | 2022-08-02 | 2022-11-29 | PCEF Allot | PALU | PALU |  |  |  | 15 | 0 | 0 | Preparing | 2022-08-02 | 2022-11-29 | [5 empty] | 66375000 | 63060000 | 129435000 | 0 | 4500473790 |  |  |  |  | ANDES LASEA KREASINDO
G2022181 | 0 | 23 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | AMBON |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 757588910 | 37389860 | 794978770 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 24 | 01E07Y05 | 007 | 73010013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | BULA |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 11684760 | 0 | 11684760 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 25 | 01E07Y05 | 007 | 73010120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | DOBO |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3489440 | 0 | 3489440 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 26 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | MASOHI |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 79594620 | 0 | 79594620 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 27 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | NAMLEA |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 16093040 | 0 | 16093040 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 28 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | PASSO |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 268270150 | 11113920 | 279384070 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 29 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | SAUMLAKI |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 10537640 | 0 | 10537640 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 30 | 01E07Y05 | 007 | 73010172 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | TIAKUR |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 507680 | 0 | 507680 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 31 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | AMBON | TUAL |  | PEKERJAAN QE ACCESS PERIODE NOVEMBER 2021, APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 110856420 | 3354800 | 114211220 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 17 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | GORONTALO | GORONTALO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-31 | [5 empty] | 115999390 | 0 | 115999390 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 18 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | GORONTALO | ISIMU |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-31 | [5 empty] | 18943380 | 0 | 18943380 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 19 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | GORONTALO | KWANDANG |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-31 | [5 empty] | 5803890 | 0 | 5803890 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 20 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | GORONTALO | LIMBOTO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-31 | [5 empty] | 19562750 | 0 | 19562750 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 21 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | GORONTALO | MARISA |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-31 | [5 empty] | 20626160 | 0 | 20626160 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 22 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | GORONTALO | TELAGA |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-31 | [5 empty] | 25101600 | 0 | 25101600 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 32 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | ABEPURA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 86158750 | 0 | 86158750 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 33 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 42487240 | 0 | 42487240 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 34 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 17524620 | 0 | 17524620 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 35 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 7159840 | 0 | 7159840 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 37 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | SARMI |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 6766820 | 0 | 6766820 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 38 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | SENTANI |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 47380320 | 0 | 47380320 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 42 | 01E07Y05 | 007 | 74030067 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | TEMBAGAPURA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 832000 | 0 | 832000 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 39 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | TIMIKA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 45591020 | 0 | 45591020 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 41 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | JAYAPURA | WAENA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 21560130 | 0 | 21560130 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 89 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | BAU-BAU |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 101082130 | 0 | 101082130 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 90 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | KENDARI |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 186601370 | 0 | 186601370 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 91 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | KOLAKA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 24976950 | 0 | 24976950 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 92 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | LASUSUA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 21134150 | 0 | 21134150 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 93 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | MANDONGA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 237003340 | 0 | 237003340 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 94 | 01E07Y05 | 007 | 72050050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | POMALAA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 10868880 | 0 | 10868880 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 95 | 01E07Y05 | 007 | 72050057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | RAHA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5240440 | 0 | 5240440 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 96 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | UNAAHA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 26346530 | 0 | 26346530 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 97 | 01E07Y05 | 007 | 72050074 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | KENDARI | WANCI |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5807820 | 0 | 5807820 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 98 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | AIR MADIDI |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 57453900 | 0 | 57453900 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 99 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | AMURANG |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 13740600 | 0 | 13740600 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 100 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | BAHU |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 45346080 | 0 | 45346080 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 101 | 01E07Y05 | 007 | 72010258 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | BEO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1314600 | 0 | 1314600 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 125 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | BITUNG |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 65319000 | 0 | 65319000 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 102 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | BOROKO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 4991400 | 0 | 4991400 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 103 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | KAUDITAN |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3970800 | 0 | 3970800 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 104 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | KOTAMOBAGU |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 31438180 | 0 | 31438180 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 105 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | LANGOWAN |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 18481500 | 0 | 18481500 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 106 | 01E07Y05 | 007 | 72010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | LOLAK |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 801300 | 0 | 801300 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 108 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | MANADO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 101610960 | 0 | 101610960 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 107 | 01E07Y05 | 007 | 72010077 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | MOLIBAGU |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1800 | 0 | 1800 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 109 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | PANIKI |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 33054300 | 0 | 33054300 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 110 | 01E07Y05 | 007 | 72010248 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | TAGULANDANG |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 396000 | 0 | 396000 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 111 | 01E07Y05 | 007 | 72010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | TAHUNA |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 7157700 | 0 | 7157700 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 112 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | TOMOHON |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5214600 | 0 | 5214600 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 113 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | TONDANO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 36422400 | 0 | 36422400 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 114 | 01E07Y05 | 007 | 72010283 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MANADO | TUTUYAN |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2381400 | 0 | 2381400 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 36 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MERAUKE | MERAUKE |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 41539610 | 0 | 41539610 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 40 | 01E07Y05 | 007 | 74050022 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | MERAUKE | TANAH MERAH |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 50 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 963040 | 0 | 963040 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 71 | 01E07Y05 | 007 | 72030159 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | AMPANA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 70 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 10232740 | 0 | 10232740 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 72 | 01E07Y05 | 007 | 72030123 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | BANGGAI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 369320 | 0 | 369320 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 73 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | BUNGKU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 74675940 | 0 | 74675940 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 74 | 01E07Y05 | 007 | 72030124 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | BUNTA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 732830 | 0 | 732830 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 75 | 01E07Y05 | 007 | 72030013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | BUOL |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 18311520 | 0 | 18311520 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 76 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | DONGGALA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 17453870 | 0 | 17453870 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 77 | 01E07Y05 | 007 | 72030104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | KOLONODALE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 5569400 | 0 | 5569400 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 78 | 01E07Y05 | 007 | 72030099 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | KOTARAYA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 8614620 | 0 | 8614620 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 79 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | LUWUK |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 85102970 | 0 | 85102970 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 80 | 01E07Y05 | 007 | 72030050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | MOUTONG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 919150 | 0 | 919150 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 81 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | PALU A |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 112614880 | 0 | 112614880 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 82 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | PALU B |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 114663130 | 0 | 114663130 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 83 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | PARIGI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 21920780 | 0 | 21920780 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 84 | 01E07Y05 | 007 | 72030101 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | POSO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 32517110 | 0 | 32517110 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 85 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | TAWAELI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 668590 | 0 | 668590 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 86 | 01E07Y05 | 007 | 72030081 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | TINOMBO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 57720 | 0 | 57720 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 87 | 01E07Y05 | 007 | 72030083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | TOLAY |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 972010 | 0 | 972010 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 88 | 01E07Y05 | 007 | 72030084 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PALU | TOLI-TOLI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-25 | [5 empty] | 31141270 | 0 | 31141270 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 47 | 01E07Y05 | 007 | 72040275 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | AJANGALE |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 1570600 | 0 | 1570600 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 48 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | BARRU |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 35272310 | 0 | 35272310 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 49 | 01E07Y05 | 007 | 72040044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | CANGADI |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 2245740 | 0 | 2245740 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 50 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | ENREKANG |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 19083170 | 0 | 19083170 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 51 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | MAJENE |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 33722240 | 0 | 33722240 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 52 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | MAKALE |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 43064630 | 0 | 43064630 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 53 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | MALILI |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 16954860 | 0 | 16954860 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 54 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | MAMASA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 3462300 | 0 | 3462300 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 55 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | MAMUJU |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 193181960 | 0 | 193181960 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 56 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | MASAMBA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 44199490 | 0 | 44199490 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 57 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | PALOPO |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 127421620 | 0 | 127421620 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 58 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | PARE-PARE |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 105770140 | 0 | 105770140 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 59 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 3805210 | 0 | 3805210 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 60 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | PINRANG |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 93028140 | 0 | 93028140 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 61 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | POLEWALI |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 10264910 | 0 | 10264910 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 62 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | RANTEPAO |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 68133840 | 0 | 68133840 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 63 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | RAPPANG |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 17878030 | 0 | 17878030 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 64 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | SENGKANG |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 30516000 | 0 | 30516000 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 65 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | SIDRAP |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 32539190 | 0 | 32539190 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 66 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | SIWA |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 2966990 | 0 | 2966990 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 67 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | SOROWAKO |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 26982970 | 0 | 26982970 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 68 | 01E07Y05 | 007 | 72040174 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | TANRUTEDONG |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 4114040 | 0 | 4114040 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 69 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 4657670 | 0 | 4657670 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 70 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | PARE-PARE | WONOMULYO |  | PEKERJAAN QE ACCESS PERIODE MARET-APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-04 | 2022-08-10 | [5 empty] | 35509920 | 0 | 35509920 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 44 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | SORONG | BIAK |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 35122850 | 0 | 35122850 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 45 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | SORONG | FAKFAK |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 97246240 | 0 | 97246240 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 46 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | SORONG | MANOKWARI |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 38166620 | 0 | 38166620 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 43 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | SORONG | SORONG |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 90 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-17 | [5 empty] | 228658950 | 0 | 228658950 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 115 | 01E07Y05 | 007 | 73020005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | GALELA |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 7899080 | 0 | 7899080 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 116 | 01E07Y05 | 007 | 73020009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | JAILOLO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 876200 | 0 | 876200 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 117 | 01E07Y05 | 007 | 73020013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | LABUHA |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 22947800 | 0 | 22947800 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 118 | 01E07Y05 | 007 | 73020057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | MANGOLE |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1760 | 0 | 1760 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 119 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | MOROTAI |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2931270 | 0 | 2931270 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 120 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | SANANA |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2765180 | 0 | 2765180 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 121 | 01E07Y05 | 007 | 73020034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | SOA SIU |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 978200 | 0 | 978200 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 122 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | SOFIFI |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 26985280 | 0 | 26985280 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 123 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | TERNATE |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 70873100 | 0 | 70873100 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022181 | 0 | 124 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005369/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 109 LOP Area Witel Gorontalo, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut Malut | 2022-08-03 | 2022-09-16 | QE AKSES | TERNATE | TOBELO |  | PEKERJAAN QE ACCESS PERIODE APRIL 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 19439240 | 0 | 19439240 | 0 | 4500474265 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 10 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-11 | [5 empty] | 8328400 | 0 | 8328400 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 11 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-11 | [5 empty] | 7661610 | 0 | 7661610 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 12 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 557190 | 0 | 557190 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 13 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 918700 | 0 | 918700 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 14 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 1362090 | 0 | 1362090 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 15 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | KIMA |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 22934910 | 0 | 22934910 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 16 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | MAROS |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 1890880 | 0 | 1890880 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 17 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 9144770 | 0 | 9144770 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 18 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 23110090 | 0 | 23110090 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 19 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-09 | [5 empty] | 894660 | 0 | 894660 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 20 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 424550 | 0 | 424550 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 21 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 1754680 | 0 | 1754680 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 22 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 18323760 | 0 | 18323760 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 23 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-11 | [5 empty] | 18481450 | 0 | 18481450 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 24 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 3469980 | 0 | 3469980 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 25 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 10451020 | 0 | 10451020 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022182 | 0 | 26 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005370/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 17 LoP Area Witel Makassar | 2022-08-03 | 2022-09-16 | QE HEM | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE HEM APRIL - MEI 2022 |  | 100 | 0 | 0 | Preparing | 2022-08-03 | 2022-08-10 | [5 empty] | 5858080 | 0 | 5858080 | 0 | 4500474266 |  |  |  |  | TELKOM AKSES
G2022183 | 0 | 7 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.005378/HK.810/R7W-7C100000/2022 | LASTMILE HEM 1 LOP WITEL SULTENG | 2022-08-04 | 2022-09-02 | HEM | PALU | BUNGKU |  | R7 PAL BKU HEM PT RISUN BAHODOPI |  | 20 | 0 | 0 | Preparing | 2022-08-04 | 2022-09-02 | [5 empty] | 421157318 | 104632090 | 525789408 | 0 | 4500474290 |  |  |  |  | TRANSDATA SATKOMINDO
G2022184 | 0 | 10 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 128229110 | 0 | 128229110 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 11 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 190389020 | 0 | 190389020 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 12 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 54699740 | 0 | 54699740 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 13 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 71715410 | 0 | 71715410 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 14 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 27363850 | 0 | 27363850 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 15 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | KIMA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 16534300 | 0 | 16534300 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 16 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | MALINO |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2172890 | 0 | 2172890 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 17 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | MAROS |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 16290040 | 0 | 16290040 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 18 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 257775120 | 0 | 257775120 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 19 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 311012100 | 0 | 311012100 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 20 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 16221460 | 0 | 16221460 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 21 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 70835160 | 0 | 70835160 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 22 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 47696550 | 0 | 47696550 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 23 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 66064820 | 0 | 66064820 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 24 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 254718940 | 0 | 254718940 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 25 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 118313020 | 0 | 118313020 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 26 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 89017280 | 0 | 89017280 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022184 | 0 | 27 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.005380/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE ACCESS 18 LoP Area Witel Makassar | 2022-08-04 | 2022-09-17 | QE AKSES | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE ACCESS PERIODE MARET-MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 176103380 | 0 | 176103380 | 0 | 4500474293 |  |  |  |  | TELKOM AKSES
G2022185 | 0 | 10 | 01E07V04 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005381/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan NIQE 3 LoP Area Witel Sulteng dan Sulut Malut | 2022-08-04 | 2022-12-01 | NIQE | MANADO | AMURANG |  | R7 MDO AMR NIQE AMURANG - BAHU |  | 20 | 0 | 0 | Preparing | 2022-08-04 | 2022-12-01 | [5 empty] | 115385932 | 28743584 | 144129516 | 0 | 4500474304 |  |  |  |  | PERKONSUMA
G2022185 | 0 | 9 | 01E07V04 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005381/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan NIQE 3 LoP Area Witel Sulteng dan Sulut Malut | 2022-08-04 | 2022-12-01 | NIQE | MANADO | TONDANO |  | R7 MDO TDN NIQE LANGOAN - TONDANO |  | 20 | 0 | 0 | Preparing | 2022-08-04 | 2022-12-01 | [5 empty] | 401224440 | 63977955 | 465202395 | 0 | 4500474304 |  |  |  |  | PERKONSUMA
G2022185 | 0 | 8 | 01E07V04 | 007 | 72030058 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005381/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan NIQE 3 LoP Area Witel Sulteng dan Sulut Malut | 2022-08-04 | 2022-12-01 | NIQE | PALU | PALU |  | R7 PAL PLA NIQE PALU - DONGGALA |  | 20 | 0 | 0 | Preparing | 2022-08-04 | 2022-12-01 | [5 empty] | 710343720 | 1179157424 | 1889501144 | 0 | 4500474304 |  |  |  |  | PERKONSUMA
G2022186 | 0 | 7 | 01E07J04 | 007 | 72080075 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005408/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 2 LoP Area Witel Makassar - PT. BAKTI SARANA PRATAMA | 2022-08-04 | 2022-10-02 | FIMO NODE-B 2022 | UJUNGPANDANG | MALINO |  | R7 MKS MAL SNS339 |  | 0 | 0 | 0 | Preparing | [7 empty] | 34313511 | 7618900 | 41932411 | 0 | 4500474397 |  |  |  |  | BAKTI SARANA PRATAMA
G2022186 | 0 | 8 | 01E07J04 | 007 | 72080075 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005408/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 2 LoP Area Witel Makassar - PT. BAKTI SARANA PRATAMA | 2022-08-04 | 2022-10-02 | FIMO NODE-B 2022 | UJUNGPANDANG | MALINO |  | R7 MKS MAL SNS233 |  | 0 | 0 | 0 | Preparing | [7 empty] | 165449296 | 47019864 | 212469160 | 0 | 4500474397 |  |  |  |  | BAKTI SARANA PRATAMA
G2022188 | 0 | 8 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.005581/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS 2 LOP Tahun 2022 Witel Sulselbar | 2022-08-09 | 2022-09-07 | LME HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM DINAS KOMINFO BPBD TORAJA |  | 0 | 0 | 0 | Preparing | [7 empty] | 15872925 | 2942734 | 18815659 | 0 | 4500474783 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022188 | 0 | 7 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.005581/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS 2 LOP Tahun 2022 Witel Sulselbar | 2022-08-09 | 2022-09-07 | LME HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM RUJAB SEKDA & DISHUB |  | 0 | 0 | 0 | Preparing | [7 empty] | 19160216 | 5052416 | 24212632 | 0 | 4500474783 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022192 | 0 | 11 | 01E07O02 | 007 | 72030013 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.005641/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 2 LOP WITEL SULTENG | 2022-08-11 | 2022-09-09 | FIMO NODE-B 2022 | PALU | BUOL |  | ODC-BUO-FA - COI961 COMBAT BUOL |  | 0 | 0 | 0 | Preparing | [7 empty] | 18798863 | 4344908 | 23143771 | 0 | 4500475060 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022192 | 0 | 10 | 01E07O02 | 007 | 72030102 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.005641/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 2 LOP WITEL SULTENG | 2022-08-11 | 2022-09-09 | FIMO NODE-B 2022 | PALU | LUWUK |  | ODC-LWU-FQ - LWK152 PST MCP KOMPO LUWUK |  | 0 | 0 | 0 | Preparing | [7 empty] | 11453516 | 4357478 | 15810994 | 0 | 4500475060 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022193 | 0 | 10 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005657/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 2 LOP STO Sudiang Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT2 ODC-SUD-FAG DS2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 22483876 | 3817899 | 26301775 | 0 | 4500475077 |  |  |  |  | SIPAKALEBBI 2
G2022193 | 0 | 9 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005657/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 2 LOP STO Sudiang Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT2 DS-SUD-FE-13-01-02/03 |  | 0 | 0 | 0 | Preparing | [7 empty] | 11733176 | 2792827 | 14526003 | 0 | 4500475077 |  |  |  |  | SIPAKALEBBI 2
G2022194 | 0 | 9 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005658/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 2A 2 LOP Area Witel Sultra | 2022-08-11 | 2022-09-24 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 DEWI BUNGA LAND NANGA2 |  | 20 | 0 | 0 | Preparing | 2022-08-11 | 2022-09-24 | [5 empty] | 95867361 | 18782629 | 114649990 | 0 | 4500475031 |  |  |  |  | INNANDA INDAH
G2022194 | 0 | 8 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005658/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 2A 2 LOP Area Witel Sultra | 2022-08-11 | 2022-09-24 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 MARGAHAYU KAMBU |  | 20 | 0 | 0 | Preparing | 2022-08-11 | 2022-09-24 | [5 empty] | 106342855 | 18848270 | 125191125 | 0 | 4500475031 |  |  |  |  | INNANDA INDAH
G2022195 | 0 | 12 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | ISIMU |  | R7 GTO ISM PT2 ALO BUHU |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 11 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | ISIMU |  | R7 GTO ISM PT2 TRANS SULAWESI MALEO (FAV) |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 13 | 01E07V01 | 007 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | LIMBOTO |  | R7 GTO LBT PT2 BONGOHULAWA |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 14 | 01E07V01 | 007 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | LIMBOTO |  | R7 GTO LBT PT2 TRANS SULAWESI TUNGGULO |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 8 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT2 DESA SIPANA |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 9 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT2 SULTAN AMAI |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 7 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT2 BALOBALONGE |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 10 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT2 TRANS SULAWESI MALEO |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 15 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | TELAGA |  | R7 GTO TLG PT2 BUNGGALO (1) |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022195 | 0 | 16 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005659/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan PT-2 Periode Juni 2022 Area Witel Gorontalo | 2022-08-11 | 2022-09-09 | OSP FO FTTH PT2 2022 | GORONTALO | TELAGA |  | R7 GTO TLG PT2 BUNGGALO (2) |  | 0 | 0 | 0 | Preparing | [7 empty] | 1722832 | 250972 | 1973804 | 0 | 4500475075 |  |  |  |  | TELKOM AKSES
G2022197 | 0 | 7 | 01E07R03 | 007 | 72010060 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.005668/HK.810/R7W-7F100000/2022 | PENGADAAN & PEMASANGAN OSP FO PT2 17 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-08-12 | 2022-09-25 | OSP FO FTTH PT2 2022 | MANADO | MANADO |  |  |  | 50 | 0 | 0 | Preparing | 2022-08-12 | 2022-09-25 | [5 empty] | 250949415 | 55269441 | 306218856 | 0 | 4500473438 |  |  |  |  | TELKOM AKSES
G2022199 | 0 | 7 | 01E07J04 | 007 | 72081020 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005681/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 2 LOP Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MAKASSAR |  |  |  | 50 | 0 | 0 | Preparing | 2022-08-12 | 2022-09-10 | [5 empty] | 86747964 | 15509786 | 102257750 | 0 | 4500475138 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022200 | 0 | 7 | 01E07V01 | 007 | 72081020 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005682/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 Tahap 2 3 LOP Area Witel Sultra | 2022-08-12 | 2022-10-10 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | MAKASSAR |  |  |  | 50 | 0 | 0 | Preparing | 2022-08-12 | 2022-10-10 | [5 empty] | 356056882 | 73251604 | 429308486 | 0 | 4500475128 |  |  |  |  | TELKOM AKSES
G2022202 | 0 | 7 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 MILDASI |  | 0 | 0 | 0 | Preparing | [7 empty] | 3333993 | 658980 | 3992973 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 8 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 Muh Alfurqan R S |  | 0 | 0 | 0 | Preparing | [7 empty] | 3333993 | 658980 | 3992973 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 9 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 WAHYUNI |  | 0 | 0 | 0 | Preparing | [7 empty] | 5376572 | 967887 | 6344459 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 10 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 Corry Lau |  | 0 | 0 | 0 | Preparing | [7 empty] | 3880322 | 576676 | 4456998 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 11 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 INDRI SARTI |  | 0 | 0 | 0 | Preparing | [7 empty] | 8616049 | 1762147 | 10378196 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 12 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 Rahman |  | 0 | 0 | 0 | Preparing | [7 empty] | 4222346 | 453015 | 4675361 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 15 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 guest house mars PT2-SUG-SYATHIRA NAHARUDDIN MYIRX-1646953369051 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3333993 | 658980 | 3992973 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 16 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 WILIANDY PHILANTHROPY |  | 0 | 0 | 0 | Preparing | [7 empty] | 3304496 | 476339 | 3780835 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 17 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 Muh Anjas asmara |  | 0 | 0 | 0 | Preparing | [7 empty] | 23806555 | 6036474 | 29843029 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 18 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 NURUL FITRIANI |  | 0 | 0 | 0 | Preparing | [7 empty] | 4430446 | 746701 | 5177147 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 19 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 jamaluddin |  | 0 | 0 | 0 | Preparing | [7 empty] | 4775760 | 865836 | 5641596 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 13 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 IFAN PNK |  | 0 | 0 | 0 | Preparing | [7 empty] | 3948423 | 873873 | 4822296 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022202 | 0 | 14 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.005684/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 13 LOP STO BAL-MAT Area Witel Makassar - PT. BAGAMAS PRIMA TEKNIK | 2022-08-12 | 2022-09-10 | OSP FO FTTH PT2 2022 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 JOELRICHARDO PASOLORAN |  | 0 | 0 | 0 | Preparing | [7 empty] | 3333993 | 658980 | 3992973 | 0 | 4500475156 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022205 | 0 | 9 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 JL MANOKWARI SP5 |  | 0 | 0 | 0 | Preparing | [7 empty] | 216081783 | 61730809 | 277812592 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 8 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 DEPAN BANDARA STENGKOL |  | 0 | 0 | 0 | Preparing | [7 empty] | 25084881 | 8661702 | 33746583 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 7 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 PASAR SENTRAL |  | 0 | 0 | 0 | Preparing | [7 empty] | 245832349 | 57084128 | 302916477 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 10 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 JL TRANSITO WOSI |  | 0 | 0 | 0 | Preparing | [7 empty] | 223574590 | 57623770 | 281198360 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 19 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR FE WOSI |  | 0 | 0 | 0 | Preparing | [7 empty] | 262833057 | 77367983 | 340201040 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 11 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 JL NANGKA |  | 0 | 0 | 0 | Preparing | [7 empty] | 90699989 | 26360027 | 117060016 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 12 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 BOROBUDUR STORE |  | 0 | 0 | 0 | Preparing | [7 empty] | 72713759 | 22179820 | 94893579 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 13 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 YOS SUDARSO |  | 0 | 0 | 0 | Preparing | [7 empty] | 62497452 | 18009500 | 80506952 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 14 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 JL S CONDRONEGORO |  | 0 | 0 | 0 | Preparing | [7 empty] | 174361190 | 49398117 | 223759307 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 15 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 JL DRS ESAU SESA |  | 0 | 0 | 0 | Preparing | [7 empty] | 175454868 | 45994509 | 221449377 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 16 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 BELAKANG BANDARA |  | 0 | 0 | 0 | Preparing | [7 empty] | 199613557 | 54582126 | 254195683 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 17 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 GG NUSANTARA |  | 0 | 0 | 0 | Preparing | [7 empty] | 148315961 | 39445112 | 187761073 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022205 | 0 | 18 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005689/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH BATCH 2A 13 LoP Area Witel Papua Barat | 2022-08-12 | 2022-11-09 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 JL PASIR PUTIH |  | 0 | 0 | 0 | Preparing | [7 empty] | 153879646 | 41631776 | 195511422 | 0 | 4500475161 |  |  |  |  | TRANSDATA SATKOMINDO
G2022207 | 0 | 10 | 01E07V01 | 007 | 74060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005691/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH PT3 2 LoP Area Witel Papua Barat | 2022-08-12 | 2022-10-10 | OSP FO FTTH PT3 2022 | SORONG | TEMINABUAN |  | R7 SON TMB PT3 RSUD SCHOLOO KEYEN |  | 0 | 0 | 0 | Preparing | [7 empty] | 285533439 | 64661540 | 350194979 | 0 | 4500475163 |  |  |  |  | TELKOM AKSES
G2022207 | 0 | 9 | 01E07V01 | 007 | 74060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005691/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH PT3 2 LoP Area Witel Papua Barat | 2022-08-12 | 2022-10-10 | OSP FO FTTH PT3 2022 | SORONG | TEMINABUAN |  | R7 SON TMB PT3 KEYEN |  | 0 | 0 | 0 | Preparing | [7 empty] | 88641472 | 22440662 | 111082134 | 0 | 4500475163 |  |  |  |  | TELKOM AKSES