## Nilai
KD_KONTRAK | NO_AMDKE | KD_WBS | KD_SGRUP | PK_OWNER | KD_LOKASI1 | UBIS_WASLAK | UNIT_WASLAK | WASLAK_HAR | UBIS_OWNER | NO_KONTRAK | NM_PROYEK | TG_EDC | TG_TOC | NM_TEMATIK | NM_WITEL | NM_LOKASI1 | PROJECT_SITE_ID | KT_LOKASI | SITE_ALAMAT | PRO_PLAN | PRO_ACTUAL | PRO_BAST | STATUS | TG_PLAN_START | TG_PLAN_FINISH | TG_ACTUAL_START | NO_UT | TG_UT | NO_BAST1 | TG_BAUT | NI_BARANG | NI_JASA | NI_KONTRAK | NI_BAST1 | NO_PO1 | NO_PO2 | NO_PO3 | NO_PO4 | NO_PO5 | NM_VENDOR | TG_BAST1
12016185 | 41 | 78 | 01C11H01 | 019 | 74010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | BIAK | BMH SUPIORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-30 | 2022-04-30 | 2021-01-25 | TEL.3472/LG.310/PND-B1060000/2021 | 2021-12-07 | TEL.0249/LG.320/DID-A0000000/2021 | 2021-12-07 | 88346064 | 266610076 | 354956140 | 354956140 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2021-12-29
12016185 | 41 | 79 | 01C11H01 | 019 | 74010059 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | BIAK | CLS SUPIORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-30 | 2022-04-30 | 2021-01-25 | TEL.3472/LG.310/PND-B1060000/2021 | 2021-12-07 | TEL.0249/LG.320/DID-A0000000/2021 | 2021-12-07 | 6377859917 | 5691624036 | 12069483953 | 12069483953 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2021-12-29
12016185 | 41 | 82 | 01C11H01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | MANOKWARI | MANOKWARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-30 | 2022-07-26 | 2020-09-30 | TEL.1901/LG.310/DID-B0400000/2022 | 2022-07-04 | TEL.1001/LG.320/DID-A0000000/2022 | 2022-07-04 | 371766334 | 399352706 | 771119040 | 771119040 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2022-07-22
12016185 | 41 | 80 | 01C11H01 | 019 | 74060055 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | BMH WAISAI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-30 | 2022-04-30 | 2021-01-25 | TEL.3472/LG.310/PND-B1060000/2021 | 2021-12-07 | TEL.0249/LG.320/DID-A0000000/2021 | 2021-12-07 | 646910516 | 871979127 | 1518889643 | 1518889643 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2021-12-29
12016185 | 41 | 55 | 01C11H01 | 019 | 74060087 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | BU.01 |  |  |  | 60 | 0 | 0 | Preparing | 2020-09-30 | 2022-10-20 | [5 empty] | 32499158263 | 17254047219 | 49753205482 | 0 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION
12016185 | 41 | 56 | 01C11H01 | 019 | 74060087 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | BU.01 |  |  |  | 60 | 0 | 0 | Preparing | 2020-09-30 | 2022-10-20 | [5 empty] | 17725666015 | 22077945379 | 39803611394 | 0 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION
12016185 | 41 | 57 | 01C11H01 | 019 | 74060088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | BU.02 |  |  |  | 60 | 0 | 0 | Preparing | 2020-09-30 | 2022-10-20 | [5 empty] | 48689856665 | 19375585635 | 68065442300 | 0 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION
12016185 | 41 | 65 | 01C11H01 | 019 | 74060088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | BU.02 |  |  |  | 60 | 0 | 0 | Preparing | 2020-09-30 | 2022-10-20 | [5 empty] | 74604771927 | 77409086451 | 152013858378 | 0 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION
12016185 | 41 | 84 | 01C11H01 | 019 | 74060052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | WAISAI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-30 | 2022-07-29 | 2020-09-30 | TEL.1901/LG.310/DID-B0400000/2022 | 2022-07-04 | TEL.1001/LG.320/DID-A0000000/2022 | 2022-07-04 | 357603355 | 373549480 | 731152835 | 731152835 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2022-07-22
12016185 | 41 | 54 | 01C11H01 | 019 | 74060052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | SORONG | WAISAI |  |  |  | 60 | 0 | 0 | Preparing | 2020-09-30 | 2022-10-20 | [5 empty] | 71860502605 | 62572427424 | 134432930029 | 0 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION
12016185 | 41 | 9 | 01C11H01 | 019 | 72080455 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | UJUNGPANDANG | 411-BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2016-05-12 | 2018-04-08 | 2016-06-21 | TEL.252/LG.232/PND-A1000000/2018 | 2018-03-07 | TEL.0528/LG.320/PND-A1000000/2018 | 2018-03-07 | 308513588669 | 131663703817 | 440177292486 | 440177292486 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2018-06-10
12016185 | 41 | 67 | 01C11H01 | 019 | 72081029 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | UJUNGPANDANG | DEPO KABEL MAKASSAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-30 | 2022-04-30 | 2021-01-25 | TEL.3654/LG.310/PND-B1060000/2021 | 2021-12-29 | TEL.0422/LG.320/DID-A0000000/2021 | 2021-12-29 | 25999459200 | 11350000000 | 37349459200 | 37349459200 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2021-12-31
12016185 | 41 | 22 | 01C11H01 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.145/HK.810/UTA-00/2016 | SKKL IGG | 2016-05-12 | 2022-10-20 | SKKL | UJUNGPANDANG | MAKASAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2016-05-12 | 2018-09-05 | 2016-06-21 | TEL.1058/LG.310/PND-B1060000/2018 | 2018-08-15 | TEL.0762/LG.320/PND-A1000000/2018 | 2018-08-15 | 8165548138 | 8355156469 | 16520704607 | 16520704607 | 4500322396 | 4500322417 |  |  |  | NEC CORPORATION | 2018-09-10
12019032 | 41 | 860 | 01C11I04 | 019 | 73010013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | BULA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 851 | 01C11I04 | 019 | 73010013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | BULA |  | STO BULA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2020-03-16 | LAMPIRAN_STO_BULA_1 | 2020-03-16 | TEL.0926/LG.320/PND-A1000000/2021 | 2020-03-16 | 1715985 | 0 | 1715985 | 1715985 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-07-30
12019032 | 41 | 992 | 01C11I04 | 019 | 73010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | LARAT |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 861 | 01C11I04 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | MASOHI |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 853 | 01C11I04 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | MASOHI |  | STO MASOHI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2020-03-16 | LAMPIRAN_STO_MASOHI_1 | 2020-03-16 | TEL.0926/LG.320/PND-A1000000/2021 | 2020-03-16 | 13061250 | 0 | 13061250 | 13061250 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-07-30
12019032 | 41 | 993 | 01C11I04 | 019 | 73010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | NAMROLE |  | Kab. Buru Selatan |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 852 | 01C11I04 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | PASSO |  | STO PASSO REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2020-03-16 | LAMPIRAN_STO_PASSO_1 | 2020-03-16 | TEL.0926/LG.320/PND-A1000000/2021 | 2020-03-16 | 19163385 | 0 | 19163385 | 19163385 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-07-30
12019032 | 41 | 862 | 01C11I04 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | PASSO |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 994 | 01C11I04 | 019 | 73010071 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | SAPARUA |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 863 | 01C11I04 | 019 | 73010089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | WAHAI |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 850 | 01C11I04 | 019 | 73010089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | AMBON | WAHAI |  | STO WAHAI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2020-03-16 | LAMPIRAN_STO_WAHAI_1 | 2020-03-16 | TEL.0926/LG.320/PND-A1000000/2021 | 2020-03-16 | 3511350 | 0 | 3511350 | 3511350 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-07-30
12019032 | 41 | 1025 | 01C11I04 | 019 | 74020007 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | FAK-FAK | KAIMANA |  | Kab. Kaimana |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 995 | 01C11I04 | 019 | 72020023 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | GORONTALO | LIMBOTO |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 996 | 01C11I04 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | GORONTALO | MARISA |  | Kab Pohuwato |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 997 | 01C11I04 | 019 | 72020038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | GORONTALO | TELAGA |  | Kab Pohuwato |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 998 | 01C11I04 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | JAYAPURA | AGATS |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 999 | 01C11I04 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | JAYAPURA | SARMI |  | Kab Sarmi |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 645 | 01C11I04 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | KOLAKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_KOLAKA_1 | 2020-04-02 | TEL.0410/LG.320/PND-A1000000/2020 | 2020-04-02 | 42542334 | 0 | 42542334 | 42542334 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-28
12019032 | 41 | 651 | 01C11I04 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | KOLAKA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 646 | 01C11I04 | 019 | 72050050 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | POMALAA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_POMALAA_1 | 2020-04-02 | TEL.0456/LG.320/PND-A1000000/2020 | 2020-04-02 | 12775077 | 0 | 12775077 | 12775077 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-29
12019032 | 41 | 657 | 01C11I04 | 019 | 72050050 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | POMALAA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 647 | 01C11I04 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | RAHA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_RAHA_1 | 2020-04-02 | TEL.0468/LG.320/PND-A1000000/2020 | 2020-04-02 | 34520985 | 0 | 34520985 | 34520985 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 658 | 01C11I04 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | RAHA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 648 | 01C11I04 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | UNAAHA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_UNAHAA_1 | 2020-04-02 | TEL.0473/LG.320/PND-A1000000/2020 | 2020-04-02 | 24218838 | 0 | 24218838 | 24218838 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 662 | 01C11I04 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | UNAAHA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 663 | 01C11I04 | 019 | 72050074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | WANCI |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 649 | 01C11I04 | 019 | 72050074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | KENDARI | WANCI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_WANCI_1 | 2020-04-02 | TEL.0474/LG.320/PND-A1000000/2020 | 2020-04-02 | 64934460 | 0 | 64934460 | 64934460 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 1022 | 01C11I04 | 019 | 74040002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | MANOKWARI | BINTUNI |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1023 | 01C11I04 | 019 | 74040010 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | MANOKWARI | RANSIKI |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1024 | 01C11I04 | 019 | 74040016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | MANOKWARI | WARMARE |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1017 | 01C11I04 | 019 | 74050005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | MERAUKE | BADE |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1018 | 01C11I04 | 019 | 74050022 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | MERAUKE | TANAH MERAH |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 640 | 01C11I04 | 019 | 72030159 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | AMPANA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_AMPANA_1 | 2020-04-02 | TEL.0406/LG.320/PND-A1000000/2020 | 2020-04-02 | 49286070 | 0 | 49286070 | 49286070 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-28
12019032 | 41 | 650 | 01C11I04 | 019 | 72030159 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | AMPANA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1006 | 01C11I04 | 019 | 72030012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | BUNGKU |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 686 | 01C11I04 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | KOTARAYA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 685 | 01C11I04 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | KOTARAYA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2021-01-14 | 2020-05-12 | LAMPIRAN_STO_KOTARAYA_1 | 2020-05-12 | TEL.0612/LG.320/PND-A1000000/2020 | 2020-05-12 | 25323030 | 0 | 25323030 | 25323030 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-06-03
12019032 | 41 | 655 | 01C11I04 | 019 | 72030050 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | MOUTONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_MOUTONG_1 | 2020-04-02 | TEL.0458/LG.320/PND-A1000000/2020 | 2020-04-02 | 441045 | 0 | 441045 | 441045 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-29
12019032 | 41 | 643 | 01C11I04 | 019 | 72030050 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | MOUTONG |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1007 | 01C11I04 | 019 | 72030125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | PAGIMANA |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 656 | 01C11I04 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | PARIGI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_PARIGI_1 | 2020-04-02 | TEL.0467/LG.320/PND-A1000000/2020 | 2020-04-02 | 8374590 | 0 | 8374590 | 8374590 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 641 | 01C11I04 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | PARIGI |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 642 | 01C11I04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | TAWAELI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_TAWAELI_1 | 2020-04-02 | TEL.0471/LG.320/PND-A1000000/2020 | 2020-04-02 | 70753905 | 0 | 70753905 | 70753905 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 660 | 01C11I04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | TAWAELI |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 661 | 01C11I04 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | TENTENA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 644 | 01C11I04 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | TENTENA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_TENTENA_1 | 2020-04-02 | TEL.0472/LG.320/PND-A1000000/2020 | 2020-04-02 | 6867180 | 0 | 6867180 | 6867180 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 707 | 01C11I04 | 019 | 72030083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | TOLAY |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 706 | 01C11I04 | 019 | 72030083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PALU | TOLAY |  | STO TOLAY REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2021-01-14 | 2019-08-20 | LAMPIRAN_STO_TOLAY_1 | 2019-08-20 | TEL.0953/LG.320/PND-A1000000/2020 | 2019-08-20 | 448335 | 0 | 448335 | 448335 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-08-24
12019032 | 41 | 1008 | 01C11I04 | 019 | 72040275 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | AJANGALE |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1036 | 01C11I04 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | ENREKANG |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1009 | 01C11I04 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | ENREKANG |  | STO ENREKANG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2021-04-10 | LAMPIRAN_STO_ENREKANG_1 | 2021-04-10 | TEL.0136/LG.320/DID-00000000/2021 | 2021-04-10 | 14904000 | 0 | 14904000 | 14904000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-09-10
12019032 | 41 | 652 | 01C11I04 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MAJENE |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 636 | 01C11I04 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MAJENE |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_MAJENE_1 | 2020-04-02 | TEL.0461/LG.320/PND-A1000000/2020 | 2020-04-02 | 195302340 | 0 | 195302340 | 195302340 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-29
12019032 | 41 | 1143 | 01C11I04 | 019 | 72040082 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MALILI |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1010 | 01C11I04 | 019 | 72040082 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MALILI |  | STO MALILI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-07-14 | 2022-03-30 | LAMPIRAN_STO_MALILI_1 | 2022-03-30 | TEL.0839/LG.320/DID-A0000000/2022 | 2022-03-30 | 17546500 | 0 | 17546500 | 17546500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2022-06-29
12019032 | 41 | 653 | 01C11I04 | 019 | 72040086 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MAMASA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_MAMASA_1 | 2020-04-02 | TEL.0460/LG.320/PND-A1000000/2020 | 2020-04-02 | 39366000 | 0 | 39366000 | 39366000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-29
12019032 | 41 | 637 | 01C11I04 | 019 | 72040086 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MAMASA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 638 | 01C11I04 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MAMUJU |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 654 | 01C11I04 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | MAMUJU |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_MAMUJU_1 | 2020-04-02 | TEL.0459/LG.320/PND-A1000000/2020 | 2020-04-02 | 29447145 | 0 | 29447145 | 29447145 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-29
12019032 | 41 | 1021 | 01C11I04 | 019 | 72040274 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | PATILI |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 659 | 01C11I04 | 019 | 72040160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | SIWA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 639 | 01C11I04 | 019 | 72040160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | SIWA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2020-01-18 | 2020-04-02 | BA_PEMBONGKARAN_STO_SIWA_1 | 2020-04-02 | TEL.0470/LG.320/PND-A1000000/2020 | 2020-04-02 | 37974825 | 0 | 37974825 | 37974825 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-04-30
12019032 | 41 | 1037 | 01C11I04 | 019 | 72040174 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | TANRUTEDONG |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1011 | 01C11I04 | 019 | 72040174 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | TANRUTEDONG |  | STO TANRUTEDONG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2021-04-10 | LAMPIRAN_STO_TANRUTEDONG_1 | 2021-04-10 | TEL.0136/LG.320/DID-00000000/2021 | 2021-04-10 | 9909135 | 0 | 9909135 | 9909135 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-09-10
12019032 | 41 | 1012 | 01C11I04 | 019 | 72040186 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | WATANSOPPENG |  | STO WATANSOPPENG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2021-04-08 | LAMPIRAN_STO_WATANSOPPENG_1 | 2021-04-08 | TEL.0136/LG.320/DID-00000000/2021 | 2021-04-10 | 503355060 | 0 | 503355060 | 503355060 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-09-10
12019032 | 41 | 1038 | 01C11I04 | 019 | 72040186 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | WATANSOPPENG |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1013 | 01C11I04 | 019 | 72040187 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | WONOMULYO |  | STO WONOMULYO REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-01-14 | 2020-09-01 | LAMPIRAN_STO_WONOMULYO_1 | 2020-09-01 | TEL.0510/LG.320/DID-00000000/2021 | 2020-09-01 | 377168000 | 0 | 377168000 | 377168000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-10-30
12019032 | 41 | 1067 | 01C11I04 | 019 | 72040187 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | PARE-PARE | WONOMULYO |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1014 | 01C11I04 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | SORONG | SERUI |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1015 | 01C11I04 | 019 | 74060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | SORONG | TEMINABUAN |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1020 | 01C11I04 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | TERNATE | WEDA |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1000 | 01C11I04 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | ANTANG |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1001 | 01C11I04 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | BALAIKOTA |  | STO BALAIKOTA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-07-14 | 2021-11-01 | LAMPIRAN_STO_BALAIKOTA_1 | 2021-11-01 | TEL.0081/LG.320/DID-A0000000/2022 | 2021-11-01 | 26933000 | 0 | 26933000 | 26933000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2022-02-22
12019032 | 41 | 1108 | 01C11I04 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | BALAIKOTA |  | Duplikat Ke-1 |  | 90 | 0 |  | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1002 | 01C11I04 | 019 | 72080064 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | KIMA |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1019 | 01C11I04 | 019 | 72080075 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | MALINO |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1109 | 01C11I04 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | PANAKUKANG |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1003 | 01C11I04 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | PANAKUKANG |  | STO PANAKUKANG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-03-26 | 2022-07-14 | 2021-11-01 | LAMPIRAN_STO_PANAKUKANG_1 | 2021-11-01 | TEL.0081/LG.320/DID-A0000000/2022 | 2021-11-01 | 82358500 | 0 | 82358500 | 82358500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2022-02-22
12019032 | 41 | 1004 | 01C11I04 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | SUDIANG |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019032 | 41 | 1005 | 01C11I04 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000624/HK.810/OPS-10000000/2019 | SP#2 Granular Modernization - Dismantling Kabel Tembaga Primer dan Barang Scrap Shutdown STO | 2019-03-26 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | TAMALANREA |  |  |  | 90 | 0 | 0 | Preparing | 2019-03-26 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019087 | 11 | 64 | 01E07V01 | 019 | 73010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | AMBON | NAMROLE |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1432/LG.310/DR7-12700000/2019 | 2019-10-16 | TEL.1578/LG.320/PND-A1000000/2019 | 2019-10-17 | 148542160 | 24393384 | 172935544 | 172935544 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 66 | 01E07V01 | 019 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | AMBON | PIRU |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1433/LG.310/DR7-12700000/2019 | 2019-10-17 | TEL.1578/LG.320/PND-A1000000/2019 | 2019-10-17 | 149383802 | 24903817 | 174287619 | 174287619 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 68 | 01E07V01 | 019 | 74030034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | JAYAPURA | JAYAPURA-2 |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1431/LG.310/DR7-12700000/2019 | 2019-09-26 | TEL.1580/LG.320/PND-A1000000/2019 | 2019-09-26 | 186085669 | 25719422 | 211805091 | 211805091 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 666 | 01E07V01 | 019 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | KENDARI | BAU-BAU |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-11-11 | 2020-02-20 | 2019-11-08 | TEL.2533/LG.310/DR7-12700000/2019 | 2020-01-23 | TEL.0305/LG.320/PND-A1000000/2020 | 2020-01-23 | 199460636 | 2521174 | 201981810 | 201981810 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 664 | 01E07V01 | 019 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | KENDARI | KENDARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-11-11 | 2020-02-20 | 2019-11-08 | TEL.2534/LG.310/DR7-12700000/2019 | 2020-01-23 | TEL.0305/LG.320/PND-A1000000/2020 | 2020-01-23 | 202776956 | 3982114 | 206759070 | 206759070 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 665 | 01E07V01 | 019 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | KENDARI | MANDONGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-11-11 | 2020-02-20 | 2019-11-08 | TEL.2535/LG.310/DR7-12700000/2019 | 2020-01-23 | TEL.0305/LG.320/PND-A1000000/2020 | 2020-01-23 | 199693484 | 2605308 | 202298792 | 202298792 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 53 | 01E07V01 | 019 | 72010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | MANADO | MANADO CENTRUM |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.2540/LG.310/DR7-12700000/2019 | 2019-12-10 | TEL.0290/LG.320/PND-A1000000/2020 | 2019-12-10 | 29030576 | 6744906 | 35775482 | 35775482 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 58 | 01E07V01 | 019 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | PALU | BUOL |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1438/LG.310/DR7-12700000/2019 | 2019-11-13 | TEL.1575/LG.320/PND-A1000000/2019 | 2019-11-14 | 161125538 | 21250598 | 182376136 | 182376136 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 59 | 01E07V01 | 019 | 72030050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | PALU | MOUTONG |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1439/LG.310/DR7-12700000/2019 | 2019-11-14 | TEL.1575/LG.320/PND-A1000000/2019 | 2019-11-14 | 144159732 | 14637167 | 158796899 | 158796899 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 60 | 01E07V01 | 019 | 72040086 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | PARE-PARE | MAMASA |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1436/LG.310/DR7-12700000/2019 | 2019-10-28 | TEL.1576/LG.320/PND-A1000000/2019 | 2019-10-28 | 179533760 | 22761271 | 202295031 | 202295031 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 62 | 01E07V01 | 019 | 72040135 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | PARE-PARE | RAPPANG |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1435/LG.310/DR7-12700000/2019 | 2019-10-17 | TEL.1576/LG.320/PND-A1000000/2019 | 2019-10-28 | 164778723 | 22173653 | 186952376 | 186952376 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 61 | 01E07V01 | 019 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | PARE-PARE | TANRUTEDONG |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1434/LG.310/DR7-12700000/2019 | 2019-10-17 | TEL.1576/LG.320/PND-A1000000/2019 | 2019-10-28 | 164723687 | 22173653 | 186897340 | 186897340 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 70 | 01E07V01 | 019 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | SORONG | SERUI |  | NEW FTM |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-27 | 2019-08-16 | TEL.1437/LG.310/DR7-12700000/2019 | 2019-11-07 | TEL.1577/LG.320/PND-A1000000/2019 | 2019-11-07 | 166327000 | 18960998 | 185287998 | 185287998 | 4500384477 |  |  |  |  | BANGTELINDO | 2019-12-11
12019087 | 11 | 612 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | UJUNGPANDANG | PANAKUKANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-15 | 2019-08-16 | TEL.2538/LG.310/DR7-12700000/2019 | 2019-11-13 | TEL.0298/LG.320/PND-A1000000/2020 | 2019-11-15 | 601837028 | 151176842 | 753013870 | 753013870 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 614 | 01E07V01 | 019 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | UJUNGPANDANG | SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-15 | 2019-08-16 | TEL.2536/LG.310/DR7-12700000/2019 | 2019-11-13 | TEL.0298/LG.320/PND-A1000000/2020 | 2019-11-15 | 334598009 | 56366589 | 390964598 | 390964598 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 615 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | UJUNGPANDANG | TAMALANREA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-15 | 2019-08-16 | TEL.2537/LG.310/DR7-12700000/2019 | 2019-11-14 | TEL.0298/LG.320/PND-A1000000/2020 | 2019-11-15 | 283601427 | 52683110 | 336284537 | 336284537 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019087 | 11 | 613 | 01E07V01 | 019 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002069/HK.810/OPS-10040000/2019 | Pengadaan dan Pemasangan FTM Tahap-1 | 2019-05-10 | 2020-04-02 | FTM | UJUNGPANDANG | WATAMPONE |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-16 | 2019-12-15 | 2019-08-16 | TEL.2539/LG.310/DR7-12700000/2019 | 2019-11-15 | TEL.0298/LG.320/PND-A1000000/2020 | 2019-11-15 | 50767476 | 5415302 | 56182778 | 56182778 | 4500384477 |  |  |  |  | BANGTELINDO | 2020-03-28
12019116 | 33 | 46 | 01C11H02 | 019 | 74020043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | FAK-FAK | ESANIA. |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2020-11-28 | 2019-05-28 | TEL.1949/LG.310/PND-B1060000/2020 | 2020-09-10 | TEL.1084/LG.320/PND-A1000000/2020 | 2020-09-10 | 1711437496 | 679871040 | 2391308536 | 2391308536 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2020-09-16
12019116 | 33 | 44 | 01C11H02 | 019 | 74020042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | FAK-FAK | MAAS |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2022-01-29 | 2019-05-28 | TEL.3691/LG.310/DID-B1060000/2021 | 2021-12-31 | TEL.0448/LG.320/DID-A0000000/2021 | 2021-12-31 | 2077880828 | 679871040 | 2757751868 | 2757751868 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2021-12-31
12019116 | 33 | 45 | 01C11H02 | 019 | 74020040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | FAK-FAK | PRIMA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2020-11-28 | 2019-05-28 | TEL.1950/LG.310/PND-B1060000/2020 | 2020-09-10 | TEL.1083/LG.320/PND-A1000000/2020 | 2020-09-10 | 1993880828 | 679871040 | 2673751868 | 2673751868 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2020-09-16
12019116 | 33 | 34 | 01C11H02 | 019 | 72050144 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | KENDARI | PUNGGALUKU |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2019-11-23 | 2019-05-28 | TEL.772/LG.310/PND-B1060000/2019 | 2019-08-09 | TEL.1152/LG.320/PND-A1000000/2019 | 2019-08-09 | 1655612682 | 595270572 | 2250883254 | 2250883254 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-09-26
12019116 | 33 | 38 | 01C11H02 | 019 | 74040002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | MANOKWARI | BINTUNI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2019-11-23 | 2019-05-28 | TEL.1194./LG.310/PND-B1060000/2019 | 2019-12-05 | TEL.1623/LG.320/PND-A1000000/2019 | 2019-12-05 | 7372649866 | 2719484160 | 10092134026 | 10092134026 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-12-17
12019116 | 33 | 40 | 01C11H02 | 019 | 74040034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | MANOKWARI | PINTU BATU |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2019-11-23 | 2019-05-28 | TEL.984/LG.310/PND-B1060000/2019 | 2019-10-07 | TEL.1372/LG.320/PND-A1000000/2019 | 2019-10-07 | 4075339337 | 3477498828 | 7552838165 | 7552838165 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-10-29
12019116 | 33 | 17 | 01C11H02 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | PALU | LUWUK |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2019-11-23 | 2019-05-28 | TEL.578/LG.310/PND-B1060000/2019 | 2019-06-17 | TEL.0841/LG.320/PND-A1000000/2019 | 2019-06-17 | 1876222148 | 1004674667 | 2880896815 | 2880896815 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-06-28
12019116 | 33 | 56 | 01C11H02 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | PALU | TOLI-TOLI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-05-28 | 2021-08-12 | 2019-05-28 | TEL.2141/LG.310/PND-B1060000/2021 | 2021-08-03 | TEL.0986/LG.320/PND-A1000000/2021 | 2021-08-03 | 6063857362 | 814199530 | 6878056892 | 6878056892 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2021-08-19
12019116 | 33 | 58 | 01C11I07 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002608/HK.810/OPS-10000000/2019 | SP#5 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-05-28 | 2022-07-23 | IP RADIO | AMBON | MASOHI |  |  |  | 100 | 20 | 0 | Preparing | 2021-05-31 | 2022-07-24 | 2019-05-28 |  |  |  |  | 9472170006 | 3434761512 | 12906931518 | 0 | 4500385252 |  |  |  |  | MULTIREKA PRIMA UTAMA
12019201 | 23 | 19 | 01C11H02 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-13 | 2020-02-08 | 2019-08-13 | TEL.1905/LG.310/PND-B1060000/2019 | 2019-11-20 | TEL.1549/LG.320/PND-A1000000/2019 | 2019-11-20 | 1136775652 | 280844086 | 1417619738 | 1417619738 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-12-02
12019201 | 23 | 12 | 01C11H02 | 019 | 74010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | BIAK | WAINDU DMT |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-13 | 2020-02-08 | 2019-08-13 | TEL.898/LG.310/PND-B1060000/2019 | 2019-09-12 | TEL.1296/LG.320/PND-A1000000/2019 | 2019-09-12 | 2308586060 | 1019806560 | 3328392620 | 3328392620 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-09-30
12019201 | 23 | 30 | 01C11H02 | 019 | 74030158 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | JAYAPURA | TSEL SP-3 |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-13 | 2020-12-28 | 2019-08-15 | TEL.3000/LG.310/PND-B1060000/2020 | 2020-12-24 | TEL.1911/LG.320/PND-A1000000/2020 | 2020-12-24 | 781497082 | 339935520 | 1121432602 | 1121432602 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2020-12-31
12019201 | 23 | 16 | 01C11H02 | 019 | 74040034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | MANOKWARI | PINTU BATU |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-08-13 | 2020-02-08 | 2019-08-13 | TEL.1006/LG.310/PND-B1060000/2019 | 2019-10-14 | TEL.1374/LG.320/PND-A1000000/2019 | 2019-10-14 | 591209800 | 1011306752 | 1602516552 | 1602516552 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2019-10-29
12019201 | 23 | 29 | 01C11I07 | 019 | 74030181 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | JAYAPURA | KTR. BUPATI DOGIYAI |  |  |  | 50 | 90 | 0 | Siap UT | 2019-08-13 | 2022-09-20 | 2019-08-13 |  |  |  |  | 0 | 679003776 | 679003776 | 0 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA
12019201 | 23 | 34 | 01C11I07 | 019 | 72010870 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | MANADO | DMT MELONGUANE |  |  |  | 35 | 50 | 0 | Mat. Delivery | 2019-08-13 | 2022-10-11 | 2019-08-13 |  |  |  |  | 811344578 | 204789586 | 1016134164 | 0 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA
12019201 | 23 | 35 | 01C11I07 | 019 | 72010872 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | MANADO | TSEL POHEYA |  |  |  | 35 | 50 | 0 | Mat. Delivery | 2019-08-13 | 2022-10-11 | 2019-08-13 |  |  |  |  | 811344578 | 202743982 | 1014088560 | 0 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA
12019201 | 23 | 28 | 01C11I07 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | SORONG | NABIRE |  |  |  | 50 | 90 | 0 | Siap UT | 2019-08-13 | 2022-10-27 | 2019-08-15 |  |  |  |  | 0 | 1810676736 | 1810676736 | 0 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA
12019201 | 23 | 46 | 01C11I07 | 019 | 73020013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004025/HK.810/OPS-10000000/2019 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-08-13 | 2022-12-20 | RADIO IP | TERNATE | LABUHA |  |  |  | 20 | 100 | 100 | BAST-1 | 2019-08-13 | 2022-12-21 | 2019-08-13 | TEL.1303/LG.310/DID-B1060000/2022 | 2022-07-13 | TEL.1080/LG.320/DID-A0000000/2022 | 2022-07-13 | 3169622580 | 1022536244 | 4192158824 | 4192158824 | 4500389153 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-07-29
12019321 | 44 | 315 | 01C11I04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | KENDARI | MANDONGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-11-12 | 2020-01-08 | 2020-05-12 | LAMPIRAN_STO_MANDONGA_1 | 2020-05-12 | TEL.0640/LG.320/PND-A1000000/2020 | 2020-05-12 | 31034340 | 0 | 31034340 | 31034340 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-06-05
12019321 | 44 | 316 | 01C11I04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | KENDARI | MANDONGA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019321 | 44 | 830 | 01C11I04 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | MANADO | AMURANG |  |  |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019321 | 44 | 831 | 01C11I04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | PALU | PALU-1 |  |  |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019321 | 44 | 379 | 01C11I04 | 019 | 72030093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | PALU | PALU-3 |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019321 | 44 | 378 | 01C11I04 | 019 | 72030093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | PALU | PALU-3 |  | STO PALU-3 REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-11-12 | 2021-01-14 | 2019-11-12 | LAMPIRAN_STO_PALU3_1 | 2019-11-12 | TEL.0957/LG.320/PND-A1000000/2020 | 2019-11-12 | 11752290 | 0 | 11752290 | 11752290 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-08-24
12019321 | 44 | 832 | 01C11I04 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | PALU | POSO |  |  |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019321 | 44 | 845 | 01C11I04 | 019 | 72040128 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | PARE-PARE | PINRANG |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019321 | 44 | 833 | 01C11I04 | 019 | 72040128 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | PARE-PARE | PINRANG |  | STO PINRANG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-11-12 | 2022-01-14 | 2021-04-06 | LAMPIRAN_STO_PINRANG_1 | 2021-04-06 | TEL.0140/LG.320/DID-00000000/2021 | 2021-04-06 | 743051475 | 0 | 743051475 | 743051475 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-09-10
12019321 | 44 | 489 | 01C11I04 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | SELAYAR |  | STO SELAYAR REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2019-11-12 | 2021-01-14 | 2020-01-21 | LAMPIRAN_STO_SELAYAR_1 | 2020-01-21 | TEL.1478/LG.320/PND-A1000000/2020 | 2020-01-21 | 27216000 | 0 | 27216000 | 27216000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-11-28
12019321 | 44 | 490 | 01C11I04 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006295/HK.810/OPS-10000000/2019 | SP#4 Granular Modernization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2019-11-12 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | SELAYAR |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2019-11-12 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12019376 | 23 | 140 | 01C11B03 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | JAYAPURA | ABEPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-08-04 | 2019-12-12 | TEL.1631/LG.310/PND-B1050000/2020 | 2020-07-08 | TEL.0848/LG.320/PND-A1000000/2020 | 2020-07-08 | 36075000 | 4387000 | 40462000 | 40462000 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-07-28
12019376 | 23 | 46 | 01C11B03 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-08-04 | 2019-12-12 | TEL.1631/LG.310/PND-B1050000/2020 | 2020-07-08 | TEL.0848/LG.320/PND-A1000000/2020 | 2020-07-08 | 72150000 | 8774000 | 80924000 | 80924000 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-07-28
12019376 | 23 | 125 | 01C11B03 | 019 | 74030028 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | JAYAPURA | JAYAPURA BASE G |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-06-08 | 2019-12-12 | TEL.705/LG.310/PND-B105000/2020 | 2020-03-23 | TEL.0318/LG.320/PND-A1000000/2020 | 2020-03-23 | 792502470 | 335627150 | 1128129620 | 1128129620 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-03-28
12019376 | 23 | 124 | 01C11B03 | 019 | 74030028 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | JAYAPURA | JAYAPURA BASE G |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-06-08 | 2019-12-12 | TEL.704/LG.310/PND-B105000/2020 | 2020-03-23 | TEL.0317/LG.320/PND-A1000000/2020 | 2020-03-23 | 704508640 | 73017340 | 777525980 | 777525980 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-03-28
12019376 | 23 | 225 | 01C11B03 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2021-08-20 | 2021-02-01 | TEL.1311/LG.310/PND-B1050000/2021 | 2021-08-10 | TEL.0102/LG.320/DID-00000000/2021 | 2021-08-10 | 797500000 | 103701400 | 901201400 | 901201400 | 4500396693 |  |  |  |  | PINS INDONESIA | 2021-08-31
12019376 | 23 | 92 | 01C11B03 | 019 | 72030167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | PALU | MOROWALI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2021-07-15 | 2021-06-01 | TEL.979/LG.310/PND-B1050000/2021 | 2021-06-23 | TEL.0841/LG.320/PND-A1000000/2021 | 2021-06-23 | 2290007750 | 286161815 | 2576169565 | 2576169565 | 4500396693 |  |  |  |  | PINS INDONESIA | 2021-07-01
12019376 | 23 | 45 | 01C11B03 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | TERNATE | TERNATE |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-08-04 | 2019-12-12 | TEL.1631/LG.310/PND-B1050000/2020 | 2020-07-08 | TEL.0848/LG.320/PND-A1000000/2020 | 2020-07-08 | 72150000 | 8774000 | 80924000 | 80924000 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-07-28
12019376 | 23 | 74 | 01C11B03 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | TERNATE | TERNATE |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-08-22 | 2019-12-12 | TEL.2018/LG.310/PND-B1050000/2020 | 2020-08-19 | TEL.1048/LG.320/PND-A1000000/2020 | 2020-08-19 | 698874700 | 73701880 | 772576580 | 772576580 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-08-31
12019376 | 23 | 208 | 01C11B03 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2021-08-20 | 2021-02-01 | TEL.1309/LG.310/PND-B1050000/2021 | 2021-08-06 | TEL.0104/LG.320/DID-00000000/2021 | 2021-08-06 | 1894008500 | 226701000 | 2120709500 | 2120709500 | 4500396693 |  |  |  |  | PINS INDONESIA | 2021-08-31
12019376 | 23 | 71 | 01C11B03 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2020-08-22 | 2019-12-12 | TEL.2018/LG.310/PND-B1050000/2020 | 2020-08-19 | TEL.1048/LG.320/PND-A1000000/2020 | 2020-08-19 | 353993600 | 37423690 | 391417290 | 391417290 | 4500396693 |  |  |  |  | PINS INDONESIA | 2020-08-31
12019376 | 23 | 231 | 01C11B03 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007773/HK.810/OPS-10000000/2019 | Pengadaan dan Pemasangan Mekanikal Elektrikal PINS | 2019-12-12 | 2021-10-18 | Mekanikal Elektrikal | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-12 | 2021-08-20 | 2021-02-01 | TEL.1309/LG.310/PND-B1050000/2021 | 2021-08-06 | TEL.0104/LG.320/DID-00000000/2021 | 2021-08-06 | 210384000 | 22584000 | 232968000 | 232968000 | 4500396693 |  |  |  |  | PINS INDONESIA | 2021-08-31
12019389 | 22 | 24 | 01C11H02 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008126/HK.810/OPS-10000000/2019 | SP#7 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-12-18 | 2022-08-02 | Radio IP | MANOKWARI | MANOKWARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-18 | 2020-06-15 | 2019-12-18 | TEL.51/LG.310/PND-B1060000/2020 | 2020-02-10 | TEL.0123/LG.320/PND-A1000000/2020 | 2020-02-10 | 1050966805 | 451878544 | 1502845349 | 1502845349 | 4500398937 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2020-02-27
12019389 | 22 | 21 | 01C11H02 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008126/HK.810/OPS-10000000/2019 | SP#7 Ekspan Kapasitas Radio IP Longhaul Eksisting Dukungan CNOP | 2019-12-18 | 2022-08-02 | Radio IP | PARE-PARE | MAMUJU |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-18 | 2020-08-30 | 2019-12-18 | TEL.1779/LG.310/PND-B1060000/2020 | 2020-08-24 | TEL.0984/LG.320/PND-A1000000/2020 | 2020-08-24 | 7227530088 | 1363042486 | 8590572574 | 8590572574 | 4500398937 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2020-08-26
12019392 | 29 | 112 | 01C11H02 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | JAYAPURA | ABEPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-08-25 | 2021-01-08 | 2020-08-25 | TEL2661/LG.310/PND-B1060000/2020 | 2020-11-20 | TEL.1602/LG.320/PND-A1000000/2020 | 2020-11-20 | 313394757 | 64225166 | 377619923 | 377619923 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2020-12-13
12019392 | 29 | 111 | 01C11H02 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | JAYAPURA | JAYAPURA-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-08-25 | 2021-01-08 | 2020-08-25 | TEL2662/LG.310/PND-B1060000/2020 | 2020-11-20 | TEL.1601/LG.320/PND-A1000000/2020 | 2020-11-20 | 2416057132 | 484964273 | 2901021405 | 2901021405 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2020-12-13
12019392 | 29 | 110 | 01C11H02 | 019 | 74030180 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | JAYAPURA | NOC TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-08-25 | 2021-02-19 | 2020-08-25 | TEL2872/LG.310/PND-B1060000/2020 | 2020-12-11 | TEL.1720/LG.320/PND-A1000000/2020 | 2020-12-11 | 3045090410 | 4450497689 | 7495588099 | 7495588099 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2020-12-24
12019392 | 29 | 118 | 01C11H02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | JAYAPURA | TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-01 | 2021-06-22 | 2020-10-15 | TEL.1123/LG.310/PND-B1060000/2021 | 2021-04-23 | TEL.0200/LG.320/DID-00000000/2021 | 2021-04-23 | 201187529 | 454287848 | 655475377 | 655475377 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2021-09-22
12019392 | 29 | 119 | 01C11H02 | 019 | 74030178 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | JAYAPURA | TTC TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-01 | 2021-06-22 | 2020-10-15 | TEL.1121/LG.310/PND-B1060000/2021 | 2021-04-23 | TEL.0199/LG.320/DID-00000000/2021 | 2021-04-23 | 1412571594 | 3137376799 | 4549948393 | 4549948393 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2021-09-22
12019392 | 29 | 70 | 01C11H02 | 019 | 73020113 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | TERNATE | BMH RAO |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-19 | 2020-08-25 | 2020-01-22 | TEL22/LG.310/PND-B1060000/2020 | 2020-05-02 | TEL.0939/LG.320/PND-A1000000/2020 | 2020-05-02 | 788214213 | 178385147 | 966599360 | 966599360 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2020-08-21
12019392 | 29 | 69 | 01C11H02 | 019 | 73020108 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008220/HK.810/OPS-10000000/2019 | Kontrak OSP FO Backbone, RMJ dan Last Mile Tahap 2 | 2019-12-19 | 2022-07-20 | OSP FO Backbone | TERNATE | BMH WAYABULA |  |  |  | 100 | 100 | 100 | BAST-1 | 2019-12-19 | 2020-08-25 | 2020-01-22 | TEL21/LG.310/PND-B1060000/2020 | 2020-05-02 | TEL.0938/LG.320/PND-A1000000/2020 | 2020-05-02 | 3028914982 | 668809858 | 3697724840 | 3697724840 | 4500398933 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2020-08-21
12020033 | 16 | 9 | 01C11H06 | 019 | 73020113 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000282/HK.810/OPS-10000000/2020 | Kontrak SKKL Labuan Bajo-Raba dan Gresik-Bawean | 2020-02-14 | 2021-05-26 | SKKL | TERNATE | BMH RAO |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-05-11 | 2020-11-16 | 2020-05-11 | TEL.969/LG.310/PND-B1060000/2020 | 2020-06-19 | TEL.0736/LG.320/PND-A1000000/2020 | 2020-06-19 | 277017338 | 6193790662 | 6470808000 | 6470808000 | 4500400735 | 4500425116 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2020-06-27
12020034 | 20 | 50 | 01C11H01 | 019 | 70000285 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KANTOR DIVRE VII | LUMORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-02-08 | 2020-02-14 | TEL.2513/LG.310/PND-B1060000/2020 | 2020-11-05 | TEL.1403/LG.320/PND-A1000000/2020 | 2020-11-05 | 0 | 1592805638 | 1592805638 | 1592805638 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2020-11-25
12020034 | 20 | 82 | 01C11H01 | 019 | 70000285 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KANTOR DIVRE VII | LUMORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-02-08 | 2020-02-14 | TEL.3085/LG.310/PND-B1060000/2020 | 2020-12-29 | TEL.1877/LG.320/PND-A1000000/2020 | 2020-12-29 | 0 | 10285836638 | 10285836638 | 10285836638 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2020-12-30
12020034 | 20 | 64 | 01C11H01 | 019 | 70000285 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KANTOR DIVRE VII | LUMORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-02-08 | 2020-02-14 | TEL.2514/LG.310/PND-B1060000/2020 | 2020-11-05 | TEL.1404/LG.320/PND-A1000000/2020 | 2020-11-05 | 23770592098 | 0 | 23770592098 | 23770592098 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2020-11-25
12020034 | 20 | 65 | 01C11H01 | 019 | 70000285 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KANTOR DIVRE VII | LUMORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-02-08 | 2020-02-14 | TEL.2759/LG.310/PND-B1060000/2020 | 2020-11-30 | TEL.1603/LG.320/PND-A1000000/2020 | 2020-11-30 | 30575428619 | 0 | 30575428619 | 30575428619 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2020-12-13
12020034 | 20 | 68 | 01C11H01 | 019 | 70000285 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KANTOR DIVRE VII | LUMORI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-07-14 | 2020-02-14 | TEL.671/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0257/LG.320/DID-A0000000/2022 | 2022-03-09 | 0 | 20018236980 | 20018236980 | 20018236980 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2022-03-24
12020034 | 20 | 77 | 01C11H01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KENDARI | KENDARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-06-26 | 2020-02-14 | TEL.1463/LG.310/PND-B1060000/2020 | 2021-05-27 | TEL.0600/LG.320/PND-A1000000/2021 | 2021-05-27 | 7886302088 | 0 | 7886302088 | 7886302088 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2021-05-30
12020034 | 20 | 79 | 01C11H01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | KENDARI | KENDARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-07-08 | 2020-02-14 | TEL.1462/LG.310/PND-B1060000/2020 | 2021-05-27 | TEL.0602/LG.320/PND-A1000000/2021 | 2021-05-27 | 0 | 14863300240 | 14863300240 | 14863300240 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2021-05-30
12020034 | 20 | 90 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | LUWUK | LUWUK |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-06-10 | 2020-02-14 | TEL.1465/LG.310/PND-B1060000/2020 | 2021-05-27 | TEL.0599/LG.320/PND-A1000000/2021 | 2021-05-27 | 7428841755 | 0 | 7428841755 | 7428841755 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2021-05-30
12020034 | 20 | 78 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | LUWUK | LUWUK |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-06-30 | 2020-02-14 | TEL.1461/LG.310/PND-B1060000/2020 | 2021-05-27 | TEL.0601/LG.320/PND-A1000000/2021 | 2021-05-27 | 0 | 24547939702 | 24547939702 | 24547939702 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2021-05-30
12020034 | 20 | 87 | 01C11H01 | 019 | 72030167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | PALU | MOROWALI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-04-15 | 2020-02-14 | TEL.962/LG.310/PND-B1060000/2021 | 2021-04-07 | TEL.0891/LG.320/PND-A1000000/2021 | 2021-04-07 | 40309575 | 35373799 | 75683374 | 75683374 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2021-07-29
12020034 | 20 | 70 | 01C11H01 | 019 | 72030167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | PALU | MOROWALI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-04-18 | 2020-02-14 | TEL.1001/LG.310/PND-B1060000/2021 | 2021-04-11 | TEL.0045/LG.320/DID-A0000000/2022 | 2021-04-11 | 383986823 | 163188280 | 547175103 | 547175103 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2022-01-31
12020034 | 20 | 91 | 01C11H01 | 019 | 72030167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | PALU | MOROWALI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-14 | 2021-06-16 | 2020-02-14 | TEL.1464/LG.310/PND-B1060000/2021 | 2021-05-27 | TEL.0890/LG.320/PND-A1000000/2021 | 2021-05-27 | 5057738132 | 0 | 5057738132 | 5057738132 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2021-07-29
12020034 | 20 | 85 | 01C11H01 | 019 | 72081029 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000283/HK.810/OPS-10000000/2020 | Kontrak SKKL Repeaterless LUMORI dan BALOM | 2020-02-14 | 2021-10-05 | SKKL | UJUNGPANDANG | DEPO KABEL MAKASSAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-06 | 2021-02-08 | 2020-02-14 | TEL.3084/LG.310/PND-B1060000/2020 | 2020-12-29 | TEL.1878/LG.320/PND-A1000000/2020 | 2020-12-29 | 0 | 10881976728 | 10881976728 | 10881976728 | 4500400730 | 4500425114 |  |  |  | KONSORSIUM TELKOMINFRA MARINE | 2020-12-30
12020039 | 14 | 217 | 01C11B03 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000306/HK.810/OPS-10000000/2020 | Kontrak Modernisasi CME Mitratel | 2020-02-19 | 2021-11-30 | CME | UJUNGPANDANG | MATTOANGIN |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-02-19 | 2021-10-29 | 2020-02-19 | TEL.1497/LG.310/PND-B1050000/2021 | 2021-09-09 | TEL.0372/LG.320/DID-00000000/2021 | 2021-09-09 | 1350135030 | 350560080 | 1700695110 | 1700695110 | 4500400731 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2021-10-09
12020058 | 26 | 626 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-01-07 | C.TEL.039/BR000/DCS-12000000/2022 | 2022-01-07 | TEL.0001/LG.320/DCS-A0000000/2022 | 2022-01-07 | 170472526 | 0 | 170472526 | 170472526 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-03-09
12020058 | 26 | 730 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-01-07 | C.TEL.039/BR000/DCS-12000000/2022 | 2022-01-07 | TEL.0002/LG.320/DCS-A0000000/2022 | 2022-01-07 | 22576503 | 0 | 22576503 | 22576503 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-03-09
12020058 | 26 | 633 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-01-07 | C.TEL.039/BR000/DCS-12000000/2022 | 2022-01-07 | TEL.0003/LG.320/DCS-A0000000/2022 | 2022-01-07 | 0 | 715115486 | 715115486 | 715115486 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-03-09
12020058 | 26 | 86 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-01 | 2020-07-24 | 2020-07-01 | C.TEL.100/UM000/DSS-10C01000/2020 | 2020-10-01 | TEL.0001/LG.320/DSS-10000000/2020 | 2020-10-01 | 276548262 | 0 | 276548262 | 276548262 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-10-29
12020058 | 26 | 93 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-01 | 2020-07-24 | 2020-07-01 | C.TEL.100/UM000/DSS-10C01000/2020 | 2020-10-01 | TEL.0002/LG.320/DSS-10000000/2020 | 2020-10-01 | 0 | 504421526 | 504421526 | 504421526 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-10-29
12020058 | 26 | 173 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-01 | 2021-01-07 | 2020-12-01 | C.TEL.169/BR.000/DSS-12000000/2021 | 2021-02-04 | TEL.0002/LG.320/DSS-10000000/2021 | 2021-02-04 | 0 | 665800870 | 665800870 | 665800870 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-04-22
12020058 | 26 | 181 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-08-01 | 2020-09-07 | 2020-11-02 | C.TEL/101/BA000/DSS-10C01000/2020 | 2020-11-19 | TEL.0003/LG.320/DSS-10000000/2020 | 2020-11-19 | 169400151 | 0 | 169400151 | 169400151 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-21
12020058 | 26 | 205 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-11-01 | 2020-12-08 | 2020-11-01 | C.TEL.104/BA000/DSS-10C01000/2020 | 2020-12-23 | TEL.0009/LG.320/DSS-10000000/2020 | 2020-12-23 | 269104407 | 0 | 269104407 | 269104407 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020058 | 26 | 131 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-01 | 2020-10-08 | 2020-09-01 | C.TEL.102/BA000/DSS-10C01000/2020 | 2020-12-10 | TEL.0007/LG.320/DSS-10000000/2020 | 2020-12-10 | 0 | 631588693 | 631588693 | 631588693 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020058 | 26 | 145 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-01 | 2020-11-07 | 2020-10-01 | C.TEL.103/BA000/DSS-10C01000/2020 | 2020-12-15 | TEL.0008/LG.320/DSS-10000000/2020 | 2020-12-15 | 0 | 653813490 | 653813490 | 653813490 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020058 | 26 | 159 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-11-01 | 2020-12-08 | 2020-11-01 | C.TEL.104/BA000/DSS-10C01000/2020 | 2020-12-23 | TEL.0010/LG.320/DSS-10000000/2020 | 2020-12-23 | 0 | 675170860 | 675170860 | 675170860 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020058 | 26 | 117 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-08-01 | 2020-09-07 | 2020-08-01 | C.TEL/101/BA000/DSS-10C01000/2020 | 2020-11-19 | TEL.0004/LG.320/DSS-10000000/2020 | 2020-11-19 | 0 | 634381023 | 634381023 | 634381023 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-21
12020058 | 26 | 514 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-03 | C.TEL.867/BA.000/DSS-12000000/2021 | 2021-06-03 | TEL.0011/LG.320/DSS-10000000/2021 | 2021-06-03 | 145898886 | 0 | 145898886 | 145898886 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 695 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-03 | C.TEL.867/BA.000/DSS-12000000/2021 | 2021-06-03 | TEL.0012/LG.320/DSS-10000000/2021 | 2021-06-03 | 18652664 | 0 | 18652664 | 18652664 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 528 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-03-26 | 2021-04-25 | 2021-06-16 | C.TEL.948/BA.000/DSS-12000000/2021 | 2021-06-16 | TEL.0014/LG.320/DSS-10000000/2021 | 2021-06-16 | 154208739 | 0 | 154208739 | 154208739 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 535 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-03-26 | 2021-04-25 | 2021-06-16 | C.TEL.948/BA.000/DSS-12000000/2021 | 2021-06-16 | TEL.0003/LG.320/DSS-10000000/2021 | 2021-06-16 | 0 | 708484962 | 708484962 | 708484962 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 702 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-03-26 | 2021-04-25 | 2021-06-16 | C.TEL.948/BA.000/DSS-12000000/2021 | 2021-06-16 | TEL.0004/LG.320/DSS-10000000/2021 | 2021-06-16 | 41532089 | 0 | 41532089 | 41532089 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 681 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-02 | C.TEL.858/BA.000/DSS-12000000/2021 | 2021-06-02 | TEL.0007/LG.320/DSS-10000000/2021 | 2021-06-02 | 12799192 | 0 | 12799192 | 12799192 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 493 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-02 | C.TEL.858/BA.000/DSS-12000000/2021 | 2021-06-02 | TEL.0005/LG.320/DSS-10000000/2021 | 2021-06-02 | 0 | 709081962 | 709081962 | 709081962 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 500 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-02 | C.TEL.861/BR.000/DSS-12000000/2021 | 2021-06-02 | TEL.0008/LG.320/DSS-10000000/2021 | 2021-06-02 | 133162577 | 0 | 133162577 | 133162577 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 507 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-02 | C.TEL.861/BR.000/DSS-12000000/2021 | 2021-06-02 | TEL.0010/LG.320/DSS-10000000/2021 | 2021-06-02 | 0 | 708231420 | 708231420 | 708231420 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 688 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-02 | C.TEL.861/BR.000/DSS-12000000/2021 | 2021-06-02 | TEL.0009/LG.320/DSS-10000000/2021 | 2021-06-02 | 29106237 | 0 | 29106237 | 29106237 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 213 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-01 | 2021-01-07 | 2020-12-01 | C.TEL.169/BR.000/DSS-12000000/2021 | 2021-02-04 | TEL.0001/LG.320/DSS-10000000/2021 | 2021-02-04 | 220178704 | 0 | 220178704 | 220178704 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-04-22
12020058 | 26 | 542 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-08-23 | C.TEL.1351/BA.000/DSS-12000000/2021 | 2021-08-23 | TEL.0015/LG.320/DSS-10000000/2021 | 2021-08-23 | 98976816 | 0 | 98976816 | 98976816 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020058 | 26 | 189 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-09-01 | 2020-10-08 | 2020-09-01 | C.TEL.102/BA000/DSS-10C01000/2020 | 2020-12-10 | TEL.0005/LG.320/DSS-10000000/2020 | 2020-12-10 | 238761200 | 0 | 238761200 | 238761200 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020058 | 26 | 486 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-02 | C.TEL.858/BA.000/DSS-12000000/2021 | 2021-06-02 | TEL.0006/LG.320/DSS-10000000/2021 | 2021-06-02 | 179612975 | 0 | 179612975 | 179612975 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 709 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-08-23 | C.TEL.1351/BA.000/DSS-12000000/2021 | 2021-08-23 | TEL.0001/LG.320/DCS-00000000/2021 | 2021-08-23 | 20147045 | 0 | 20147045 | 20147045 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020058 | 26 | 549 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-08-23 | C.TEL.1351/BA.000/DSS-12000000/2021 | 2021-08-23 | TEL.0002/LG.320/DCS-00000000/2021 | 2021-08-23 | 0 | 712513588 | 712513588 | 712513588 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020058 | 26 | 521 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-06-03 | C.TEL.867/BA.000/DSS-12000000/2021 | 2021-06-03 | TEL.0013/LG.320/DSS-10000000/2021 | 2021-06-03 | 0 | 712038593 | 712038593 | 712038593 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020058 | 26 | 821 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 263 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 779 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 772 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 835 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 378 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 228 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 413 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 364 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 448 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 455 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 427 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 842 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 828 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 420 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 357 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 786 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 399 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 814 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 262 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 406 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 392 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 259 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 260 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 261 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 800 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 371 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 807 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 441 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 793 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 584450 | 584450 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 434 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 350 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 608803 | 608803 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 385 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 0 | 0 | Preparing | 2020-12-25 | 2021-01-24 | [5 empty] | 0 | 807367747 | 807367747 | 0 | 4500404458 |  |  |  |  | TELKOM AKSES
12020058 | 26 | 647 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-26 | 2021-12-25 | 2022-03-24 | C.TEL.507/BR000/DCS-12000000/2022 | 2022-03-24 | TEL.0006/LG.320/DCS-A0000000/2022 | 2022-03-24 | 0 | 709898526 | 709898526 | 709898526 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-04-20
12020058 | 26 | 294 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-03-28 | C.TEL.525/BR000/DCS-12000000/2022 | 2022-03-28 | TEL.0008/LG.320/DCS-A0000000/2022 | 2022-03-28 | 136191162 | 0 | 136191162 | 136191162 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-04-22
12020058 | 26 | 301 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-03-28 | C.TEL.525/BR000/DCS-12000000/2022 | 2022-03-28 | TEL.0007/LG.320/DCS-A0000000/2022 | 2022-03-28 | 0 | 714800230 | 714800230 | 714800230 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-04-22
12020058 | 26 | 336 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.930/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0016/LG.320/DCS-A0000000/2022 | 2022-06-20 | 147973083 | 0 | 147973083 | 147973083 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 343 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.930/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0018/LG.320/DCS-A0000000/2022 | 2022-06-20 | 0 | 718465777 | 718465777 | 718465777 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 758 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.927/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0014/LG.320/DCS-A0000000/2022 | 2022-06-20 | 19455223 | 0 | 19455223 | 19455223 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 640 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-26 | 2021-12-25 | 2022-03-24 | C.TEL.507/BR000/DCS-12000000/2022 | 2022-03-24 | TEL.0004/LG.320/DCS-A0000000/2022 | 2022-03-24 | 102942058 | 0 | 102942058 | 102942058 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-04-20
12020058 | 26 | 737 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-26 | 2021-12-25 | 2022-03-24 | C.TEL.507/BR000/DCS-12000000/2022 | 2022-03-24 | TEL.0005/LG.320/DCS-A0000000/2022 | 2022-03-24 | 19157680 | 0 | 19157680 | 19157680 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-04-20
12020058 | 26 | 744 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-03-28 | C.TEL.525/BR000/DCS-12000000/2022 | 2022-03-28 | TEL.0009/LG.320/DCS-A0000000/2022 | 2022-03-28 | 14835471 | 0 | 14835471 | 14835471 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-04-22
12020058 | 26 | 605 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-12-06 | C.TEL.2028/BR000/DCS-12000000/2021 | 2021-12-06 | TEL.0012/LG.320/DCS-A0000000/2021 | 2021-12-06 | 0 | 723360230 | 723360230 | 723360230 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020058 | 26 | 308 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.924/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0010/LG.320/DCS-A0000000/2022 | 2022-06-20 | 158277329 | 0 | 158277329 | 158277329 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 751 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.924/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0011/LG.320/DCS-A0000000/2022 | 2022-06-20 | 25985695 | 0 | 25985695 | 25985695 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 322 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.927/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0013/LG.320/DCS-A0000000/2022 | 2022-06-20 | 118252920 | 0 | 118252920 | 118252920 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 765 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.930/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0017/LG.320/DCS-A0000000/2022 | 2022-06-20 | 23428178 | 0 | 23428178 | 23428178 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 315 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.924/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0012/LG.320/DCS-A0000000/2022 | 2022-06-20 | 0 | 713770777 | 713770777 | 713770777 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 329 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2022-06-20 | C.TEL.927/BR000/DCS-12000000/2022 | 2022-06-20 | TEL.0015/LG.320/DCS-A0000000/2022 | 2022-06-20 | 0 | 711425777 | 711425777 | 711425777 | 4500404458 |  |  |  |  | TELKOM AKSES | 2022-07-15
12020058 | 26 | 563 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-10-26 | C.TEL.1758/BR000/DCS-12000000/2021 | 2021-10-26 | TEL.0003/LG.320/DCS-A0000000/2021 | 2021-10-26 | 0 | 697963135 | 697963135 | 697963135 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 570 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-10-27 | C.TEL.1767/BR000/DCS-12000000/2021 | 2021-10-27 | TEL.0004/LG.320/DCS-A0000000/2021 | 2021-10-26 | 106261511 | 0 | 106261511 | 106261511 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 577 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-10-27 | C.TEL.1767/BR000/DCS-12000000/2021 | 2021-10-27 | TEL.0006/LG.320/DCS-A0000000/2021 | 2021-10-27 | 0 | 713284378 | 713284378 | 713284378 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 863 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-07-26 | 2021-08-25 | 2021-10-28 | C.TEL.1776/BR000/DCS-12000000/2021 | 2021-10-28 | TEL.0008/LG.320/DCS-A0000000/2021 | 2021-10-28 | 26076695 | 0 | 26076695 | 26076695 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 856 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-10-27 | C.TEL.1767/BR000/DCS-12000000/2021 | 2021-10-27 | TEL.0005/LG.320/DCS-A0000000/2021 | 2021-10-27 | 19815409 | 0 | 19815409 | 19815409 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 584 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-07-26 | 2021-08-25 | 2021-10-28 | C.TEL.1776/BR000/DCS-12000000/2021 | 2021-10-28 | TEL.0007/LG.320/DCS-A0000000/2021 | 2021-10-28 | 117556570 | 0 | 117556570 | 117556570 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 591 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-07-26 | 2021-08-25 | 2021-10-28 | C.TEL.1776/BR000/DCS-12000000/2021 | 2021-10-28 | TEL.0009/LG.320/DCS-A0000000/2021 | 2021-10-28 | 0 | 707841326 | 707841326 | 707841326 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 197 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-01 | 2020-11-07 | 2020-10-01 | C.TEL.103/BA000/DSS-10C01000/2020 | 2020-12-15 | TEL.0006/LG.320/DSS-10000000/2020 | 2020-12-15 | 209849457 | 0 | 209849457 | 209849457 | 4500404458 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020058 | 26 | 849 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-10-26 | C.TEL.1758/BR000/DCS-12000000/2021 | 2021-10-26 | TEL.0002/LG.320/DCS-A0000000/2021 | 2021-10-26 | 14904659 | 0 | 14904659 | 14904659 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020058 | 26 | 612 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-12-06 | C.TEL.2031/BR000/DCS-12000000/2021 | 2021-12-06 | TEL.0013/LG.320/DCS-A0000000/2021 | 2021-12-06 | 200162372 | 0 | 200162372 | 200162372 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020058 | 26 | 716 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-12-06 | C.TEL.2028/BR000/DCS-12000000/2021 | 2021-12-06 | TEL.0011/LG.320/DCS-A0000000/2021 | 2021-12-06 | 34221096 | 0 | 34221096 | 34221096 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020058 | 26 | 723 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-12-06 | C.TEL.2031/BR000/DCS-12000000/2021 | 2021-12-06 | TEL.0014/LG.320/DCS-A0000000/2021 | 2021-12-06 | 18899547 | 0 | 18899547 | 18899547 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020058 | 26 | 619 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-12-06 | C.TEL.2031/BR000/DCS-12000000/2021 | 2021-12-06 | TEL.0015/LG.320/DCS-A0000000/2021 | 2021-12-06 | 0 | 721290777 | 721290777 | 721290777 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020058 | 26 | 598 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-12-06 | C.TEL.2028/BR000/DCS-12000000/2021 | 2021-12-06 | TEL.0010/LG.320/DCS-A0000000/2021 | 2021-12-06 | 160662553 | 0 | 160662553 | 160662553 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020058 | 26 | 556 | 01C13K07 | 038 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUE DFU INTERFACE SERVICE MGT | ENTERPRISE SERVICE QUALITY MGT | DIGITAL CONNECTIVITY SERVICE | K.TEL.000976/HK.810/OPS-10000000/2020 | Kontrak Provisioning Pelanggan EBIS | 2020-03-23 | 2023-03-22 | Provisioning Pelanggan EBIS | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-01-24 | 2021-10-26 | C.TEL.1758/BR000/DCS-12000000/2021 | 2021-10-26 | TEL.0001/LG.320/DCS-A0000000/2021 | 2021-10-26 | 105826812 | 0 | 105826812 | 105826812 | 4500404458 |  |  |  |  | TELKOM AKSES | 2021-12-02
12020081 | 30 | 171 | 01C11I04 | 019 | 73010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001897/HK.810/OPS-10040000/2020 | SP#15 Penjualan Barang Scrap dan Kabel Tembaga PT TA | 2020-04-16 | 2022-12-31 | PELOLOSAN | AMBON | BANDA NEIRA |  |  |  | 90 | 0 | 0 | Preparing | 2020-04-16 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12020081 | 30 | 172 | 01C11I04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001897/HK.810/OPS-10040000/2020 | SP#15 Penjualan Barang Scrap dan Kabel Tembaga PT TA | 2020-04-16 | 2022-12-31 | PELOLOSAN | AMBON | NAMLEA |  |  |  | 90 | 0 | 0 | Preparing | 2020-04-16 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12020081 | 30 | 173 | 01C11I04 | 019 | 73010119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001897/HK.810/OPS-10040000/2020 | SP#15 Penjualan Barang Scrap dan Kabel Tembaga PT TA | 2020-04-16 | 2022-12-31 | PELOLOSAN | AMBON | TUAL |  | STO TUAL REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-04-16 | 2021-07-14 | 2020-04-16 | LAMPIRAN_STO_TUAL_1 | 2020-04-16 | TEL.0934/LG.320/PND-A1000000/2021 | 2020-04-16 | 26529120 | 0 | 26529120 | 26529120 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020081 | 30 | 297 | 01C11I04 | 019 | 73010119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001897/HK.810/OPS-10040000/2020 | SP#15 Penjualan Barang Scrap dan Kabel Tembaga PT TA | 2020-04-16 | 2022-12-31 | PELOLOSAN | AMBON | TUAL |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2020-04-16 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12020081 | 30 | 174 | 01C11I04 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001897/HK.810/OPS-10040000/2020 | SP#15 Penjualan Barang Scrap dan Kabel Tembaga PT TA | 2020-04-16 | 2022-12-31 | PELOLOSAN | PALU | LUWUK |  | STO LUWUK REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-04-16 | 2021-01-14 | 2020-04-16 | LAMPIRAN_STO_LUWUK_1 | 2020-04-16 | TEL.1481/LG.320/PND-A1000000/2020 | 2020-04-16 | 62534025 | 0 | 62534025 | 62534025 | 0000000000 |  |  |  |  | TELKOM AKSES | 2020-11-28
12020081 | 30 | 215 | 01C11I04 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001897/HK.810/OPS-10040000/2020 | SP#15 Penjualan Barang Scrap dan Kabel Tembaga PT TA | 2020-04-16 | 2022-12-31 | PELOLOSAN | PALU | LUWUK |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2020-04-16 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12020098 | 16 | 26 | 01C11H02 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002659/HK.810/OPS-10040000/2020 | Surat Pesanan-8 (SP#8) Pengadaan dan Pemasangan Ekspan Kapasitas Link Radio IP Longhaul | 2020-05-14 | 2022-08-08 | Radio IP | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-05-14 | 2021-05-07 | 2020-05-14 | TEL.1161/LG.310/PND-B1060000/2021 | 2021-04-27 | TEL.0647/LG.320/PND-A1000000/2021 | 2021-04-27 | 4999959710 | 1189016874 | 6188976584 | 6188976584 | 4500407963 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2021-06-23
12020098 | 16 | 10 | 01C11H02 | 019 | 74020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002659/HK.810/OPS-10040000/2020 | Surat Pesanan-8 (SP#8) Pengadaan dan Pemasangan Ekspan Kapasitas Link Radio IP Longhaul | 2020-05-14 | 2022-08-08 | Radio IP | FAK-FAK | FAKFAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-05-14 | 2020-11-09 | 2020-05-14 | TEL.2159/LG.310/PND-B1060000/2020 | 2020-10-02 | TEL.1290/LG.320/PND-A1000000/2020 | 2020-10-02 | 2800776040 | 1439431653 | 4240207693 | 4240207693 | 4500407963 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2020-10-26
12020098 | 16 | 28 | 01C11I07 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002659/HK.810/OPS-10040000/2020 | Surat Pesanan-8 (SP#8) Pengadaan dan Pemasangan Ekspan Kapasitas Link Radio IP Longhaul | 2020-05-14 | 2022-08-08 | Radio IP | TERNATE | TERNATE |  |  |  | 50 | 20 | 0 | Preparing | 2020-05-14 | 2022-08-09 | 2020-05-14 |  |  |  |  | 6369259586 | 1256532258 | 7625791844 | 0 | 4500407963 |  |  |  |  | MULTIREKA PRIMA UTAMA
12020104 | 30 | 992 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1524/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 52151840 | 60748960 | 112900800 | 112900800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 347 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1016/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 37108040 | 43011760 | 80119800 | 80119800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1880 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0286/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 6017520 | 6974880 | 12992400 | 12992400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1082 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1582/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 86251120 | 100423280 | 186674400 | 186674400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 496 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1050/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1267/LG.320/PND-A1000000/2020 | 2020-07-15 | 97283240 | 112910560 | 210193800 | 210193800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2179 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-4 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1354/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 8023360 | 9299840 | 17323200 | 17323200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2205 | 01E07V01 | 019 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | AMBON |  | TAHAP-3 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1391/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 4513140 | 5231160 | 9744300 | 9744300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1881 | 01E07V01 | 019 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | DOBO |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0287/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 349 | 01E07V01 | 019 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | DOBO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1017/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 18554020 | 21505880 | 40059900 | 40059900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 994 | 01E07V01 | 019 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | DOBO |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1525/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2180 | 01E07V01 | 019 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | DOBO |  | TAHAP-4 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1355/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2181 | 01E07V01 | 019 | 73010125 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | LARAT |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1356/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 530 | 01E07V01 | 019 | 73010125 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | LARAT |  | ODC-LRA-FAA (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-07-01 | TEL.2007/LG.310/DR7-12700000/2020 | 2020-11-28 | TEL.0482/LG.320/PND-A1000000/2021 | 2021-03-15 | 146074339 | 42888032 | 188962371 | 188962371 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020104 | 30 | 350 | 01E07V01 | 019 | 73010125 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | LARAT |  | MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0288/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 7521900 | 8718600 | 16240500 | 16240500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2182 | 01E07V01 | 019 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | PASSO |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1357/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1823 | 01E07V01 | 019 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | PASSO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1584/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 997 | 01E07V01 | 019 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | PASSO |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1526/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 5516060 | 6393640 | 11909700 | 11909700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2206 | 01E07V01 | 019 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | PASSO |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1392/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 352 | 01E07V01 | 019 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | PASSO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1018/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2507300 | 2906200 | 5413500 | 5413500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2207 | 01E07V01 | 019 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | SAUMLAKI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1393/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 5516060 | 6393640 | 11909700 | 11909700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1883 | 01E07V01 | 019 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | SAUMLAKI |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0289/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 354 | 01E07V01 | 019 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | SAUMLAKI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1019/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 4011680 | 4649920 | 8661600 | 8661600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 999 | 01E07V01 | 019 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | AMBON | SAUMLAKI |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1527.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 29084680 | 33711920 | 62796600 | 62796600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1786 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | GORONTALO | GORONTALO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1565.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2151 | 01E07V01 | 019 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | ABEPURA |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1358/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1885 | 01E07V01 | 019 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | ABEPURA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1529.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2507300 | 3056200 | 5563500 | 5563500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2152 | 01E07V01 | 019 | 74030163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-1 |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1359/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 2507300 | 3056200 | 5563500 | 5563500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1886 | 01E07V01 | 019 | 74030163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-1 |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1530.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 32594900 | 40030600 | 72625500 | 72625500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1893 | 01E07V01 | 019 | 74030163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-1 |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0290/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1825 | 01E07V01 | 019 | 74030163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-1 |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1587/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 13539420 | 16143480 | 29682900 | 29682900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2208 | 01E07V01 | 019 | 74030163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-1 |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1394/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 358 | 01E07V01 | 019 | 74030034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-2 |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1020/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1003 | 01E07V01 | 019 | 74030034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-2 |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1528/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2153 | 01E07V01 | 019 | 74030034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-2 |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1360/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1826 | 01E07V01 | 019 | 74030034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | JAYAPURA-2 |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1588/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2154 | 01E07V01 | 019 | 74030043 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | KUALA KENCANA |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1361/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 731240 | 1232700 | 1232700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 359 | 01E07V01 | 019 | 74030043 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | KUALA KENCANA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1021/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2155 | 01E07V01 | 019 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | SENTANI |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1363/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 1002920 | 1312480 | 2315400 | 2315400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1888 | 01E07V01 | 019 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | SENTANI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1532.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1827 | 01E07V01 | 019 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | SENTANI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1591/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 5014600 | 5812400 | 10827000 | 10827000 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2209 | 01E07V01 | 019 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TEMBAGAPURA |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1395/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 2507300 | 2906200 | 5413500 | 5413500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2050 | 01E07V01 | 019 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TEMBAGAPURA |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1364/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1896 | 01E07V01 | 019 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TEMBAGAPURA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0291/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1828 | 01E07V01 | 019 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TEMBAGAPURA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1592/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1889 | 01E07V01 | 019 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TEMBAGAPURA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1533.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 14542340 | 16855960 | 31398300 | 31398300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2210 | 01E07V01 | 019 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TIMIKA |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1396/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1829 | 01E07V01 | 019 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TIMIKA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1593/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1897 | 01E07V01 | 019 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TIMIKA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0292/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 731240 | 1232700 | 1232700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1890 | 01E07V01 | 019 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | TIMIKA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1534.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 4011680 | 4649920 | 8661600 | 8661600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1891 | 01E07V01 | 019 | 74030072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | JAYAPURA | WAENA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1535.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1852 | 01E07V01 | 019 | 72050057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | KENDARI | RAHA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1628/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1912 | 01E07V01 | 019 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | LUWUK | LUWUK |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1549.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1931 | 01E07V01 | 019 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | AIR MADIDI |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0296/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1916 | 01E07V01 | 019 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | AIR MADIDI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1556.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 13037960 | 15112240 | 28150200 | 28150200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1917 | 01E07V01 | 019 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | AMURANG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1557.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1853 | 01E07V01 | 019 | 72010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BAHU |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1633/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 731240 | 1232700 | 1232700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 443 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BEO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0298/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 4513140 | 5231160 | 9744300 | 9744300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 534 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BEO |  | DRM ODC-BEO-FAD (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-05-18 | TEL.1112/LG.310/DR7-12700000/2021 | 2020-12-23 | TEL.0482/LG.320/PND-A1000000/2021 | 2021-03-15 | 465329684 | 109124900 | 574454584 | 574454584 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020104 | 30 | 528 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BEO |  | DRM UPLINK STO BEO DRM UPLINK (SS#1) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-03-20 | 2020-05-18 | TEL.2008/LG.310/DR7-12700000/2020 | 2021-03-15 | TEL.0482/LG.320/PND-A1000000/2021 | 2021-03-15 | 2306913279 | 452418619 | 2759331898 | 2759331898 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020104 | 30 | 2186 | 01E07V01 | 019 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BITUNG |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1401/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1854 | 01E07V01 | 019 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BITUNG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1634/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 2507300 | 2906200 | 5413500 | 5413500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1918 | 01E07V01 | 019 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | BITUNG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1558.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1062 | 01E07V01 | 019 | 72010267 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | HULU SIAU |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1550/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 446 | 01E07V01 | 019 | 72010267 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | HULU SIAU |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1041/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1919 | 01E07V01 | 019 | 72010045 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | KAUDITAN |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1559.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2167 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | KOTAMOBAGU |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1371/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1063 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | KOTAMOBAGU |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1551/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 447 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | KOTAMOBAGU |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1042/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1920 | 01E07V01 | 019 | 72010055 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | LANGOAN |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1560.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1940 | 01E07V01 | 019 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1402/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1855 | 01E07V01 | 019 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1637/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 51148920 | 59286480 | 110435400 | 110435400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1921 | 01E07V01 | 019 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1561.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 26075920 | 30374480 | 56450400 | 56450400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1936 | 01E07V01 | 019 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0299/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 454 | 01E07V01 | 019 | 72010133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO - PANIKI |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1553.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1260 | 01E07V01 | 019 | 72010064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO BAHU |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1552.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1927 | 01E07V01 | 019 | 72010064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO BAHU |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0297/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 453 | 01E07V01 | 019 | 72010064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO BAHU |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1043/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2169 | 01E07V01 | 019 | 72010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO CENTRUM |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1372/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 505 | 01E07V01 | 019 | 72010067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO PANIKI |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1044/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1267/LG.320/PND-A1000000/2020 | 2020-07-15 | 7521900 | 8718600 | 16240500 | 16240500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2171 | 01E07V01 | 019 | 72010067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO PANIKI |  | TAHAP-1 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1374/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1086 | 01E07V01 | 019 | 72010067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANADO PANIKI |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1629/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 470 | 01E07V01 | 019 | 72010277 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANGOLE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0300/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 36105120 | 41849280 | 77954400 | 77954400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2054 | 01E07V01 | 019 | 72010277 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MANGOLE |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1373/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2189 | 01E07V01 | 019 | 72010275 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | MOROTAI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1403/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 321 | 01E07V01 | 019 | 72010248 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAGULANDANG |  | ODC-TAG-F.. (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-05-18 | TEL.1643/LG.310/DR7-12700000/2020 | 2020-11-13 | TEL.1569/LG.320/PND-A1000000/2020 | 2020-11-13 | 397344767 | 90388894 | 487733661 | 487733661 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 535 | 01E07V01 | 019 | 72010248 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAGULANDANG |  | UPLINK TAGULANDANG (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-05-18 | TEL.1644/LG.310/DR7-12700000/2020 | 2020-11-13 | TEL.1569/LG.320/PND-A1000000/2020 | 2020-11-13 | 217820249 | 47028810 | 264849059 | 264849059 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 2172 | 01E07V01 | 019 | 72010248 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAGULANDANG |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1376/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 308 | 01E07V01 | 019 | 72010248 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAGULANDANG |  | FEEDER TAGULANDANG (SS#1) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-11-12 | TEL.1642/LG.310/DR7-12700000/2020 | 2020-11-13 | TEL.1570/LG.320/PND-A1000000/2020 | 2020-11-13 | 63397522 | 21765524 | 85163046 | 85163046 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 472 | 01E07V01 | 019 | 72010248 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAGULANDANG |  | MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0301/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2173 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAHUNA |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1377/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1937 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAHUNA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0302/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1922 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAHUNA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1562.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 21061320 | 24412080 | 45473400 | 45473400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1856 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TAHUNA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1639/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 7521900 | 8718600 | 16240500 | 16240500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1923 | 01E07V01 | 019 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TOMOHON |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1563.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 11533580 | 13668520 | 25202100 | 25202100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2175 | 01E07V01 | 019 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TOMOHON |  | TAHAP-2 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1379/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1857 | 01E07V01 | 019 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TOMOHON |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1640/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1858 | 01E07V01 | 019 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TONDANO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1641/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 7020440 | 8137360 | 15157800 | 15157800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1924 | 01E07V01 | 019 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MANADO | TONDANO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1564.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 4513140 | 5231160 | 9744300 | 9744300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1894 | 01E07V01 | 019 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MERAUKE | MERAUKE |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1362/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1887 | 01E07V01 | 019 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | MERAUKE | MERAUKE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1531.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 407 | 01E07V01 | 019 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | BUNGKU |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1033/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1041 | 01E07V01 | 019 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | BUOL |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1546/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 415 | 01E07V01 | 019 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | BUOL |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1034/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2005840 | 2474960 | 4480800 | 4480800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2212 | 01E07V01 | 019 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | BUOL |  | TAHAP-1 MIGRASI EBIS SS-4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1398/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 430 | 01E07V01 | 019 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | KOLONODALE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1035/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 5516060 | 6543640 | 12059700 | 12059700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2183 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | LUWUK |  | TAHAP-1 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1368/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 504 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-1 |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1051/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1267/LG.320/PND-A1000000/2020 | 2020-07-15 | 27078840 | 31986960 | 59065800 | 59065800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1049 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-1 |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1547/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1084 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-1 |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1618/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 4513140 | 5231160 | 9744300 | 9744300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 435 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-1 |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1036/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 3510220 | 4218680 | 7728900 | 7728900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2184 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-1 |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1369/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2213 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-1 |  | TAHAP-3 MIGRASI EBIS SS-4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1399/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 436 | 01E07V01 | 019 | 72030156 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-2 |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1037/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1051 | 01E07V01 | 019 | 72030156 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-2 |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1548/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1848 | 01E07V01 | 019 | 72030156 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-2 |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1624/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2185 | 01E07V01 | 019 | 72030156 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PALU-2 |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1370/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1849 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PARIGI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1625/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1504380 | 2043720 | 3548100 | 3548100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 438 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | PARIGI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1038/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 11533580 | 13368520 | 24902100 | 24902100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 439 | 01E07V01 | 019 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | POSO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1039/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2214 | 01E07V01 | 019 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | POSO |  | TAHAP-2 MIGRASI EBIS SS-4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1400/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1850 | 01E07V01 | 019 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | POSO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1626LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 441 | 01E07V01 | 019 | 72030083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PALU | TOLAY |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1040/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 365 | 01E07V01 | 019 | 72040275 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | AJANGALE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1024/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 366 | 01E07V01 | 019 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | BARRU |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1025/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1019 | 01E07V01 | 019 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | BARRU |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1540/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1835 | 01E07V01 | 019 | 72040049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | ENREKANG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1601/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 8524820 | 10031080 | 18555900 | 18555900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 367 | 01E07V01 | 019 | 72040049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | ENREKANG |  | MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0295/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1836 | 01E07V01 | 019 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | MAJENE |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1602/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1837 | 01E07V01 | 019 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | MAKALE |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1603/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1838 | 01E07V01 | 019 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | MALILI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1604/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 369 | 01E07V01 | 019 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | MALILI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1026/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1839 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | MASAMBA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1605/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 371 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | MASAMBA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1027/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1840 | 01E07V01 | 019 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | PALOPO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1606/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 5014600 | 5962400 | 10977000 | 10977000 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1811 | 01E07V01 | 019 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | PALOPO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1542.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1812 | 01E07V01 | 019 | 72040117 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | PARE-PARE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1543.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1841 | 01E07V01 | 019 | 72040201 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | PARE-PARE2 |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1607/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 9026280 | 11512320 | 20538600 | 20538600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 373 | 01E07V01 | 019 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | PINRANG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1028/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 6017520 | 6974880 | 12992400 | 12992400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1842 | 01E07V01 | 019 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | PINRANG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1608/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 400 | 01E07V01 | 019 | 72040195 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | POLEWALI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1029/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1909 | 01E07V01 | 019 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | RANTEPAO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1544.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1843 | 01E07V01 | 019 | 72040135 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | RAPPANG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1611/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 2005840 | 2474960 | 4480800 | 4480800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1814 | 01E07V01 | 019 | 72040135 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | RAPPANG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1545.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 27580300 | 31968200 | 59548500 | 59548500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1034 | 01E07V01 | 019 | 72040158 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | SIDRAP |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1541/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 401 | 01E07V01 | 019 | 72040158 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | SIDRAP |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1030/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 4011680 | 4649920 | 8661600 | 8661600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1844 | 01E07V01 | 019 | 72040158 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | SIDRAP |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1613/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 7020440 | 8137360 | 15157800 | 15157800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 402 | 01E07V01 | 019 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | TANRUTEDONG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1031/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 32594900 | 37780600 | 70375500 | 70375500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1845 | 01E07V01 | 019 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | TANRUTEDONG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1615/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1846 | 01E07V01 | 019 | 72040186 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | WATANSOPPENG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1616/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 6518980 | 7556120 | 14075100 | 14075100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 404 | 01E07V01 | 019 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | WONOMULYO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1032/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1847 | 01E07V01 | 019 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | PARE-PARE | WONOMULYO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1617/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 731240 | 1232700 | 1232700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1899 | 01E07V01 | 019 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | BIAK |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1537.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1903 | 01E07V01 | 019 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | BIAK |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0293/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1831 | 01E07V01 | 019 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | BIAK |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1595/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 360 | 01E07V01 | 019 | 74060037 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | BINTUINI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1022/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1900 | 01E07V01 | 019 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | NABIRE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1538.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 5516060 | 6693640 | 12209700 | 12209700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1904 | 01E07V01 | 019 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | NABIRE |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0294/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2052 | 01E07V01 | 019 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | NABIRE |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1365/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 11032120 | 12937280 | 23969400 | 23969400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2211 | 01E07V01 | 019 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | NABIRE |  | TAHAP-1 MIGRASI EBIS SS-4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1397/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 4513140 | 5231160 | 9744300 | 9744300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2248 | 01E07V01 | 019 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | SERUI |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-16 | TEL.1366/LG.310/DR7-12700000/2021 | 2021-09-16 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1832 | 01E07V01 | 019 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | SERUI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1596/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1901 | 01E07V01 | 019 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | SERUI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1539.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2507300 | 2906200 | 5413500 | 5413500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2161 | 01E07V01 | 019 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | SORONG |  | TAHAP-1 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1367/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1833 | 01E07V01 | 019 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | SORONG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1597/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1013 | 01E07V01 | 019 | 74060042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | WARMARE / PRAFI |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1536.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 364 | 01E07V01 | 019 | 74060042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | SORONG | WARMARE / PRAFI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1023/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 529 | 01E07V01 | 019 | 73020057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | MANGOLE |  | FE-MGL-01-01 MANGOLE (SS#1) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-05-18 | K.TEL.1463/LG.310/DR7-12700000/2020 | 2020-10-16 | TEL.1570/LG.320/PND-A1000000/2020 | 2020-11-13 | 75930138 | 19546488 | 95476626 | 95476626 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 531 | 01E07V01 | 019 | 73020057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | MANGOLE |  | MANGOLE ODC-MGL-F.. (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-05-18 | TEL.1464/LG.310/DR7-12700000/2020 | 2020-11-12 | TEL.1569/LG.320/PND-A1000000/2020 | 2020-11-13 | 300798334 | 72126499 | 372924833 | 372924833 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 1941 | 01E07V01 | 019 | 73020034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | SOA SIU |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-22 | TEL.1638/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2187 | 01E07V01 | 019 | 73020034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | SOA SIU |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1404/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2176 | 01E07V01 | 019 | 73020034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | SOA SIU |  | TAHAP-1 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1375/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2188 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-3 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1405/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 506 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1052/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1267/LG.320/PND-A1000000/2020 | 2020-07-15 | 45632860 | 54242840 | 99875700 | 99875700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2055 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-4 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1378/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1087 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1630/LG.310/DR7-12700000/2020 | 2020-12-22 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 8023360 | 9299840 | 17323200 | 17323200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 474 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1045/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 36105120 | 42149280 | 78254400 | 78254400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1074 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1554/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 15043800 | 17437200 | 32481000 | 32481000 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1929 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TERNATE |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0303/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 479 | 01E07V01 | 019 | 73020044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | TERNATE | TOBELO |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1555/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2041 | 01E07V01 | 019 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | ANTANG |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1343/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 5516060 | 6393640 | 11909700 | 11909700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1784 | 01E07V01 | 019 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | ANTANG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1512.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 20058400 | 23249600 | 43308000 | 43308000 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1859 | 01E07V01 | 019 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | ANTANG |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0276/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2195 | 01E07V01 | 019 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | ANTANG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1380/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1860 | 01E07V01 | 019 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BALAIKOTA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1513/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 278811760 | 323319440 | 602131200 | 602131200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2196 | 01E07V01 | 019 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BALAIKOTA |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1381/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 48140160 | 56099040 | 104239200 | 104239200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2042 | 01E07V01 | 019 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BALAIKOTA |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1344/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 320432940 | 372462360 | 692895300 | 692895300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1787 | 01E07V01 | 019 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BALAIKOTA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1569.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 23568620 | 27318280 | 50886900 | 50886900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1861 | 01E07V01 | 019 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BALAIKOTA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0277/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 61679580 | 71942520 | 133622100 | 133622100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1862 | 01E07V01 | 019 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BANTAENG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1514.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1788 | 01E07V01 | 019 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BULUKUMBA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1571.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2215 | 01E07V01 | 019 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BULUKUMBA |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1382/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1877 | 01E07V01 | 019 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BULUKUMBA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1345/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 13037960 | 15112240 | 28150200 | 28150200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1863 | 01E07V01 | 019 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | BULUKUMBA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1515.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 10029200 | 11624800 | 21654000 | 21654000 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 987 | 01E07V01 | 019 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | JENEPONTO |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1507.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1789 | 01E07V01 | 019 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | JENEPONTO |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1572.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 324 | 01E07V01 | 019 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | JENEPONTO |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1011/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 2197 | 01E07V01 | 019 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | JENEPONTO |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1383/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2043 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-4 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1346/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 4513140 | 5231160 | 9744300 | 9744300 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 988 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1508/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2198 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-3 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1384/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 3008760 | 3787440 | 6796200 | 6796200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1780 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0278/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 327 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1012/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 11032120 | 12787280 | 23819400 | 23819400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 481 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1048/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1267/LG.320/PND-A1000000/2020 | 2020-07-15 | 19055480 | 22087120 | 41142600 | 41142600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1079 | 01E07V01 | 019 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | KIMA |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1566/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 6518980 | 7556120 | 14075100 | 14075100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2091 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | JL. POROS CAMBA (ODC) SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-01-13 | 2021-06-01 | 2021-03-01 | TEL.0646/LG.310/DR7-12700000/2021 | 2021-05-03 | TEL.0713/LG.320/PND-A1000000/2021 | 2021-05-03 | 48752930 | 13502407 | 62255337 | 62255337 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-06-28
12020104 | 30 | 525 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | NEW FEEDER NEW ODC 1 JL. POROS MAROS (SS#1) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-07-01 | TEL.1449/LG.310/DR7-12700000/2020 | 2020-09-03 | TEL.1570/LG.320/PND-A1000000/2020 | 2020-11-13 | 67556603 | 34191462 | 101748065 | 101748065 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 989 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1509/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 2507300 | 2906200 | 5413500 | 5413500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 526 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | NEW FEEDER NEW ODC 2 JL. POROS MARUMPA MAROS (SS#1) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-07-01 | TEL.1450/LG.310/DR7-12700000/2020 | 2020-09-03 | TEL.1570/LG.320/PND-A1000000/2020 | 2020-11-13 | 185769796 | 69531416 | 255301212 | 255301212 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 527 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | NEW FEEDER NEW ODC 03 JL.POLEJIWA (SS#1) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-07-01 | TEL.1458/LG.310/DR7-12700000/2020 | 2020-11-01 | TEL.1570/LG.320/PND-A1000000/2020 | 2020-11-13 | 152738826 | 41746289 | 194485115 | 194485115 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 532 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | NEW ODC 2 PERUM BOSOWA (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-10-01 | TEL.1460/LG.310/DR7-12700000/2020 | 2020-11-12 | TEL.1569/LG.320/PND-A1000000/2020 | 2020-11-13 | 109591186 | 28804491 | 138395677 | 138395677 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 533 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | ODC-SUD-OGP STTF 2 2020 JL. DARUL ISTIQOMAH (SS#2) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-17 | 2020-07-01 | TEL.1459/LG.310/DR7-12700000/2020 | 2020-11-12 | TEL.1569/LG.320/PND-A1000000/2020 | 2020-11-13 | 55974796 | 14930581 | 70905377 | 70905377 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-07
12020104 | 30 | 2147 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | TAHAP-3 MIGRASI CONS SS-3 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1347/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1790 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1573.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 15545260 | 18018440 | 33563700 | 33563700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2092 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | JL. POROS CAMBA (NEW MINI OLT) SS#1 FEEDER |  | 100 | 100 | 100 | BAST-1 | 2021-01-13 | 2021-06-01 | 2021-03-01 | TEL.0647/LG.310/DR7-12700000/2021 | 2021-05-03 | TEL.0714/LG.320/PND-A1000000/2021 | 2021-05-03 | 51641028 | 16835329 | 68476357 | 68476357 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-06-28
12020104 | 30 | 328 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MAROS |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1013/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 2005840 | 2324960 | 4330800 | 4330800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1080 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-2 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1567.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 36606580 | 46630520 | 83237100 | 83237100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2199 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-3 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1385/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2057 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-4 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1348/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 28583220 | 33130680 | 61713900 | 61713900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1782 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0279/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 16046720 | 18599680 | 34646400 | 34646400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 482 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-1 MIGRASI EBIS (SS#4) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1049/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1267/LG.320/PND-A1000000/2020 | 2020-07-15 | 46635780 | 55105320 | 101741100 | 101741100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 329 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1014/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 67697100 | 78467400 | 146164500 | 146164500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 990 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | MATTOANGIN |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1510/LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 87755500 | 102317000 | 190072500 | 190072500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2044 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANAKUKANG |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1349/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 96280320 | 111598080 | 207878400 | 207878400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1791 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANAKUKANG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1574.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 13539420 | 15843480 | 29382900 | 29382900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1864 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANAKUKANG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1517.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 216129260 | 250514440 | 466643700 | 466643700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1878 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANAKUKANG |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0280/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 12536500 | 14531000 | 27067500 | 27067500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2200 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANAKUKANG |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1386/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 63183960 | 73686240 | 136870200 | 136870200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2045 | 01E07V01 | 019 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANGKEP |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1350/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 2507300 | 2906200 | 5413500 | 5413500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1865 | 01E07V01 | 019 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANGKEP |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1518.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 13539420 | 15693480 | 29232900 | 29232900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2201 | 01E07V01 | 019 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANGKEP |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1387/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1879 | 01E07V01 | 019 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANGKEP |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0281/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 1792 | 01E07V01 | 019 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | PANGKEP |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1575.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1793 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SINJAI |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1576.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 330 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SINJAI |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-07-01 | TEL.1015/LG.310/DR7-12700000/2020 | 2020-07-15 | TEL.1266/LG.320/PND-A1000000/2020 | 2020-07-15 | 15545260 | 18018440 | 33563700 | 33563700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-10-13
12020104 | 30 | 1783 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SINJAI |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0282/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 991 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SINJAI |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-11-30 | TEL.1511.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1794 | 01E07V01 | 019 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUDIANG |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1577.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1866 | 01E07V01 | 019 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUDIANG |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1519.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 32594900 | 37780600 | 70375500 | 70375500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2202 | 01E07V01 | 019 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUDIANG |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1388/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 1504380 | 1743720 | 3248100 | 3248100 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1872 | 01E07V01 | 019 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUDIANG |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0283/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 3008760 | 3487440 | 6496200 | 6496200 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2047 | 01E07V01 | 019 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUDIANG |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1351/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 7020440 | 8137360 | 15157800 | 15157800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1867 | 01E07V01 | 019 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUNGGUMINASA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1520.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 55662060 | 64817640 | 120479700 | 120479700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1873 | 01E07V01 | 019 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUNGGUMINASA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0284/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 3510220 | 4068680 | 7578900 | 7578900 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2203 | 01E07V01 | 019 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUNGGUMINASA |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1389/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 501460 | 581240 | 1082700 | 1082700 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 2048 | 01E07V01 | 019 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUNGGUMINASA |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1352/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 5014600 | 5812400 | 10827000 | 10827000 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1795 | 01E07V01 | 019 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | SUNGGUMINASA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1578.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 2507300 | 3056200 | 5563500 | 5563500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1868 | 01E07V01 | 019 | 72080120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | TAKALAR |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1521.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1875 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | TAMALANREA |  | TAHAP-2 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-06-07 | 2021-03-15 | TEL.0285/LG.310/DR7-12700000/2021 | 2021-03-15 | TEL.0309/LG.320/PND-A1000000/2021 | 2021-03-15 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020104 | 30 | 2204 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | TAMALANREA |  | TAHAP-2 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1390/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0299/LG.320/DID-00000000/2021 | 2021-09-07 | 2005840 | 2474960 | 4480800 | 4480800 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1869 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | TAMALANREA |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1522.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 11032120 | 12787280 | 23819400 | 23819400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 2049 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | TAMALANREA |  | TAHAP-3 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-10-07 | 2021-09-07 | TEL.1353/LG.310/DR7-12700000/2021 | 2021-09-07 | TEL.0298/LG.320/DID-00000000/2021 | 2021-09-16 | 4011680 | 4799920 | 8811600 | 8811600 | 4500408290 |  |  |  |  | TELKOM AKSES | 2021-09-30
12020104 | 30 | 1822 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | TAMALANREA |  | TAHAP-1 MIGRASI EBIS SS4 |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1580.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1830/LG.320/PND-A1000000/2020 | 2020-12-22 | 7521900 | 8718600 | 16240500 | 16240500 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020104 | 30 | 1870 | 01E07V01 | 019 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002752/HK.810/OPS-10000000/2020 | SP#17 Granular Modernization - OSP FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2020-05-18 | 2021-09-30 | GRANULAR 2020 | UJUNGPANDANG | WATAMPONE |  | TAHAP-1 MIGRASI CONS (SS#3) |  | 100 | 100 | 100 | BAST-1 | 2020-05-18 | 2021-01-19 | 2020-12-21 | TEL.1523.LG.310/DR7-12700000/2020 | 2020-12-21 | TEL.1829/LG.320/PND-A1000000/2020 | 2020-12-21 | 1002920 | 1162480 | 2165400 | 2165400 | 4500408290 |  |  |  |  | TELKOM AKSES | 2020-12-29
12020110 | 32 | 91 | 01C11G01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | GORONTALO | ISIMU |  | ISM029 (ATINGOLA2 - ODC KWD FAE) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7548/LG.310/PND-C1010000/2020 | 2020-06-18 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 71122712 | 20525269 | 91647981 | 91647981 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 92 | 01C11G01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | GORONTALO | ISIMU |  | ISM012 (TANJUNG KARANG - OCD KWD FAB) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7549/LG.310/PND-C1010000/2020 | 2020-06-18 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 151479928 | 46768007 | 198247935 | 198247935 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 202 | 01C11G01 | 019 | 72020019 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | GORONTALO | KWANDANG |  | ISM026 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2020-12-27 | 2020-09-01 | TEL.8869/LG.310/PND-C1010000/2020 | 2020-10-26 | TEL.1539/LG.320/PND-A1000000/2020 | 2020-10-26 | 9579072 | 3011850 | 12590922 | 12590922 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-11-30
12020110 | 32 | 152 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | ABEPURA |  | WRS042 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | 8009/LG.310/PND-C1010000/2020 | 2020-08-03 | TEL.0071/LG.320/PND-A1000000/2021 | 2020-09-22 | 193573105 | 45313093 | 238886198 | 238886198 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-01
12020110 | 32 | 148 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | ABEPURA |  | WRS003 (ARSO PIR II) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-03-07 | 2020-06-01 | TEL.314/LG.310/PND-C1010000/2021 | 2021-02-01 | TEL.0292/LG.320/PND-A1000000/2021 | 2021-02-01 | 1942802087 | 2859817082 | 4802619169 | 4802619169 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020110 | 32 | 151 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | ABEPURA |  | JAP759 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | 8499/LG.310/PND-C1010000/2020 | 2020-09-22 | TEL.0071/LG.320/PND-A1000000/2021 | 2020-09-22 | 324759226 | 60806343 | 385565569 | 385565569 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-01
12020110 | 32 | 149 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | ABEPURA |  | WRS006 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-03-07 | 2020-06-01 | TEL.484/LG.310/PND-C1010000/2021 | 2021-02-18 | TEL.0487/LG.320/PND-A1000000/2021 | 2021-04-23 | 625152274 | 131721944 | 756874218 | 756874218 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020110 | 32 | 150 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | ABEPURA |  | WRS002 (KOYA BARAT) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | TEL.8761/LG.310/PND-C1010000/2020 | 2020-10-16 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 288918948 | 118593152 | 407512100 | 407512100 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 154 | 01C11G01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | JAYAPURA |  | WRS037 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | 8011/LG.310/PND-C1010000/2020 | 2020-08-10 | TEL.0071/LG.320/PND-A1000000/2021 | 2020-09-22 | 70168808 | 21599882 | 91768690 | 91768690 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-01
12020110 | 32 | 153 | 01C11G01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | JAYAPURA |  | COK070 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | 8010/LG.310/PND-C1010000/2020 | 2020-08-03 | TEL.0071/LG.320/PND-A1000000/2021 | 2020-09-22 | 99216402 | 35470661 | 134687063 | 134687063 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-01
12020110 | 32 | 159 | 01C11G01 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | NABIRE |  | NAB010 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8031/LG.310/PND-C1010000/2020 | 2020-08-05 | TEL.1539/LG.320/PND-A1000000/2020 | 2020-10-26 | 16075919 | 7357467 | 23433386 | 23433386 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-11-30
12020110 | 32 | 158 | 01C11G01 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | NABIRE |  | NAB008 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-01-17 | 2020-05-22 | TEL.9506/LG.310/PND-C1010000/2020 | 2020-12-29 | TEL.1832/LG.320/PND-A1000000/2020 | 2020-12-29 | 1587869553 | 395595760 | 1983465313 | 1983465313 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020110 | 32 | 258 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | JAYAPURA | WAMENA |  | WRS086 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-06-16 | TEL.3350/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 100624813 | 22376623 | 123001436 | 123001436 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 247 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU008 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-05-18 | TEL.3351/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 26058074 | 8399489 | 34457563 | 34457563 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 137 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU056 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-08-01 | 8238/LG.310/PND-C1010000/2020 | 2020-08-25 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 8701790 | 4246477 | 12948267 | 12948267 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 135 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU022 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7629/LG.310/PND-C1010000/2020 | 2020-06-26 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 3706814007 | 734634850 | 4441448857 | 4441448857 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 138 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU024 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7631/LG.310/PND-C1010000/2020 | 2020-06-26 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 245615925 | 60644682 | 306260607 | 306260607 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 134 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU003 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7628/LG.310/PND-C1010000/2020 | 2020-06-26 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 14945674 | 5981122 | 20926796 | 20926796 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 139 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU023 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7630/LG.310/PND-C1010000/2020 | 2020-06-26 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 47561812 | 16526027 | 64087839 | 64087839 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 246 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | BAU-BAU |  | BAU036 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-05-18 | TEL.3261/LG.310/PND-C1010000/2021 | 2021-10-25 | TEL.0603/LG.320/DID-00000000/2021 | 2021-10-25 | 985826290 | 164071653 | 1149897943 | 1149897943 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-11-26
12020110 | 32 | 143 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KENDARI |  | ADL045 (LADONGI KENDARI) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7900/LG.310/PND-C1010000/2020 | 2020-07-24 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 535798370 | 107087406 | 642885776 | 642885776 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 249 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KENDARI |  | KDI076 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-05-10 | TEL.3352/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 369634089 | 77899009 | 447533098 | 447533098 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 142 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KENDARI |  | KDI013 (LANDONO MANDONGA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7899/LG.310/PND-C1010000/2020 | 2020-07-24 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 1469671709 | 331187323 | 1800859032 | 1800859032 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 140 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KENDARI |  | ADL035 (LASOLO) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-02-11 | 2020-05-22 | TEL.0269/LG.310/PND-C1010000/2021 | 2021-01-28 | TEL.0195/LG.320/DID-00000000/2021 | 2021-01-28 | 3980303663 | 1100054700 | 5080358363 | 5080358363 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-09-21
12020110 | 32 | 208 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KOLAKA |  | KKA180 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2021-01-01 | 2020-12-01 | TEL.9472/LG.310/PND-C1010000/2020 | 2020-12-28 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 130529059 | 31096883 | 161625942 | 161625942 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 144 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KOLAKA |  | KKA018 (ULU KONAWEHA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8159./LG.310/PND-C1010000/2020 | 2020-08-18 | TEL.1832/LG.320/PND-A1000000/2020 | 2020-12-29 | 2050647298 | 421001407 | 2471648705 | 2471648705 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020110 | 32 | 243 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KOLAKA |  | KKA053 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-05-10 | TEL.3262/LG.310/PND-C1010000/2021 | 2021-10-25 | TEL.0603/LG.320/DID-00000000/2021 | 2021-10-25 | 698899813 | 117633004 | 816532817 | 816532817 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-11-26
12020110 | 32 | 244 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KOLAKA |  | KKA060 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-05-10 | TEL.3263/LG.310/PND-C1010000/2021 | 2021-10-25 | TEL.0603/LG.320/DID-00000000/2021 | 2021-10-25 | 27126636 | 8208157 | 35334793 | 35334793 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-11-26
12020110 | 32 | 245 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | KOLAKA |  | KKA032 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-05-10 | TEL.3264/LG.310/PND-C1010000/2021 | 2021-10-25 | TEL.0603/LG.320/DID-00000000/2021 | 2021-10-25 | 8581212 | 3340317 | 11921529 | 11921529 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-11-26
12020110 | 32 | 127 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | RAHA |  | RHA009 (LAWA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-02-11 | 2020-05-22 | TEL.0211/LG.310/PND-C1010000/2021 | 2021-01-22 | TEL.0292/LG.320/PND-A1000000/2021 | 2021-02-01 | 62182047 | 31210123 | 93392170 | 93392170 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020110 | 32 | 126 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | RAHA |  | RHA007 (TONGKUNO) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-02-11 | 2020-05-22 | TEL.0191//LG.310/PND-C1010000/2021 | 2021-01-20 | TEL.0579/LG.320/PND-A1000000/2021 | 2021-03-31 | 2698938618 | 2620767143 | 5319705761 | 5319705761 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-05-29
12020110 | 32 | 131 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | RAHA |  | KKA027 (BONEA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-02-11 | 2020-05-22 | TEL.9507/LG.310/PND-C1010000/2020 | 2020-12-29 | TEL.0292/LG.320/PND-A1000000/2021 | 2021-02-01 | 700578339 | 136718554 | 837296893 | 837296893 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020110 | 32 | 130 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | RAHA |  | RHA019 (WATUPUTE) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8763/LG.310/PND-C1010000/2020 | 2020-10-16 | TEL.0292/LG.320/PND-A1000000/2021 | 2021-02-01 | 62753761 | 24994857 | 87748618 | 87748618 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020110 | 32 | 129 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | RAHA |  | RHA010 (WASOLANGKA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-02-11 | 2020-05-22 | TEL.0182/LG.310/PND-C1010000/2021 | 2021-01-19 | TEL.0292/LG.320/PND-A1000000/2021 | 2021-02-01 | 317029023 | 692253240 | 1009282263 | 1009282263 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020110 | 32 | 128 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | KENDARI | RAHA |  | RHA008 (KABAWO) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-02-11 | 2020-05-22 | TEL.0181/LG.310/PND-C1010000/2021 | 2021-01-19 | TEL.0292/LG.320/PND-A1000000/2021 | 2021-02-01 | 61337834 | 40403219 | 101741053 | 101741053 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-03-28
12020110 | 32 | 86 | 01C11G01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANADO | BITUNG |  | BIT012 (MARINSOW - NEW ODC) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-04-14 | 2020-06-01 | TEL.899/LG.310/PND-C1010000/2021 | 2021-03-31 | TEL.0579/LG.320/PND-A1000000/2021 | 2021-03-31 | 260027163 | 371852451 | 631879614 | 631879614 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-05-29
12020110 | 32 | 87 | 01C11G01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANADO | BITUNG |  | BIT801 (MARINSOW - NEW ODC) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-04-14 | 2020-06-01 | TEL.900/LG.310/PND-C1010000/2021 | 2021-03-31 | TEL.0579/LG.320/PND-A1000000/2021 | 2021-03-31 | 610286189 | 787915217 | 1398201406 | 1398201406 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-05-29
12020110 | 32 | 88 | 01C11G01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANADO | BITUNG |  | BIT009 (MARINSOW - NEW ODC) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-04-14 | 2020-06-01 | TEL.901/LG.310/PND-C1010000/2021 | 2021-03-31 | TEL.0579/LG.320/PND-A1000000/2021 | 2021-03-31 | 107718348 | 134382779 | 242101127 | 242101127 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-05-29
12020110 | 32 | 89 | 01C11G01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANADO | BITUNG |  | BIT017 (MARINSOW - NEW ODC) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-04-14 | 2020-06-01 | TEL.902/LG.310/PND-C1010000/2021 | 2021-03-31 | TEL.0579/LG.320/PND-A1000000/2021 | 2021-03-31 | 167378392 | 211951761 | 379330153 | 379330153 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-05-29
12020110 | 32 | 90 | 01C11G01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANADO | TONDANO |  | TDO020 (TANAHWANGKO - ODC BAH FZA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7618/LG.310/PND-C1010000/2020 | 2020-06-25 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 25389181 | 15697770 | 41086951 | 41086951 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 156 | 01C11G01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANOKWARI | MANOKWARI |  | MWR081 (ODC MWR FM) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8030/LG.310/PND-C1010000/2020 | 2020-08-05 | TEL.1539/LG.320/PND-A1000000/2020 | 2020-10-26 | 143721913 | 45376748 | 189098661 | 189098661 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-11-30
12020110 | 32 | 155 | 01C11G01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | MANOKWARI | MANOKWARI |  | MWR009 (ODC MWR FM) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-01-31 | 2020-05-22 | TEL.0131/LG.310/PND-C1010000/2021 | 2021-01-15 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 1311149524 | 376361748 | 1687511272 | 1687511272 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 94 | 01C11G01 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | BANGGAI |  | SAK027 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8501/LG.310/PND-C1010000/2020 | 2020-09-23 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 732960664 | 147372081 | 880332745 | 880332745 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 93 | 01C11G01 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | BANGGAI |  | SAK006 (REPEATER ALAKASING) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8500/LG.310/PND-C1010000/2020 | 2020-09-23 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 664169738 | 124079842 | 788249580 | 788249580 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 95 | 01C11G01 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | BANGGAI |  | SAK007 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8502/LG.310/PND-C1010000/2020 | 2020-09-23 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 3963307178 | 733170297 | 4696477475 | 4696477475 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 252 | 01C11G01 | 019 | 72030012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | BUNGKU |  | COI608 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-09-01 | TEL.3354/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 20204157 | 3995314 | 24199471 | 24199471 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 96 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | DONGGALA |  | DGL003 (REPEATER TAZAN) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-08-15 | 2020-06-01 | TEL.2162/LG.310/PND-C1010000/2021 | 2021-07-24 | TEL.0033/LG.320/DID-00000000/2021 | 2021-07-24 | 464426481 | 417313735 | 881740216 | 881740216 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-08-29
12020110 | 32 | 98 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | DONGGALA |  | DGL027 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-08-15 | 2020-06-01 | TEL.2161/LG.310/PND-C1010000/2021 | 2021-07-24 | TEL.0033/LG.320/DID-00000000/2021 | 2021-07-24 | 19878573 | 8946526 | 28825099 | 28825099 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-08-29
12020110 | 32 | 97 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | DONGGALA |  | DGL008 (LOMBONGA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-08-15 | 2020-06-01 | TEL.2158/LG.310/PND-C1010000/2021 | 2021-07-24 | TEL.0033/LG.320/DID-00000000/2021 | 2021-07-24 | 1599468348 | 1330168658 | 2929637006 | 2929637006 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-08-29
12020110 | 32 | 100 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | DONGGALA |  | DGL006 (ALINDAU) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-08-15 | 2020-06-01 | TEL.2160/LG.310/PND-C1010000/2021 | 2021-07-24 | TEL.0033/LG.320/DID-00000000/2021 | 2021-07-24 | 2458936215 | 1450622789 | 3909559004 | 3909559004 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-08-29
12020110 | 32 | 99 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | DONGGALA |  | DGL007 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-08-15 | 2020-06-01 | TEL.2159/LG.310/PND-C1010000/2021 | 2021-07-24 | TEL.0033/LG.320/DID-00000000/2021 | 2021-07-24 | 31244915 | 10527412 | 41772327 | 41772327 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-08-29
12020110 | 32 | 255 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | KOLONODALE |  | MRW058 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-09-01 | TEL.3356/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 144508511 | 21902541 | 166411052 | 166411052 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 254 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | KOLONODALE |  | MRW100 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-09-01 | TEL.3357/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 141313736 | 20810542 | 162124278 | 162124278 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 253 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | KOLONODALE |  | MRW030 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-09-01 | TEL.3355/LG.310/PND-C1010000/202 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 60075593 | 10963971 | 71039564 | 71039564 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 103 | 01C11G01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | LUWUK |  | LWK059 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-05-14 | 2020-05-22 | TEL.1129/LG.310/PND-C1010000/2021 | 2021-04-23 | TEL.0487/LG.320/PND-A1000000/2021 | 2021-04-23 | 506328808 | 146350683 | 652679491 | 652679491 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020110 | 32 | 101 | 01C11G01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | LUWUK |  | LWK002 (TOILI) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | TEL.8764/LG.310/PND-C1010000/2020 | 2020-10-16 | TEL.0487/LG.320/PND-A1000000/2021 | 2021-04-23 | 566388862 | 430227544 | 996616406 | 996616406 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020110 | 32 | 102 | 01C11G01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | LUWUK |  | LWK070 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-06-01 | TEL.8765/LG.310/PND-C1010000/2021 | 2020-10-16 | TEL.0487/LG.320/PND-A1000000/2021 | 2021-04-23 | 135066011 | 123135092 | 258201103 | 258201103 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020110 | 32 | 256 | 01C11G01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | LUWUK |  | LWK140 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-09-01 | TEL.3358/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 28468604 | 5804163 | 34272767 | 34272767 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 105 | 01C11G01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | PALU |  | PAL017 (MARANATHA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8111/LG.310/PND-C1010000/2020 | 2020-08-18 | TEL.1051/LG.320/PND-A1000000/2020 | 2020-08-18 | 149869345 | 34128090 | 183997435 | 183997435 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-08-31
12020110 | 32 | 206 | 01C11G01 | 019 | 72030092 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | PALU B |  | PAL113 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2021-01-01 | 2020-10-06 | TEL.9496/LG.310/PND-C1010000/2020 | 2020-12-29 | TEL.0135/LG.320/PND-A1000000/2021 | 2021-01-15 | 25690697 | 6226712 | 31917409 | 31917409 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-02-27
12020110 | 32 | 104 | 01C11G01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | PARIGI |  | PGI008 (TINOMBO) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8112/LG.310/PND-C1010000/2020 | 2020-08-18 | TEL.1051/LG.320/PND-A1000000/2020 | 2020-08-18 | 24643979 | 6516581 | 31160560 | 31160560 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-08-31
12020110 | 32 | 207 | 01C11G01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PALU | TAWAELI |  | DGL105 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2021-04-02 | 2020-06-01 | TEL.9508/LG.310/PND-C1010000/2020 | 2020-12-29 | TEL.0487/LG.320/PND-A1000000/2021 | 2021-04-23 | 27468185 | 10096431 | 37564616 | 37564616 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-04-30
12020110 | 32 | 115 | 01C11G01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PARE-PARE | MAMUJU |  | MAM006 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-07-06 | 8489/LG.310/PND-C1010000/2020 | 2020-09-18 | TEL.1539/LG.320/PND-A1000000/2020 | 2020-10-26 | 59642863 | 18190360 | 77833223 | 77833223 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-11-30
12020110 | 32 | 108 | 01C11G01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PARE-PARE | PASANG KAYU |  | PSK011 |  | 95 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-12-14 | 2020-05-22 | TEL.3639/LG.310/PND-C1010000/2021 | 2021-11-17 | TEL.0605/LG.320/DID-00000000/2021 | 2021-11-17 | 379481142 | 425931091 | 805412233 | 805412233 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-11-26
12020110 | 32 | 106 | 01C11G01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PARE-PARE | PASANG KAYU |  | PSK086 |  | 95 | 100 | 100 | BAST-1 | 2020-05-22 | 2021-12-14 | 2021-05-01 | TEL.3640/LG.310/PND-C1010000/2021 | 2021-11-17 | TEL.0605/LG.320/DID-00000000/2021 | 2021-11-17 | 19505911 | 12425106 | 31931017 | 31931017 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-11-26
12020110 | 32 | 114 | 01C11G01 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PARE-PARE | SENGKANG |  | SKG006 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | 8488/LG.310/PND-C1010000/2020 | 2020-09-18 | TEL.1539/LG.320/PND-A1000000/2020 | 2020-10-26 | 359275470 | 78034708 | 437310178 | 437310178 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-11-30
12020110 | 32 | 113 | 01C11G01 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PARE-PARE | SENGKANG |  | SKG001 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | 7940/LG.310/PND-C1010000/2020 | 2020-07-31 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 6637980 | 1609587 | 8247567 | 8247567 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 112 | 01C11G01 | 019 | 72040186 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | PARE-PARE | WATANSOPPENG |  | WTG004 |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | 7939/LG.310/PND-C1010000/0000/2020 | 2020-07-31 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 7011424 | 2152635 | 9164059 | 9164059 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 147 | 01C11G01 | 019 | 73020019 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | TERNATE | MOROTAI |  | TOB008 (REPEATER PACA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8169/LG.310/PND-C1010000/2020 | 2020-08-21 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 1505072978 | 1143206847 | 2648279825 | 2648279825 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 146 | 01C11G01 | 019 | 73020019 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | TERNATE | MOROTAI |  | TOB006 (DARU PEDIWANG) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.8159/LG.310/PND-C1010000/2020 | 2020-08-21 | TEL.1206/LG.320/PND-A1000000/2020 | 2020-08-25 | 1108214097 | 1365165522 | 2473379619 | 2473379619 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-09-29
12020110 | 32 | 145 | 01C11G01 | 019 | 73020032 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | TERNATE | SANANA |  | SNN005 (TBG WAIHAMA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7594/LG.310/PND-C1010000/2020 | 2020-06-23 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 27623409 | 8268172 | 35891581 | 35891581 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 125 | 01C11G01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | SIN007 (MANNANTI) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7561/LG.310/PND-C1010000/2020 | 2020-06-19 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 839816953 | 177295494 | 1017112447 | 1017112447 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 250 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | SKG036 |  | 95 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-14 | 2021-10-04 | TEL.3353/LG.310/PND-C1010000/2021 | 2021-10-27 | TEL.0488/LG.320/DID-00000000/2021 | 2021-10-27 | 510155232 | 89866945 | 600022177 | 600022177 | 4500408544 |  |  |  |  | TELKOM AKSES | 2021-10-30
12020110 | 32 | 124 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP057 (AJANGALE) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7558/LG.310/PND-C1010000/2020 | 2020-06-19 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 625505503 | 129706099 | 755211602 | 755211602 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 123 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP015 (CAMMING) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7560/LG.310/PND-C1010000/2020 | 2020-06-19 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 420725947 | 115592858 | 536318805 | 536318805 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 204 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP084 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2020-12-27 | 2020-09-23 | TEL.9313/LG.310/PND-C1010000/2020 | 2020-12-11 | TEL.1832/LG.320/PND-A1000000/2020 | 2020-12-29 | 93784304 | 27023707 | 120808011 | 120808011 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020110 | 32 | 205 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP050 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2020-12-27 | 2020-09-23 | TEL.9312/LG.310/PND-C1010000/2020 | 2020-12-11 | TEL.1832/LG.320/PND-A1000000/2020 | 2020-12-29 | 7776533 | 2582065 | 10358598 | 10358598 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-12-30
12020110 | 32 | 203 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP004 |  | 100 | 100 | 100 | BAST-1 | 2020-08-27 | 2020-12-27 | 2020-09-01 | TEL.8870/LG.310/PND-C1010000/2020 | 2020-10-26 | TEL.1539/LG.320/PND-A1000000/2020 | 2020-10-26 | 6032338 | 1786179 | 7818517 | 7818517 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-11-30
12020110 | 32 | 120 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP031 (BENGO BONE) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7559/LG.310/PND-C1010000/2020 | 2020-06-19 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 46904810 | 14400201 | 61305011 | 61305011 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020110 | 32 | 121 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002846/HK.810/OPS-10000000/2020 | Surat Pesanan-19 (SP#19) Pengadaan dan Pemasangan Granular Modernization - OSP FO Node-B Telkomsel | 2020-05-22 | 2021-11-30 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | WTP039 (RAJA) |  | 100 | 100 | 100 | BAST-1 | 2020-05-22 | 2020-11-01 | 2020-05-22 | TEL.7562/LG.310/PND-C1010000/2020 | 2020-06-19 | TEL.0908/LG.320/PND-A1000000/2020 | 2020-06-25 | 69787590 | 21452650 | 91240240 | 91240240 | 4500408544 |  |  |  |  | TELKOM AKSES | 2020-07-29
12020119 | 26 | 59 | 01C11I04 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | GORONTALO | GORONTALO |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 107 | 01C11I04 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | KENDARI | KENDARI |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 60 | 01C11I04 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | KENDARI | KENDARI |  | STO KENDARI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | LAMPIRAN_KENDARI_1 | 2020-05-29 | TEL.1299/LG.320/PND-A1000000/2020 | 2020-05-29 | 108474900 | 0 | 108474900 | 108474900 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-10-27
12020119 | 26 | 67 | 01C11I04 | 019 | 72040193 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | BARRU |  | STO BARRU REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | LAMPIRAN_BARRU_1 | 2020-05-29 | TEL.1299/LG.320/PND-A1000000/2020 | 2020-05-29 | 311321350 | 0 | 311321350 | 311321350 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-10-27
12020119 | 26 | 105 | 01C11I04 | 019 | 72040193 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | BARRU |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 68 | 01C11I04 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | PALOPO |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 66 | 01C11I04 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | PARE-PARE |  | STO PARE-PARE REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | TEL.075/PRE/MML/PRIM-13022025 | 2020-05-29 | TEL.1299/LG.320/PND-A1000000/2020 | 2020-05-29 | 1706780522 | 0 | 1706780522 | 1706780522 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-10-27
12020119 | 26 | 215 | 01C11I04 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | PARE-PARE |  | STO PARE-PARE REKON-02 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2022-01-14 | 2020-07-11 | LAMPIRAN_STO_PARE_PARE_2 | 2020-07-11 | TEL.0451/LG.320/DID-A0000000/2022 | 2020-07-11 | 293984570 | 0 | 293984570 | 293984570 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12020119 | 26 | 109 | 01C11I04 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | PARE-PARE |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 216 | 01C11I04 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | RANTEPAO |  | STO RANTEPAO REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2022-01-14 | 2020-07-11 | LAMPIRAN_STO_RANTEPAO_1 | 2020-07-11 | TEL.0451/LG.320/DID-A0000000/2022 | 2020-07-11 | 127959220 | 0 | 127959220 | 127959220 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12020119 | 26 | 69 | 01C11I04 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | RANTEPAO |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 70 | 01C11I04 | 019 | 72040135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | RAPPANG |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 217 | 01C11I04 | 019 | 72040135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | RAPPANG |  | STO RAPPANG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2022-01-14 | 2020-06-11 | LAMPIRAN_STO_RAPPANG_1 | 2020-06-11 | TEL.0451/LG.320/DID-A0000000/2022 | 2020-07-11 | 72610030 | 0 | 72610030 | 72610030 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12020119 | 26 | 71 | 01C11I04 | 019 | 72040158 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | SIDRAP |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 72 | 01C11I04 | 019 | 72040161 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | PARE-PARE | SOROWAKO |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 65 | 01C11I04 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | TERNATE | TERNATE |  |  |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 61 | 01C11I04 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | BULUKUMBA |  | STO BULUKUMBA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | LAMPIRAN_BULUKUMBA_1 | 2020-05-29 | TEL.1299/LG.320/PND-A1000000/2020 | 2020-05-29 | 82368250 | 0 | 82368250 | 82368250 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-10-27
12020119 | 26 | 106 | 01C11I04 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | BULUKUMBA |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 214 | 01C11I04 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | MATTOANGIN |  | STO MATTOANGIN REKON-02 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2022-01-14 | 2020-05-29 | LAMPIRAN_STO_MATTOANGIN_2 | 2020-05-29 | TEL.0451/LG.320/DID-A0000000/2022 | 2020-07-11 | 138352350 | 0 | 138352350 | 138352350 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12020119 | 26 | 62 | 01C11I04 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | MATTOANGIN |  | STO MATTOANGIN REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | TEL.294/MTN/MML/30042020 | 2020-07-05 | TEL.1114/LG.320/PND-A1000000/2020 | 2020-07-05 | 4661315540 | 0 | 4661315540 | 4661315540 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-09-18
12020119 | 26 | 88 | 01C11I04 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | MATTOANGIN |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 108 | 01C11I04 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | PANGKEP |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 63 | 01C11I04 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | PANGKEP |  | STO PANGKEP REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | LAMPIRAN_PANGKEP_1 | 2020-05-29 | TEL.1299/LG.320/PND-A1000000/2020 | 2020-05-29 | 45869550 | 0 | 45869550 | 45869550 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-10-27
12020119 | 26 | 110 | 01C11I04 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | SUNGGUMINASA |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-05-29 | 2022-01-14 | 2020-05-29 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020119 | 26 | 87 | 01C11I04 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | SUNGGUMINASA |  | STO SUNGGUMINASA REKON-02 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | LAMPIRAN_SUNGGUMINASA_2 | 2020-05-29 | TEL.1299/LG.320/PND-A1000000/2020 | 2020-05-29 | 174942700 | 0 | 174942700 | 174942700 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-10-27
12020119 | 26 | 64 | 01C11I04 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002959/HK.810/OPS-10000000/2020 | Surat Pesanan-4 (SP#4) Penjualan Barang Scrap TELKOM | 2020-05-29 | 2022-06-30 | PELOLOSAN | UJUNGPANDANG | SUNGGUMINASA |  | STO SUNGGUMINASA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-05-29 | 2021-01-01 | 2020-05-29 | TEL.362/SNS/MML/01042020 | 2020-05-29 | TEL.1114/LG.320/PND-A1000000/2020 | 2020-07-05 | 7247618113 | 0 | 7247618113 | 7247618113 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2020-09-18
12020169 | 28 | 82 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | GORONTALO |  | GORONTALO GTO193 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-01-28 | 2021-01-21 | TEL.1920/LG.310/DR7-12700000/2020 | 2021-01-27 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 9709728 | 2828420 | 12538148 | 12538148 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 83 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | GORONTALO |  | GORONTALO GTO194 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-01-28 | 2021-01-21 | TEL.1916/LG.310/DR7-12700000/2020 | 2021-01-27 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 10377709 | 2870394 | 13248103 | 13248103 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 80 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | GORONTALO |  | GORONTALO ISM130 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-01-28 | 2021-01-21 | TEL.1918/LG.310/DR7-12700000/2020 | 2021-01-27 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 6758476 | 2167453 | 8925929 | 8925929 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 81 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | GORONTALO |  | GORONTALO GTO188 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-01-28 | 2021-01-21 | TEL.1919/LG.310/DR7-12700000/2020 | 2021-01-27 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 64644502 | 17312980 | 81957482 | 81957482 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 84 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | GORONTALO |  | GORONTALO GTO199 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-01-28 | 2021-01-21 | TEL.1917/LG.310/DR7-12700000/2020 | 2021-01-27 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 53216678 | 16386824 | 69603502 | 69603502 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 79 | 01E07V01 | 019 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | MARISA |  | MARISA COI938 eks COI978 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-05-22 | 2021-08-25 | TEL.1282/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0079/LG.320/DID-00000000/2021 | 2021-08-26 | 99980074 | 21443005 | 121423079 | 121423079 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-08-31
12020169 | 28 | 48 | 01E07V01 | 019 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | GORONTALO | MARISA |  | MARISA (MRA005) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-05-22 | 2021-08-25 | TEL.1283/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0079/LG.320/DID-00000000/2021 | 2021-08-26 | 694966347 | 332171977 | 1027138324 | 1027138324 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-08-31
12020169 | 28 | 159 | 01E07V01 | 019 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | KENDARI |  | KENDARI ADL035 eks ADL100 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-16 | 2021-12-29 | TEL.645/LG.310/DR7-12700000/2022 | 2022-02-16 | TEL.0143/LG.320/DID-A0000000/2022 | 2022-02-16 | 1843918675 | 376954275 | 2220872950 | 2220872950 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-02-27
12020169 | 28 | 163 | 01E07V01 | 019 | 72050123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | MUNA |  | RAHA PULAU MUNA BAU014 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-03-08 | TEL.0309/LG.310/DR7-12700000/2020 | 2021-03-23 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 931639125 | 202438680 | 1134077805 | 1134077805 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 166 | 01E07V01 | 019 | 72050123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | MUNA |  | RAHA PULAU MUNA BAU082 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-03-08 | TEL.0311/LG.310/DR7-12700000/2020 | 2021-03-20 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 157994051 | 40559248 | 198553299 | 198553299 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 161 | 01E07V01 | 019 | 72050123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | MUNA |  | RAHA PULAU MUNA BAU234 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-03-08 | TEL.0312/LG.310/DR7-12700000/2020 | 2021-03-20 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 869559004 | 177820237 | 1047379241 | 1047379241 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 160 | 01E07V01 | 019 | 72050123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | MUNA |  | RAHA PULAU MUNA BAU075 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-03-08 | TEL.0310/LG.310/DR7-12700000/2020 | 2021-03-20 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 1057537748 | 225974837 | 1283512585 | 1283512585 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 78 | 01E07V01 | 019 | 72050123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | MUNA |  | RAHA PULAU MUNA RHA028 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-03-19 | TEL.0314/LG.310/DR7-12700000/2020 | 2021-03-23 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 310624584 | 64902590 | 375527174 | 375527174 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 165 | 01E07V01 | 019 | 72050123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | MUNA |  | RAHA PULAU MUNA RHA012 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-03-19 | TEL.0313/LG.310/DR7-12700000/2020 | 2021-03-20 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 820865433 | 171719213 | 992584646 | 992584646 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 157 | 01E07V01 | 019 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | POMALAA |  | POMALAA KKA166 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-09-09 | TEL.1590/LG.310/DR7-12700000/2021 | 2021-09-14 | TEL.0595/LG.320/DID-00000000/2021 | 2021-09-14 | 242191321 | 87676123 | 329867444 | 329867444 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-11-23
12020169 | 28 | 65 | 01E07V01 | 019 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | POMALAA |  | POMALAA (KKA091) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-03-23 | TEL.1589/LG.310/DR7-12700000/2021 | 2021-09-13 | TEL.0595/LG.320/DID-00000000/2021 | 2021-09-14 | 1921072281 | 382433150 | 2303505431 | 2303505431 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-11-23
12020169 | 28 | 153 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA UNH015 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-19 | 2021-09-03 | TEL.1292/LG.310/DR7-12700000/2021 | 2021-09-06 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 591403550 | 118381869 | 709785419 | 709785419 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 152 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA UNH032 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-21 | 2021-09-03 | TEL.1293/LG.310/DR7-12700000/2021 | 2021-09-06 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 10992702 | 4689815 | 15682517 | 15682517 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 64 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA (KDI085) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-12-03 | TEL.2103/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0143/LG.320/DID-A0000000/2022 | 2022-02-16 | 1632508253 | 343457869 | 1975966122 | 1975966122 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-02-27
12020169 | 28 | 63 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA (KDI031) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-12-03 | TEL.2099/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0356/LG.320/DID-A0000000/2021 | 2021-12-29 | 37077289 | 25618760 | 62696049 | 62696049 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-30
12020169 | 28 | 154 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA KDI054 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-12-03 | TEL.2100/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0356/LG.320/DID-A0000000/2021 | 2021-12-29 | 2513998346 | 483104334 | 2997102680 | 2997102680 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-30
12020169 | 28 | 155 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA KDI086 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-12-03 | TEL2102/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0356/LG.320/DID-A0000000/2021 | 2021-12-29 | 35473967 | 24611144 | 60085111 | 60085111 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-30
12020169 | 28 | 156 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | KENDARI | UNAAHA |  | UNAHAA KDI065 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-10-16 | 2021-12-03 | TEL.2101/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0356/LG.320/DID-A0000000/2021 | 2021-12-29 | 52286956 | 27213328 | 79500284 | 79500284 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-30
12020169 | 28 | 187 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | BEO |  | BEO MGN019 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-05-04 | 2021-04-29 | TEL.0519/LG.310/DR7-12700000/2021 | 2021-05-08 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 702051176 | 159880682 | 861931858 | 861931858 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 186 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | BEO |  | BEO MGN003 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-05-04 | 2021-04-29 | TEL.0518/LG.310/DR7-12700000/2021 | 2021-05-08 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 44301155 | 13273549 | 57574704 | 57574704 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 185 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | BEO |  | BEO MGN007 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2022-03-19 | 2022-03-18 | TEL.727/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0636/LG.320/DID-A0000000/2022 | 2022-03-18 | 508067238 | 764238240 | 1272305478 | 1272305478 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-05-29
12020169 | 28 | 49 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | KOTAMOBAGU |  | KOTAMOBAGU (KTG045) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-09-01 | 2020-12-16 | TEL.1498/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0486/LG.320/DID-00000000/2021 | 2021-09-15 | 405169039 | 305532020 | 710701059 | 710701059 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-10-30
12020169 | 28 | 184 | 01E07V01 | 019 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | PANIKI |  | PANIKI TDO033 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-03-29 | TEL.1921/LG.310/DR7-12700000/2020. | 2021-03-29 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 354427836 | 74838807 | 429266643 | 429266643 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 126 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | TAHUNA |  | TAHUNA THN056 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-02 | 2021-03-30 | TEL.0514/LG.310/DR7-12700000/2021 | 2021-04-01 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 16069619 | 4463811 | 20533430 | 20533430 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 106 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | TAHUNA |  | TAHUNA THN074 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-02 | 2021-03-30 | TEL.0515/LG.310/DR7-12700000/2021 | 2021-04-01 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 20701518 | 7267232 | 27968750 | 27968750 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 95 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | TAHUNA |  | TAHUNA THN077 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-02 | 2021-03-30 | TEL.0516/LG.310/DR7-12700000/2021 | 2021-04-01 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 26027527 | 8892496 | 34920023 | 34920023 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 94 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | TAHUNA |  | TAHUNA THN085 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-02 | 2021-03-30 | TEL.0517/LG.310/DR7-12700000/2021 | 2021-04-01 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 71252660 | 18899106 | 90151766 | 90151766 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 127 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | TAHUNA |  | TAHUNA THN005 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-22 | 2021-09-11 | TEL.1511/LG.310/DR7-12700000/2021 | 2021-09-15 | TEL.0486/LG.320/DID-00000000/2021 | 2021-09-15 | 938509902 | 180384891 | 1118894793 | 1118894793 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-10-30
12020169 | 28 | 128 | 01E07V01 | 019 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | MANADO | TAHUNA |  | TAHUNA THN016 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-22 | 2021-09-03 | TEL.1512/LG.310/DR7-12700000/2021 | 2021-09-15 | TEL.0486/LG.320/DID-00000000/2021 | 2021-09-15 | 701151157 | 160583898 | 861735055 | 861735055 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-10-30
12020169 | 28 | 59 | 01E07V01 | 019 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | BUNGKU |  | BUNGKU (MRW015) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2021-09-08 | TEL.1650/LG.310/DR7-12700000/2021 | 2021-09-21 | TEL.0628/LG.320/DID-00000000/2021 | 2021-09-21 | 750021187 | 450863698 | 1200884885 | 1200884885 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-11-27
12020169 | 28 | 58 | 01E07V01 | 019 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | BUNGKU |  | BUNGKU (MRW005) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2021-09-08 | TEL.1649/LG.310/DR7-12700000/2021 | 2021-09-21 | TEL.0628/LG.320/DID-00000000/2021 | 2021-09-21 | 940079093 | 548808803 | 1488887896 | 1488887896 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-11-27
12020169 | 28 | 61 | 01E07V01 | 019 | 72030099 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | KOTARAYA |  | KOTARAYA (PGI060) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2021-12-13 | TEL.2097/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0212/LG.320/DID-A0000000/2021 | 2021-12-23 | 228268397 | 252512185 | 480780582 | 480780582 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-28
12020169 | 28 | 151 | 01E07V01 | 019 | 72030099 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | KOTARAYA |  | KOTARAYA PGI034 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2021-12-12 | TEL.2098/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0212/LG.320/DID-A0000000/2021 | 2021-12-23 | 1463131004 | 1049876245 | 2513007249 | 2513007249 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-28
12020169 | 28 | 145 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK LWK018 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-27 | 2021-05-31 | TEL.1286/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 758590555 | 156675293 | 915265848 | 915265848 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 140 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK LWK071 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-27 | 2021-05-31 | TEL.1289/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 372471459 | 332937044 | 705408503 | 705408503 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 142 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK LWK181 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-28 | 2021-05-31 | TEL.1290/LG.310/DR7-12700000/2021 | 2021-08-27 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 197763547 | 226698096 | 424461643 | 424461643 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 141 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK LWK051 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-27 | 2021-05-31 | TEL.1287/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 462987504 | 509881175 | 972868679 | 972868679 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 139 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK LWK139 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-27 | 2021-05-31 | TEL.1284/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 454345915 | 200643877 | 654989792 | 654989792 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 57 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK (LWK012) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-27 | 2021-05-31 | TEL.1285/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 246259382 | 275152016 | 521411398 | 521411398 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 143 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | LUWUK |  | LUWUK LWK015 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-08-27 | 2021-05-31 | TEL.1288/LG.310/DR7-12700000/2021 | 2021-08-26 | TEL.0196/LG.320/DID-00000000/2021 | 2021-09-06 | 284283232 | 231760523 | 516043755 | 516043755 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-09-21
12020169 | 28 | 149 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | PARIGI |  | PARIGI PGI059 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2021-10-20 | TEL.800/LG.310/DR7-12700000/2022 | 2022-03-25 | TEL.0835/LG.320/DID-A0000000/2022 | 2022-05-24 | 241441068 | 203282149 | 444723217 | 444723217 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-06-29
12020169 | 28 | 150 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | PARIGI |  | PARIGI PGI023 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2022-05-23 | TEL.901/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0835/LG.320/DID-A0000000/2022 | 2022-05-24 | 677334946 | 513076168 | 1190411114 | 1190411114 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-06-29
12020169 | 28 | 148 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | PARIGI |  | PARIGI PGI024 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2021-10-20 | TEL.799/LG.310/DR7-12700000/2022 | 2022-03-25 | TEL.0835/LG.320/DID-A0000000/2022 | 2022-05-24 | 1836749667 | 1278278089 | 3115027756 | 3115027756 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-06-29
12020169 | 28 | 60 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PALU | PARIGI |  | PARIGI (PGI004) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-11-11 | 2022-05-23 | TEL.900/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0835/LG.320/DID-A0000000/2022 | 2022-05-24 | 305343921 | 249620589 | 554964510 | 554964510 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-06-29
12020169 | 28 | 51 | 01E07V01 | 019 | 72040049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | ENREKANG |  | ENREKANG (ENR008) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-01-25 | TEL.0315/LG.310/DR7-12700000/2021 | 2021-03-30 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 568430173 | 148546794 | 716976967 | 716976967 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 132 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | MASAMBA |  | MASAMBA MAS092 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-02-27 | 2021-01-22 | TEL.0176/LG.310/DR7-12700000/2021 | 2021-02-26 | TEL.0645/LG.320/PND-A1000000/2021 | 2021-05-08 | 457949862 | 346942729 | 804892591 | 804892591 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-06-21
12020169 | 28 | 53 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | MASAMBA |  | MASAMBA (MAS043) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-02-27 | 2021-01-22 | TEL.0177/LG.310/DR7-12700000/2021 | 2021-02-26 | TEL.0413/LG.320/PND-A1000000/2021 | 2021-03-23 | 617547074 | 113870274 | 731417348 | 731417348 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-19
12020169 | 28 | 54 | 01E07V01 | 019 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | RANTEPAO |  | RANTEPAO (MLE020) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-01-25 | TEL.0316/LG.310/DR7-12700000/2021 | 2021-03-29 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 392548608 | 72334853 | 464883461 | 464883461 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 133 | 01E07V01 | 019 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | RANTEPAO |  | RANTEPAO MLE097 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-01-25 | TEL.0317/LG.310/DR7-12700000/2021 | 2021-03-29 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 202357268 | 46331351 | 248688619 | 248688619 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 134 | 01E07V01 | 019 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | RANTEPAO |  | RANTEPAO MLE110 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-03-30 | 2021-01-25 | TEL.0318/LG.310/DR7-12700000/2021 | 2021-03-29 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 6909735 | 2072453 | 8982188 | 8982188 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 138 | 01E07V01 | 019 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | SENGKANG |  | SENGKANG SKG122 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-03-30 | TEL.0308/LG.310/DR7-12700000/2021 | 2021-03-30 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 20958765 | 4771626 | 25730391 | 25730391 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 136 | 01E07V01 | 019 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | SENGKANG |  | SENGKANG SKG033 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-03-30 | TEL.0305/LG.310/DR7-12700000/2021 | 2021-03-30 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 111787311 | 23463565 | 135250876 | 135250876 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 135 | 01E07V01 | 019 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | SENGKANG |  | SENGKANG SKG070 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-03-30 | TEL.0304/LG.310/DR7-12700000/2021 | 2021-03-30 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 268841369 | 50747831 | 319589200 | 319589200 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 55 | 01E07V01 | 019 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | SENGKANG |  | SENGKANG (SKG005) |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-01-24 | TEL.0307/LG.310/DR7-12700000/2021 | 2021-03-30 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 12877020 | 5243879 | 18120899 | 18120899 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
12020169 | 28 | 137 | 01E07V01 | 019 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003802/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Feeder dan Node-B | 2020-07-07 | 2022-03-18 | OSP FO Feeder dan Node-B | PARE-PARE | SENGKANG |  | SENGKANG SKG049 |  | 100 | 100 | 100 | BAST-1 | 2020-07-07 | 2021-04-01 | 2021-03-30 | TEL.0306/LG.310/DR7-12700000/2021 | 2021-03-30 | TEL.0485/LG.320/PND-A1000000/2021 | 2021-03-30 | 87453207 | 20010246 | 107463453 | 107463453 | 4500410933 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-04-30
G2020361 | 0 | 136 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | AMBON |  | AMBON |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 591259064 | 0 | 591259064 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 140 | 01E07V01 | 007 | 73010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | BANDA NEIRA |  | BANDA NEIRA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 14019442 | 0 | 14019442 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 137 | 01E07V01 | 007 | 73010013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | BULA |  | BULA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 18228943 | 0 | 18228943 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 138 | 01E07V01 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | DOBO |  | DOBO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 278570116 | 0 | 278570116 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 139 | 01E07V01 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | MASOHI |  | MASOHI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 259078262 | 0 | 259078262 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 141 | 01E07V01 | 007 | 73010046 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | NAMLEA |  | NAMLEA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 153203436 | 0 | 153203436 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 142 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | PASSO |  | PASSO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 481327460 | 0 | 481327460 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 143 | 01E07V01 | 007 | 73010071 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | SAPARUA |  | SAPARUA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 43119109 | 0 | 43119109 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 146 | 01E07V01 | 007 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | SAUMLAKI |  | SAUMLAKI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1390939 | 0 | 1390939 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 144 | 01E07V01 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | TUAL |  | TUAL |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 178280078 | 0 | 178280078 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 145 | 01E07V01 | 007 | 73010089 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | AMBON | WAHAI |  | WAHAI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 40777439 | 0 | 40777439 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 53 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | GORONTALO | GORONTALO |  | GORONTALO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1263927899 | 0 | 1263927899 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 54 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | GORONTALO | ISIMU |  | ISIMU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 233099689 | 0 | 233099689 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 55 | 01E07V01 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | GORONTALO | KWANDANG |  | KWANDANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 263891927 | 0 | 263891927 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 56 | 01E07V01 | 007 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | GORONTALO | LIMBOTO |  | LIMBOTO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 321899390 | 0 | 321899390 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 57 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | GORONTALO | MARISA |  | MARISA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 456066278 | 0 | 456066278 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 58 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | GORONTALO | TELAGA |  | TELAGA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 291849381 | 0 | 291849381 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 148 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | ABEPURA |  | ABEPURA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 355698318 | 0 | 355698318 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 149 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | JAYAPURA A |  | JAYAPURA 1 |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 350056247 | 0 | 350056247 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 150 | 01E07V01 | 007 | 74030026 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | JAYAPURA B |  | JAYAPURA 2 |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 119930784 | 0 | 119930784 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 151 | 01E07V01 | 007 | 74030043 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | KUALA KENCANA |  | KUALA KENCANA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 47787213 | 0 | 47787213 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 163 | 01E07V01 | 007 | 74030176 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | NABIRE |  | NABIRE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 148181616 | 0 | 148181616 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 154 | 01E07V01 | 007 | 74030060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | SARMI |  | SARMI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 55596118 | 0 | 55596118 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 153 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | SENTANI |  | SENTANI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 524129632 | 0 | 524129632 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 155 | 01E07V01 | 007 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | TEMBAGAPURA |  | TEMBAGAPURA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 44948259 | 0 | 44948259 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 156 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | TIMIKA |  | TIMIKA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 592686216 | 0 | 592686216 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 157 | 01E07V01 | 007 | 74030072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | JAYAPURA | WAENA |  | WAENA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 129365527 | 0 | 129365527 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 60 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | BAU-BAU |  | BAU-BAU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 508572991 | 0 | 508572991 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 61 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | KENDARI |  | KENDARI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 595801144 | 0 | 595801144 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 147 | 01E07V01 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | KOLAKA |  | KOLAKA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 183168653 | 0 | 183168653 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 62 | 01E07V01 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | LASUSUA |  | LASUSUA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 48643017 | 0 | 48643017 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 63 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | MANDONGA |  | MANDONGA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1057957562 | 0 | 1057957562 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 64 | 01E07V01 | 007 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | POMALAA |  | POMALA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 150651437 | 0 | 150651437 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 65 | 01E07V01 | 007 | 72050057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | RAHA |  | RAHA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 89872544 | 0 | 89872544 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 66 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | UNAAHA |  | UNAAHA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 173891388 | 0 | 173891388 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 67 | 01E07V01 | 007 | 72050074 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | KENDARI | WANCI |  | WANCI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 83697029 | 0 | 83697029 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 26 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | AIR MADIDI |  | AIR MADIDI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 446094652 | 0 | 446094652 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 27 | 01E07V01 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | AMURANG |  | AMURANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 320160097 | 0 | 320160097 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 28 | 01E07V01 | 007 | 72010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | BAHU |  | BAHU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 587817334 | 0 | 587817334 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 29 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | BEO |  | BEO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 103606011 | 0 | 103606011 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 30 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | BITUNG |  | BITUNG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 416021785 | 0 | 416021785 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 31 | 01E07V01 | 007 | 72010012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | BOROKO |  | BOROKO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 66442592 | 0 | 66442592 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 43 | 01E07V01 | 007 | 72010273 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | GALELA |  | GALELA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 37995561 | 0 | 37995561 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 32 | 01E07V01 | 007 | 72010267 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | HULU SIAU |  | HULU SIAU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 57580680 | 0 | 57580680 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 33 | 01E07V01 | 007 | 72010045 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | KAUDITAN |  | KAUDITAN |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 38416606 | 0 | 38416606 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 34 | 01E07V01 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | KOTAMOBAGU |  | KOTAMOBAGU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 577506696 | 0 | 577506696 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 35 | 01E07V01 | 007 | 72010055 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | LANGOAN |  | LANGOAN |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 185763314 | 0 | 185763314 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 36 | 01E07V01 | 007 | 72010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | LOLAK |  | LOLAK |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 45164571 | 0 | 45164571 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 37 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | MANADO |  | MANADO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1014150370 | 0 | 1014150370 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 46 | 01E07V01 | 007 | 72010275 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | MOROTAI |  | MOROTAI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 49893437 | 0 | 49893437 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 38 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | PANIKI |  | PANIKI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 490055945 | 0 | 490055945 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 48 | 01E07V01 | 007 | 72010276 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | SANANA |  | SANANA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 12738552 | 0 | 12738552 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 40 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | TAHUNA |  | TAHUNA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 104510931 | 0 | 104510931 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 41 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | TOMOHON |  | TOMOHON |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 284930777 | 0 | 284930777 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 39 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | TONDANO |  | TONDANO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 192674018 | 0 | 192674018 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 42 | 01E07V01 | 007 | 72010283 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANADO | TUTUYAN |  | TUTUYAN |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 119703988 | 0 | 119703988 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 162 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MANOKWARI | MANOKWARI |  | MANOKWARI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 207201522 | 0 | 207201522 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 152 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | MERAUKE | MERAUKE |  | MERAUKE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 426978552 | 0 | 426978552 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 92 | 01E07V01 | 007 | 72030159 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | AMPANA |  | AMPANA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 117164718 | 0 | 117164718 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 93 | 01E07V01 | 007 | 72030123 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | BANGGAI |  | BANGGAI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 120331306 | 0 | 120331306 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 94 | 01E07V01 | 007 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | BUNGKU |  | BUNGKU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 132369883 | 0 | 132369883 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 96 | 01E07V01 | 007 | 72030124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | BUNTA |  | BUNTA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 32171541 | 0 | 32171541 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 95 | 01E07V01 | 007 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | BUOL |  | BUOL |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 213653618 | 0 | 213653618 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 97 | 01E07V01 | 007 | 72030017 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | DONGGALA |  | DONGGALA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 43094940 | 0 | 43094940 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 98 | 01E07V01 | 007 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | KOLONODALE |  | KOLONODALE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 86196127 | 0 | 86196127 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 99 | 01E07V01 | 007 | 72030099 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | KOTARAYA |  | KOTARAYA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 26584394 | 0 | 26584394 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 100 | 01E07V01 | 007 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | LUWUK |  | LUWUK |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 450744426 | 0 | 450744426 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 101 | 01E07V01 | 007 | 72030050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | MOUTONG |  | MOUTONG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 56078399 | 0 | 56078399 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 103 | 01E07V01 | 007 | 72030125 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | PAGIMANA |  | PAGIMANA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 32145057 | 0 | 32145057 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 104 | 01E07V01 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | PALU A |  | PALU A |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1203788264 | 0 | 1203788264 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 105 | 01E07V01 | 007 | 72030092 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | PALU B |  | PALU B |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1141165741 | 0 | 1141165741 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 102 | 01E07V01 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | PARIGI |  | PARIGI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 139217823 | 0 | 139217823 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 106 | 01E07V01 | 007 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | POSO |  | POSO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 173206836 | 0 | 173206836 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 111 | 01E07V01 | 007 | 72030088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | TAWAELI |  | TAWAELI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 160517561 | 0 | 160517561 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 107 | 01E07V01 | 007 | 72030139 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | TENTENA |  | TENTENA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 23970279 | 0 | 23970279 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 109 | 01E07V01 | 007 | 72030081 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | TINOMBO |  | TINOMBO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 16017123 | 0 | 16017123 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 108 | 01E07V01 | 007 | 72030083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | TOLAY |  | TOLAY |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 10604208 | 0 | 10604208 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 110 | 01E07V01 | 007 | 72030084 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PALU | TOLI-TOLI |  | TOLI-TOLI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 119180938 | 0 | 119180938 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 112 | 01E07V01 | 007 | 72040275 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | AJANGALE |  | AJANGALE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 20030638 | 0 | 20030638 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 113 | 01E07V01 | 007 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | BARRU |  | BARRU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 124127675 | 0 | 124127675 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 114 | 01E07V01 | 007 | 72040044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | CANGADI |  | CANGADI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 70733059 | 0 | 70733059 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 115 | 01E07V01 | 007 | 72040049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | ENREKANG |  | ENREKANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 88485460 | 0 | 88485460 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 116 | 01E07V01 | 007 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | MAJENE |  | MAJENE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 263519074 | 0 | 263519074 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 117 | 01E07V01 | 007 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | MAKALE |  | MAKALE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 131875240 | 0 | 131875240 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 120 | 01E07V01 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | MALILI |  | MALILI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 109080606 | 0 | 109080606 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 121 | 01E07V01 | 007 | 72040086 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | MAMASA |  | MAMASA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 43303320 | 0 | 43303320 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 118 | 01E07V01 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | MAMUJU |  | MAMUJU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 555373135 | 0 | 555373135 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 119 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | MASAMBA |  | MASAMBA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 43451068 | 0 | 43451068 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 124 | 01E07V01 | 007 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | PALOPO |  | PALOPO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 638838805 | 0 | 638838805 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 126 | 01E07V01 | 007 | 72040117 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | PARE-PARE |  | PARE-PARE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 518654977 | 0 | 518654977 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 123 | 01E07V01 | 007 | 72040119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | PASANG KAYU |  | PASANG KAYU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 55382114 | 0 | 55382114 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 122 | 01E07V01 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | PINRANG |  | PINRANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 521315734 | 0 | 521315734 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 125 | 01E07V01 | 007 | 72040195 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | POLEWALI |  | POLEWALI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 319183442 | 0 | 319183442 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 128 | 01E07V01 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | RANTEPAO |  | RANTEPAO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 265772947 | 0 | 265772947 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 127 | 01E07V01 | 007 | 72040135 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | RAPPANG |  | RAPPANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 88347509 | 0 | 88347509 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 131 | 01E07V01 | 007 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | SENGKANG |  | SENGKANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 255149814 | 0 | 255149814 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 129 | 01E07V01 | 007 | 72040158 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | SIDRAP |  | SIDRAP |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 309006507 | 0 | 309006507 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 130 | 01E07V01 | 007 | 72040160 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | SIWA |  | SIWA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 28131542 | 0 | 28131542 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 132 | 01E07V01 | 007 | 72040161 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | SOROWAKO |  | SOROWAKO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 267911027 | 0 | 267911027 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 133 | 01E07V01 | 007 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | TANRUTEDONG |  | TANRUREDONG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 13513819 | 0 | 13513819 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 135 | 01E07V01 | 007 | 72040186 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | WATANSOPPENG |  | WATANSOPPENG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 165479568 | 0 | 165479568 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 134 | 01E07V01 | 007 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | PARE-PARE | WONOMULYO |  | WONOMULYA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 156127773 | 0 | 156127773 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 158 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | BIAK |  | BIAK |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 166740388 | 0 | 166740388 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 159 | 01E07V01 | 007 | 74060037 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | BINTUINI |  | BINTUNI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 58374576 | 0 | 58374576 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 160 | 01E07V01 | 007 | 74060038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | FAKFAK |  | FAKFAK |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 239916378 | 0 | 239916378 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 161 | 01E07V01 | 007 | 74060078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | KAIMANA |  | KAIMANA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 117494481 | 0 | 117494481 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 165 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | SERUI |  | SERUI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 258529135 | 0 | 258529135 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 164 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | SORONG |  | SORONG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1071481940 | 0 | 1071481940 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 166 | 01E07V01 | 007 | 74060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | TEMINABUAN |  | TINAMBUAN |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 44903520 | 0 | 44903520 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 167 | 01E07V01 | 007 | 74060042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | SORONG | WARMARE / PRAFI |  | WARMARE PRAFI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 44903520 | 0 | 44903520 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 44 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | TERNATE | JAILOLO |  | JAILOLO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 38178972 | 0 | 38178972 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 45 | 01E07V01 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | TERNATE | LABUHA |  | LABUHA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 45624238 | 0 | 45624238 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 49 | 01E07V01 | 007 | 73020034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | TERNATE | SOA SIU |  | SOA SIU |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 32431802 | 0 | 32431802 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 47 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | TERNATE | SOFIFI |  | SOFIFI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 130437886 | 0 | 130437886 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 50 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | TERNATE | TERNATE |  | TERNATE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1009743241 | 0 | 1009743241 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 51 | 01E07V01 | 007 | 73020044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | TERNATE | TOBELO |  | TOBELO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 105203894 | 0 | 105203894 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 70 | 01E07V01 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | ANTANG |  | ANTANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 423883131 | 0 | 423883131 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 71 | 01E07V01 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | BALAIKOTA |  | BALAIKOTA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 600223333 | 0 | 600223333 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 73 | 01E07V01 | 007 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | BANTAENG |  | BANTAENG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 139752389 | 0 | 139752389 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 72 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | BULUKUMBA |  | BULUKUMBA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 346706544 | 0 | 346706544 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 74 | 01E07V01 | 007 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | JENEPONTO |  | JENEPONTO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 140343381 | 0 | 140343381 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 75 | 01E07V01 | 007 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | KIMA |  | KIMA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 69776903 | 0 | 69776903 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 76 | 01E07V01 | 007 | 72080075 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | MALINO |  | MALINO |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 18632550 | 0 | 18632550 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 69 | 01E07V01 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | MAROS |  | MAROS |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 285416051 | 0 | 285416051 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 77 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | MATTOANGIN |  | MATTOANGING |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 763099344 | 0 | 763099344 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 79 | 01E07V01 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | PANAKUKANG |  | PANAKUKKANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 1046322797 | 0 | 1046322797 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 78 | 01E07V01 | 007 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | PANGKEP |  | PANGKEP |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 253479374 | 0 | 253479374 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 81 | 01E07V01 | 007 | 72080112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | SELAYAR |  | SELAYAR |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 95146582 | 0 | 95146582 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 80 | 01E07V01 | 007 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | SINJAI |  | SINJAI |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 210375293 | 0 | 210375293 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 82 | 01E07V01 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | SUDIANG |  | SUDIANG |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 628085147 | 0 | 628085147 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 83 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | SUNGGUMINASA |  | SUNGGUMINASA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 895531441 | 0 | 895531441 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 84 | 01E07V01 | 007 | 72080120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | TAKALAR |  | TAKALAR |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 185138808 | 0 | 185138808 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 85 | 01E07V01 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | TAMALANREA |  | TAMALANREA |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 554901274 | 0 | 554901274 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
G2020361 | 0 | 86 | 01E07V01 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.3889/HK.810/DR7-10000000/2020 | SP - Pengadaan Pekerjaan Imbal Jasa Pasang Sambung Baru (PSB) INDIHOME Triwulan-I Periode April 2020 | 2020-07-09 | 2020-08-22 | PSB | UJUNGPANDANG | WATAMPONE |  | WATAMPONE |  | 100 | 90 | 0 | Siap UT | 2020-07-09 | 2020-08-07 | 2020-07-09 |  |  |  |  | 575074693 | 0 | 575074693 | 0 | 4500411111 |  |  |  |  | TELKOM AKSES
12020177 | 11 | 21 | 01C11H02 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004208/HK.810/OPS-10000000/2020 | Kontrak OSP FO Backbone, RMJ dan Last Mile KTI | 2020-07-20 | 2022-02-13 | OSP FO Backbone | GORONTALO | GORONTALO |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-20 | 2021-09-08 | 2020-07-20 | TEL.2511/LG.310/DID-B1060000/2021 | 2021-09-08 | TEL.0360/LG.320/DID-00000000/2021 | 2021-09-08 | 2922484995 | 5253004318 | 8175489313 | 8175489313 | 4500411461 |  |  |  |  | PERKONSUMA | 2021-09-30
12020177 | 11 | 27 | 01C11H02 | 019 | 72020068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004208/HK.810/OPS-10000000/2020 | Kontrak OSP FO Backbone, RMJ dan Last Mile KTI | 2020-07-20 | 2022-02-13 | OSP FO Backbone | GORONTALO | KTG023 |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-20 | 2021-03-10 | 2020-07-20 | TEL.641/LG.310/PND-B1060000/2021 | 2021-03-06 | TEL.0526/LG.320/PND-A1000000/2021 | 2021-03-06 | 1136877420 | 1525726435 | 2662603855 | 2662603855 | 4500411461 |  |  |  |  | PERKONSUMA | 2021-05-24
12020177 | 11 | 26 | 01C11H02 | 019 | 72020067 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004208/HK.810/OPS-10000000/2020 | Kontrak OSP FO Backbone, RMJ dan Last Mile KTI | 2020-07-20 | 2022-02-13 | OSP FO Backbone | GORONTALO | KTG181 SINOMBAYUGA2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-20 | 2022-02-13 | 2020-07-20 | TEL.431/LG.310/D10-B1060000/2022 | 2022-02-13 | TEL.0195/LG.320/DID-A0000000/2022 | 2022-02-13 | 4220580113 | 4581808573 | 8802388686 | 8802388686 | 4500411461 |  |  |  |  | PERKONSUMA | 2022-02-27
12020177 | 11 | 23 | 01C11H02 | 019 | 72020066 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004208/HK.810/OPS-10000000/2020 | Kontrak OSP FO Backbone, RMJ dan Last Mile KTI | 2020-07-20 | 2022-02-13 | OSP FO Backbone | GORONTALO | SWW005 REPEATER TALUDAA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-20 | 2021-12-27 | 2020-07-20 | TEL.3636/LG.310/D10-B1060000 | 2021-12-27 | TEL.0416/LG.320/DID-A0000000/2021 | 2021-12-27 | 3976355465 | 5392990049 | 9369345514 | 9369345514 | 4500411461 |  |  |  |  | PERKONSUMA | 2021-12-31
12020177 | 11 | 19 | 01C11H02 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004208/HK.810/OPS-10000000/2020 | Kontrak OSP FO Backbone, RMJ dan Last Mile KTI | 2020-07-20 | 2022-02-13 | OSP FO Backbone | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-07-20 | 2022-01-30 | 2020-07-24 | TEL.802/LG.310/D10-B1060000/2022 | 2022-03-21 | TEL.0406/LG.320/DID-A0000000/2022 | 2022-03-21 | 1944081154 | 1758078587 | 3702159741 | 3702159741 | 4500411461 |  |  |  |  | PERKONSUMA | 2022-03-31
G2020302 | 2 | 18 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | KAIMANA |  | KMN009-COAKAIMANA(PROTELINDO) |  | 100 | 95 | 0 | BAUT | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.182/LG.000/R7W-7H100000/2021 | 2021-03-30 |  |  | 136993028 | 42922409 | 179915437 | 0 | 4500412233 |  |  |  |  | TELKOM AKSES
G2020302 | 2 | 16 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | NABIRE |  | NAB012 |  | 100 | 95 | 0 | BAUT | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.180/LG.000/R7W-7H100000/2021 | 2021-03-30 |  |  | 57206138 | 14937100 | 72143238 | 0 | 4500412233 |  |  |  |  | TELKOM AKSES
G2020302 | 2 | 13 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | NABIRE |  | NAB025 |  | 100 | 95 | 0 | BAUT | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.184/LG.000/R7W-7H100000/2021 | 2021-03-30 |  |  | 12367524 | 4697550 | 17065074 | 0 | 4500412233 |  |  |  |  | TELKOM AKSES
G2020302 | 2 | 14 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | NABIRE |  | NAB019-NABIRE |  | 100 | 95 | 0 | BAUT | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.183/LG.000/R7W-7H100000/2021 | 2021-03-30 |  |  | 25987087 | 9960110 | 35947197 | 0 | 4500412233 |  |  |  |  | TELKOM AKSES
G2020302 | 2 | 15 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | NABIRE |  | NAB017 |  | 100 | 95 | 0 | BAUT | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.181/LG.000/R7W-7H100000/2021 | 2021-03-30 |  |  | 7327458 | 3859876 | 11187334 | 0 | 4500412233 |  |  |  |  | TELKOM AKSES
G2020302 | 2 | 11 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | SERUI |  | SRU007 |  | 100 | 100 | 100 | BAST-1 | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.850/LG.000/R7W-7H100000/2020 | 2020-08-28 | TEL.0022/LG.320/R7W-7H100000/2020 | 2020-09-05 | 17504432 | 8721569 | 26226001 | 26226001 | 4500412233 |  |  |  |  | TELKOM AKSES | 2020-09-30
G2020302 | 2 | 8 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | SERUI |  | SRU011 |  | 100 | 100 | 100 | BAST-1 | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.852/LG.000/R7W-7H100000/2020 | 2020-09-05 | TEL.0022/LG.320/R7W-7H100000/2020 | 2020-09-05 | 16521714 | 7304762 | 23826476 | 23826476 | 4500412233 |  |  |  |  | TELKOM AKSES | 2020-09-30
G2020302 | 2 | 9 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | SERUI |  | SRU008 |  | 100 | 100 | 100 | BAST-1 | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.851/LG.000/R7W-7H100000/2020 | 2020-08-28 | TEL.0022/LG.320/R7W-7H100000/2020 | 2020-09-05 | 21022634 | 8436843 | 29459477 | 29459477 | 4500412233 |  |  |  |  | TELKOM AKSES | 2020-09-30
G2020302 | 2 | 10 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004467/HK.810/R7W-7H100000/2020 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 11 LOP AREA WITEL PAPUA BARAT | 2020-07-28 | 2020-09-25 | Node-B 2020 | SORONG | SERUI |  | SRU010 |  | 100 | 100 | 100 | BAST-1 | 2020-07-28 | 2020-09-04 | 2020-07-28 | TEL.853/LG.000/R7W-7H100000/2020 | 2020-08-28 | TEL.0022/LG.320/R7W-7H100000/2020 | 2020-09-05 | 23251026 | 11228819 | 34479845 | 34479845 | 4500412233 |  |  |  |  | TELKOM AKSES | 2020-09-30
32020152 | 0 | 10 | 01C12J04 | 039 | 74030162 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.005870/HK.810/DSO-01000000/2020 | Surat Pesanan Kedua Puluh Tiga (SP#23) Dukungan Penyediaan Support Facility Raio IP Long Haul Jayapura-Sarmi | 2020-10-06 | 2021-10-05 | Support Facility | JAYAPURA | JAYAPURA |  | Periode Ketiga |  | 100 | 90 | 0 | Siap UT | 2020-10-06 | 2021-10-05 | 2020-10-06 |  |  |  |  | 0 | 483000000 | 483000000 | 0 | 4500415542 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020152 | 0 | 11 | 01C12J04 | 039 | 74030162 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.005870/HK.810/DSO-01000000/2020 | Surat Pesanan Kedua Puluh Tiga (SP#23) Dukungan Penyediaan Support Facility Raio IP Long Haul Jayapura-Sarmi | 2020-10-06 | 2021-10-05 | Support Facility | JAYAPURA | JAYAPURA |  | Periode Kedua |  | 100 | 90 | 0 | Siap UT | 2020-10-06 | 2021-10-05 | 2020-10-06 |  |  |  |  | 0 | 483000000 | 483000000 | 0 | 4500415542 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020152 | 0 | 13 | 01C12J04 | 039 | 74030162 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.005870/HK.810/DSO-01000000/2020 | Surat Pesanan Kedua Puluh Tiga (SP#23) Dukungan Penyediaan Support Facility Raio IP Long Haul Jayapura-Sarmi | 2020-10-06 | 2021-10-05 | Support Facility | JAYAPURA | JAYAPURA |  | Periode Keempat |  | 100 | 90 | 0 | Siap UT | 2020-10-06 | 2021-10-05 | 2020-10-06 |  |  |  |  | 0 | 483000000 | 483000000 | 0 | 4500415542 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020152 | 0 | 12 | 01C12J04 | 039 | 74030162 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.005870/HK.810/DSO-01000000/2020 | Surat Pesanan Kedua Puluh Tiga (SP#23) Dukungan Penyediaan Support Facility Raio IP Long Haul Jayapura-Sarmi | 2020-10-06 | 2021-10-05 | Support Facility | JAYAPURA | JAYAPURA |  | Periode Pertama |  | 100 | 90 | 0 | Siap UT | 2020-10-06 | 2021-10-05 | 2020-10-06 |  |  |  |  | 0 | 483000000 | 483000000 | 0 | 4500415542 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020152 | 0 | 8 | 01C12J04 | 039 | 74030162 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.005870/HK.810/DSO-01000000/2020 | Surat Pesanan Kedua Puluh Tiga (SP#23) Dukungan Penyediaan Support Facility Raio IP Long Haul Jayapura-Sarmi | 2020-10-06 | 2021-10-05 | Support Facility | JAYAPURA | JAYAPURA |  |  |  | 100 | 90 | 0 | Siap UT | 2020-10-06 | 2021-10-05 | 2020-10-06 |  |  |  |  | 0 | 960000000 | 960000000 | 0 | 4500415542 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020285 | 7 | 12 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | MANADO | MANADO |  | BRAS |  | 100 | 100 | 100 | BAST-1 | 2020-10-07 | 2021-03-30 | 2020-10-07 | TEL.269/LG.310/PND-B1050000/2021 | 2021-03-09 | TEL.0328/LG.320/PND-A1000000/2021 | 2021-03-09 | 1914120000 | 91648000 | 2005768000 | 2005768000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-03-29
12020285 | 7 | 37 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | MANADO | MANADO |  |  |  | 80 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2218/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0166/LG.320/DID-A0000000/2021 | 2021-12-22 | 156351000 | 19551000 | 175902000 | 175902000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020285 | 7 | 13 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | MANADO | PANIKI |  | BRAS |  | 100 | 100 | 100 | BAST-1 | 2020-10-07 | 2021-03-30 | 2020-10-07 | TEL.269/LG.310/PND-B1050000/2021 | 2021-03-09 | TEL.0328/LG.320/PND-A1000000/2021 | 2021-03-09 | 1914120000 | 91648000 | 2005768000 | 2005768000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-03-29
12020285 | 7 | 38 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | MANADO | PANIKI |  |  |  | 80 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2218/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0166/LG.320/DID-A0000000/2021 | 2021-12-22 | 156351000 | 19551000 | 175902000 | 175902000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020285 | 7 | 35 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | BALAIKOTA |  |  |  | 80 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2218/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0166/LG.320/DID-A0000000/2021 | 2021-12-22 | 493740000 | 61740000 | 555480000 | 555480000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020285 | 7 | 21 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | PETTARANI |  | WAG |  | 80 | 100 | 100 | BAST-1 | 2020-10-07 | 2021-12-30 | 2020-10-07 | TEL.2219/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0167/LG.320/DID-A0000000/2021 | 2021-12-22 | 1115077000 | 276186000 | 1391263000 | 1391263000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020285 | 7 | 36 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | PETTARANI |  |  |  | 80 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2218/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0166/LG.320/DID-A0000000/2021 | 2021-12-22 | 493740000 | 61740000 | 555480000 | 555480000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020285 | 7 | 27 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | PETTARANI |  | WAG |  | 80 | 100 | 100 | BAST-1 | 2020-10-07 | 2021-12-30 | 2020-10-07 | TEL.2220/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0168/LG.320/DID-A0000000/2021 | 2021-12-22 | 0 | 22495000 | 22495000 | 22495000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020285 | 7 | 28 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005885/HK.810/OPS-10040000/2020 | Kontrak Ekspan BRAS dan WAG Platform Ericsson | 2020-10-07 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | PETTARANI |  | WAG |  | 70 | 100 | 100 | BAST-1 | 2020-10-07 | 2021-12-30 | 2020-10-07 | TEL.2221/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0169/LG.320/DID-A0000000/2021 | 2021-12-22 | 0 | 40900000 | 40900000 | 40900000 | 4500415308 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020290 | 16 | 740 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | GORONTALO |  | WONOSARI SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2734/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 303 | 01E07V01 | 019 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | GORONTALO |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1005/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 442736800 | 9176156 | 451912956 | 451912956 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 335 | 01E07V01 | 019 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | ISIMU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.457/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 741 | 01E07V01 | 019 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | ISIMU |  | JL. UMAR SADIKI SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2800/LG.235/PND-A103000000/2021(UMARSADIKI) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 337 | 01E07V01 | 019 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | KWANDANG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1006/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 333189440 | 6141768 | 339331208 | 339331208 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 338 | 01E07V01 | 019 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | LIMBOTO |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.464/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 220642080 | 4606326 | 225248406 | 225248406 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 739 | 01E07V01 | 019 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | MARISA |  | BOALEMO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2735/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 334 | 01E07V01 | 019 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | GORONTALO | MARISA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1007/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 259642080 | 4606326 | 264248406 | 264248406 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 773 | 01E07V01 | 019 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | BAU-BAU |  | UMALAOGE SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2785/LG.235/PND-A103000000/2021(UMALAOGE) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 117267155 | 11037019 | 128304174 | 128304174 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 772 | 01E07V01 | 019 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | BAU-BAU |  | SAMPOLAWA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2778/LG.235/PND-A103000000/2021(SAMPOLAWA) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 339 | 01E07V01 | 019 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | BAU-BAU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.996/LG.235/PND-C103000000/2020 | 2020-12-09 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 591284160 | 12210544 | 603494704 | 603494704 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 774 | 01E07V01 | 019 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | BAU-BAU |  | LEA LEA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2785/LG.235/PND-A103000000/2021(LEALEA) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 429 | 01E07V01 | 019 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | KENDARI |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-02-26 | 2020-10-09 | TEL.1004/LG.235/PND-C10300000/2020 | 2020-12-09 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 148547360 | 3034388 | 151581748 | 151581748 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 345 | 01E07V01 | 019 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | KENDARI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.447/LG.235/PND-C1030000/2020 | 2020-11-25 | TEL.1594/LG.320/PND-A1000000/2020 | 2020-11-25 | 320189440 | 6141768 | 326331208 | 326331208 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-11
12020290 | 16 | 770 | 01E07V01 | 019 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | KENDARI |  | SAMPARA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2778/LG.235/PND-A103000000/2021(SAMPARA) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 213154856 | 27804509 | 240959365 | 240959365 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 771 | 01E07V01 | 019 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | KOLAKA |  | TOSIBA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2782/LG.235/PND-A103000000/2021(TOSIBA) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20907767 | 145065263 | 145065263 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 775 | 01E07V01 | 019 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | KOLAKA |  | WUNDULAKO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2782/LG.235/PND-A103000000/2021(WUNDULAKO) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 341 | 01E07V01 | 019 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | KOLAKA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.448/LG.235/PND-C1030000/2020 | 2020-11-25 | TEL.1594/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-11
12020290 | 16 | 769 | 01E07V01 | 019 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | MANDONGA |  | ANOVA GARDEN SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2778/LG.235/PND-A103000000/2021(ANOVAGARDEN) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 18409242 | 145016738 | 145016738 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 767 | 01E07V01 | 019 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | MANDONGA |  | KASIPUTE SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2778/LG.235/PND-A103000000/2021(KASIPUTE) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 768 | 01E07V01 | 019 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | MANDONGA |  | ODC PUNGGALUKU SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2778/LG.235/PND-A103000000/2021(PUNGGALUKU) | 2021-07-28 | TEL.0194/LG.320/DID-00000000/2021 | 2021-07-30 | 213154856 | 19944684 | 233099540 | 233099540 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-09-21
12020290 | 16 | 344 | 01E07V01 | 019 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | MANDONGA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1001/LG.235/PND-C10300000/2020 | 2020-12-09 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 441284160 | 9212652 | 450496812 | 450496812 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 342 | 01E07V01 | 019 | 72050082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | POMAALA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1000/LG.235/PND-C10300000/2020 | 2020-12-09 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 248094720 | 4569830 | 252664550 | 252664550 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 508 | 01E07V01 | 019 | 72050057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | RAHA |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL273/LG.235/PND-A103000000/2021(SS#4SARPEN) | 2021-01-19 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 5663500 | 453352 | 6116852 | 6116852 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 304 | 01E07V01 | 019 | 72050057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | RAHA |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL273/LG.235/PND-A103000000/2021 | 2021-01-19 | TEL.0339/LG.320/PND-A1000000/2021 | 2021-01-19 | 172114411 | 21150822 | 193265233 | 193265233 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-03-30
12020290 | 16 | 388 | 01E07V01 | 019 | 72050057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | RAHA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.449/LG.235/PND-C1030000/2020 | 2020-11-25 | TEL.1594/LG.320/PND-A1000000/2020 | 2020-11-25 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-11
12020290 | 16 | 343 | 01E07V01 | 019 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | UNAAHA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1002/LG.235/PND-C10300000/2020 | 2020-12-09 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 748473600 | 15354420 | 763828020 | 763828020 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 305 | 01E07V01 | 019 | 72050074 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | KENDARI | WANCI |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.324/LG.235/PND-A10300000/2021 | 2021-01-22 | TEL.0575/LG.320/PND-A1000000/2021 | 2021-01-22 | 172157011 | 21166434 | 193323445 | 193323445 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 357 | 01E07V01 | 019 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | AIR MADIDI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1037/LG.235/PND-C10300000/2020 | 2020-12-15 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 346189440 | 6141768 | 352331208 | 352331208 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 777 | 01E07V01 | 019 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | AIR MADIDI |  | KOKOLE SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(KOKOLE) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20209602 | 144367098 | 144367098 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 323 | 01E07V01 | 019 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | AMURANG |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.999/LG.235/PND-C103000000/2020 | 2020-12-04 | TEL.0173/LG.320/PND-A1000000/2021 | 2020-12-04 | 173749366 | 21338255 | 195087621 | 195087621 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 528 | 01E07V01 | 019 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | AMURANG |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.999/LG.235/PND-C103000000/2020(SS#4SARPEN) | 2020-12-04 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 5541300 | 425500 | 5966800 | 5966800 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 778 | 01E07V01 | 019 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | AMURANG |  | ONGKAW SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2879/LG.235/PND-A103000000/2021ONGKAW | 2021-07-30 | TEL.0194/LG.320/DID-00000000/2021 | 2021-07-30 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-09-21
12020290 | 16 | 779 | 01E07V01 | 019 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | AMURANG |  | PASLATEN & SULU SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(PASLATENSULU | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 529 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | BEO |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.967/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-12-15 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 2730000 | 247900 | 2977900 | 2977900 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 324 | 01E07V01 | 019 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | BEO |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.967/LG.235/PND-C1030000/2020 | 2021-01-15 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 325816586 | 5591971 | 331408557 | 331408557 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 780 | 01E07V01 | 019 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | BITUNG |  | RINONDORAN SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(RINONDORAN) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 533 | 01E07V01 | 019 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | BITUNG |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.305/LG.235/PND-A10300000/2021(SS#4SARPEN) | 2021-01-21 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 5495000 | 422900 | 5917900 | 5917900 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 325 | 01E07V01 | 019 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | BITUNG |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.305/LG.235/PND-A10300000/2021 | 2021-01-21 | TEL.0575/LG.320/PND-A1000000/2021 | 2021-01-22 | 264027781 | 23443697 | 287471478 | 287471478 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 359 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | KOTAMOBAGU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1030/LG.235/PND-C10300000/2020 | 2020-12-15 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 783 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | KOTAMOBAGU |  | MODOINDING SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(MODOINDING) | 2021-07-29 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 119017155 | 11757019 | 130774174 | 130774174 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 784 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | KOTAMOBAGU |  | MOLIBAGU SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(MOLIBAGU) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20209602 | 144367098 | 144367098 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 785 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | KOTAMOBAGU |  | MOPUGAT SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(MOPUGAT) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 781 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | KOTAMOBAGU |  | KOSIO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(KOSIO) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20209602 | 144367098 | 144367098 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 782 | 01E07V01 | 019 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | KOTAMOBAGU |  | MODOMANG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(MODOMANG) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 360 | 01E07V01 | 019 | 72010055 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | LANGOAN |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.456/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 788 | 01E07V01 | 019 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | LANGOWAN |  | TOMBATU SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(TOMBATU) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 786 | 01E07V01 | 019 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | LANGOWAN |  | KAWANGKOAN SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(KAWANGKOAN) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20209602 | 144367098 | 144367098 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 787 | 01E07V01 | 019 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | LANGOWAN |  | RASI SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(RASI) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 789 | 01E07V01 | 019 | 72010133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | MANADO - PANIKI |  | WORI SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(WORI) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 213154856 | 27106344 | 240261200 | 240261200 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 361 | 01E07V01 | 019 | 72010064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | MANADO BAHU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1031/LG.235/PND-C10300000/2020 | 2020-12-15 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 161547360 | 3034388 | 164581748 | 164581748 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 438 | 01E07V01 | 019 | 72010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | MANADO CENTRUM |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-02-26 | 2020-10-09 | TEL.1032/LG.235/PND-C10300000/2020 | 2020-12-15 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 173094720 | 3070884 | 176165604 | 176165604 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 362 | 01E07V01 | 019 | 72010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | MANADO CENTRUM |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.458/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 363 | 01E07V01 | 019 | 72010067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | MANADO PANIKI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1033/LG.235/PND-C10300000/2020 | 2020-12-15 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 161547360 | 3034388 | 164581748 | 164581748 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 790 | 01E07V01 | 019 | 72010277 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | MANGOLE |  | MANGOLE SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2709/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 117267155 | 11037019 | 128304174 | 128304174 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 791 | 01E07V01 | 019 | 72010248 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | TAGULANDANG |  | TAGULANDANG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2710/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 117267155 | 11037019 | 128304174 | 128304174 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 794 | 01E07V01 | 019 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | TOMOHON |  | KASURATAN SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2879/LG.235/PND-A103000000/2021 | 2021-07-30 | TEL.0194/LG.320/DID-00000000/2021 | 2021-07-30 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-09-21
12020290 | 16 | 795 | 01E07V01 | 019 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | TOMOHON |  | SONDER SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(SONDER) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20209602 | 144367098 | 144367098 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 331 | 01E07V01 | 019 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | TONDANO |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.962/LG.235/PND-C1030000/2020 | 2020-12-02 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 176647946 | 22001693 | 198649639 | 198649639 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 526 | 01E07V01 | 019 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | TONDANO |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.962/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-12-02 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 10516500 | 559452 | 11075952 | 11075952 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 332 | 01E07V01 | 019 | 72010283 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | MANADO | TUTUYAN |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.306/LG.235/PND-A10300000/2021 | 2021-01-21 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 344303341 | 22379811 | 366683152 | 366683152 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 764 | 01E07V01 | 019 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | BUNGKU |  | BAHODOPI SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2761/LG.235/PND-A103000000/2021 | 2021-07-28 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 213154856 | 19944684 | 233099540 | 233099540 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 370 | 01E07V01 | 019 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | BUOL |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1008/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 312 | 01E07V01 | 019 | 72030017 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | DONGGALA |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1155/LG.235/PND-C10300000/2020 | 2020-12-04 | TEL.0575/LG.320/PND-A1000000/2021 | 2021-01-22 | 171122682 | 21411303 | 192533985 | 192533985 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 517 | 01E07V01 | 019 | 72030017 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | DONGGALA |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.1155/LG.235/PND-C10300000/2020(SS#4SRAPEN) | 2020-12-04 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 9599000 | 511700 | 10110700 | 10110700 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 439 | 01E07V01 | 019 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | LUWUK |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL1524/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 366 | 01E07V01 | 019 | 72030050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | MOUTONG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1009/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 86547360 | 1535442 | 88082802 | 88082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 440 | 01E07V01 | 019 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | PALU A |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-02-26 | 2020-10-09 | TEL.1010/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 441284160 | 9212652 | 450496812 | 450496812 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 371 | 01E07V01 | 019 | 72030155 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | PALU-1 |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.455/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 372 | 01E07V01 | 019 | 72030156 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | PALU-2 |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1011/LG.235/PND-C10300000/2020 | 2020-12-07 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 147094720 | 3070884 | 150165604 | 150165604 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 368 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | PARIGI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1012/LG.235/PND-C10300000/2020 | 2020-12-08 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 763 | 01E07V01 | 019 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | PARIGI |  | AMPIBABO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2762/LG.235/PND-A103000000/2021 | 2021-07-28 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 313 | 01E07V01 | 019 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | POSO |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.472/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1688/LG.320/PND-A1000000/2020 | 2020-11-26 | 171549759 | 19904846 | 191454605 | 191454605 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 374 | 01E07V01 | 019 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | POSO |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1013/LG.235/PND-C10300000/2020 | 2020-12-08 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 373 | 01E07V01 | 019 | 72030088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TAWAELI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1014/LG.235/PND-C10300000/2020 | 2020-12-08 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 514831520 | 10748094 | 525579614 | 525579614 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 314 | 01E07V01 | 019 | 72030088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TAWAELI |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1154/LG.235/PND-C10300000/2020 | 2020-12-08 | TEL.0575/LG.320/PND-A1000000/2021 | 2021-01-22 | 343899687 | 24463699 | 368363386 | 368363386 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 369 | 01E07V01 | 019 | 72030091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TOLAI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1015/LG.235/PND-C10300000/2020 | 2020-12-08 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 86547360 | 1535442 | 88082802 | 88082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 765 | 01E07V01 | 019 | 72030083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TOLAY |  | SAUSU SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2764/LG.235/PND-A103000000/2021 | 2021-07-28 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 213154856 | 27804509 | 240959365 | 240959365 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 315 | 01E07V01 | 019 | 72030084 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TOLI-TOLI |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.323/LG.235/PND-A10300000/2021 | 2021-01-22 | TEL.0575/LG.320/PND-A1000000/2021 | 2021-01-22 | 173202096 | 21316822 | 194518918 | 194518918 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 518 | 01E07V01 | 019 | 72030084 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TOLI-TOLI |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.323/LG.235/PND-A10300000/2021(SS#4SARPEN) | 2021-01-22 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 421000 | 42100 | 463100 | 463100 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 762 | 01E07V01 | 019 | 72030084 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PALU | TOLI-TOLI |  | DESA GALUMPANG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2763/LG.235/PND-A103000000/2021 | 2021-07-28 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 755 | 01E07V01 | 019 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | BARRU |  | PAKKAE SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2712/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 124157496 | 20907767 | 145065263 | 145065263 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 383 | 01E07V01 | 019 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | BARRU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.468/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 148547360 | 3034388 | 151581748 | 151581748 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 754 | 01E07V01 | 019 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | BARRU |  | MANGKOSO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2736/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 124157496 | 20907767 | 145065263 | 145065263 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 522 | 01E07V01 | 019 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAJENE |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.924/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-11-26 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 578500 | 57852 | 636352 | 636352 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 317 | 01E07V01 | 019 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAJENE |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.924/LG.235/PND-C1030000/2020 | 2020-11-26 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 172348411 | 21186822 | 193535233 | 193535233 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 353 | 01E07V01 | 019 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAKALE |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.461/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 376 | 01E07V01 | 019 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MALILI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.466/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 756 | 01E07V01 | 019 | 72040086 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAMASA |  | SUMARORONG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2737/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 18409242 | 145016738 | 145016738 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 384 | 01E07V01 | 019 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAMUJU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.997/LG.235/PND-C103000000/2020 | 2020-11-27 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 220642080 | 4606326 | 225248406 | 225248406 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 520 | 01E07V01 | 019 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAMUJU |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.781/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-11-27 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 157500 | 15752 | 173252 | 173252 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 757 | 01E07V01 | 019 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAMUJU |  | PAPPALANG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2718/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 18409242 | 145016738 | 145016738 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 318 | 01E07V01 | 019 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAMUJU |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.981/LG.235/PND-C1030000/2020 | 2020-11-27 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 239430216 | 13644129 | 253074345 | 253074345 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 758 | 01E07V01 | 019 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MAMUJU |  | TAPPALANG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2716/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 18409242 | 145016738 | 145016738 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 428 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MASAMBA |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1521/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 147094720 | 3070884 | 150165604 | 150165604 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 521 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MASAMBA |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.926/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-11-27 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 4847000 | 398702 | 5245702 | 5245702 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 319 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MASAMBA |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.926/LG.235/PND-C1030000/2020 | 2020-11-27 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 172681546 | 21423205 | 194104751 | 194104751 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 365 | 01E07V01 | 019 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | MASAMBA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.467/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 752 | 01E07V01 | 019 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PALOPO |  | SUPPA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2715/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 124157496 | 13047942 | 137205438 | 137205438 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 749 | 01E07V01 | 019 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PALOPO |  | BUA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2738/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 385 | 01E07V01 | 019 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PALOPO |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1019/LG.235/PND-C10300000/2020 | 2020-12-04 | TEL.0340/LG.320/PND-A1000000/2021 | 2020-12-04 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-03-30
12020290 | 16 | 751 | 01E07V01 | 019 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PALOPO |  | LAROMPONG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2739/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 441 | 01E07V01 | 019 | 72040117 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PARE-PARE |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL1522/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 86547360 | 1535442 | 88082802 | 88082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 377 | 01E07V01 | 019 | 72040117 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PARE-PARE |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.460/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 753 | 01E07V01 | 019 | 72040119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PASANG KAYU |  | TIKKE SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2717/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 750 | 01E07V01 | 019 | 72040119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PASANG KAYU |  | KANTOR KECAMATAN BARAS SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2740/LG.235/PND-A103000000/2021 | 2021-07-27 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 378 | 01E07V01 | 019 | 72040119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PASANG KAYU |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.994/LG.235/PND-C103000000/2020 | 2020-12-04 | TEL.0340/LG.320/PND-A1000000/2021 | 2020-12-04 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-03-30
12020290 | 16 | 386 | 01E07V01 | 019 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PINRANG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.463/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 148547360 | 3034388 | 151581748 | 151581748 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 442 | 01E07V01 | 019 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PINRANG |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL1523/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0576/LG.320/PND-A1000000/2021 | 2021-03-19 | 367736800 | 7677210 | 375414010 | 375414010 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 759 | 01E07V01 | 019 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | PINRANG |  | PASAR BENTENG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2711/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 26269067 | 152876563 | 152876563 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 320 | 01E07V01 | 019 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | RANTEPAO |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.960/LG.235/PND-C1030000/2020 | 2020-12-01 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 152343466 | 2494599 | 154838065 | 154838065 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 523 | 01E07V01 | 019 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | RANTEPAO |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.960/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-12-01 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 192000 | 19200 | 211200 | 211200 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 760 | 01E07V01 | 019 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | SENGKANG |  | MAJAULENG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2713/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 126607496 | 18409242 | 145016738 | 145016738 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 380 | 01E07V01 | 019 | 72040158 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | SIDRAP |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.462/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 387 | 01E07V01 | 019 | 72040160 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | SIWA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1018/LG.235/PND-C10300000/2020 | 2020-12-03 | TEL.0340/LG.320/PND-A1000000/2021 | 2020-12-04 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-03-30
12020290 | 16 | 748 | 01E07V01 | 019 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | TANRUTEDONG |  | ANABANUA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2714/LG.235/PND-A103000000/2021 | 2021-07-26 | TEL.0903/LG.320/PND-A1000000/2021 | 2021-07-28 | 213154856 | 27804509 | 240959365 | 240959365 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-07-30
12020290 | 16 | 382 | 01E07V01 | 019 | 72040186 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | WATANSOPPENG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.459/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 321 | 01E07V01 | 019 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | WONOMULYO |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.980/LG.235/PND-C1030000/2020 | 2020-11-25 | TEL.0040/LG.320/PND-A1000000/2021 | 2021-01-15 | 169480966 | 19015415 | 188496381 | 188496381 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-01-28
12020290 | 16 | 524 | 01E07V01 | 019 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | PARE-PARE | WONOMULYO |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.923/LG.235/PND-C1030000/2020(SS#4SARPEN) | 2020-11-25 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 578500 | 57852 | 636352 | 636352 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 515 | 01E07V01 | 019 | 72070016 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | POSO | POSO |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.472/LG.235/PND-C10300000/2020(SS#4SARPEN) | 2020-11-25 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 157500 | 15752 | 173252 | 173252 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 431 | 01E07V01 | 019 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | JAILOLO |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-02-26 | 2020-10-09 | TEL.1029/LG.235/PND-C10300000/2020 | 2020-12-15 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 326 | 01E07V01 | 019 | 73020081 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | MABA |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.319/LG.235/PND-A10300000/2021 | 2021-01-22 | TEL.0575/LG.320/PND-A1000000/2021 | 2021-01-22 | 172438011 | 21232334 | 193670345 | 193670345 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 327 | 01E07V01 | 019 | 73020034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | SOA SIU |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.275/LG.235/PND-A10300000/2021 | 2021-01-20 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 259220771 | 22772264 | 281993035 | 281993035 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 527 | 01E07V01 | 019 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | SOFIFI |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.1153/LG.235/PND-C10300000/2020(SS#4SARPEN) | 2020-12-11 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 229000 | 22900 | 251900 | 251900 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 328 | 01E07V01 | 019 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | SOFIFI |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1153/LG.235/PND-C10300000/2020 | 2020-12-11 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 173095211 | 21317578 | 194412789 | 194412789 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 531 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TERNATE |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.321/LG.235/PND-A10300000/2021(SS#4SARPEN) | 2021-01-22 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 3820500 | 260250 | 4080750 | 4080750 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 329 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TERNATE |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.321/LG.235/PND-A10300000/2021 | 2021-01-22 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 174428411 | 21506822 | 195935233 | 195935233 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 550 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TERNATE |  | SS#2 GPON CARD-2 |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL1565/LG.235/PND-A103000000/2021 | 2021-03-23 | TEL.0772/LG.320/PND-A1000000/2021 | 2021-03-23 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 364 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TERNATE |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.465/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 147094720 | 3070884 | 150165604 | 150165604 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 792 | 01E07V01 | 019 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TERNATE |  | PT. NHM NUSA HALMAHERA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(PT.NHM) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 126607496 | 25570902 | 152178398 | 152178398 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 330 | 01E07V01 | 019 | 73020044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TOBELO |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.322/LG.235/PND-A10300000/2021 | 2021-01-22 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 174970011 | 21611534 | 196581545 | 196581545 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 793 | 01E07V01 | 019 | 73020044 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | TERNATE | TOBELO |  | CLUSTER TOMAHALU SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2788/LG.235/PND-A103000000/2021(TOMAHALU) | 2021-07-28 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 213154856 | 27106344 | 240261200 | 240261200 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 347 | 01E07V01 | 019 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | ANTANG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.469/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 430 | 01E07V01 | 019 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | BALAIKOTA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1514/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0576/LG.320/PND-A1000000/2021 | 2021-03-19 | 441284160 | 9212652 | 450496812 | 450496812 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-05-29
12020290 | 16 | 350 | 01E07V01 | 019 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | BANTAENG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1022/LG.235/PND-C10300000/2020 | 2020-12-10 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 346 | 01E07V01 | 019 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | BULUKUMBA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1023/LG.235/PND-C10300000/2020 | 2020-12-10 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 348 | 01E07V01 | 019 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | JENEPONTO |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.470/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1689/LG.320/PND-A1000000/2020 | 2020-11-25 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 743 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | MAROS |  | CAMBA SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2765/LG.235/PND-A103000000/2021(CAMBA) | 2021-07-29 | TEL.0038/LG.320/DID-00000000/2021 | 2021-07-29 | 210704856 | 14583384 | 225288240 | 225288240 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 432 | 01E07V01 | 019 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | MAROS |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1515/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 147094720 | 3070884 | 150165604 | 150165604 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 433 | 01E07V01 | 019 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | MATTOANGIN |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1516/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 349 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | PANAKUKANG |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1025/LG.235/PND-C10300000/2020 | 2020-12-10 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 294189440 | 6141768 | 300331208 | 300331208 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 513 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | PANAKUKANG |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.1152/LG.235/PND-C10300000/2020(SS#4SARPEN) | 2020-12-02 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 12915000 | 957100 | 13872100 | 13872100 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 307 | 01E07V01 | 019 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | PANAKUKANG |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1152/LG.235/PND-C10300000/2020 | 2020-12-02 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 163831011 | 21001834 | 184832845 | 184832845 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 434 | 01E07V01 | 019 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | PANGKEP |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1517/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 75000000 | 1498946 | 76498946 | 76498946 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 352 | 01E07V01 | 019 | 72080112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | SELAYAR |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1026/LG.235/PND-C10300000/2020 | 2020-12-10 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 435 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | SINJAI |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1518/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 511 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | SINJAI |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.486/LG.235/PND-C10300000/2020(SS#4SARPEN) | 2020-11-26 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 5916500 | 388652 | 6305152 | 6305152 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 308 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | SINJAI |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.486/LG.235/PND-C10300000/2020 | 2020-11-26 | TEL.1688/LG.320/PND-A1000000/2020 | 2020-11-26 | 172499546 | 21395205 | 193894751 | 193894751 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 746 | 01E07V01 | 019 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | SINJAI |  | SALOMEKO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2842/LG.235/PND-A103000000/2021(SALOMEKO) | 2021-07-29 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 117267155 | 11037019 | 128304174 | 128304174 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 355 | 01E07V01 | 019 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | SUNGGUMINASA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1027/LG.235/PND-C10300000/2020 | 2020-12-10 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 516284160 | 10711598 | 526995758 | 526995758 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 745 | 01E07V01 | 019 | 72080120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | TAKALAR |  | POROS GALESONG SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2765/LG.235/PND-A103000000/2021(GALESONG) | 2021-07-26 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 124157496 | 20907767 | 145065263 | 145065263 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 436 | 01E07V01 | 019 | 72080120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | TAKALAR |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1519/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 147094720 | 3070884 | 150165604 | 150165604 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020290 | 16 | 356 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | TAMALANREA |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.1028/LG.235/PND-C10300000/2020 | 2020-12-10 | TEL.0174/LG.320/PND-A1000000/2021 | 2020-12-15 | 220642080 | 4606326 | 225248406 | 225248406 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-02-27
12020290 | 16 | 309 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | TAMALANREA |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.320/LG.235/PND-A10300000/2021 | 2021-01-22 | TEL.0771/LG.320/PND-A1000000/2021 | 2021-01-22 | 173400011 | 21380334 | 194780345 | 194780345 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 512 | 01E07V01 | 019 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | TAMALANREA |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.320/LG.235/PND-A10300000/2021(SS#4SARPEN) | 2021-01-22 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 24908000 | 1869200 | 26777200 | 26777200 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 510 | 01E07V01 | 019 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | WATAMPONE |  | SS#4 SARPEN BIG OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-07 | 2020-10-09 | TEL.471/LG.235/PND-C10300000/2020(SS#4SARPEN) | 2020-11-25 | TEL.0773/LG.320/PND-A1000000/2021 | 2021-01-22 | 5695300 | 374652 | 6069952 | 6069952 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-06-30
12020290 | 16 | 310 | 01E07V01 | 019 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | WATAMPONE |  | SS#1 OLT |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-20 | 2020-10-09 | TEL.471/LG.235/PND-C10300000/2020 | 2020-11-25 | TEL.1688/LG.320/PND-A1000000/2020 | 2020-11-26 | 250300211 | 23151524 | 273451735 | 273451735 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2020-12-22
12020290 | 16 | 744 | 01E07V01 | 019 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | WATAMPONE |  | LAMPOKO SS#5 MINI OLT |  | 100 | 100 | 100 | BAST-1 | 2021-04-06 | 2021-07-31 | 2021-07-19 | TEL.2841/LG.235/PND-A103000000/2021(LAMPOKO) | 2021-07-29 | TEL.0037/LG.320/DID-00000000/2021 | 2021-07-29 | 117267155 | 11037019 | 128304174 | 128304174 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-08-29
12020290 | 16 | 437 | 01E07V01 | 019 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005922/HK.810/OPS-10000000/2020 | Kontrak OLT Platform Fiberhome | 2020-10-09 | 2021-07-31 | OLT Platform Fiberhome | UJUNGPANDANG | WATAMPONE |  | SS#2 GPON CARD |  | 100 | 100 | 100 | BAST-1 | 2020-10-09 | 2021-04-06 | 2020-10-09 | TEL.1520/LG.235/PND-A103000000/2021 | 2021-03-19 | TEL.0446/LG.320/PND-A1000000/2021 | 2021-03-19 | 73547360 | 1535442 | 75082802 | 75082802 | 4500415551 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-04-27
12020296 | 7 | 122 | 01C11B03 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | JAYAPURA | ABEPURA |  |  |  | 28 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-18 | 2020-10-13 | TEL.1616/LG.310/PND-B1050000/2021 | 2021-09-24 | TEL.0349/LG.320/DID-00000000/2021 | 2021-09-24 | 613492950 | 104367075 | 717860025 | 717860025 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020296 | 7 | 121 | 01C11B03 | 019 | 74030028 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | JAYAPURA | JAYAPURA BASE G |  |  |  | 28 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-18 | 2020-10-13 | TEL.1616/LG.310/PND-B1050000/2021 | 2021-09-24 | TEL.0349/LG.320/DID-00000000/2021 | 2021-09-24 | 538318000 | 95997000 | 634315000 | 634315000 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020296 | 7 | 119 | 01C11B03 | 019 | 74030034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | JAYAPURA | JAYAPURA-2 |  |  |  | 28 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-18 | 2020-10-13 | TEL.1616/LG.310/PND-B1050000/2021 | 2021-09-24 | TEL.0349/LG.320/DID-00000000/2021 | 2021-09-24 | 561462700 | 181457630 | 742920330 | 742920330 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020296 | 7 | 120 | 01C11B03 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | JAYAPURA | SARMI |  |  |  | 28 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-18 | 2020-10-13 | TEL.1616/LG.310/PND-B1050000/2021 | 2021-09-24 | TEL.0349/LG.320/DID-00000000/2021 | 2021-09-24 | 373433000 | 99663000 | 473096000 | 473096000 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020296 | 7 | 63 | 01C11B03 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | JAYAPURA | SENTANI |  |  |  | 90 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-28 | 2020-10-13 | TEL.2231/LG.310/PND-B105000/2021 | 2021-12-23 | TEL.0412/LG.320/DID-A0000000/2021 | 2021-12-23 | 373853000 | 68623000 | 442476000 | 442476000 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 71 | 01C11B03 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | JAYAPURA | WAENA |  |  |  | 35 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-10 | 2020-10-13 | TEL.2127/LG.310/PND-B105000/2021 | 2021-12-09 | TEL.0411/LG.320/DID-A0000000/2021 | 2021-12-09 | 328643400 | 43297340 | 371940740 | 371940740 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 79 | 01C11B03 | 019 | 74040010 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | MANOKWARI | RANSIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-19 | 2020-10-13 | TEL.2176/LG.310/PND-B105000/2021 | 2021-12-16 | TEL.0410/LG.320/DID-A0000000/2021 | 2021-12-16 | 314805400 | 33211340 | 348016740 | 348016740 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 157 | 01C11B03 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | PALU | BANGGAI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-19 | 2020-10-13 | TEL.2176/LG.310/PND-B105000/2021 | 2021-12-16 | TEL.0410/LG.320/DID-A0000000/2021 | 2021-12-16 | 324720400 | 34044340 | 358764740 | 358764740 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 72 | 01C11B03 | 019 | 72030013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | PALU | BUOL |  |  |  | 35 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-10 | 2020-10-13 | TEL.2127/LG.310/PND-B105000/2021 | 2021-12-09 | TEL.0411/LG.320/DID-A0000000/2021 | 2021-12-09 | 328575400 | 32597340 | 361172740 | 361172740 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 80 | 01C11B03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | PALU | KOTARAYA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-19 | 2020-10-13 | TEL.2176/LG.310/PND-B105000/2021 | 2021-12-16 | TEL.0410/LG.320/DID-A0000000/2021 | 2021-12-16 | 328805400 | 35211340 | 364016740 | 364016740 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 57 | 01C11B03 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | PALU | PALU |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-09-11 | 2020-10-13 | TEL.1483/LG.310/PND-B1050000/2021 | 2021-09-07 | TEL.0348/LG.320/DID-00000000/2021 | 2021-09-07 | 1137192000 | 187273500 | 1324465500 | 1324465500 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020296 | 7 | 61 | 01C11B03 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | PALU | PALU-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-08-17 | 2020-10-13 | TEL.1322/LG.310/PND-B1050000/2021 | 2021-08-16 | TEL.0347/LG.320/DID-00000000/2021 | 2021-08-16 | 672722950 | 164472375 | 837195325 | 837195325 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020296 | 7 | 64 | 01C11B03 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | PARE-PARE | MAMUJU |  |  |  | 90 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-12-28 | 2020-10-13 | TEL.2231/LG.310/PND-B105000/2021 | 2021-12-23 | TEL.0412/LG.320/DID-A0000000/2021 | 2021-12-23 | 368783000 | 67963000 | 436746000 | 436746000 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-12-31
12020296 | 7 | 105 | 01C11B03 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005989/HK.810/OPS-10000000/2020 | Kontrak Mekanikal Elektrikal PINS | 2020-10-13 | 2021-12-27 | Mekanikal Elektrikal | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-10-13 | 2021-09-11 | 2020-10-13 | TEL.1483/LG.310/PND-B1050000/2021 | 2021-09-07 | TEL.0348/LG.320/DID-00000000/2021 | 2021-09-07 | 2124623000 | 424218000 | 2548841000 | 2548841000 | 4500415552 |  |  |  |  | PINS INDONESIA | 2021-09-30
12020329 | 7 | 28 | 01C11I01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | KENDARI | KENDARI |  | SDN 03 Lalohao |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-23 | TEL.0918/LG.310/PND-C1030000/2021 | 2021-09-15 22:05 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 196947696 | 25744275 | 222691971 | 222691971 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020329 | 7 | 30 | 01C11I01 | 019 | 72050135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | KENDARI | PASARWAJO |  | STO Pasar Wajo |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-23 | TEL.0922/LG.310/PND-C1030000/2021 | 2021-09-17 05:29 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 184001321 | 13242976 | 197244297 | 197244297 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020329 | 7 | 29 | 01C11I01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | KENDARI | RAHA |  | Tengkuno |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-23 | TEL.0923/LG.310/PND-C1030000/2021 | 2021-09-17 05:29 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 193313696 | 15385288 | 208698984 | 208698984 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020329 | 7 | 32 | 01C11I01 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | PALU | POSO |  | Betalemba |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-29 | TEL.0911/LG.310/PND-C1030000/2021 | 2021-09-13 21:38 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 349042416 | 24483377 | 373525793 | 373525793 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020329 | 7 | 25 | 01C11I01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | PARE-PARE | ENREKANG |  | Kalosi |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-15 | TEL.0912/LG.310/PND-C1030000/2021 | 2021-09-13 21:38 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 196947696 | 25744275 | 222691971 | 222691971 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020329 | 7 | 26 | 01C11I01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | PARE-PARE | MAMUJU |  | Beru Beru |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-14 | TEL.0919/LG.310/PND-C1030000/2021 | 2021-09-15 22:05 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 201947696 | 23746556 | 225694252 | 225694252 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020329 | 7 | 24 | 01C11I01 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006708/HK.810/OPS-10040000/2020 | Kontrak Mini OLT Platform Nokia | 2020-11-10 | 2021-12-17 | MINI OLT | PARE-PARE | SENGKANG |  | Solobulo |  | 100 | 100 | 100 | BAST-1 | 2020-11-10 | 2021-10-01 | 2021-01-12 | TEL.0920/LG.310/PND-C1030000/2021 | 2021-09-15 22:06 | TEL.0651/LG.320/DID-00000000/2021 | 2021-09-17 | 201947696 | 25744275 | 227691971 | 227691971 | 4500417155 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-29
12020336 | 23 | 577 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-09-25 | 2023-11-11 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 514 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-05-25 | 2023-07-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 335 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 50 | 90 | 0 | Siap UT | 2022-06-25 | 2022-08-17 | 2022-07-01 |  |  |  |  | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 507 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-04-25 | 2023-06-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 377 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-09-25 | 2022-11-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 458 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-01-25 | 2023-03-19 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 202 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-08-25 | 2021-10-17 | 2021-09-01 | TEL.579/YN000/DWS-B1090000/2021 | 2021-11-25 | TEL.0016/LG.320/DWS-A0000000/2021 | 2021-11-25 | 0 | 252487211 | 252487211 | 252487211 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-12-26
12020336 | 23 | 167 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-06-25 | 2021-08-17 | 2021-07-01 | TEL.476/YN000/DWS-A1000000/2021 | 2021-09-29 | TEL.0009/LG.320/DWS-A0000000/2021 | 2021-09-29 | 5603552 | 0 | 5603552 | 5603552 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-10-22
12020336 | 23 | 216 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-09-25 | 2021-11-17 | 2021-10-01 | TEL.581/YN000/DWS-B1090000/2021 | 2021-11-25 | TEL.0014/LG.320/DWS-A0000000/2021 | 2021-11-25 | 0 | 251607211 | 251607211 | 251607211 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-12-26
12020336 | 23 | 223 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-25 | 2021-12-17 | 2021-11-01 | TEL.637/YN000/DWS-B1090000/2021 | 2021-12-29 | TEL.0001/LG.320/DWS-A0000000/2022 | 2021-12-29 | 5215614 | 0 | 5215614 | 5215614 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-01-10
12020336 | 23 | 230 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-25 | 2021-12-17 | 2021-11-01 | TEL.637/YN000/DWS-B1090000/2021 | 2021-12-29 | TEL.0002/LG.320/DWS-A0000000/2022 | 2021-12-29 | 0 | 250337211 | 250337211 | 250337211 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-01-10
12020336 | 23 | 17 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-01 | 2021-01-13 | 2020-12-01 | C.TEL.106/BAPR000/DSS-12000000/2021 | 2021-02-22 | TEL.0001/LG.320/DWS-A1000000/2021 | 2021-02-22 | 3496500 | 0 | 3496500 | 3496500 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-06-22
12020336 | 23 | 24 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-01 | 2021-01-13 | 2020-12-01 | C.TEL.106/BAPR000/DSS-12000000/2021 | 2021-02-22 | TEL.0002/LG.320/DWS-A1000000/2021 | 2021-02-22 | 0 | 145494858 | 145494858 | 145494858 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-06-22
12020336 | 23 | 153 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-07-17 | 2021-06-02 | TEL.416/YN000/DWS-A1000000/2021 | 2021-08-18 | TEL.0007/LG.320/DWS-A0000000/2021 | 2021-08-18 | 6489240 | 0 | 6489240 | 6489240 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020336 | 23 | 118 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-02-25 | 2021-04-19 | 2021-03-01 | TEL.352/YN000/DWS-A1000000/2021 | 2021-07-12 | TEL.0002/LG.320/DWS-A0000000/2021 | 2021-07-12 | 0 | 240072306 | 240072306 | 240072306 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-07-29
12020336 | 23 | 90 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-25 | 2021-02-16 | 2021-01-01 | C.TEL.107/BAPR000/DSS-12000000/2021 | 2021-02-22 | TEL.0004/LG.320/DWS-A1000000/2021 | 2021-02-22 | 0 | 161636132 | 161636132 | 161636132 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-06-22
12020336 | 23 | 132 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-03-25 | 2021-05-17 | 2021-04-01 | TEL.354/YN000/DWS-A1000000/2021 | 2021-07-12 | TEL.0004/LG.320/DWS-A0000000/2021 | 2021-07-12 | 0 | 245295045 | 245295045 | 245295045 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-08-03
12020336 | 23 | 139 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-04-25 | 2021-06-17 | 2021-05-01 | TEL.414/YN000/DWS-A1000000/2021 | 2021-08-18 | TEL.0005/LG.320/DWS-A0000000/2021 | 2021-08-18 | 5797974 | 0 | 5797974 | 5797974 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020336 | 23 | 111 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-02-25 | 2021-04-19 | 2021-03-01 | TEL.352/YN000/DWS-A1000000/2021 | 2021-07-12 | TEL.0001/LG.320/DWS-A0000000/2021 | 2021-07-12 | 8731800 | 0 | 8731800 | 8731800 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-07-29
12020336 | 23 | 146 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-04-25 | 2021-06-17 | 2021-05-01 | TEL.414/YN000/DWS-A1000000/2021 | 2021-08-18 | TEL.0006/LG.320/DWS-A0000000/2021 | 2021-08-18 | 0 | 247456182 | 247456182 | 247456182 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020336 | 23 | 160 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-07-17 | 2021-06-02 | TEL.416/YN000/DWS-A1000000/2021 | 2021-08-18 | TEL.0008/LG.320/DWS-A0000000/2021 | 2021-08-18 | 0 | 252480360 | 252480360 | 252480360 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-09-13
12020336 | 23 | 104 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-01-25 | 2021-03-19 | 2021-02-01 | C.TEL.108/BAPR000/DSS-12000000/2021 | 2021-02-22 | TEL.0006/LG.320/DWS-A1000000/2021 | 2021-02-22 | 0 | 227021049 | 227021049 | 227021049 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-06-22
12020336 | 23 | 125 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-03-25 | 2021-05-17 | 2021-04-01 | TEL.354/YN000/DWS-A1000000/2021 | 2021-07-12 | TEL.0003/LG.320/DWS-A0000000/2021 | 2021-07-12 | 17530482 | 0 | 17530482 | 17530482 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-08-03
12020336 | 23 | 451 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-12-25 | 2023-02-16 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 321 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 90 | 0 | Siap UT | 2022-05-25 | 2022-07-17 | 2022-06-01 |  |  |  |  | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 500 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-04-25 | 2023-06-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 328 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 90 | 0 | Siap UT | 2022-05-25 | 2022-07-17 | 2022-06-01 |  |  |  |  | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 307 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 90 | 0 | Siap UT | 2022-04-25 | 2022-06-17 | 2022-05-01 |  |  |  |  | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 521 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-05-25 | 2023-07-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 356 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 50 | 0 | 0 | Preparing | 2022-07-25 | 2022-09-16 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 405 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-11-25 | 2023-01-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 584 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-10-25 | 2023-11-11 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 342 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 50 | 90 | 0 | Siap UT | 2022-06-25 | 2022-08-17 | 2022-07-01 |  |  |  |  | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 370 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-08-25 | 2022-10-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 412 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-11-25 | 2023-01-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 556 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-08-25 | 2023-10-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 314 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 90 | 0 | Siap UT | 2022-04-25 | 2022-06-17 | 2022-05-01 |  |  |  |  | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 549 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-07-25 | 2023-09-16 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 363 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-08-25 | 2022-10-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 384 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-09-25 | 2022-11-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 542 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-07-25 | 2023-09-16 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 472 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-02-25 | 2023-04-19 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 398 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-10-25 | 2022-12-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 479 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-02-25 | 2023-04-19 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 563 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-08-25 | 2023-10-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 570 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-09-25 | 2023-11-11 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 391 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-10-25 | 2022-12-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 528 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-06-25 | 2023-08-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 591 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-10-25 | 2023-11-11 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 444 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2022-12-25 | 2023-02-16 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 535 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-06-25 | 2023-08-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 465 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-01-25 | 2023-03-19 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 486 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-03-25 | 2023-05-17 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 493 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 0 | 0 | 0 | Preparing | 2023-03-25 | 2023-05-17 | [5 empty] | 0 | 278652319 | 278652319 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 293 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-05-17 | 2022-04-01 | TEL.285/YN000/DWS-A0105000/2022 | 2022-06-03 | TEL.0005/LG.320/DWS-A1000000/2022 | 2022-06-03 | 13180328 | 0 | 13180328 | 13180328 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-06-30
12020336 | 23 | 279 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 |  |  |  | TEL.283/YN000/DWS-A0105000/2022 | 2022-06-03 | TEL.0003/LG.320/DWS-A1000000/2022 | 2022-06-03 | 0 | 0 | 0 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-06-30
12020336 | 23 | 237 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-01-17 | 2021-12-01 | TEL.660/YN000/DWS-B1090000/2022 | 2022-02-25 | TEL.0003/LG.320/DWS-A0000000/2022 | 2022-02-25 | 9074438 | 0 | 9074438 | 9074438 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-03-15
12020336 | 23 | 265 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-25 | 2022-03-19 | 2022-02-01 | TEL.281/YN000/DWS-A0105000/2022 | 2022-06-03 | TEL.0001/LG.320/DWS-A1000000/2022 | 2022-06-03 | 7820389 | 0 | 7820389 | 7820389 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-06-30
12020336 | 23 | 272 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-25 | 2022-03-19 | 2022-02-01 | TEL.281/YN000/DWS-A0105000/2022 | 2022-06-03 | TEL.0002/LG.320/DWS-A1000000/2022 | 2022-06-03 | 0 | 265874457 | 265874457 | 265874457 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-06-30
12020336 | 23 | 286 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-04-19 | 2022-03-01 | TEL.283/YN000/DWS-A0105000/2022 | 2022-06-03 | TEL.0004/LG.320/DWS-A1000000/2022 | 2022-06-03 | 0 | 257533334 | 257533334 | 257533334 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-06-30
12020336 | 23 | 300 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-05-17 | 2022-04-01 | TEL.285/YN000/DWS-A0105000/2022 | 2022-06-03 | TEL.0006/LG.320/DWS-A1000000/2022 | 2022-06-03 | 0 | 253803334 | 253803334 | 253803334 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-06-30
12020336 | 23 | 244 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-01-17 | 2021-12-01 | TEL.660/YN000/DWS-B1090000/2022 | 2022-02-25 | TEL.0004/LG.320/DWS-A0000000/2022 | 2022-02-25 | 0 | 253852211 | 253852211 | 253852211 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-03-15
12020336 | 23 | 251 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2022-02-16 | 2022-01-01 | TEL.100/YN000/DWS-A0105000/2022 | 2022-02-25 | TEL.0005/LG.320/DWS-A0000000/2022 | 2022-02-25 | 8988250 | 0 | 8988250 | 8988250 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-03-15
12020336 | 23 | 349 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 50 | 0 | 0 | Preparing | 2022-07-25 | 2022-09-16 | [5 empty] | 0 | 361596 | 361596 | 0 | 4500417952 |  |  |  |  | TELKOM AKSES
12020336 | 23 | 258 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2022-02-16 | 2022-01-01 | TEL.100/YN000/DWS-A0105000/2022 | 2022-02-25 | TEL.0006/LG.320/DWS-A0000000/2022 | 2022-02-25 | 0 | 261722211 | 261722211 | 261722211 | 4500417952 |  |  |  |  | TELKOM AKSES | 2022-03-15
12020336 | 23 | 209 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-09-25 | 2021-11-17 | 2021-10-01 | TEL.581/YN000/DWS-B1090000/2021 | 2021-11-25 | TEL.0015/LG.320/DWS-A0000000/2021 | 2021-11-25 | 5301564 | 0 | 5301564 | 5301564 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-12-26
12020336 | 23 | 174 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-06-25 | 2021-08-17 | 2021-07-01 | TEL.476/YN000/DWS-A1000000/2021 | 2021-09-29 | TEL.0010/LG.320/DWS-A0000000/2021 | 2021-09-29 | 0 | 250694192 | 250694192 | 250694192 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-10-22
12020336 | 23 | 181 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-07-25 | 2021-09-16 | 2021-08-01 | TEL.477/YN000/DWS-A1000000/2021 | 2021-09-29 | TEL.0011/LG.320/DWS-A0000000/2021 | 2021-09-29 | 7208747 | 0 | 7208747 | 7208747 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-10-22
12020336 | 23 | 188 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-07-25 | 2021-09-16 | 2021-08-02 | TEL.477/YN000/DWS-A1000000/2021 | 2021-09-29 | TEL.0012/LG.320/DWS-A0000000/2021 | 2021-09-29 | 0 | 250207211 | 250207211 | 250207211 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-10-22
12020336 | 23 | 195 | 01C13H07 | 034 | 70000014 | DIGITAL CONNECTIVITY SERVICE | CFUC CFUW INTERFACE SERVICE MGT | WHOLESALE PROV & INT AREA TREG 4,5,6,7 | DIVISI WHOLESALE SERVICE | K.TEL.006772/HK.810/OPS-10000000/2020 | Kontrak Fulfillment Pelanggan Wholesale | 2020-11-12 | 2022-11-11 | Fullfilment | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-08-25 | 2021-10-17 | 2021-09-01 | TEL.579/YN000/DWS-B1090000/2021 | 2021-11-25 | TEL.0017/LG.320/DWS-A0000000/2021 | 2021-11-25 | 14212923 | 0 | 14212923 | 14212923 | 4500417952 |  |  |  |  | TELKOM AKSES | 2021-12-26
G2020466 | 6 | 10 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | BULUKUMBA |  | BLK076 - TBG Poros Manjalling_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.40/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 263662441 | 63538443 | 327200884 | 327200884 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 11 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | BULUKUMBA |  | BLK078 - TBG Jawi-Jawi_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.41/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 44151672 | 12281780 | 56433452 | 56433452 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 12 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | BULUKUMBA |  | BLK004 - Tanjung Bira_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.38/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 45481193 | 10874144 | 56355337 | 56355337 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 7 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | BULUKUMBA |  | BLK043 - TBG Bakum-Bakum_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | BLK043-TBGBAKUM-BAKUMDCS | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 15294342 | 4310633 | 19604975 | 19604975 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 8 | 01E07J04 | 007 | 72080054 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | JENEPONTO |  | JNP027 - DMT Mallasoro_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.42/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 202674329 | 40769587 | 243443916 | 243443916 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 6 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | SINJAI |  | SIN07 - DMT MCP Rofina Sinjai_DCS |  | 100 | 0 | 0 | Preparing | 2020-11-20 | 2021-01-18 | [5 empty] | 5041880 | 1964113 | 7005993 | 0 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2020466 | 6 | 21 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD943 - Hotel Rinra Makassar_DCS |  | 100 | 0 | 0 | Preparing | 2020-11-20 | 2021-01-18 | [5 empty] | 5443083 | 6489668 | 11932751 | 0 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2020466 | 6 | 14 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD734 - Bank Mega Makassar_DCS |  | 100 | 0 | 0 | Preparing | 2020-11-20 | 2021-01-18 | [5 empty] | 4491756 | 1794088 | 6285844 | 0 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2020466 | 6 | 13 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD509 - Protelindo Tanjung Merdeka_DCS |  | 100 | 0 | 0 | Preparing | 2020-11-20 | 2021-01-18 | [5 empty] | 12842718 | 4169087 | 17011805 | 0 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2020466 | 6 | 9 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD401 - Goald Coast_DCS |  | 100 | 0 | 0 | Preparing | 2020-11-20 | 2021-01-18 | [5 empty] | 17720314 | 5313901 | 23034215 | 0 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2020466 | 6 | 22 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD522 - Protelindo Tanjung Bunga Selatan_DCS |  | 100 | 0 | 0 | Preparing | 2020-11-20 | 2021-01-18 | [5 empty] | 29240290 | 8810128 | 38050418 | 0 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2020466 | 6 | 15 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD788 - Protelindo Aston_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.43/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 10294045 | 3402474 | 13696519 | 13696519 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 16 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD867 - MC Bajigau_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.44/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 7046155 | 2495457 | 9541612 | 9541612 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 17 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD872 - MC Kasuari_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.45/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 12430235 | 4099929 | 16530164 | 16530164 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 18 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD890 - MC Bajiminasa Dalam_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.46/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 15809600 | 4939614 | 20749214 | 20749214 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 20 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD942 - Hotel Gamara Makassar_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.48/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 19253711 | 5995387 | 25249098 | 25249098 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
G2020466 | 6 | 19 | 01E07J04 | 007 | 72080135 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006991/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan OSP FIMO NODE-B 17 LOP Area WiteL Makassar - PT.ABG | 2020-11-20 | 2021-04-20 | Node-B 2020 | UJUNGPANDANG | UJUNG PANDANG |  | UPD893 - MC Bajiminasa_DCS |  | 100 | 100 | 100 | BAST-1 | 2020-11-20 | 2021-01-18 | 2021-02-01 | TEL.47/LG310/R7W-7A330000/2021 | 2021-02-16 | TEL.0007/LG.320/R7W-7A100000/2021 | 2021-02-16 | 6551748 | 2405943 | 8957691 | 8957691 | 4500418375 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2021-03-15
12020356 | 10 | 35 | 01C11B03 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007109/HK.810/OPS-10000000/2020 | Kontrak Sipil Ekspan Ruang NGN dan Pembangunan CLS SKKL | 2020-11-23 | 2021-11-12 | GEDUNG NGN | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-11-23 | 2021-07-01 | 2021-01-01 | TEL.1196/LG.310/PND-B1050000/2021 | 2021-06-18 | TEL.0957/LG.320/PND-A1000000/2021 | 2021-06-18 | 336313372 | 65274654 | 401588026 | 401588026 | 4500416761 |  |  |  |  | GRAHA SARANA DUTA | 2021-07-30
12020356 | 10 | 59 | 01C11B03 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007109/HK.810/OPS-10000000/2020 | Kontrak Sipil Ekspan Ruang NGN dan Pembangunan CLS SKKL | 2020-11-23 | 2021-11-12 | GEDUNG NGN | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-11-23 | 2021-09-30 | 2020-11-23 | TEL.1628/LG.310/PND-131050000/2021 | 2021-09-28 | TEL.0401/LG.320/DID-A0000000/2021 | 2021-09-28 | 674824250 | 129363250 | 804187500 | 804187500 | 4500416761 |  |  |  |  | GRAHA SARANA DUTA | 2021-12-31
12020356 | 10 | 44 | 01C11B03 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007109/HK.810/OPS-10000000/2020 | Kontrak Sipil Ekspan Ruang NGN dan Pembangunan CLS SKKL | 2020-11-23 | 2021-11-12 | GEDUNG NGN | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-11-23 | 2021-07-01 | 2021-02-02 | TEL.1195/LG.310/PND-B1050000/2021 | 2021-06-18 | TEL.0960/LG.320/PND-A1000000/2021 | 2021-06-18 | 696095728 | 282223473 | 978319201 | 978319201 | 4500416761 |  |  |  |  | GRAHA SARANA DUTA | 2021-07-30
32020190 | 0 | 9 | 01C12J04 | 039 | 74010005 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.007204/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Empat (SP#24) Dukungan Penyediaan Support Facility Radio IP Long Haul Biak-Sarmi | 2020-11-24 | 2021-11-23 | Support Facility | BIAK | BIAK |  | Periode-3 24 Mei 2021 sd 23 Agustus 2021 |  | 100 | 90 | 0 | Siap UT | 2020-11-24 | 2021-11-23 | 2020-11-24 |  |  |  |  | 0 | 1629000000 | 1629000000 | 0 | 4500418625 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020190 | 0 | 12 | 01C12J04 | 039 | 74010005 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.007204/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Empat (SP#24) Dukungan Penyediaan Support Facility Radio IP Long Haul Biak-Sarmi | 2020-11-24 | 2021-11-23 | Support Facility | BIAK | BIAK |  | Periode-4 24 Agustus 2021 sd 23 November 2021 |  | 100 | 90 | 0 | Siap UT | 2020-11-24 | 2021-11-23 | 2020-11-24 |  |  |  |  | 0 | 1629000000 | 1629000000 | 0 | 4500418625 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020190 | 0 | 13 | 01C12J04 | 039 | 74010005 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.007204/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Empat (SP#24) Dukungan Penyediaan Support Facility Radio IP Long Haul Biak-Sarmi | 2020-11-24 | 2021-11-23 | Support Facility | BIAK | BIAK |  |  |  | 100 | 90 | 0 | Siap UT | 2020-11-24 | 2021-11-23 | 2020-11-24 |  |  |  |  | 0 | 11292000000 | 11292000000 | 0 | 4500418625 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020190 | 0 | 10 | 01C12J04 | 039 | 74010005 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.007204/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Empat (SP#24) Dukungan Penyediaan Support Facility Radio IP Long Haul Biak-Sarmi | 2020-11-24 | 2021-11-23 | Support Facility | BIAK | BIAK |  | Periode-2 24 February 2021 sd 23 Mei 2021 |  | 100 | 90 | 0 | Siap UT | 2020-11-24 | 2021-11-23 | 2020-11-24 |  |  |  |  | 0 | 1629000000 | 1629000000 | 0 | 4500418625 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020190 | 0 | 11 | 01C12J04 | 039 | 74010005 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.007204/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Empat (SP#24) Dukungan Penyediaan Support Facility Radio IP Long Haul Biak-Sarmi | 2020-11-24 | 2021-11-23 | Support Facility | BIAK | BIAK |  | periode -1 24 November 2020 sd 23 Februari 2021 |  | 100 | 90 | 0 | Siap UT | 2020-11-24 | 2021-11-23 | 2020-11-24 |  |  |  |  | 0 | 1629000000 | 1629000000 | 0 | 4500418625 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
G2020491 | 1 | 186 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | MUZAKKIR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01945/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1351010 | 1054788 | 2405798 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 185 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | KHASRIANA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-31 | 2020-12-02 | TEL.01944/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1049158 | 852526 | 1901684 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 184 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | JUMADI WARIS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-27 | 2020-12-01 | TEL.01943/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1016348 | 830541 | 1846889 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 183 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | HASRAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01942/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1652862 | 1257050 | 2909912 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 182 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | SURIYATI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-24 | 2020-12-01 | TEL.01940/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 917918 | 764586 | 1682504 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 181 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | SULFIYA QADRI SYUKRI, S.PD |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-31 | 2020-12-02 | TEL.01941/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1305076 | 1024009 | 2329085 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 180 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | ANTANG |  | ERWIN MAKMUR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01763/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1344448 | 1050391 | 2394839 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 168 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | QIRAN ARYA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01921/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1226332 | 971245 | 2197577 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 169 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | FR AREA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01922/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1291952 | 1015215 | 2307167 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 170 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | ILHAM ARSYAD |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01923/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1095092 | 883305 | 1978397 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 171 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | AULIA CORNER |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01924/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 871984 | 733807 | 1605791 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 172 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | SAMPURNO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01926/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 173 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | DRS.MUSTAFA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01927/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1062282 | 861320 | 1923602 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 174 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | KANTOR KUA UJUNG LOE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01928/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1121340 | 900893 | 2022233 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 152 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | Ervina Winger |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01765/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1016348 | 830541 | 1846889 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 175 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | THE RIZAL TENDRA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01929/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 760430 | 659058 | 1419488 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 153 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | FAIZAL ASSIDIQ |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01914/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 983538 | 808556 | 1792094 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 154 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | YUSRI CIDU |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01925/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1036034 | 843732 | 1879766 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 155 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | YUNUS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01930/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 714496 | 628279 | 1342775 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 156 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | REEZKY AMELYA B |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01931/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 157 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | arya arnita hamid |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01932/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 583256 | 540339 | 1123595 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 158 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | ASDAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01933/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2939014 | 2118862 | 5057876 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 159 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | AYU PUTRI JUMRA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2020-12-22 | 2020-12-01 | TEL.01934/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 167 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | MUHAMMAD QADRI SALAM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01920/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 885108 | 742601 | 1627709 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 166 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | RATNAWATI SE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01919/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1226332 | 971245 | 2197577 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 165 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | WARKOP ALAMI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01918/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 694810 | 615088 | 1309898 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 164 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | SALTI MAIS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01917/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1101654 | 887702 | 1989356 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 163 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | POS ALPUNG |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01916/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1889094 | 1415342 | 3304436 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 162 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | NARDIN HERMANSYAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01915/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 931042 | 773380 | 1704422 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 161 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | KURNIAWAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01936/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 681686 | 606294 | 1287980 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 160 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BALAIKOTA |  | Ramliah |  | 100 | 95 | 0 | BAUT | 2020-11-27 | 2021-01-15 | 2020-12-01 | TEL.01935/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2591228 | 1885821 | 4477049 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 193 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | KANTOR LAKPESDAM |  | 100 | 95 | 0 | BAUT | 2020-11-27 | 2021-01-15 | 2020-12-01 | TEL.01951/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2361558 | 1731926 | 4093484 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 192 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | H. Muh. Untung |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-02 | TEL.01950/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1541308 | 1182301 | 2723609 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 191 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | ANZAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01949/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1718482 | 1301020 | 3019502 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 190 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | ADY NURSIAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01948/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 766992 | 663455 | 1430447 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 189 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | A. SUDARMAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01947/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1324762 | 1037200 | 2361962 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 188 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | RESKI AFRILINDA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01946/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1948152 | 1454915 | 3403067 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 187 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | BULUKUMBA |  | Drs. SYAMSUDDIN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01764/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1337886 | 1045994 | 2383880 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 177 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | KIMA |  | KHAIRUL AKBAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01766/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 438892 | 443605 | 882497 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 124 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | WARKOP CITTA MAROLA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01889/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1180398 | 940466 | 2120864 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 123 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | MUH RAFSANJANI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01888/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 557008 | 522751 | 1079759 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 122 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | MUHAMMAD IKHSAN H |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01887/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 766992 | 663455 | 1430447 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 121 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | FAHMI LUTFI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01886/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1436316 | 1111949 | 2548265 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 120 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | EMIL |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01885/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1311638 | 1028406 | 2340044 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 119 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | BUDI UTOMO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01884/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 668562 | 597500 | 1266062 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 118 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | AHMAD AKBAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01767/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1134464 | 909687 | 2044151 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 125 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MAROS |  | TISNA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01890/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1928466 | 1441724 | 3370190 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 149 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | NUSANTARA ELEKTRO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01906/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 760430 | 659058 | 1419488 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 126 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | A. TENRI ABENG |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01768/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1101654 | 887702 | 1989356 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 147 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | A.IMRAN MUNIR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01904/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 557008 | 522751 | 1079759 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 146 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | PEGADAIAN MARISO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01903/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 812926 | 694234 | 1507160 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 145 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | Ibrahim Chaidar |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01901/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 786678 | 676646 | 1463324 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 144 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | SYAHRIL SYAM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01900/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1186960 | 944863 | 2131823 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 143 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | NURHAYATI TALIB |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01899/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 766992 | 663455 | 1430447 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 142 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | MARTERINA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01898/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 141 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | HERRY JAMES |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01897/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 140 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | FEBRIANTI RAMADHAN A |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01896/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 642314 | 579912 | 1222226 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 139 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | BAHARUDDIN T |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01895/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1226332 | 971245 | 2197577 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 138 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | ASRIANI TRAKTOR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01894/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 648876 | 584309 | 1233185 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 137 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | ARETHA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01893/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1167274 | 931672 | 2098946 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 136 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | ANDI IMRAN MUNIR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01892/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 557008 | 522751 | 1079759 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 135 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | HERMAWATI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01913/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 786678 | 676646 | 1463324 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 134 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | WICO ARYANTI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01912/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1022910 | 834938 | 1857848 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 133 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | RUJAB REKTOR UNM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01911/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 826050 | 703028 | 1529078 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 132 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | M NABIL NIRWAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01910/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 983538 | 808556 | 1792094 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 131 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | WARKOP CITTA MAROLA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01909/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1180398 | 940466 | 2120864 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 130 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | DESCHA NOVILITA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01908/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 950728 | 786571 | 1737299 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 129 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | ALHADI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01907/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 819488 | 698631 | 1518119 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 128 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | DAENG TATA 77 |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01902/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1324762 | 1037200 | 2361962 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 127 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | Ahdan Mulyawan |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01891/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 622628 | 566721 | 1189349 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 148 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | MATTOANGIN |  | SHAVIRA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01905/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 904794 | 755792 | 1660586 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 50 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | ERNA MEYKE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01818/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1036034 | 843732 | 1879766 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 49 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | ANSHAR AHMAD |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01817/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 151 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | WARKOP NURA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01937/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 747306 | 650264 | 1397570 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 150 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | DINAS PENDIDIKAN KOTA MAKASSAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01769/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 90 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | DEMIYANUS HEBINGADATE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01852/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 766992 | 663455 | 1430447 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 89 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | BAPEDA PROGRAM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01851/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1790664 | 1349387 | 3140051 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 88 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | WICO ERNA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01849/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 707934 | 623882 | 1331816 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 87 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | TATA IBRAHIM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01848/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 86 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | widiastuty |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01847/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 668562 | 597500 | 1266062 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 85 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MASJID JAMI AL-ITTIHAD |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01846/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1062282 | 861320 | 1923602 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 84 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | INI CAFE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01845/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1095092 | 883305 | 1978397 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 83 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | PEGADAIAN 11302 TODDOPULI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01844/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1121340 | 900893 | 2022233 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 82 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HERWATY ST |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01843/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 734182 | 641470 | 1375652 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 81 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | ASFIHANUDDIN MUHTAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01842/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 648876 | 584309 | 1233185 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 80 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MANIAS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01841/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 622628 | 566721 | 1189349 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 79 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | WARKOP AW |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01840/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1062282 | 861320 | 1923602 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 78 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | KIOS LOLA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01838/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 616066 | 562324 | 1178390 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 77 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | YUSTISIA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01837/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 662000 | 593103 | 1255103 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 76 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | WHEELS COFFE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01836/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 707934 | 623882 | 1331816 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 75 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | TEDY PUTRA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01835/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1534746 | 1177904 | 2712650 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 74 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | SYAFIAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01834/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 622628 | 566721 | 1189349 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 73 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | RESTY PUSPITASARI HUSLY |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01833/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1331324 | 1041597 | 2372921 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 72 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | RED CORNER |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01832/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 71 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | RAHMAWAN BUSRAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01858/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 616066 | 562324 | 1178390 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 70 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MUHAMMAD ICHSAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01830/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 668562 | 597500 | 1266062 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 69 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MUH. ERLANGGA H |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01829/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1423192 | 1103155 | 2526347 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 68 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MISRAWATI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01828/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 67 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MEYRYZA FARID |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01827/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 66 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | JARWAL COPY MAKASSAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01826/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 714496 | 628279 | 1342775 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 65 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | INDRA SAPUTRA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01825/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 589818 | 544736 | 1134554 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 64 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HJ.NURBAYANI ARQAM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01824/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 760430 | 659058 | 1419488 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 63 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HERLIA PASAPAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01823/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 62 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HASAN WALINONO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01822/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 589818 | 544736 | 1134554 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 61 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HARIYANTO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01821/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 602942 | 553530 | 1156472 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 60 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HARIYANTO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01820/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 602942 | 553530 | 1156472 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 59 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HAMRI HAIYA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01819/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1167274 | 931672 | 2098946 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 58 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | Rizal Tendra |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01857/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 701372 | 619485 | 1320857 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 57 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | ISLAMUDDIN DINI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01856/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1127902 | 905290 | 2033192 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 56 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | IMRAN RAUF |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01855/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1141026 | 914084 | 2055110 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 55 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | MARCELINA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01854/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 694810 | 615088 | 1309898 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 54 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | HASYRUL KAMAL |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01853/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 609504 | 557927 | 1167431 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 53 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | WICO THE TUPS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01850/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 786678 | 676646 | 1463324 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 52 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | ADYN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-02 | TEL.01839/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1246018 | 984436 | 2230454 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 51 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | PANAKUKANG |  | RAHMAWANG BUSRAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01831/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 983538 | 808556 | 1792094 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 176 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | NURDIANA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01938/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 642314 | 579912 | 1222226 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 101 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | ARHAM RAHIM |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01770/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 113 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | MUH. MAULANA RAHMAT |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01871/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 806364 | 689837 | 1496201 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 112 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | DEDI ARMAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01870/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 832612 | 707425 | 1540037 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 111 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | SD INPRES DAYA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01869/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 885108 | 742601 | 1627709 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 110 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | SEKRETARIAT DEMOKRAT |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01883/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1410068 | 1094361 | 2504429 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 109 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | MUH DANI ERLANGGA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01882/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1003224 | 821747 | 1824971 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 108 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | ARSYAD NIPPI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01881/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 845736 | 716219 | 1561955 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 107 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | MUSRIANI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01880/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1049158 | 852526 | 1901684 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 106 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | FIRMAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01879/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1114778 | 896496 | 2011274 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 105 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | WAHYU MUH A LING |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01878/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1022910 | 834938 | 1857848 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 104 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | SRI HIDAYATI. S. KEP |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01877/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2125326 | 1573634 | 3698960 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 114 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | FAJAR IMANUDDIN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01872/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 780116 | 672249 | 1452365 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 102 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | MUH HAERIL |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01868/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 957290 | 790968 | 1748258 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 103 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | SAHWANI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01876/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2046582 | 1520870 | 3567452 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 115 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | H. FAISAL HF |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01873/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1200084 | 953657 | 2153741 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 116 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | FADLY |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01874/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 117 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUDIANG |  | OJAK PAROLOAN SITINJAK |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01875/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 34 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | BIRO PERLENGKAPAN 1 |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01795/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 793240 | 681043 | 1474283 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 40 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | KANTOR LURAH TETEBATU |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01802/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 727620 | 637073 | 1364693 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 32 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | BIRO UMUM PERLENGKAPAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01793/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1055720 | 856923 | 1912643 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 31 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | JAHARUDDING INDAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01792/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 766992 | 663455 | 1430447 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 30 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | CEL22 |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01791/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 799802 | 685440 | 1485242 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 29 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | GO SULSEL |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01790/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 28 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | TOKO AR - RAZZAK |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01789/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 865422 | 729410 | 1594832 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 27 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | SUDIRMANTO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01788/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 26 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | SIRAJUDDIN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01787/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 622628 | 566721 | 1189349 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 25 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | RAODAH FABRIYATI BUSRAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01785/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 766992 | 663455 | 1430447 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 24 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | NURSYAIFULLAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01784/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 688248 | 610691 | 1298939 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 23 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | NURAIDA BASIR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01783/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1278828 | 1006421 | 2285249 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 22 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | MUSLIMIN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01782/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1364134 | 1063582 | 2427716 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 21 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | MUHAMMAD ATTAS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01781/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 20 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | KANTOR KAU KEC. PALLANGGA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01780/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 635752 | 575515 | 1211267 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 19 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | JASMIANDI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01779/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 806364 | 689837 | 1496201 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 18 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | ILHAM RAHMAT |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01778/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1843160 | 1384563 | 3227723 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 17 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | IHSAN MURAD |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01777/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 753868 | 654661 | 1408529 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 16 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | HERIYANTO KULLE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-02 | TEL.01776/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1154150 | 922878 | 2077028 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 15 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | NUR ASMIYANTY |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01816/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 963852 | 795365 | 1759217 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 14 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LAATANSA 99 |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01815/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2374682 | 1740720 | 4115402 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 13 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | PELANGGAN CHAERO INDRA PRAYATMA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01814/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2794650 | 2022128 | 4816778 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 12 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | M.YANIS |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01813/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2368120 | 1736323 | 4104443 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 11 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | YASSER ARAFAT |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01812/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 10 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | ARMAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01808/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 878546 | 738204 | 1616750 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 9 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | ANGRY MOMS WICO 2.0 |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01797/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 852298 | 720616 | 1572914 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 8 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | RUSTAM,SE.M.Si |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01786/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 668562 | 597500 | 1266062 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 7 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | HENDRA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01775/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 983538 | 808556 | 1792094 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 6 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | HAMSAL HAMID |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01771/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 48 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | BEVY JOSEPH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01811/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 681686 | 606294 | 1287980 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 47 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | HAMZAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01810/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2177822 | 1608810 | 3786632 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 46 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | KANTOR KAU KEC. BAJENG |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01809/LG310/R7W-7A330000/2020 | 2020-12-18 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 45 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | AKBAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01807/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 983538 | 808556 | 1792094 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 44 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | A.ARDIMAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01806/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 950728 | 786571 | 1737299 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 43 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | MUH. TAMRIN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01805/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1042596 | 848129 | 1890725 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 42 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | SYINTHA WARACHMA TAUFIQ |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01804/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1016348 | 830541 | 1846889 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 41 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | KUA KEC. PALLANGGA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01803/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 622628 | 566721 | 1189349 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 35 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | ASRIANI S.P |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01796/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1180398 | 940466 | 2120864 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 36 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Madi Cell |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01798/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 852298 | 720616 | 1572914 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 37 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | MUH.IDRIS, S. AG |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01799/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2197508 | 1622001 | 3819509 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 38 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | ARIEL JAYA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01800/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 39 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | ABDULLAH TAWAKKAL |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01801/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 826050 | 703028 | 1529078 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 33 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | SUNGGUMINASA |  | BIRO UMUM PERLENGKAPAN 2 |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01794/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1055720 | 856923 | 1912643 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 178 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAKALAR |  | NUR AFIAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01773/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1134464 | 909687 | 2044151 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 179 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAKALAR |  | KONWIL DIKNAS BONTO NOMPO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01939/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 793240 | 681043 | 1474283 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 98 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | STIMIK DIPANEGARA MAKASSAR |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01865/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 996662 | 817350 | 1814012 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 91 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | MITRA RIANI AISYAH |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01772/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 681686 | 606294 | 1287980 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 96 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | ORYZA COFFEE |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01863/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 668562 | 597500 | 1266062 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 95 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | PRATIWI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01861/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 707934 | 623882 | 1331816 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 94 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | VICKY |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01862/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 714496 | 628279 | 1342775 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 93 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | NUR CHOLIS TAQWA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01860/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 655438 | 588706 | 1244144 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 92 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | MUSRIADI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01859/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 917918 | 764586 | 1682504 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 99 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | M.FADLY AFRIANTO |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01866/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1639738 | 1248256 | 2887994 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 100 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | IR.SELLE HAFID MSI |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01867/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 721058 | 632676 | 1353734 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 97 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | TAMALANREA |  | Kost Akhwat |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01864/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1246018 | 984436 | 2230454 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 196 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | WATAMPONE |  | PT.AMIN JAYA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01953/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1167274 | 931672 | 2098946 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 194 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | WATAMPONE |  | NURLINA |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01774/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 1305076 | 1024009 | 2329085 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
G2020491 | 1 | 195 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.007311/HK.810/R7W-7A100000/2020 | Pengadaan dan Pemasangan LME WiFi 191 LoP Area Witel Makassar - PT.RATI UTAMA KARYA | 2020-11-26 | 2021-01-24 | LME WIFI | UJUNGPANDANG | WATAMPONE |  | RISMAN |  | 100 | 95 | 0 | BAUT | 2020-11-26 | 2021-01-14 | 2020-12-01 | TEL.01952/LG310/R7W-7A330000/2020 | 2020-12-17 |  |  | 2151574 | 1591222 | 3742796 | 0 | 4500418736 |  |  |  |  | RATI UTAMA KARYA
12020367 | 7 | 50 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007619/HK.810/OPS-10040000/2020 | Kontrak Ekspansi BRAS dan WAG Ericsson | 2020-12-02 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | BALAIKOTA |  |  |  | 70 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2217/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0172/LG.320/DID-A0000000/2021 | 2021-12-22 | 1108515000 | 238462000 | 1346977000 | 1346977000 | 4500419128 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020367 | 7 | 12 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007619/HK.810/OPS-10040000/2020 | Kontrak Ekspansi BRAS dan WAG Ericsson | 2020-12-02 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-02 | 2021-04-30 | 2020-12-02 | TEL.566/LG.310/PND-B1050000/2021 | 2021-04-30 | TEL.0626/LG.320/PND-A1000000/2021 | 2021-04-30 | 1143074000 | 58150000 | 1201224000 | 1201224000 | 4500419128 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-05-31
12020367 | 7 | 49 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007619/HK.810/OPS-10040000/2020 | Kontrak Ekspansi BRAS dan WAG Ericsson | 2020-12-02 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | BALAIKOTA |  |  |  | 75 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2224/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0175/LG.320/DID-A0000000/2021 | 2021-12-22 | 0 | 40900000 | 40900000 | 40900000 | 4500419128 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020367 | 7 | 53 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007619/HK.810/OPS-10040000/2020 | Kontrak Ekspansi BRAS dan WAG Ericsson | 2020-12-02 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | BALAIKOTA |  |  |  | 42 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2222/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0173/LG.320/DID-A0000000/2021 | 2021-12-22 | 131664000 | 16464000 | 148128000 | 148128000 | 4500419128 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020367 | 7 | 48 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007619/HK.810/OPS-10040000/2020 | Kontrak Ekspansi BRAS dan WAG Ericsson | 2020-12-02 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | BALAIKOTA |  |  |  | 75 | 100 | 100 | BAST-1 | 2021-10-21 | 2021-12-30 | 2021-11-29 | TEL.2223/LG.310/PND-B1050000/2021 | 2021-12-22 | TEL.0174/LG.320/DID-A0000000/2021 | 2021-12-22 | 0 | 17996000 | 17996000 | 17996000 | 4500419128 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-12-27
12020367 | 7 | 13 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007619/HK.810/OPS-10040000/2020 | Kontrak Ekspansi BRAS dan WAG Ericsson | 2020-12-02 | 2021-12-30 | Ekspan BRAS & WAG | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-02 | 2021-04-30 | 2020-12-02 | TEL.566/LG.310/PND-B1050000/2021 | 2021-04-30 | TEL.0626/LG.320/PND-A1000000/2021 | 2021-04-30 | 1143074000 | 58150000 | 1201224000 | 1201224000 | 4500419128 |  |  |  |  | KONSORSIUM BINAINFO LOKATARA | 2021-05-31
12020371 | 19 | 160 | 01C11I02 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007729/HK.810/OPS-10000000/2020 | SP#21 Granular Modernization - OSP FO Feeder FTTH Tahap-2 dan FTM Recovery STO Pekanbaru | 2020-12-03 | 2022-04-16 | GRANULAR | MANADO | PANIKI |  | PIK FE-09 SS#1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-04 | 2022-03-04 | 2020-12-04 | TEL.0111/LG.310/DID-C0200000/2022 | 2022-02-25 17:49 | TEL.0144/LG.320/DID-A0000000/2022 | 2022-02-25 | 735215086 | 249407186 | 984622272 | 984622272 | 4500419542 |  |  |  |  | TELKOM AKSES | 2022-02-27
12020371 | 19 | 159 | 01C11I02 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007729/HK.810/OPS-10000000/2020 | SP#21 Granular Modernization - OSP FO Feeder FTTH Tahap-2 dan FTM Recovery STO Pekanbaru | 2020-12-03 | 2022-04-16 | GRANULAR | MANADO | PANIKI |  | PIK FE-08 SS#1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-04 | 2022-03-04 | 2020-12-04 | TEL.0111/LG.310/DID-C0200000/2022 | 2022-02-25 17:49 | TEL.0144/LG.320/DID-A0000000/2022 | 2022-02-25 | 742624245 | 121143429 | 863767674 | 863767674 | 4500419542 |  |  |  |  | TELKOM AKSES | 2022-02-27
12020371 | 19 | 161 | 01C11I02 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007729/HK.810/OPS-10000000/2020 | SP#21 Granular Modernization - OSP FO Feeder FTTH Tahap-2 dan FTM Recovery STO Pekanbaru | 2020-12-03 | 2022-04-16 | GRANULAR | MANADO | PANIKI |  | PIK FE-10 SS#1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-04 | 2022-01-03 | 2020-12-04 | TEL.0074/LG.310/DID-C0200000/2021 | 2021-12-27 22:18 | TEL.0251/LG.320/DID-A0000000/2021 | 2021-12-27 | 621628465 | 142480226 | 764108691 | 764108691 | 4500419542 |  |  |  |  | TELKOM AKSES | 2021-12-29
12020371 | 19 | 157 | 01C11I02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007729/HK.810/OPS-10000000/2020 | SP#21 Granular Modernization - OSP FO Feeder FTTH Tahap-2 dan FTM Recovery STO Pekanbaru | 2020-12-03 | 2022-04-16 | GRANULAR | SORONG | SORONG |  | FE Rute-1 SS#1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-04 | 2021-12-03 | 2020-12-04 | TEL.1245/LG.310/PND-C1030000/2021 | 2021-11-26 07:36 | TEL.0678/LG.320/DID-00000000/2021 | 2021-11-26 | 1301115632 | 386017703 | 1687133335 | 1687133335 | 4500419542 |  |  |  |  | TELKOM AKSES | 2021-11-29
12020371 | 19 | 158 | 01C11I02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007729/HK.810/OPS-10000000/2020 | SP#21 Granular Modernization - OSP FO Feeder FTTH Tahap-2 dan FTM Recovery STO Pekanbaru | 2020-12-03 | 2022-04-16 | GRANULAR | SORONG | SORONG |  | FE Rute-2 SS#1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-04 | 2021-11-23 | 2020-12-04 | TEL.1245/LG.310/PND-C1030000/2021 | 2021-11-26 07:36 | TEL.0678/LG.320/DID-00000000/2021 | 2021-11-26 | 896841722 | 281569765 | 1178411487 | 1178411487 | 4500419542 |  |  |  |  | TELKOM AKSES | 2021-11-29
12020374 | 22 | 523 | 01C11G03 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007906/HK.810/OPS-10040000/2020 | Kontrak Radio IP Akses CNOP Platform Huawei | 2020-12-07 | 2022-02-06 | RADIO IP | AMBON | MALUKU |  | MSH091-MSH090 |  | 100 | 100 | 100 | BAST-1 | 2020-12-09 | 2021-08-02 | 2021-06-01 | TEL.1866/LG.310/PND-C1010000/2021 | 2021-06-26 | TEL.0823/LG.320/PND-A1000000/2021 | 2021-06-26 | 0 | 3946774 | 3946774 | 3946774 | 4500419163 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-06-30
12020376 | 23 | 216 | 01C11I04 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | BANGGAI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 217 | 01C11I04 | 019 | 72030013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | BUOL |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 218 | 01C11I04 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | KOLONODALE |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 219 | 01C11I04 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | LUWUK |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 50 | 01C11I04 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | PALU-2 |  | STO PALU-2 B REKON-02 |  | 100 | 100 | 100 | BAST-1 | 2020-12-08 | 2022-01-14 | 2021-03-29 | LAMPIRAN_STO_PALU_2_B_2 | 2021-03-29 | TEL.0421/LG.320/DID-00000000/2021 | 2021-03-29 | 124633980 | 0 | 124633980 | 124633980 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2021-10-27
12020376 | 23 | 49 | 01C11I04 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | PALU-2 |  | STO PALU-2 B REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2020-12-08 | 2021-07-14 | 2021-03-18 | TEL.PL-B/117/MML/PRIM/17032021 | 2021-03-30 | TEL.0462/LG.320/PND-A1000000/2021 | 2021-03-30 | 3056775566 | 0 | 3056775566 | 3056775566 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2021-04-29
12020376 | 23 | 100 | 01C11I04 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PALU | PALU-2 |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 220 | 01C11I04 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PARE-PARE | MASAMBA |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 222 | 01C11I04 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PARE-PARE | PASANG KAYU |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 221 | 01C11I04 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | PARE-PARE | SENGKANG |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020376 | 23 | 223 | 01C11I04 | 019 | 74060049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007974/HK.810/OPS-10000000/2020 | Surat Pesanan-1 (SP#1) Penjualan Barang Scrap TELKOM | 2020-12-08 | 2022-06-30 | PELOLOSAN | SORONG | RAJA AMPAT |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-08 | 2022-07-14 | 2020-12-08 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12020380 | 26 | 2441 | 01C11I02 | 019 | 73010120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | AMBON | DOBO |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0137/LG.310/DID-C0200000/2021 | 2021-12-29 21:31 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 581240 | 1082700 | 1082700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 1547 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | FEEDER NOC |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0709/LG.310/DID-C0200000/2022 | 2022-06-29 15:36 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 56216079 | 18814726 | 75030805 | 75030805 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 1548 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | DISTRIBUSI 1 FTTH ASMAT |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0713/LG.310/DID-C0200000/2022 | 2022-06-29 15:38 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 174749484 | 76213559 | 250963043 | 250963043 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 1549 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | DISTRIBUSI 2 FTTH ASMAT |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0713/LG.310/DID-C0200000/2022 | 2022-06-29 15:38 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 527757023 | 312946802 | 840703825 | 840703825 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 1550 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | DISTRIBUSI 3 FTTH ASMAT |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0713/LG.310/DID-C0200000/2022 | 2022-06-29 15:38 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 198751261 | 98305434 | 297056695 | 297056695 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 1551 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | DISTRIBUSI 4 FTTH ASMAT |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0713/LG.310/DID-C0200000/2022 | 2022-06-29 15:38 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 304160099 | 151253794 | 455413893 | 455413893 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 1552 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | DISTRIBUSI 5 FTTH ASMAT |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0713/LG.310/DID-C0200000/2022 | 2022-06-29 15:38 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 257373184 | 119389611 | 376762795 | 376762795 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 1553 | 01C11I02 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | AGATS |  | DISTRIBUSI 6 FTTH ASMAT |  | 90 | 100 | 100 | BAST-1 | 2021-06-04 | 2022-07-05 | 2022-03-22 | TEL.0713/LG.310/DID-C0200000/2022 | 2022-06-29 15:38 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 339876426 | 195464329 | 535340755 | 535340755 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 142 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | NABIRE |  | KARANG MULIA SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-07-14 | 2021-03-18 | TEL.0086/LG.310/PND-C1030000/2021 | 2021-06-29 18:19 | TEL.0820/LG.320/PND-A1000000/2021 | 2021-06-29 | 212425643 | 54958870 | 267384513 | 267384513 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020380 | 26 | 174 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | NABIRE |  | KARANG TUMARITIS SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-07-14 | 2021-03-19 | TEL.0086/LG.310/PND-C1030000/2021 | 2021-06-29 18:19 | TEL.0820/LG.320/PND-A1000000/2021 | 2021-06-29 | 521037583 | 131886105 | 652923688 | 652923688 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020380 | 26 | 2509 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | TIMIKA |  | MIGRASI C2F CONSUMER TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0140/LG.310/DID-C0200000/2021 | 2021-12-29 21:35 | TEL.0389/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 731240 | 1232700 | 1232700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 136 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | JAYAPURA | WAMENA |  | PT3 NEW ODC WAM SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-11-30 | 2021-05-25 | TEL.1258/LG.310/PND-C1030000/2021 | 2021-11-26 16:47 | TEL.0719/LG.320/DID-00000000/2021 | 2021-11-26 | 1429006137 | 394503708 | 1823509845 | 1823509845 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-11-30
12020380 | 26 | 1217 | 01C11I02 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | MANADO | AIR MADIDI |  | KOKOLEH SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-09-06 | 2021-04-02 | TEL.0829/LG.310/PND-C1030000/2021 | 2021-08-24 10:25 | TEL.0090/LG.320/DID-00000000/2021 | 2021-08-24 | 315052600 | 99399225 | 414451825 | 414451825 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-08-31
12020380 | 26 | 1216 | 01C11I02 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | MANADO | AIR MADIDI |  | KAWERUAN SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-09-07 | 2021-04-05 | TEL.0829/LG.310/PND-C1030000/2021 | 2021-08-24 10:25 | TEL.0090/LG.320/DID-00000000/2021 | 2021-08-24 | 298121139 | 79719971 | 377841110 | 377841110 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-08-31
12020380 | 26 | 149 | 01C11I02 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | MANADO | TONDANO |  | RINEGETAN SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-09-07 | 2021-04-13 | TEL.0829/LG.310/PND-C1030000/2021 | 2021-08-24 10:25 | TEL.0090/LG.320/DID-00000000/2021 | 2021-08-24 | 77652018 | 32144531 | 109796549 | 109796549 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-08-31
12020380 | 26 | 1215 | 01C11I02 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | MANADO | TONDANO |  | WAWALONTOAN SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-09-07 | 2021-04-16 | TEL.0829/LG.310/PND-C1030000/2021 | 2021-08-24 10:25 | TEL.0090/LG.320/DID-00000000/2021 | 2021-08-24 | 128605062 | 32258072 | 160863134 | 160863134 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-08-31
12020380 | 26 | 2458 | 01C11I02 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | MANOKWARI | MANOKWARI |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0130/LG.310/DID-C0200000/2021 | 2021-12-29 21:22 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 731240 | 1232700 | 1232700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 2493 | 01C11I02 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | PALU | BANGGAI |  | MIGRASI C2F CONSUMER TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0135/LG.310/DID-C0200000/2021 | 2021-12-29 21:31 | TEL.0389/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 581240 | 1082700 | 1082700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 2436 | 01C11I02 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | PALU | PALU-1 |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0138/LG.310/DID-C0200000/2021 | 2021-12-29 21:32 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 581240 | 1082700 | 1082700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 1207 | 01C11I02 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | SORONG | NABIRE |  | Jl. Frans Kaisepo PT3 DS.01 SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-07-14 | 2021-03-19 | TEL.0086/LG.310/PND-C1030000/2021 | 2021-06-29 18:19 | TEL.0820/LG.320/PND-A1000000/2021 | 2021-06-29 | 160793981 | 42334639 | 203128620 | 203128620 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020380 | 26 | 1206 | 01C11I02 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | SORONG | NABIRE |  | JL. PERINTIS SS#2 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-07-14 | 2021-03-19 | TEL.0086/LG.310/PND-C1030000/2021 | 2021-06-29 18:19 | TEL.0820/LG.320/PND-A1000000/2021 | 2021-06-29 | 353090392 | 88198110 | 441288502 | 441288502 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020380 | 26 | 1378 | 01C11I02 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | SORONG | NABIRE |  | Jl. Frans Kaisepo PT3 NEW ODC-NAB-FK SS#1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2021-07-14 | 2021-03-19 | TEL.0084/LG.310/PND-C1030000/2021 | 2021-06-29 18:19 | TEL.0821/LG.320/PND-A1000000/2021 | 2021-06-29 | 189481177 | 54787934 | 244269111 | 244269111 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020380 | 26 | 2461 | 01C11I02 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | SORONG | SERUI |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0131/LG.310/DID-C0200000/2021 | 2021-12-29 21:22 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 581240 | 1082700 | 1082700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 223 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0129/LG.310/DID-C0200000/2021 | 2021-12-29 21:22 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 11533580 | 13368520 | 24902100 | 24902100 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 1334 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | BULUKUMBA |  | PALANGISANG SS#2 |  | 90 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-07-14 | 2021-06-25 | TEL.0704/LG.310/DID-C0200000/2022 | 2022-06-29 14:01 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 1346984005 | 681552839 | 2028536844 | 2028536844 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 224 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0129/LG.310/DID-C0200000/2021 | 2021-12-29 21:22 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 8023360 | 9299840 | 17323200 | 17323200 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 2483 | 01C11I02 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | SINJAI |  | MIGRASI C2F CONSUMER TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0136/LG.310/DID-C0200000/2021 | 2021-12-29 21:31 | TEL.0389/LG.320/DID-A0000000/2021 | 2021-12-29 | 501460 | 581240 | 1082700 | 1082700 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 221 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | SUDIANG |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0129/LG.310/DID-C0200000/2021 | 2021-12-29 21:22 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 2005840 | 2324960 | 4330800 | 4330800 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020380 | 26 | 2534 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | SUNGGUMINASA |  | TAENG DISTRIBUSI SS#2 |  | 90 | 100 | 100 | BAST-1 | 2022-05-24 | 2022-07-01 | 2022-06-08 | TEL.0704/LG.310/DID-C0200000/2022 | 2022-06-29 14:01 | TEL.0876/LG.320/DID-A0000000/2022 | 2022-06-29 | 226745137 | 47560243 | 274305380 | 274305380 | 4500419698 |  |  |  |  | TELKOM AKSES | 2022-06-29
12020380 | 26 | 222 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008062/HK.810/OPS-10000000/2020 | SP#22 Granular Modernization - OSP FO FTTH dan Migrasi T-Cloud Tahap-2 | 2020-12-10 | 2022-06-30 | GRANULAR 2020 | UJUNGPANDANG | TAMALANREA |  | MIGRASI C2F EBIS TAHAP 1 |  | 100 | 100 | 100 | BAST-1 | 2020-12-10 | 2022-02-02 | 2021-12-29 | TEL.0129/LG.310/DID-C0200000/2021 | 2021-12-29 21:22 | TEL.0390/LG.320/DID-A0000000/2021 | 2021-12-29 | 4011680 | 4649920 | 8661600 | 8661600 | 4500419698 |  |  |  |  | TELKOM AKSES | 2021-12-31
12020389 | 11 | 55 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA09 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-02-19 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 88714986 | 31219425 | 119934411 | 119934411 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 53 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA07 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-02-25 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 793198626 | 274844758 | 1068043384 | 1068043384 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 52 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA06 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-03-06 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 550641318 | 181584124 | 732225442 | 732225442 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 47 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA01 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-02-17 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 890420670 | 299963777 | 1190384447 | 1190384447 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 50 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA04 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-02-20 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 310554529 | 92476512 | 403031041 | 403031041 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 49 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA03 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-03-06 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 360532919 | 69148654 | 429681573 | 429681573 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 48 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA02 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-02-22 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 563158461 | 153865442 | 717023903 | 717023903 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020389 | 11 | 51 | 01C11I02 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008569/HK.810/OPS-10040000/2020 | Kontrak OSP FO Feeder FTTH | 2020-12-16 | 2022-08-18 | OSP-FO | KENDARI | MANDONGA |  | FE-ODC-MDG-FA05 |  | 100 | 100 | 100 | BAST-1 | 2020-12-16 | 2021-11-22 | 2021-03-06 | TEL.1280/LG.310/PND-C1030000/2021 | 2021-11-27 13:02 | TEL.0723/LG.320/DID-00000000/2021 | 2021-11-27 | 193952429 | 54525663 | 248478092 | 248478092 | 4500420995 |  |  |  |  | BANGTELINDO | 2021-11-30
12020397 | 18 | 45 | 01C11H02 | 019 | 72010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008750/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Backbone, RMJ dan Last Mile Tahap-2 | 2020-12-18 | 2022-07-26 | OSP FO Backbone | MANADO | TELLING |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-09-02 | 2020-12-18 | TEL.2430/LG.310/DID-B1060000/2021 | 2021-08-31 | TEL.0266/LG.320/DID-00000000/2021 | 2021-08-31 | 206876025 | 46227584 | 253103609 | 253103609 | 4500421304 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2021-09-29
12020397 | 18 | 44 | 01C11H02 | 019 | 72010869 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008750/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Backbone, RMJ dan Last Mile Tahap-2 | 2020-12-18 | 2022-07-26 | OSP FO Backbone | MANADO | TTC PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-09-02 | 2020-12-18 | TEL.2429/LG.310/DID-B1060000/2021 | 2021-08-31 | TEL.0265/LG.320/DID-00000000/2021 | 2021-08-31 | 1115859240 | 1514987715 | 2630846955 | 2630846955 | 4500421304 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2021-09-29
12020397 | 18 | 29 | 01C11H02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008750/HK.810/OPS-10000000/2020 | Pengadaan dan Pemasangan OSP FO Backbone, RMJ dan Last Mile Tahap-2 | 2020-12-18 | 2022-07-26 | OSP FO Backbone | UJUNGPANDANG | SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-12-10 | 2020-12-18 | TEL.3162/LG.310/DID-B1060000/2021 | 2021-11-12 | TEL.0709/LG.320/DID-00000000/2021 | 2021-11-12 | 1034842520 | 875350701 | 1910193221 | 1910193221 | 4500421304 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2021-11-30
12020400 | 27 | 311 | 01C11G04 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | AMBON | PASSO |  | AMB052 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1419/LG.310/PND-C1010000/2021 | 2021-06-14 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 540306773 | 125196306 | 665503079 | 665503079 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 312 | 01C11G04 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | JAYAPURA | ABEPURA |  | JAP015 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-06-29 | 2021-04-01 | TEL.1371/LG.310/PND-C1010000/2021 | 2021-05-17 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 4057517 | 2148373 | 6205890 | 6205890 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 313 | 01C11G04 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | JAYAPURA | TIMIKA |  | TIM001 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-06-29 | 2021-04-01 | TEL.1389/LG.310/PND-C1010000/2021 | 2021-05-19 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 4463720 | 3143697 | 7607417 | 7607417 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 451 | 01C11G04 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | JAYAPURA | WAMENA |  | WRS058 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-12-13 | TEL.4209/LG.310/PND-C1010000/2021 | 2021-12-14 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 43180263 | 15682384 | 58862647 | 58862647 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 449 | 01C11G04 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | JAYAPURA | WAMENA |  | WRS016 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-12-13 | TEL.4267/LG.310/PND-C1010000/2021 | 2021-12-20 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 8862100 | 4250250 | 13112350 | 13112350 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 448 | 01C11G04 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | JAYAPURA | WAMENA |  | WRS014 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-12-13 | TEL.4211/LG.310/PND-C1010000/2021 | 2021-12-14 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 43202656 | 15689198 | 58891854 | 58891854 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 450 | 01C11G04 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | JAYAPURA | WAMENA |  | WRS053 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-12-13 | TEL.4210/LG.310/PND-C1010000/2021 | 2021-12-14 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 1645902345 | 348100371 | 1994002716 | 1994002716 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 272 | 01C11G04 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | BAU-BAU |  | BAU027 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-07-14 | 2021-04-25 | TEL.1313/LG.310/PND-C1010000/2021 | 2021-06-09 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 53788876 | 16076532 | 69865408 | 69865408 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 273 | 01C11G04 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | KENDARI |  | KDI010 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-07-14 | 2021-04-26 | TEL.1269/LG.310/PND-C1010000/2021 | 2021-06-09 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 667069472 | 118442926 | 785512398 | 785512398 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 446 | 01C11G04 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | KOLAKA |  | KKA086 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-11-16 | TEL.3637/LG.310/PND-C1010000/2021 | 2021-11-19 | TEL.0630/LG.320/DID-00000000/2021 | 2021-11-22 | 52872219 | 16497026 | 69369245 | 69369245 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-11-27
12020400 | 27 | 445 | 01C11G04 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | KOLAKA |  | KKA191 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-11-16 | TEL.3638/LG.310/PND-C1010000/2021 | 2021-11-19 | TEL.0630/LG.320/DID-00000000/2021 | 2021-11-22 | 1173709377 | 224182846 | 1397892223 | 1397892223 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-11-27
12020400 | 27 | 346 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL015 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-09 | TEL.1645/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 6205511 | 2110845 | 8316356 | 8316356 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 274 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL007 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-09 | TEL.1643/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 1347266760 | 251821484 | 1599088244 | 1599088244 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 458 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL007 |  | 100 | 100 | 100 | BAST-1 | 2021-09-25 | 2021-12-22 | 2021-12-13 | TEL.4207/LG.310/PND-C1010000/2021 | 2021-12-14 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 13929618 | 5455600 | 19385218 | 19385218 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 347 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL046 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-09 | TEL.1646/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 82747170 | 15190521 | 97937691 | 97937691 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 348 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL107 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1648/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 12275301 | 3127010 | 15402311 | 15402311 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 349 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL057 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-09 | TEL.1647/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 25798808 | 6735685 | 32534493 | 32534493 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 350 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | MANDONGA |  | ADL008 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-09 | TEL.1644/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 130493963 | 22780128 | 153274091 | 153274091 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 276 | 01C11G04 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | UNAAHA |  | UNH001 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-07-14 | 2021-05-27 | TEL.1608/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 52775631 | 13246191 | 66021822 | 66021822 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 275 | 01C11G04 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | UNAAHA |  | KKA012 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-07-14 | 2021-04-26 | TEL.1566/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 180832571 | 45920584 | 226753155 | 226753155 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 277 | 01C11G04 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | KENDARI | UNAAHA |  | KKA040 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-07-14 | 2021-06-10 | TEL.1314/LG.310/PND-C1010000/2021 | 2021-06-14 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 389213245 | 64720107 | 453933352 | 453933352 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 302 | 01C11G04 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | LUWUK | LUWUK |  | LWK052 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1574/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 253485684 | 43122281 | 296607965 | 296607965 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 261 | 01C11G04 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | AIR MADIDI |  | TDO010 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-17 | TEL.1635/LG.310/PND-C1010000/2021 | 2021-06-23 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 41845623 | 12714123 | 54559746 | 54559746 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 265 | 01C11G04 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | HULU SIAU |  | THN009 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-28 | TEL.3323/LG.310/PND-C1010000/2021 | 2021-10-28 | TEL.0539/LG.320/DID-00000000/2021 | 2021-10-29 | 948396595 | 179380802 | 1127777397 | 1127777397 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-10-31
12020400 | 27 | 264 | 01C11G04 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | HULU SIAU |  | THN012 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-07-01 | TEL.3723/LG.310/PND-C1010000/2021 | 2021-11-22 | TEL.0630/LG.320/DID-00000000/2021 | 2021-11-22 | 850112850 | 191062467 | 1041175317 | 1041175317 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-11-27
12020400 | 27 | 262 | 01C11G04 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | HULU SIAU |  | THN039 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-28 | TEL.3325/LG.310/PND-C1010000/2021 | 2021-10-28 | TEL.0539/LG.320/DID-00000000/2021 | 2021-10-29 | 24259309 | 8393795 | 32653104 | 32653104 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-10-31
12020400 | 27 | 263 | 01C11G04 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | HULU SIAU |  | THN058 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-28 | TEL.3324/LG.310/PND-C1010000/2021 | 2021-10-28 | TEL.0539/LG.320/DID-00000000/2021 | 2021-10-29 | 16950450 | 6291927 | 23242377 | 23242377 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-10-31
12020400 | 27 | 358 | 01C11G04 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | HULU SIAU |  | THN040 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-28 | TEL.3724/LG.310/PND-C1010000/2021 | 2021-11-22 | TEL.0630/LG.320/DID-00000000/2021 | 2021-11-22 | 14926751 | 6225317 | 21152068 | 21152068 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-11-27
12020400 | 27 | 268 | 01C11G04 | 019 | 72010055 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LANGOAN |  | TDO009 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-21 | TEL.1813/LG.310/PND-C1010000/2021 | 2021-06-23 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 43354830 | 11848848 | 55203678 | 55203678 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 255 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG025 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4252/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 65174125 | 46865263 | 112039388 | 112039388 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 254 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG156 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4248/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 43110579 | 13081456 | 56192035 | 56192035 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 259 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG013 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4253/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 2628616412 | 2871328077 | 5499944489 | 5499944489 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 260 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG211 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4249/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 16644098 | 13907219 | 30551317 | 30551317 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 258 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG040 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4251/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 28003906 | 26335715 | 54339621 | 54339621 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 256 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG086 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4250/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 84802946 | 88478195 | 173281141 | 173281141 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 257 | 01C11G04 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | LOLAK |  | KTG134 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-21 | TEL.4247/LG.310/PND-C1010000/2021 | 2021-12-18 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 11454121 | 8291465 | 19745586 | 19745586 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 270 | 01C11G04 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | MANADO CENTRUM |  | MDO029 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-21 | TEL.2245/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 345276209 | 66186723 | 411462932 | 411462932 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 269 | 01C11G04 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | MANADO CENTRUM |  | MDO492 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-21 | TEL.1633/LG.310/PND-C1010000/2021 | 2021-06-23 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 17180830 | 6736349 | 23917179 | 23917179 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 271 | 01C11G04 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | MANADO | MANADO CENTRUM |  | MDO004 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-21 | TEL.1634/LG.310/PND-C1010000/2021 | 2021-06-23 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 13911021 | 6230805 | 20141826 | 20141826 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 279 | 01C11G04 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | BANGGAI |  | SAK001 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-10-27 | TEL.3363/LG.310/PND-C1010000/2021 | 2021-10-29 | TEL.0539/LG.320/DID-00000000/2021 | 2021-10-29 | 186088152 | 47740274 | 233828426 | 233828426 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-10-31
12020400 | 27 | 281 | 01C11G04 | 019 | 72030013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | BUOL |  | BUO007 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1404/LG.310/PND-C1010000/2021 | 2021-06-14 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 82575286 | 16624504 | 99199790 | 99199790 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 447 | 01C11G04 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | KOLONODALE |  | MRW019 |  | 100 | 100 | 100 | BAST-1 | 2021-10-01 | 2021-12-22 | 2021-10-27 | TEL.3359/LG.310/PND-C1010000/2021 | 2021-10-29 | TEL.0537/LG.320/DID-00000000/2021 | 2021-10-29 | 73985526 | 12068064 | 86053590 | 86053590 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-10-31
12020400 | 27 | 301 | 01C11G04 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | LUWUK |  | LWK069 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1409/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 102102597 | 25138467 | 127241064 | 127241064 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 303 | 01C11G04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | PALU-1 |  | PAL005 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1573/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 4918722 | 2112470 | 7031192 | 7031192 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 306 | 01C11G04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | PALU-1 |  | PAL356 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1569/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 3651763 | 1764330 | 5416093 | 5416093 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 305 | 01C11G04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | PALU-1 |  | PAL006 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1572/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 17860431 | 4992913 | 22853344 | 22853344 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 304 | 01C11G04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | PALU-1 |  | PAL125 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1570/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 5448365 | 2090737 | 7539102 | 7539102 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 459 | 01C11G04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | TAWAELI |  | PAL006 |  | 100 | 100 | 100 | BAST-1 | 2021-09-25 | 2021-12-22 | 2021-11-18 | TEL.3693/LG.310/PND-C1010000/2021 | 2021-11-19 | TEL.0630/LG.320/DID-00000000/2021 | 2021-11-22 | 154599952 | 45643579 | 200243531 | 200243531 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-11-27
12020400 | 27 | 310 | 01C11G04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PALU | TAWAELI |  | PAL016 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-10 | TEL.1571/LG.310/PND-C1010000/2021 | 2021-06-11 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 3634145 | 1726619 | 5360764 | 5360764 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 308 | 01C11G04 | 019 | 72040135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PARE-PARE | RAPPANG |  | SDR006 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2022-01-03 | 2021-06-25 | TEL.4127/LG.310/PND-C1010000/2021 | 2021-12-06 | TEL.0055/LG.320/DID-A0000000/2021 | 2021-12-20 | 802196493 | 385009146 | 1187205639 | 1187205639 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-12-23
12020400 | 27 | 309 | 01C11G04 | 019 | 72040186 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | PARE-PARE | WATANSOPPENG |  | WTG001 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-06-29 | 2021-05-28 | TEL.1380/LG.310/PND-C1010000/2021 | 2021-06-09 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 35944883 | 11788011 | 47732894 | 47732894 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 314 | 01C11G04 | 019 | 74060035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | SORONG | BIAK |  | BIA038 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-06-29 | 2021-05-28 | TEL.1382/LG.310/PND-C1010000/2021 | 2021-06-10 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 7997520 | 6661398 | 14658918 | 14658918 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020400 | 27 | 266 | 01C11G04 | 019 | 73020009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | TERNATE | JAILOLO |  | TER006 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-17 | TEL.1637/LG.310/PND-C1010000/2021 | 2021-06-23 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 38338654 | 11650222 | 49988876 | 49988876 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 267 | 01C11G04 | 019 | 73020013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | TERNATE | LABUHA |  | LBA005 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-08-13 | 2021-06-17 | TEL.1636/LG.310/PND-C1010000/2021 | 2021-06-17 | TEL.0941/LG.320/PND-A1000000/2021 | 2021-07-26 | 104489011 | 24933805 | 129422816 | 129422816 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-07-30
12020400 | 27 | 278 | 01C11G04 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008834/HK.810/OPS-10000000/2020 | SP#26 Granular Modernization - OSP Fiberisasi Node-B Telkomsel | 2020-12-18 | 2021-12-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | UPD104 |  | 100 | 100 | 100 | BAST-1 | 2020-12-18 | 2021-06-29 | 2021-05-28 | TEL.1381/LG.310/PND-C1010000/2021 | 2021-06-09 | TEL.0776/LG.320/PND-A1000000/2021 | 2021-06-23 | 8872702 | 3929410 | 12802112 | 12802112 | 4500421655 |  |  |  |  | TELKOM AKSES | 2021-06-30
12020403 | 12 | 120 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA061 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.1718/LG.310/DID-C0300000/2022 | 2022-05-21 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 775350669 | 619337930 | 1394688599 | 1394688599 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 119 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA270 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2175/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 722079591 | 714552409 | 1436632000 | 1436632000 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 118 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA091 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2177/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 775802330 | 837748632 | 1613550962 | 1613550962 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 116 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA027 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.1720/LG.310/DID-C0300000/2022 | 2022-05-21 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 243833067 | 235408746 | 479241813 | 479241813 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 113 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA016 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | 2021-01-11 |  |  |  |  | 1317458709 | 1535035525 | 2852494234 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 114 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA051 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2176/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 911849341 | 975067229 | 1886916570 | 1886916570 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 112 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA018 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.1801/LG.310/DID-C0300000/2022 | 2022-05-21 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 249418284 | 247704124 | 497122408 | 497122408 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 117 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA087 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | 2021-01-11 |  |  |  |  | 481584303 | 550508992 | 1032093295 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 115 | 01C11G04 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | AMBON | NAMLEA |  | NLA017 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.1719/LG.310/DID-C0300000/2022 | 2022-05-21 | TEL.0944/LG.320/DID-A0000000/2022 | 2022-06-27 | 216179406 | 224785877 | 440965283 | 440965283 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-06-30
12020403 | 12 | 87 | 01C11G04 | 019 | 72050041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | LASUSUA |  | KKA062 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2645/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.1163/LG.320/DID-A0000000/2022 | 2022-06-27 | 362247396 | 84810849 | 447058245 | 447058245 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-07-30
12020403 | 12 | 85 | 01C11G04 | 019 | 72050041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | LASUSUA |  | KKA041 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2643/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.1163/LG.320/DID-A0000000/2022 | 2022-06-27 | 576920240 | 124674764 | 701595004 | 701595004 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-07-30
12020403 | 12 | 88 | 01C11G04 | 019 | 72050041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | LASUSUA |  | KKA025 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2642/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.1163/LG.320/DID-A0000000/2022 | 2022-06-27 | 567565809 | 129561083 | 697126892 | 697126892 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-07-30
12020403 | 12 | 89 | 01C11G04 | 019 | 72050041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | LASUSUA |  | KKA132 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2646/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.1163/LG.320/DID-A0000000/2022 | 2022-06-27 | 27066486 | 7856991 | 34923477 | 34923477 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-07-30
12020403 | 12 | 90 | 01C11G04 | 019 | 72050041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | LASUSUA |  | KKA045 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-07-02 | 2021-01-11 | TEL.2644/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.1163/LG.320/DID-A0000000/2022 | 2022-06-27 | 231386424 | 60092542 | 291478966 | 291478966 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-07-30
12020403 | 12 | 94 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | MANDONGA |  | ADL108 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 8467740 | 3752072 | 12219812 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 93 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | MANDONGA |  | ADL042 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 545167618 | 636205735 | 1181373353 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 128 | 01C11G04 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | KENDARI | MANDONGA |  | ADL011 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | 2021-01-11 |  |  |  |  | 52618895 | 76803122 | 129422017 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 75 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG119 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0611/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 1160418898 | 436032611 | 1596451509 | 1596451509 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 74 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG114 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0610/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 14231611 | 4739475 | 18971086 | 18971086 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 80 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG019 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0615/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 9664139 | 4533219 | 14197358 | 14197358 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 76 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG015 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0612/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 512960436 | 325436347 | 838396783 | 838396783 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 77 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG207 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0613/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 23560040 | 6079391 | 29639431 | 29639431 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 79 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG146 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0614/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 9906337 | 3823443 | 13729780 | 13729780 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 73 | 01C11G04 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | MANADO | BOROKO |  | KTG107 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0609/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0272/LG.320/DID-A0000000/2022 | 2022-02-26 | 186621127 | 39579096 | 226200223 | 226200223 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 101 | 01C11G04 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PALU | KOTARAYA |  | TLI008 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 1140484867 | 984720051 | 2125204918 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 158 | 01C11G04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PALU | TAWAELI |  | DGL137 |  | 90 |  |  |  | 2022-01-03 | 2022-10-02 | [5 empty] | 39298793 | 49619954 | 88918747 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 99 | 01C11G04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PALU | TAWAELI |  | DGL044 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 4356499 | 8352928 | 12709427 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 98 | 01C11G04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PALU | TAWAELI |  | DGL030 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 1260619753 | 1658850319 | 2919470072 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 97 | 01C11G04 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PALU | TAWAELI |  | DGL010 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 4356499 | 8352928 | 12709427 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 100 | 01C11G04 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PALU | TENTENA |  | PSO085 |  | 90 | 50 | 0 | Mat. Delivery | 2021-05-10 | 2022-10-02 | [5 empty] | 908049364 | 333898430 | 1241947794 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 96 | 01C11G04 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PARE-PARE | ENREKANG |  | ENR007 |  | 100 | 90 | 0 | Siap UT | 2021-05-10 | 2022-07-02 | 2021-01-11 |  |  |  |  | 60708439 | 12251028 | 72959467 | 0 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020403 | 12 | 83 | 01C11G04 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PARE-PARE | MAJENE |  | MAJ022 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-01-30 | 2021-01-11 | TEL.0113/LG.310/DID-C0300000/2022 | 2022-01-12 | TEL.0515/LG.320/DID-A0000000/2022 | 2022-01-12 | 10150998 | 2832262 | 12983260 | 12983260 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-04-27
12020403 | 12 | 81 | 01C11G04 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PARE-PARE | MAJENE |  | MAJ004 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-01-30 | 2021-01-11 | TEL.0111/LG.310/DID-C0300000/2022 | 2022-01-12 | TEL.0515/LG.320/DID-A0000000/2022 | 2022-01-12 | 20686405 | 4791245 | 25477650 | 25477650 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-04-27
12020403 | 12 | 82 | 01C11G04 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | PARE-PARE | MAJENE |  | MAJ017 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-01-30 | 2021-01-11 | TEL.0112/LG.310/DID-C0300000/2022 | 2022-01-12 | TEL.0515/LG.320/DID-A0000000/2022 | 2022-01-12 | 17693713 | 4249080 | 21942793 | 21942793 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-04-27
12020403 | 12 | 121 | 01C11G04 | 019 | 72080009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | UJUNGPANDANG | BANTAENG |  | BTN003 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0331/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0271/LG.320/DID-A0000000/2022 | 2022-02-19 | 514325911 | 110458321 | 624784232 | 624784232 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 122 | 01C11G04 | 019 | 72080009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | UJUNGPANDANG | BANTAENG |  | JNP029 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0332/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0271/LG.320/DID-A0000000/2022 | 2022-02-19 | 73396602 | 14106729 | 87503331 | 87503331 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 111 | 01C11G04 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | UJUNGPANDANG | SELAYAR |  | SLY005 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-02-01 | 2021-01-11 | TEL.4614/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0271/LG.320/DID-A0000000/2022 | 2022-02-19 | 921755154 | 265276121 | 1187031275 | 1187031275 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
12020403 | 12 | 110 | 01C11G04 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009042/HK.810/OPS-10000000/2020 | Kontrak OSP FO Node-B | 2020-12-22 | 2022-09-30 | Node-B 2020 | UJUNGPANDANG | WATAMPONE |  | SKG013 |  | 100 | 100 | 100 | BAST-1 | 2021-05-10 | 2022-04-30 | 2021-01-11 | TEL.0523/LG.310/DID-C0300000/2022 | 2022-02-19 | TEL.0271/LG.320/DID-A0000000/2022 | 2022-02-19 | 1046819588 | 222804748 | 1269624336 | 1269624336 | 4500421912 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK | 2022-03-27
32020225 | 0 | 7 | 01C12J04 | 039 | 74030060 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009202/HK.810/DSO-00000000/2020 | Surat Pesanan Dua Puluh Sembilan (SP#29) Dukungan Penyediaan Support Facility Radio IP Long Haul Sarmi-Nabire | 2020-12-24 | 2021-12-23 | Support Facility | JAYAPURA | SARMI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 0 | 5609400000 | 5609400000 | 0 | 4500422124 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020225 | 0 | 10 | 01C12J04 | 039 | 74030060 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009202/HK.810/DSO-00000000/2020 | Surat Pesanan Dua Puluh Sembilan (SP#29) Dukungan Penyediaan Support Facility Radio IP Long Haul Sarmi-Nabire | 2020-12-24 | 2021-12-23 | Support Facility | JAYAPURA | SARMI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 0 | 1182000000 | 1182000000 | 0 | 4500422124 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020225 | 0 | 12 | 01C12J04 | 039 | 74030060 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009202/HK.810/DSO-00000000/2020 | Surat Pesanan Dua Puluh Sembilan (SP#29) Dukungan Penyediaan Support Facility Radio IP Long Haul Sarmi-Nabire | 2020-12-24 | 2021-12-23 | Support Facility | JAYAPURA | SARMI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 0 | 1182000000 | 1182000000 | 0 | 4500422124 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020225 | 0 | 9 | 01C12J04 | 039 | 74030060 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009202/HK.810/DSO-00000000/2020 | Surat Pesanan Dua Puluh Sembilan (SP#29) Dukungan Penyediaan Support Facility Radio IP Long Haul Sarmi-Nabire | 2020-12-24 | 2021-12-23 | Support Facility | JAYAPURA | SARMI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 0 | 1182000000 | 1182000000 | 0 | 4500422124 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020225 | 0 | 11 | 01C12J04 | 039 | 74030060 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009202/HK.810/DSO-00000000/2020 | Surat Pesanan Dua Puluh Sembilan (SP#29) Dukungan Penyediaan Support Facility Radio IP Long Haul Sarmi-Nabire | 2020-12-24 | 2021-12-23 | Support Facility | JAYAPURA | SARMI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 0 | 1182000000 | 1182000000 | 0 | 4500422124 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020226 | 0 | 10 | 01C12J04 | 039 | 74060025 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009203/HK.810/DSO-01000000/2020 | Surat Pesanan Ketiga Puluh (SP#30) Dukungan Penyediaan Support Facility Radio IP Long Haul Sorong Teminabuhan | 2020-12-24 | 2021-12-23 | SF (Supporting Facility) | SORONG | SORONG |  | Periode Ketiga 24 Juni 2021 s/d 23 September 2021 |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 792000000 | 0 | 792000000 | 0 | 4500422127 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020226 | 0 | 9 | 01C12J04 | 039 | 74060025 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009203/HK.810/DSO-01000000/2020 | Surat Pesanan Ketiga Puluh (SP#30) Dukungan Penyediaan Support Facility Radio IP Long Haul Sorong Teminabuhan | 2020-12-24 | 2021-12-23 | SF (Supporting Facility) | SORONG | SORONG |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 3552000000 | 0 | 3552000000 | 0 | 4500422127 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020226 | 0 | 13 | 01C12J04 | 039 | 74060025 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009203/HK.810/DSO-01000000/2020 | Surat Pesanan Ketiga Puluh (SP#30) Dukungan Penyediaan Support Facility Radio IP Long Haul Sorong Teminabuhan | 2020-12-24 | 2021-12-23 | SF (Supporting Facility) | SORONG | SORONG |  | Periode Keempat 24 September 2021 s/d 23 Desember 2021 |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 792000000 | 0 | 792000000 | 0 | 4500422127 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020226 | 0 | 11 | 01C12J04 | 039 | 74060025 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009203/HK.810/DSO-01000000/2020 | Surat Pesanan Ketiga Puluh (SP#30) Dukungan Penyediaan Support Facility Radio IP Long Haul Sorong Teminabuhan | 2020-12-24 | 2021-12-23 | SF (Supporting Facility) | SORONG | SORONG |  | Periode Kedua 24 Maret 2021 s/d 23 Juni 2021 |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 792000000 | 0 | 792000000 | 0 | 4500422127 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020226 | 0 | 12 | 01C12J04 | 039 | 74060025 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009203/HK.810/DSO-01000000/2020 | Surat Pesanan Ketiga Puluh (SP#30) Dukungan Penyediaan Support Facility Radio IP Long Haul Sorong Teminabuhan | 2020-12-24 | 2021-12-23 | SF (Supporting Facility) | SORONG | SORONG |  | Periode Kesatu 24 Desember 2020 s/d 23 Maret 2021 |  | 100 | 90 | 0 | Siap UT | 2020-12-24 | 2021-12-23 | 2020-12-24 |  |  |  |  | 792000000 | 0 | 792000000 | 0 | 4500422127 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020224 | 0 | 12 | 01C12J04 | 039 | 74060037 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009201/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Delapan (SP#28) Dukungan Penyediaan Support Facility Ruas Bintuni -Teluk Wondana Dan Manokwari - Bintuni | 2020-12-27 | 2021-12-26 | SF (Supporting Facility) | SORONG | BINTUINI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-27 | 2021-12-26 | 2020-12-27 |  |  |  |  | 0 | 1653000000 | 1653000000 | 0 | 4500422222 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020224 | 0 | 11 | 01C12J04 | 039 | 74060037 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009201/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Delapan (SP#28) Dukungan Penyediaan Support Facility Ruas Bintuni -Teluk Wondana Dan Manokwari - Bintuni | 2020-12-27 | 2021-12-26 | SF (Supporting Facility) | SORONG | BINTUINI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-27 | 2021-12-26 | 2020-12-27 |  |  |  |  | 0 | 1653000000 | 1653000000 | 0 | 4500422222 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020224 | 0 | 10 | 01C12J04 | 039 | 74060037 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009201/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Delapan (SP#28) Dukungan Penyediaan Support Facility Ruas Bintuni -Teluk Wondana Dan Manokwari - Bintuni | 2020-12-27 | 2021-12-26 | SF (Supporting Facility) | SORONG | BINTUINI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-27 | 2021-12-26 | 2020-12-27 |  |  |  |  | 0 | 1653000000 | 1653000000 | 0 | 4500422222 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020224 | 0 | 9 | 01C12J04 | 039 | 74060037 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009201/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Delapan (SP#28) Dukungan Penyediaan Support Facility Ruas Bintuni -Teluk Wondana Dan Manokwari - Bintuni | 2020-12-27 | 2021-12-26 | SF (Supporting Facility) | SORONG | BINTUINI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-27 | 2021-12-26 | 2020-12-27 |  |  |  |  | 0 | 1653000000 | 1653000000 | 0 | 4500422222 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
32020224 | 0 | 13 | 01C12J04 | 039 | 74060037 | DIVISI SERVICE OPERATION | OPERATION ENGINEERING | NETWORK INTEGRATION MANAGEMENT | DIVISI SERVICE OPERATION | K.TEL.009201/HK.810/DSO-00000000/2020 | Surat Pesanan Kedua Puluh Delapan (SP#28) Dukungan Penyediaan Support Facility Ruas Bintuni -Teluk Wondana Dan Manokwari - Bintuni | 2020-12-27 | 2021-12-26 | SF (Supporting Facility) | SORONG | BINTUINI |  |  |  | 100 | 90 | 0 | Siap UT | 2020-12-27 | 2021-12-26 | 2020-12-27 |  |  |  |  | 0 | 8716800000 | 8716800000 | 0 | 4500422222 |  |  |  |  | DAYAMITRA TELEKOMUNIKASI TBK
12020414 | 11 | 91 | 01C11H01 | 019 | 73010167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | AMBON | AMBON PATIMURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 1807354400 | 246862300 | 2054216700 | 2054216700 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 100 | 01C11H01 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | FAK-FAK | FAK-FAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1604/LG.310/PND-B1060000/2021 | 2021-06-10 | TEL.0859/LG.320/PND-A1000000/2021 | 2021-06-10 | 1807354400 | 246862300 | 2054216700 | 2054216700 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-21
12020414 | 11 | 97 | 01C11H01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | KENDARI | KENDARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 1241606000 | 159136100 | 1400742100 | 1400742100 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 27 | 01C11H01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | KENDARI | KENDARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-08-06 | 2020-12-29 | TEL.2031/LG.310/PND-B1060000/2021 | 2021-07-23 | TEL.0955/LG.320/PND-A1000000/2021 | 2021-07-23 | 7367099900 | 664266200 | 8031366100 | 8031366100 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-30
12020414 | 11 | 90 | 01C11H01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | KENDARI | KENDARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1419/LG.310/PND-B1060000/2021 | 2021-05-30 | TEL.0364/LG.320/DID-00000000/2021 | 2021-05-30 | 882052600 | 104308800 | 986361400 | 986361400 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 89 | 01C11H01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | KENDARI | MANDONGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1419/LG.310/PND-B1060000/2021 | 2021-05-30 | TEL.0364/LG.320/DID-00000000/2021 | 2021-05-30 | 956732000 | 111057400 | 1067789400 | 1067789400 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 96 | 01C11H01 | 019 | 72050152 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | KENDARI | TTC KENDARI MANDONGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 5402437800 | 718076460 | 6120514260 | 6120514260 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 10 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | LUWUK | LUWUK |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2022-07-10 | 2020-12-29 | TEL.1651/LG.310/DID-B0400000/2022 | 2022-06-10 | TEL.0862/LG.320/DID-A0000000/2022 | 2022-06-10 | 2517378490 | 227676270 | 2745054760 | 2745054760 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-29
12020414 | 11 | 141 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2771/LG.310/DID-B1060000/2021 | 2021-10-04 | TEL.0707/LG.320/DID-00000000/2021 | 2021-10-04 | 338180500 | 44938600 | 383119100 | 383119100 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12020414 | 11 | 92 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 7564551800 | 1029284280 | 8593836080 | 8593836080 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 23 | 01C11H01 | 019 | 72010283 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | MANADO | TUTUYAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2022-07-10 | 2020-12-29 | TEL.1651/LG.310/DID-B0400000/2022 | 2022-06-10 | TEL.0862/LG.320/DID-A0000000/2022 | 2022-06-10 | 2516743490 | 227579670 | 2744323160 | 2744323160 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-29
12020414 | 11 | 130 | 01C11H01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | PALU | DONGGALA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1614/LG.310/PND-B1060000/2021 | 2021-06-09 | TEL.0857/LG.320/PND-A1000000/2021 | 2021-06-09 | 2319282900 | 209163700 | 2528446600 | 2528446600 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-21
12020414 | 11 | 26 | 01C11H01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | PALU | LUWUK |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-08-06 | 2020-12-29 | TEL.2031/LG.310/PND-B1060000/2021 | 2021-07-23 | TEL.0955/LG.320/PND-A1000000/2021 | 2021-07-23 | 7367099900 | 664266200 | 8031366100 | 8031366100 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-30
12020414 | 11 | 30 | 01C11H01 | 019 | 72030167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | PALU | MOROWALI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-08-06 | 2020-12-29 | TEL.2031/LG.310/PND-B1060000/2021 | 2021-07-23 | TEL.0955/LG.320/PND-A1000000/2021 | 2021-07-23 | 5208844500 | 471699400 | 5680543900 | 5680543900 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-30
12020414 | 11 | 131 | 01C11H01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | PALU | PALU |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1614/LG.310/PND-B1060000/2021 | 2021-06-09 | TEL.0857/LG.320/PND-A1000000/2021 | 2021-06-09 | 1006647900 | 88487100 | 1095135000 | 1095135000 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-21
12020414 | 11 | 129 | 01C11H01 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1266/LG.310/PND-B1060000/2021 | 2021-05-07 | TEL.0854/LG.320/PND-A1000000/2021 | 2021-05-07 | 2427901000 | 218958400 | 2646859400 | 2646859400 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-21
12020414 | 11 | 144 | 01C11H01 | 019 | 74060085 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | SORONG | SAOKA |  |  |  | 20 |  |  |  | 2020-12-29 | 2022-10-06 | [5 empty] | 581840000 | 1319060000 | 1900900000 | 0 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12020414 | 11 | 93 | 01C11H01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | TERNATE | TERNATE |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 2126074400 | 288362300 | 2414436700 | 2414436700 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 85 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1419/LG.310/PND-B1060000/2021 | 2021-05-30 | TEL.0364/LG.320/DID-00000000/2021 | 2021-05-30 | 478832000 | 55573500 | 534405500 | 534405500 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 136 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-09-27 | 2020-12-29 | TEL.2171/LG.310/DID-B1060000/2021 | 2021-08-06 | TEL.0365/LG.320/DID-00000000/2021 | 2021-08-06 | 750990040 | 67895600 | 818885640 | 818885640 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 50 | 01C11H01 | 019 | 72080416 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | MAKASAR PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1266/LG.310/PND-B1060000/2021 | 2021-05-07 | TEL.0854/LG.320/PND-A1000000/2021 | 2021-05-07 | 2427901000 | 218958400 | 2646859400 | 2646859400 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-21
12020414 | 11 | 118 | 01C11H01 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | MAKASSAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-11-19 | 2020-12-29 | TEL.3241/LG.310/DID-B1060000/2021 | 2021-11-19 | TEL.0706/LG.320/DID-00000000/2021 | 2021-11-19 | 12426048000 | 7833952000 | 20260000000 | 20260000000 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12020414 | 11 | 95 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 3322572600 | 438200380 | 3760772980 | 3760772980 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 87 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1419/LG.310/PND-B1060000/2021 | 2021-05-30 | TEL.0364/LG.320/DID-00000000/2021 | 2021-05-30 | 2706171000 | 312204400 | 3018375400 | 3018375400 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 138 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-09-27 | 2020-12-29 | TEL.2171/LG.310/DID-B1060000/2021 | 2021-08-06 | TEL.0365/LG.320/DID-00000000/2021 | 2021-08-06 | 750990040 | 67895600 | 818885640 | 818885640 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 101 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1604/LG.310/PND-B1060000/2021 | 2021-06-10 | TEL.0859/LG.320/PND-A1000000/2021 | 2021-06-10 | 1807354400 | 246862300 | 2054216700 | 2054216700 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-07-21
12020414 | 11 | 94 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2673/LG.310/PND-B1060000/2021 | 2021-09-24 | TEL.0366/LG.320/DID-00000000/2021 | 2021-09-24 | 2339605300 | 314301600 | 2653906900 | 2653906900 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 137 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-09-27 | 2020-12-29 | TEL.2171/LG.310/DID-B1060000/2021 | 2021-08-06 | TEL.0365/LG.320/DID-00000000/2021 | 2021-08-06 | 750990040 | 67895600 | 818885640 | 818885640 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 86 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1419/LG.310/PND-B1060000/2021 | 2021-05-30 | TEL.0364/LG.320/DID-00000000/2021 | 2021-05-30 | 956732000 | 111057400 | 1067789400 | 1067789400 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 142 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-10-07 | 2020-12-29 | TEL.2771/LG.310/DID-B1060000/2021 | 2021-10-04 | TEL.0707/LG.320/DID-00000000/2021 | 2021-10-04 | 338180500 | 44938600 | 383119100 | 383119100 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12020414 | 11 | 88 | 01C11H01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-06-24 | 2020-12-29 | TEL.1419/LG.310/PND-B1060000/2021 | 2021-05-30 | TEL.0364/LG.320/DID-00000000/2021 | 2021-05-30 | 1748973000 | 201102200 | 1950075200 | 1950075200 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12020414 | 11 | 139 | 01C11H01 | 019 | 72080523 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009358/HK.810/OPS-10000000/2020 | Kontrak DWDM Platform Nokia | 2020-12-29 | 2022-09-22 | DWDM ALU | UJUNGPANDANG | TTC SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2020-12-29 | 2021-09-27 | 2020-12-29 | TEL.2171/LG.310/DID-B1060000/2021 | 2021-08-06 | TEL.0365/LG.320/DID-00000000/2021 | 2021-08-06 | 750990040 | 67895600 | 818885640 | 818885640 | 4500422269 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-09-30
12021102 | 28 | 1597 | 01C11I02 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | AMBON |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1489 | 01C11I02 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | AMBON |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0028/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 846 | 01C11I02 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | AMBON |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1423/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 881 | 01C11I02 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | AMBON |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0026/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1590 | 01C11I02 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | AMBON |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0150/LG.310/DID-C0200000/2022 | 2022-02-26 07:13 | TEL.0170/LG.320/DID-A0000000/2022 | 2022-02-26 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 1676 | 01C11I02 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | AMBON |  | MIGRASI C2F CONSUMER SS3 TAHAP-4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 4011680 | 4649920 | 8661600 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 847 | 01C11I02 | 019 | 73010120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | DOBO |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1423/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1488 | 01C11I02 | 019 | 73010120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | DOBO |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1692 | 01C11I02 | 019 | 73010120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | DOBO |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 848 | 01C11I02 | 019 | 73010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | LARAT |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3008760 | 3487440 | 6496200 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 882 | 01C11I02 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | PASSO |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 849 | 01C11I02 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | PASSO |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 883 | 01C11I02 | 019 | 73010103 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | AMBON | SAUMLAKI |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 804 | 01C11I02 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | ABEPURA |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1704 | 01C11I02 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | JAYAPURA-1 |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 4011680 | 4649920 | 8661600 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1598 | 01C11I02 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | JAYAPURA-1 |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 805 | 01C11I02 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | JAYAPURA-1 |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 875 | 01C11I02 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | JAYAPURA-1 |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0024/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 806 | 01C11I02 | 019 | 74030034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | JAYAPURA-2 |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1705 | 01C11I02 | 019 | 74030034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | JAYAPURA-2 |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3510220 | 4068680 | 7578900 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 807 | 01C11I02 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | KUALA KENCANA |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1701 | 01C11I02 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | KUALA KENCANA |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1693 | 01C11I02 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | KUALA KENCANA |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-25 | TEL.0151/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 811 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | NABIRE |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1424/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1312480 | 2315400 | 2315400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1601 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | NABIRE |  | MIGRASI C2F EBIS SS4 TAHAP-3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 13539420 | 15243480 | 28782900 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1511 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | NABIRE |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0025/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1677 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | NABIRE |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 98787620 | 114354280 | 213141900 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1491 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | NABIRE |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0153/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 2005840 | 2324960 | 4330800 | 4330800 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 879 | 01C11I02 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | NABIRE |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1426/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 2507300 | 3356200 | 5863500 | 5863500 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 808 | 01C11I02 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | SENTANI |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1591 | 01C11I02 | 019 | 74030067 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | TEMBAGAPURA |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 876 | 01C11I02 | 019 | 74030067 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | TEMBAGAPURA |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 809 | 01C11I02 | 019 | 74030067 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | TEMBAGAPURA |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0029/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 877 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | TIMIKA |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0024/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1599 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | TIMIKA |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1671 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | TIMIKA |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3510220 | 4068680 | 7578900 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 874 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | WAMENA |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1427/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 795 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | WAMENA |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0029/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 5516060 | 6393640 | 11909700 | 11909700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1702 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | WAMENA |  | MIGRASI C2F EBIS SS4 TAHAP-3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 6017520 | 6974880 | 12992400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1600 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | WAMENA |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0151/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 7020440 | 8137360 | 15157800 | 15157800 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 1592 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | WAMENA |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0007/LG.310/PND-C1030000/2022 | 2022-02-26 07:14 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 15043800 | 17437200 | 32481000 | 32481000 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 1703 | 01C11I02 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | JAYAPURA | WAMENA |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 31090520 | 36036880 | 67127400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 861 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | MANADO |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1431/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 887 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | MANADO |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1428/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1512 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | MANADO |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1497 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | MANADO |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1153 | 01C11I02 | 019 | 72010277 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | MANGOLE |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 890 | 01C11I02 | 019 | 72010275 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | MOROTAI |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 862 | 01C11I02 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | PANIKI |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 865 | 01C11I02 | 019 | 72010248 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MANADO | TAGULANDANG |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1698 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MERAUKE | MERAUKE |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0148/LG.310/DID-C0200000/2022 | 2022-02-26 07:13 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 1699 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | MERAUKE | MERAUKE |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3008760 | 3487440 | 6496200 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1495 | 01C11I02 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | LUWUK |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1700 | 01C11I02 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | LUWUK |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1696 | 01C11I02 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | LUWUK |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0152/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 851 | 01C11I02 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | LUWUK |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1425/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1496 | 01C11I02 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | PALU-1 |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1697 | 01C11I02 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | PALU-1 |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 852 | 01C11I02 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | PALU-1 |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1425/LG.310/PND-C1030000/2021 | 2021-12-17 18:42 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 853 | 01C11I02 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | PALU-2 |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 886 | 01C11I02 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | PALU | POSO |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 843 | 01C11I02 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | SORONG | SERUI |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1694 | 01C11I02 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | SORONG | SERUI |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1695 | 01C11I02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | SORONG | SORONG |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1678 | 01C11I02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | SORONG | SORONG |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 844 | 01C11I02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | SORONG | SORONG |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0008/LG.310/PND-C1030000/2022 | 2022-02-26 07:14 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 888 | 01C11I02 | 019 | 73020034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | TERNATE | SOA SIU |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 863 | 01C11I02 | 019 | 73020034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | TERNATE | SOA SIU |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 864 | 01C11I02 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | TERNATE | TERNATE |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 889 | 01C11I02 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | TERNATE | TERNATE |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 801 | 01C11I02 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | ANTANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1504380 | 1743720 | 3248100 | 3248100 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1485 | 01C11I02 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | ANTANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 90 | 0 | Siap UT | 2021-04-23 | 2022-03-03 | 2022-02-24 |  |  |  |  | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1683 | 01C11I02 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | ANTANG |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 6017520 | 6974880 | 12992400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1672 | 01C11I02 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | ANTANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0149/LG.310/DID-C0200000/2022 | 2022-02-26 07:13 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 24 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | Pelabuhan Soekarno-Hatta SS2 DISTRIBUSI |  | 100 |  | 0 |  | 2021-04-23 | 2021-12-23 | [5 empty] | 182165110 | 154553203 | 336718313 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 22 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA | WORTL-2021019263 | Terong, Bayam, Kubis, Kangkung Barat & Timur, Veteran Utara SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-28 | TEL.1298/LG.310/PND-C1030000/2021 | 2021-11-28 20:36 | TEL.0772/LG.320/DID-00000000/2021 | 2021-11-28 | 110720073 | 27016425 | 137736498 | 137736498 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-11-30
12021102 | 28 | 1501 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0030/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 2507300 | 2906200 | 5413500 | 5413500 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 797 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 43627020 | 50717880 | 94344900 | 94344900 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1584 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0149/LG.310/DID-C0200000/2022 | 2022-02-26 07:13 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 6017520 | 6974880 | 12992400 | 12992400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 23 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA | WORTL-2021019264 | G. Latimojong, Marga Mas, S. Kelara, G. Lompobattang, Bawakaraeng SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 134784717 | 31841010 | 166625727 | 166625727 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 21 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA | WORTL-2021017487 | Bonerate, Flores, Jampea, Bali, Ahmad Yani SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 94402223 | 21991141 | 116393364 | 116393364 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 20 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA | WORTL-2021018872 | Nusantara, Sulawesi, Pasar butung SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-28 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 61894699 | 16365356 | 78260055 | 78260055 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 19 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA | WORTL-2021019261 | Da'wah, Salemo, Nusantara Baru, Yos Sudarso SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1182/LG.310/PND-C1030000/2021 | 2021-10-29 17:22 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 218914670 | 51325897 | 270240567 | 270240567 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 18 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA | WORTL-2021017486 | Cakalang, Pannampu, Sibula Dalam SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1182/LG.310/PND-C1030000/2021 | 2021-10-29 17:22 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 73420496 | 16628367 | 90048863 | 90048863 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 1482 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0027/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 3008760 | 3487440 | 6496200 | 6496200 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1673 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F CONSUMER SS3 TAHAP-4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 148432160 | 171897040 | 320329200 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1593 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F EBIS SS4 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0154/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 1679 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F EBIS SS4 TAHAP-4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3510220 | 4068680 | 7578900 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 868 | 01C11I02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BALAIKOTA |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1429/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 5516060 | 6393640 | 11909700 | 11909700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1664 | 01C11I02 | 019 | 72080009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BANTAENG |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 6017520 | 6974880 | 12992400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1684 | 01C11I02 | 019 | 72080009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BANTAENG |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1272 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | MANJALLING/UJUNG LOE, PALANGISANG SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2021-12-23 | 2021-12-15 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 405426883 | 100430714 | 505857597 | 505857597 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 1278 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | JL. POROS BANTAENG BULUKUMBA SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2021-12-23 | 2021-12-15 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 156470656 | 37939862 | 194410518 | 194410518 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 1276 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | BONTO SUNGGU SS#1 FEEDER |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2022-04-05 | 2022-02-25 | TEL.0373/LG.310/DID-C0200000/2022 | 2022-03-30 11:33 | TEL.0389/LG.320/DID-A0000000/2022 | 2022-03-30 | 170694223 | 64673912 | 235368135 | 235368135 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 1274 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | SAM RATULANGI SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2021-12-23 | 2021-12-15 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 65233982 | 17248776 | 82482758 | 82482758 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 1273 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | PALANGISANG SS#1 FEEDER |  | 100 | 90 | 0 | Siap UT | 2021-08-18 | 2022-04-05 | 2021-12-16 |  |  |  |  | 610730171 | 573926685 | 1184656856 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1275 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | BONTO SUNGGU SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2022-04-05 | 2021-12-15 | TEL.0373/LG.310/DID-C0200000/2022 | 2022-03-30 11:33 | TEL.0390/LG.320/DID-A0000000/2022 | 2022-03-30 | 579775633 | 114779736 | 694555369 | 694555369 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 1277 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | JL. ABD.AZIS SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2021-12-23 | 2021-12-15 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 142611561 | 36370464 | 178982025 | 178982025 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 729 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 12536500 | 14531000 | 27067500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 727 | 01C11I02 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | BULUKUMBA |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 462346120 | 535903280 | 998249400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 872 | 01C11I02 | 019 | 72080054 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | JENEPONTO |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 4011680 | 4649920 | 8661600 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1665 | 01C11I02 | 019 | 72080054 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | JENEPONTO |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 5516060 | 6393640 | 11909700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 799 | 01C11I02 | 019 | 72080064 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | KIMA |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 2005840 | 2324960 | 4330800 | 4330800 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 870 | 01C11I02 | 019 | 72080064 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | KIMA |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1429/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1484 | 01C11I02 | 019 | 72080064 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | KIMA |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1503 | 01C11I02 | 019 | 72080064 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | KIMA |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1685 | 01C11I02 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MAROS |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1666 | 01C11I02 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MAROS |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 6518980 | 7556120 | 14075100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 36 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN | WORTL-2021019271 | Hati Murni, Bajiminasa, Nuri Baru, Tanjung, Baji Pamai SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-08-16 | TEL.1182/LG.310/PND-C1030000/2021 | 2021-10-29 17:22 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 268663579 | 63820651 | 332484230 | 332484230 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 1674 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F CONSUMER SS3 TAHAP-4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 7020440 | 8137360 | 15157800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 35 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | Telaga SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-08-16 | TEL.1298/LG.310/PND-C1030000/2021 | 2021-11-28 20:36 | TEL.0772/LG.320/DID-00000000/2021 | 2021-11-28 | 163934925 | 31866792 | 195801717 | 195801717 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-11-30
12021102 | 28 | 34 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN | WORTL-2020045506 | Taman Metropolitan SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1298/LG.310/PND-C1030000/2021 | 2021-11-28 20:36 | TEL.0772/LG.320/DID-00000000/2021 | 2021-11-28 | 47263816 | 12566780 | 59830596 | 59830596 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-11-30
12021102 | 28 | 33 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN | WORTL-2020045508 | Taman Masamba SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1298/LG.310/PND-C1030000/2021 | 2021-11-28 20:36 | TEL.0772/LG.320/DID-00000000/2021 | 2021-11-28 | 32390849 | 8696398 | 41087247 | 41087247 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-11-30
12021102 | 28 | 1594 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F EBIS SS4 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0154/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 2005840 | 2324960 | 4330800 | 4330800 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 1483 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0027/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 798 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 12536500 | 14531000 | 27067500 | 27067500 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1502 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0030/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 1504380 | 1743720 | 3248100 | 3248100 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 869 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1429/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 1504380 | 1743720 | 3248100 | 3248100 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1681 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F EBIS SS4 TAHAP-4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1002920 | 1162480 | 2165400 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1585 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0149/LG.310/DID-C0200000/2022 | 2022-02-26 07:13 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 2005840 | 2324960 | 4330800 | 4330800 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 37 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | MATTOANGIN | WORTL-2021019272 | Anggrek, Ks. Tubun, Nusa Indah, Matahari, Flamboyan SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-08-16 | TEL.1182/LG.310/PND-C1030000/2021 | 2021-10-29 17:22 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 184848429 | 42198509 | 227046938 | 227046938 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 1586 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0149/LG.310/DID-C0200000/2022 | 2022-02-26 07:13 | TEL.0391/LG.320/DID-A0000000/2022 | 2022-02-26 | 2005840 | 2324960 | 4330800 | 4330800 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021102 | 28 | 867 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1429/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1498 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0030/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 6518980 | 7556120 | 14075100 | 14075100 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 796 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 20559860 | 23980840 | 44540700 | 44540700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1467 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0027/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 3008760 | 3487440 | 6496200 | 6496200 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1680 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F EBIS SS4 TAHAP-4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 1504380 | 1743720 | 3248100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1295 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | Bumi Aeropala SS#2 DISTRIBUSI |  | 100 |  | 0 |  | 2021-08-18 | 2021-12-23 | [5 empty] | 117684769 | 26469204 | 144153973 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1675 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 47137240 | 54486560 | 101623800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1279 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | Anggrek Raya Minasaupa, Tun Abdul Razak, Hertasning Baru SS#2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-08-18 | 2021-12-23 | 2021-11-09 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 106789449 | 28535072 | 135324521 | 135324521 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 32 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018514 | Galangan Kapal, Sinassara, Teuku Umar, Kalukubodoa SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-09 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 138133885 | 34814328 | 172948213 | 172948213 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 31 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018513 | Komp. UNHAS Sunu, Griya Harapan SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-24 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 127051397 | 28975834 | 156027231 | 156027231 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 30 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018512 | Monginsidi Baru, Pelita 2, Rappocni Lr 7-9, Ballaparang SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-24 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 144840528 | 32627217 | 177467745 | 177467745 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 29 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018511 | Massenrempulu, Asrama Bara-barayya, Muh Yamin, SS2 DISTRIBUSI Ablam |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-09 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 113217653 | 25824820 | 139042473 | 139042473 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 28 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018510 | Veteran Utara, Ablam, Ja'jala, Lure SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-09 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 98634672 | 21652056 | 120286728 | 120286728 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 27 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018509 | Maccini Gusung, Sawah & Baru SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-12 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 90500464 | 20430709 | 110931173 | 110931173 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 26 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018508 | Adipura, Adipura 1 & 2 SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-08 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 112430099 | 26831064 | 139261163 | 139261163 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 25 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG | WORTL-2021018507 | DPRD Prov, Gedung Keuangan SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-11-09 | TEL.1443/LG.310/PND-C1030000/2021 | 2021-12-18 10:35 | TEL.0128/LG.320/DID-A0000000/2021 | 2021-12-18 | 67417470 | 15945235 | 83362705 | 83362705 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-25
12021102 | 28 | 1595 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANAKUKANG |  | MIGRASI C2F EBIS SS4 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0154/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 14542340 | 16855960 | 31398300 | 31398300 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 1283 | 01C11I02 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANGKEP |  | NEW ODC - Jl. Biringksasi, Bonsai SS#2 DISTRIBUSI |  | 100 |  | 0 |  | 2021-08-18 | 2022-04-05 | [5 empty] | 72931804 | 16958155 | 89889959 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1587 | 01C11I02 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANGKEP |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 551104540 | 638782760 | 1189887300 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1282 | 01C11I02 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANGKEP |  | NEW ODC - Jl. Biringksasi, Bonsai SS#1 FEEDER |  | 100 | 0 | 0 | Preparing | 2021-08-18 | 2022-04-05 | [5 empty] | 180945406 | 119782727 | 300728133 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 791 | 01C11I02 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANGKEP |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0027/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 866 | 01C11I02 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | PANGKEP |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 56664980 | 65680120 | 122345100 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1686 | 01C11I02 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SELAYAR |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3008760 | 3487440 | 6496200 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1667 | 01C11I02 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SELAYAR |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1687 | 01C11I02 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SINJAI |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1668 | 01C11I02 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SINJAI |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 3510220 | 4068680 | 7578900 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 860 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021018504 | NEW FEEDER + NEW ODC SS1 FEEDER |  | 100 | 0 | 0 | Preparing | 2021-04-23 | 2022-04-05 | [5 empty] | 175998008 | 142794821 | 318792829 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1688 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 47 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021019268 | Pergudangan Parangloe |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-15 | TEL.1182/LG.310/PND-C1030000/2021 | 2021-10-29 17:22 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 229237364 | 43768085 | 273005449 | 273005449 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 45 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG |  | Pergudangan Lantebung, Bontoa Indah & Tamalanrea2 SS2 DISTRIBUSI |  | 100 |  | 0 |  | 2021-04-23 | 2022-04-05 | [5 empty] | 286922005 | 64489938 | 351411943 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 49 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021018505 | NEW ODC A DS1 & DS2 SS2 DISTRIBUSI |  | 100 | 70.25 | 0 | Instalasi | 2021-04-23 | 2022-04-05 | 2021-11-06 |  |  |  |  | 182354094 | 45596430 | 227950524 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 50 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021018506 | NEW ODC B DS1 & DS2 SS2 DISTRIBUSI |  | 100 | 29.5 | 0 | Mat. Delivery | 2021-04-23 | 2022-04-05 | 2021-11-06 |  |  |  |  | 138065593 | 37392343 | 175457936 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1588 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 802 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 3510220 | 4068680 | 7578900 | 7578900 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 48 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021019269 | Auri Perintis-Daya SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-15 | TEL.1182/LG.310/PND-C1030000/2021 | 2021-10-29 17:22 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 65244191 | 15854970 | 81099161 | 81099161 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 1486 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0027/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 1504380 | 1743720 | 3248100 | 3248100 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 859 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021019265 | Pergudangan Lantebung, Bontoa Indah & Tamalanrea SS1 FEEDER |  | 100 | 0 | 0 | Preparing | 2021-04-23 | 2022-04-05 | [5 empty] | 107862704 | 131166668 | 239029372 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 46 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG | WORTL-2021019267 | Komp. Mula Baru-Kapasa Raya SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-21 | TEL.1298/LG.310/PND-C1030000/2021 | 2021-11-28 20:36 | TEL.0772/LG.320/DID-00000000/2021 | 2021-11-28 | 72353235 | 18644078 | 90997313 | 90997313 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-11-30
12021102 | 28 | 51 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUDIANG |  | KOSTRAD KARIANGO SURVEY 2 & PENAMBAHAN KARIANGO/SDN SUDIRMAN 24, RACHITA GARDEN,PURI ZARINDAH MADANI,PADAELO REGENCY SS2 DISTRIBUSI |  | 100 | 10 | 0 | Preparing | 2021-04-23 | 2021-12-23 | 2021-11-29 |  |  |  |  | 568785710 | 119053089 | 687838799 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1290 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Jl. Poros Malino SS#1 FEEDER |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-20 |  |  |  |  | 1195870031 | 323185895 | 1519055926 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1689 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 803 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | MIGRASI C2F CONSUMER SS3 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.0023/LG.310/DID-C0200000/2021 | 2021-12-17 18:43 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 4513140 | 5231160 | 9744300 | 9744300 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1487 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | MIGRASI C2F CONSUMER SS3 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0027/LG.310/DID-C0200000/2021 | 2021-12-17 18:45 | TEL.0441/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1589 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | MIGRASI C2F CONSUMER SS3 TAHAP-3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1285 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Rindam Pakatto SS#2 DISTRIBUSI |  | 100 |  | 0 |  | 2021-08-18 | 2022-04-05 | [5 empty] | 193269173 | 40306046 | 233575219 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1287 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Poros Duta Baru, Komp. Bumi Tamarunang SS#2 DISTRIBUSI |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-25 |  |  |  |  | 181975715 | 38625240 | 220600955 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1288 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Andi Tonro, Tumanurung, Sirajuddin Rani, Gagak, Wahidin Sudirohusodo SS#2 DISTRIBUSI |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-25 |  |  |  |  | 172538433 | 37130306 | 209668739 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1289 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | BTN Nusa Indah, Pelita Asri, Jenetallasa SS#2 DISTRIBUSI |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-25 |  |  |  |  | 204886569 | 46650516 | 251537085 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1292 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | JL. POROS MALINO, BILI-BILI SS#2 DISTRIBUSI |  | 100 |  | 0 |  | 2021-08-18 | 2022-04-05 | [5 empty] | 148597953 | 54505105 | 203103058 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1293 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | STP Gowa, Celebes Land Samata SS#2 DISTRIBUSI |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-25 |  |  |  |  | 130075726 | 29766314 | 159842040 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1291 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Andi Tonro, Abdul Muthalib, Mustafa Dg Bunga[ SS#1 FEEDER |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-20 |  |  |  |  | 514854504 | 77213608 | 592068112 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1286 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Jenetallasa Baso Dg Ngawing Poros Limbung SS#1 FEEDER |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-20 |  |  |  |  | 1025846287 | 486036718 | 1511883005 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1294 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | SUNGGUMINASA |  | Kalegowa, Baso Dg Ngawing SS#2 DISTRIBUSI |  | 100 | 20 | 0 | Preparing | 2021-08-18 | 2022-04-05 | 2022-07-25 |  |  |  |  | 240475018 | 55692135 | 296167153 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1690 | 01C11I02 | 019 | 72080120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAKALAR |  | MIGRASI C2F EBIS SS4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1669 | 01C11I02 | 019 | 72080120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAKALAR |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 4011680 | 4649920 | 8661600 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 40 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA | WORTL-2021017183 | UNHAS SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-09-27 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 246966850 | 53452846 | 300419696 | 300419696 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 39 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA | WORTL-2021017182 | Perintis Kemerdekaan, UKIP SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-08-17 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 36584805 | 10335671 | 46920476 | 46920476 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 1682 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA |  | MIGRASI C2F EBIS SS4 TAHAP-4 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 501460 | 581240 | 1082700 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 871 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA |  | MIGRASI C2F EBIS SS4 TAHAP-1 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-11-29 | TEL.1429/LG.310/PND-C1030000/2021 | 2021-12-17 18:43 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1596 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA |  | MIGRASI C2F EBIS SS4 TAHAP-3 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2022-03-03 | 2022-02-24 | TEL.0154/LG.310/DID-C0200000/2022 | 2022-02-26 07:14 | TEL.0171/LG.320/DID-A0000000/2022 | 2022-02-26 | 1002920 | 1162480 | 2165400 | 2165400 | 4500426203 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021102 | 28 | 800 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2005840 | 2324960 | 4330800 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 41 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA | WORTL-2021017184 | Politeknik SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-08-18 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 81610466 | 19422383 | 101032849 | 101032849 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 42 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA | WORTL-2021017185 | Perintis Kemerdekaan km 7 SS2 DISTRIBUSI |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-23 | 2021-08-18 | TEL.1181/LG.310/PND-C1030000/2021 | 2021-10-29 17:21 | TEL.0496/LG.320/DID-00000000/2021 | 2021-10-29 | 75975560 | 20924106 | 96899666 | 96899666 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-10-30
12021102 | 28 | 1509 | 01C11I02 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | TAMALANREA |  | MIGRASI C2F EBIS SS4 TAHAP-2 |  | 100 | 100 | 100 | BAST-1 | 2021-04-23 | 2021-12-21 | 2021-12-16 | TEL.0030/LG.310/DID-C0200000/2021 | 2021-12-17 18:47 | TEL.0442/LG.320/DID-A0000000/2021 | 2021-12-17 | 501460 | 581240 | 1082700 | 1082700 | 4500426203 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021102 | 28 | 1691 | 01C11I02 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | MIGRASI C2F EBIS SS4 |  | 100 |  | 0 |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021102 | 28 | 1670 | 01C11I02 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001456/HK.810/OPS-10000000/2021 | SP#30 Granular Modernization - OSP FO FTTH dan Migrasi TREG-4, TREG-5 dan TREG-7 | 2021-04-23 | 2022-08-31 | GRANULAR | UJUNGPANDANG | WATAMPONE |  | MIGRASI C2F CONSUMER SS3 |  | 100 |  |  |  | 2021-04-23 | 2022-03-03 | [5 empty] | 2507300 | 2906200 | 5413500 | 0 | 4500426203 |  |  |  |  | TELKOM AKSES
12021107 | 21 | 108 | 01C11I01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001701/HK.810/OPS-10040000/2021 | Surat Pesanan-31 (SP#31) Pengadaan dan Pemasangan Granular Modernization - Revitalisasi Fiber Termination Management (FTM) | 2021-04-27 | 2022-07-19 | FTM | UJUNGPANDANG | BALAIKOTA |  | MIGRASI FTM |  | 100 | 0 |  | Preparing | 2021-04-27 | 2022-07-20 | [5 empty] | 306103260 | 506884574 | 812987834 | 0 | 4500426752 |  |  |  |  | TELKOM AKSES
12021107 | 21 | 52 | 01C11I01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001701/HK.810/OPS-10040000/2021 | Surat Pesanan-31 (SP#31) Pengadaan dan Pemasangan Granular Modernization - Revitalisasi Fiber Termination Management (FTM) | 2021-04-27 | 2022-07-19 | FTM | UJUNGPANDANG | BALAIKOTA |  | INSTALASI FTM |  | 100 | 69 | 0 | Instalasi | 2021-04-27 | 2022-07-20 | 2022-04-22 |  |  |  |  | 1696301390 | 132178030 | 1828479420 | 0 | 4500426752 |  |  |  |  | TELKOM AKSES
12021107 | 21 | 51 | 01C11I01 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001701/HK.810/OPS-10040000/2021 | Surat Pesanan-31 (SP#31) Pengadaan dan Pemasangan Granular Modernization - Revitalisasi Fiber Termination Management (FTM) | 2021-04-27 | 2022-07-19 | FTM | UJUNGPANDANG | PANAKUKANG |  | INSTALASI FTM |  | 100 | 69 | 0 | Instalasi | 2021-04-27 | 2022-06-24 | 2022-05-19 |  |  |  |  | 758038911 | 53191441 | 811230352 | 0 | 4500426752 |  |  |  |  | TELKOM AKSES
12021107 | 21 | 109 | 01C11I01 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001701/HK.810/OPS-10040000/2021 | Surat Pesanan-31 (SP#31) Pengadaan dan Pemasangan Granular Modernization - Revitalisasi Fiber Termination Management (FTM) | 2021-04-27 | 2022-07-19 | FTM | UJUNGPANDANG | PANAKUKANG |  | MIGRASI FTM |  | 100 | 0 | 0 | Preparing | 2021-04-27 | 2022-06-24 | [5 empty] | 328045110 | 302449148 | 630494258 | 0 | 4500426752 |  |  |  |  | TELKOM AKSES
12021127 | 23 | 803 | 01C11G01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002282/HK.810/OPS-10000000/2021 | SP#33 OSP FO Node-B TREG-1 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | UNAAHA |  | WGU007 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-17 | TEL.1773/LG.310/DID-C0300000/202 | 2022-05-29 | TEL.0681/LG.320/DID-A0000000/2022 | 2022-05-29 | 6836259 | 3335900 | 10172159 | 10172159 | 4500428281 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 467 | 01C11G01 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | AMBON | MASOHI |  | MSH022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-15 | TEL.1715/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 298930962 | 56955804 | 355886766 | 355886766 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 403 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | ABEPURA |  | JAP444 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0264/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 8075741 | 3632885 | 11708626 | 11708626 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 404 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | ABEPURA |  | JAP304 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-29 | TEL.4566/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 10530334 | 3114673 | 13645007 | 13645007 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 405 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | ABEPURA |  | JAP676 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-29 | TEL.4567/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 11523762 | 3211467 | 14735229 | 14735229 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 400 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | ABEPURA |  | COK322 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0261/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 14205173 | 5527187 | 19732360 | 19732360 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 150 | 01C11G01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | ABEPURA |  | COK125 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-23 | TEL.0514/LG.310/DID-C0300000/2022 | 2022-02-24 | TEL.0178/LG.320/DID-A0000000/2022 | 2022-02-24 | 17730718 | 5717704 | 23448422 | 23448422 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021128 | 27 | 420 | 01C11G01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | JAYAPURA |  | JAP368 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0265/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 10065597 | 4222925 | 14288522 | 14288522 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 421 | 01C11G01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | JAYAPURA |  | JAP423 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0266/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 9451599 | 4169963 | 13621562 | 13621562 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 422 | 01C11G01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | JAYAPURA |  | JAP526 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0267/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 17800766 | 7155848 | 24956614 | 24956614 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 396 | 01C11G01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | JAYAPURA |  | COK343 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0257/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 2496265 | 1667353 | 4163618 | 4163618 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 423 | 01C11G01 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | KUALA KENCANA |  | TIM144 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0268/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 47284349 | 16464799 | 63749148 | 63749148 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 390 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | JAP246 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-25 | TEL.0252/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 9526426 | 3650682 | 13177108 | 13177108 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 424 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK342 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0269/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 7634147 | 3349183 | 10983330 | 10983330 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 402 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK187 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0263/LG.310/DID-C0300000/2022 | 2022-01-27 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 75718197 | 35631177 | 111349374 | 111349374 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 399 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK326 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0260/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 9307508 | 3752590 | 13060098 | 13060098 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 395 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK329 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0256/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 11947359 | 4185698 | 16133057 | 16133057 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 394 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK328 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0255/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 9127914 | 3693119 | 12821033 | 12821033 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 392 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK331 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0253/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 5314662 | 2509511 | 7824173 | 7824173 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 391 | 01C11G01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SENTANI |  | COK451 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-25 | TEL.0251/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 21148235 | 7529699 | 28677934 | 28677934 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 397 | 01C11G01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | TIMIKA |  | TIM325 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-25 | TEL.0258/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 9471442 | 2831347 | 12302789 | 12302789 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 398 | 01C11G01 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAENA |  | COK323 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-25 | TEL.0259/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 3951818 | 2050185 | 6002003 | 6002003 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 401 | 01C11G01 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAENA |  | TIM068 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-25 | TEL.0262/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 100273131 | 27195852 | 127468983 | 127468983 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 406 | 01C11G01 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAENA |  | WRS019 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-29 | TEL.4568/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 12045842 | 4256890 | 16302732 | 16302732 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 154 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS013 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-23 | TEL.0516/LG.310/DID-C0300000/2022 | 2022-02-24 | TEL.0178/LG.320/DID-A0000000/2022 | 2022-02-24 | 686476351 | 143100062 | 829576413 | 829576413 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021128 | 27 | 152 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS005 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-23 | TEL.0517/LG.310/DID-C0300000/2022 | 2022-02-24 | TEL.0178/LG.320/DID-A0000000/2022 | 2022-02-24 | 6289576 | 2221169 | 8510745 | 8510745 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021128 | 27 | 151 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS001 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-23 | TEL.0513/LG.310/DID-C0300000/2022 | 2022-02-24 | TEL.0178/LG.320/DID-A0000000/2022 | 2022-02-24 | 717112686 | 146697758 | 863810444 | 863810444 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021128 | 27 | 228 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS004 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-18 | TEL.2550/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0320/LG.320/DID-00000000/2021 | 2021-09-18 | 26666547 | 10326116 | 36992663 | 36992663 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-09-30
12021128 | 27 | 153 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS011 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2021-12-13 | TEL.4212/LG.310/PND-C1010000/2021 | 2021-12-14 | TEL.0095/LG.320/DID-A0000000/2021 | 2021-12-14 | 325445015 | 74462027 | 399907042 | 399907042 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-24
12021128 | 27 | 225 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS036 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2021-12-13 | TEL.4213/LG.310/PND-C1010000/2021 | 2021-12-14 | TEL.0095/LG.320/DID-A0000000/2021 | 2021-12-14 | 15810928 | 6149276 | 21960204 | 21960204 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-24
12021128 | 27 | 156 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS046 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-23 | TEL.0515/LG.310/DID-C0300000/2022 | 2022-02-24 | TEL.0178/LG.320/DID-A0000000/2022 | 2022-02-24 | 3678732 | 1731403 | 5410135 | 5410135 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021128 | 27 | 229 | 01C11G01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | WAMENA |  | WRS012 |  | 85 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-08-29 | 2022-01-15 | TEL.2641/LG.310/DID-C0300000/2022 | 2022-07-27 | TEL.1174/LG.320/DID-A0000000/2022 | 2022-07-27 | 751581696 | 143051761 | 894633457 | 894633457 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-07-30
12021128 | 27 | 466 | 01C11G01 | 019 | 72050137 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | ANDOLO |  | ADL096 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-03-01 | TEL.1712/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 490055466 | 105150072 | 595205538 | 595205538 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 257 | 01C11G01 | 019 | 72050137 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | ANDOLO |  | ADL031 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2179/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 127694993 | 32006544 | 159701537 | 159701537 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 260 | 01C11G01 | 019 | 72050137 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | ANDOLO |  | ADL143 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2181/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 36671174 | 7587982 | 44259156 | 44259156 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 261 | 01C11G01 | 019 | 72050137 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | ANDOLO |  | ADL109 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2180/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 11341601 | 3441834 | 14783435 | 14783435 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 471 | 01C11G01 | 019 | 72050137 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | ANDOLO |  | ADL022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-06-28 | TEL.2226/LG.310/DID-C0300000/2022 | 2022-06-28 | TEL.0949/LG.320/DID-A0000000/2022 | 2022-06-28 | 31619874 | 7420367 | 39040241 | 39040241 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-06-30
12021128 | 27 | 472 | 01C11G01 | 019 | 72050137 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | ANDOLO |  | ADL023 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-06-28 | TEL.2227/LG.310/DID-C0300000/2022 | 2022-06-28 | TEL.0949/LG.320/DID-A0000000/2022 | 2022-06-28 | 272249478 | 49175471 | 321424949 | 321424949 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-06-30
12021128 | 27 | 235 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | BAU-BAU |  | BAU222 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-20 | TEL.2604/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 28123698 | 6950333 | 35074031 | 35074031 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 324 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | BAU-BAU |  | BAU059 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-20 | TEL.2522/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 44486679 | 11890909 | 56377588 | 56377588 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 234 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | BAU-BAU |  | BAU071 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-20 | TEL.2523/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 21821481 | 5459191 | 27280672 | 27280672 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 240 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | KENDARI |  | KDI014 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2182/LG.310/PND-C1010000/2021 | 2021-08-27 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 9710168 | 3429205 | 13139373 | 13139373 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 241 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | KENDARI |  | KDI297 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2184/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 18542437 | 6526464 | 25068901 | 25068901 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 238 | 01C11G01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | KENDARI |  | KDI295 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2183/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 15412593 | 3296092 | 18708685 | 18708685 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 246 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | KOLAKA |  | KKA088 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-18 | TEL.2606/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 19993210 | 6362617 | 26355827 | 26355827 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 247 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | KOLAKA |  | KKA058 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-18 | TEL.2605/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 24452872 | 5660655 | 30113527 | 30113527 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 245 | 01C11G01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | KOLAKA |  | KKA139 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-18 | TEL.2607/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 10658771 | 4208581 | 14867352 | 14867352 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 439 | 01C11G01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | MANDONGA |  | ADL081 |  | 100 | 100 | 100 | BAST-1 | 2022-02-28 | 2022-05-14 | 2022-03-21 | TEL.0896/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0346/LG.320/DID-A0000000/2022 | 2022-03-24 | 14851712 | 3607509 | 18459221 | 18459221 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 438 | 01C11G01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | MANDONGA |  | ADL062 |  | 100 | 100 | 100 | BAST-1 | 2022-02-28 | 2022-05-14 | 2022-03-21 | TEL.0895/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0346/LG.320/DID-A0000000/2022 | 2022-03-24 | 10707659 | 2367450 | 13075109 | 13075109 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 437 | 01C11G01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | MANDONGA |  | ADL010 |  | 100 | 100 | 100 | BAST-1 | 2022-02-28 | 2022-05-14 | 2022-03-21 | TEL.0894/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0346/LG.320/DID-A0000000/2022 | 2022-03-24 | 2314740482 | 386229928 | 2700970410 | 2700970410 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 407 | 01C11G01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | MANDONGA |  | ADL090 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4569/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 46777246 | 14561078 | 61338324 | 61338324 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 252 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA020 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-20 | TEL.2608/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 18571294 | 3935050 | 22506344 | 22506344 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 251 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA023 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-23 | TEL.2609/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 83446599 | 14796452 | 98243051 | 98243051 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 250 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA035 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-23 | TEL.2610/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 18898990 | 3990785 | 22889775 | 22889775 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 411 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA063 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4573/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 53163615 | 12646634 | 65810249 | 65810249 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 410 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA022 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4572/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 8369929 | 3339535 | 11709464 | 11709464 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 248 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA049 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-18 | TEL.2611/LG.310/PND-C1010000/2021 | 2021-08-26 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 72036736 | 16849076 | 88885812 | 88885812 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 408 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA046 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4570/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 64109780 | 12356692 | 76466472 | 76466472 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 249 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA086 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-18 | TEL.2612/LG.310/PND-C1010000/2021 | 2021-08-27 | TEL.0044/LG.320/DID-00000000/2021 | 2021-08-27 | 10780291 | 2949874 | 13730165 | 13730165 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-08-29
12021128 | 27 | 409 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | KENDARI | RAHA |  | RHA056 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4571/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 102947266 | 18821654 | 121768920 | 121768920 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 167 | 01C11G01 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | MANADO | HULU SIAU |  | THN006 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-27 | TEL.2807/LG.310/PND-C1010000/2021 | 2021-09-17 | TEL.0320/LG.320/DID-00000000/2021 | 2021-09-18 | 16402347 | 6304059 | 22706406 | 22706406 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-09-30
12021128 | 27 | 272 | 01C11G01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | MANADO | KOTAMOBAGU |  | KTG083 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-09-09 | TEL.3814/LG.310/PND-C1010000/2021 | 2021-11-27 | TEL.0801/LG.320/DID-00000000/2021 | 2021-11-27 | 631494940 | 303743783 | 935238723 | 935238723 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-11-30
12021128 | 27 | 464 | 01C11G01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | MERAUKE | MERAUKE |  | MRK734 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-16 | TEL.1711/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 1225962916 | 256925404 | 1482888320 | 1482888320 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 393 | 01C11G01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | MERAUKE | MERAUKE |  | COK330 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2022-01-24 | TEL.0254/LG.310/DID-C0300000/2022 | 2022-01-26 | TEL.0048/LG.320/DID-A0000000/2022 | 2022-01-27 | 3084749 | 1697095 | 4781844 | 4781844 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021128 | 27 | 461 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL175 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-01 | TEL.1721/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 21421243 | 8845619 | 30266862 | 30266862 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 281 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL091 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2157/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 21169734 | 4373529 | 25543263 | 25543263 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 282 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL130 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2156/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 20466794 | 11418461 | 31885255 | 31885255 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 283 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL026 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2155/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 29634848 | 12833152 | 42468000 | 42468000 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 284 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL046 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2154/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 28259904 | 12269930 | 40529834 | 40529834 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 285 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL129 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2153/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 33687057 | 13286073 | 46973130 | 46973130 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 286 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | DONGGALA |  | DGL136 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2152/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 30840220 | 12975644 | 43815864 | 43815864 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 183 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | KOLONODALE |  | MRW082 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2021-12-29 | TEL.4596/LG.310/PND-C1010000/2021 | 2021-12-30 | TEL.0393/LG.320/DID-A0000000/2021 | 2021-12-30 | 42151306 | 11070281 | 53221587 | 53221587 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021128 | 27 | 181 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | KOLONODALE |  | MRW050 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2021-12-29 | TEL.4578/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0393/LG.320/DID-A0000000/2021 | 2021-12-30 | 10295259 | 4174968 | 14470227 | 14470227 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021128 | 27 | 175 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | KOLONODALE |  | MRW007 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2021-12-29 | TEL.4575/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0393/LG.320/DID-A0000000/2021 | 2021-12-30 | 1292847958 | 180551141 | 1473399099 | 1473399099 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021128 | 27 | 178 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | KOLONODALE |  | MRW031 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2021-12-29 | TEL.4577/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0393/LG.320/DID-A0000000/2021 | 2021-12-30 | 12375937 | 7202264 | 19578201 | 19578201 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-31
12021128 | 27 | 463 | 01C11G01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | PALU |  | PAL169 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-01 | TEL.1714/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 201122292 | 39370491 | 240492783 | 240492783 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 291 | 01C11G01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TAWAELI |  | DGL079 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0916/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 10456983 | 6534941 | 16991924 | 16991924 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 293 | 01C11G01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TAWAELI |  | DGL022 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0918/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 7961129 | 6196696 | 14157825 | 14157825 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 292 | 01C11G01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TAWAELI |  | DGL021 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0917/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 9826898 | 6417894 | 16244792 | 16244792 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 290 | 01C11G01 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TINOMBO |  | PGI011 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0921/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 1660599513 | 975551912 | 2636151425 | 2636151425 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 186 | 01C11G01 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TINOMBO |  | DGL082 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0915/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 4386053899 | 2109084735 | 6495138634 | 6495138634 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 187 | 01C11G01 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TINOMBO |  | PGI073 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0919/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 16531515 | 4842442 | 21373957 | 21373957 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 289 | 01C11G01 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TINOMBO |  | PGI069 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-05-14 | 2022-03-23 | TEL.0920/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 21200810 | 8118888 | 29319698 | 29319698 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 462 | 01C11G01 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PALU | TOLI-TOLI |  | TLI096 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-01 | TEL.1731/LG.310/DID-C0300000/2022 | 2022-05-25 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 318386105 | 54685101 | 373071206 | 373071206 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021128 | 27 | 304 | 01C11G01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | PASANG KAYU |  | PSK015 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-27 | TEL.2178/LG.310/PND-C1010000/2021 | 2021-07-27 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 18973848 | 3556330 | 22530178 | 22530178 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 419 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR076 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4559/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 31422136 | 8142074 | 39564210 | 39564210 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 301 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR004 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-24 | TEL.0620/LG.310/DID-C0300000/2022 | 2022-02-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 1916525308 | 453629744 | 2370155052 | 2370155052 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 297 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR120 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-27 | TEL.2175/LG.310/PND-C1010000/2021 | 2021-07-27 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 15833596 | 7171679 | 23005275 | 23005275 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 298 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR042 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-26 | TEL.2174/LG.310/PND-C1010000/2021 | 2021-07-26 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 59052560 | 13629056 | 72681616 | 72681616 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 299 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR033 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-24 | TEL.0619/LG.310/DID-C0300000/2022 | 2022-02-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 8217503 | 1656891 | 9874394 | 9874394 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 300 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR098 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2022-03-14 | 2022-02-24 | TEL.0621/LG.310/DID-C0300000/2022 | 2022-02-25 | TEL.0345/LG.320/DID-A0000000/2022 | 2022-03-25 | 137605838 | 29703628 | 167309466 | 167309466 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021128 | 27 | 296 | 01C11G01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | MANOKWARI |  | MWR096 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-27 | TEL.2176/LG.310/PND-C1010000/2021 | 2021-07-27 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 9826314 | 3116362 | 12942676 | 12942676 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 340 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB072 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-09-06 | TEL.2814/LG.310/PND-C1010000/2021 | 2021-09-18 | TEL.0320/LG.320/DID-00000000/2021 | 2021-09-18 | 7364593 | 2835286 | 10199879 | 10199879 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-09-30
12021128 | 27 | 323 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB016 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-27 | TEL.2172/LG.310/PND-C1010000/2021 | 2021-07-27 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 34045496 | 8290544 | 42336040 | 42336040 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 322 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB037 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-27 | TEL.2173/LG.310/PND-C1010000/2021 | 2021-07-27 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 135048562 | 31251964 | 166300526 | 166300526 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 412 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB021 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4561/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 22481333 | 5304443 | 27785776 | 27785776 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 418 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB071 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4565/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 21469326 | 7866543 | 29335869 | 29335869 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 415 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB045 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4562/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 103139284 | 33004588 | 136143872 | 136143872 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 416 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB067 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4564/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 9508063 | 3743382 | 13251445 | 13251445 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 417 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB053 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4563/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 34832400 | 11535751 | 46368151 | 46368151 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 413 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | SORONG | NABIRE |  | NAB003 |  | 100 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-03-14 | 2021-12-28 | TEL.4560/LG.310/PND-C1010000/2021 | 2021-12-29 | TEL.0286/LG.320/DID-A0000000/2021 | 2021-12-29 | 122739302 | 27538690 | 150277992 | 150277992 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-12-30
12021128 | 27 | 288 | 01C11G01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | BULUKUMBA |  | BLK040 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2806/LG.310/PND-C1010000/2021 | 2021-09-17 | TEL.0320/LG.320/DID-00000000/2021 | 2021-09-18 | 272117365 | 47607623 | 319724988 | 319724988 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-09-30
12021128 | 27 | 287 | 01C11G01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | BULUKUMBA |  | BLK032 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-08-16 | TEL.2805/LG.310/PND-C1010000/2021 | 2021-09-17 | TEL.0320/LG.320/DID-00000000/2021 | 2021-09-18 | 35498895 | 10223345 | 45722240 | 45722240 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-09-30
12021128 | 27 | 277 | 01C11G01 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | MAKASSAR |  | WTP130 |  | 100 | 100 | 100 | BAST-1 | 2021-05-07 | 2021-12-14 | 2021-07-27 | TEL.2177/LG.310/PND-C1010000/2021 | 2021-07-27 | TEL.0898/LG.320/PND-A1000000/2021 | 2021-07-27 | 20040704 | 4575270 | 24615974 | 24615974 | 4500428282 |  |  |  |  | TELKOM AKSES | 2021-07-29
12021128 | 27 | 468 | 01C11G01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002283/HK.810/OPS-10000000/2021 | SP#34 OSP FO Node-B TREG-4, TREG-5, TREG-6 dan TREG-7 | 2021-05-07 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SINJAI |  | SIN040 |  | 100 | 100 | 100 | BAST-1 | 2022-05-01 | 2022-07-02 | 2022-02-21 | TEL.1713/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0685/LG.320/DID-A0000000/2022 | 2022-05-25 | 12947499 | 2950580 | 15898079 | 15898079 | 4500428282 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021150 | 12 | 116 | 01C11H01 | 019 | 74020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | FAK-FAK | FAKFAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-03 | 2021-05-21 | TEL.3303/LG.310/DID-B1060000/2021 | 2021-11-27 | TEL.0777/LG.320/DID-00000000/2021 | 2021-11-27 | 1941707400 | 194540100 | 2136247500 | 2136247500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 250 | 01C11H01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | GORONTALO |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1186697000 | 106808400 | 1293505400 | 1293505400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 126 | 01C11H01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | GORONTALO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2896/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0473/LG.320/DID-00000000/2021 | 2021-10-16 | 375853800 | 35187200 | 411041000 | 411041000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 251 | 01C11H01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | GORONTALO |  | 1 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1668697000 | 150188400 | 1818885400 | 1818885400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 252 | 01C11H01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | GORONTALO |  | 2 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 348320000 | 31348000 | 379668000 | 379668000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 161 | 01C11H01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | GORONTALO |  |  |  | 85 | 15 | 0 | Preparing | 2021-05-27 | 2022-09-05 | 2021-12-09 |  |  |  |  | 146282200 | 13413300 | 159695500 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 164 | 01C11H01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | GORONTALO |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.2125/LG.310/DID-B0400000/2022 | 2022-07-26 | TEL.1071/LG.320/DID-A0000000/2022 | 2022-07-26 | 745836040 | 67251600 | 813087640 | 813087640 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-29
12021150 | 12 | 312 | 01C11H01 | 019 | 72020078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ILA SALONGO MALIBAGU |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.2125/LG.310/DID-B0400000/2022 | 2022-07-26 | TEL.1071/LG.320/DID-A0000000/2022 | 2022-07-26 | 745836040 | 67251600 | 813087640 | 813087640 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-29
12021150 | 12 | 294 | 01C11H01 | 019 | 72020078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ILA SALONGO MALIBAGU |  |  |  | 85 | 15 | 0 | Preparing | 2021-05-27 | 2022-09-05 | 2021-12-09 |  |  |  |  | 612489700 | 83234400 | 695724100 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 313 | 01C11H01 | 019 | 72020078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ILA SALONGO MALIBAGU |  |  |  | 85 |  |  |  | 2021-05-27 | 2022-09-05 | [5 empty] | 146268400 | 13411900 | 159680300 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 315 | 01C11H01 | 019 | 72020078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ILA SALONGO MALIBAGU |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.2126/LG.310/DID-B0400000/2022 | 2022-07-26 | TEL.1072/LG.320/DID-A0000000/2022 | 2022-07-26 | 745836040 | 67251600 | 813087640 | 813087640 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-29
12021150 | 12 | 293 | 01C11H01 | 019 | 72020077 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ILA SINUMBAYUGA |  |  |  | 85 | 15 | 0 | Preparing | 2021-05-27 | 2022-09-05 | 2021-12-09 |  |  |  |  | 329774500 | 57194200 | 386968700 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 292 | 01C11H01 | 019 | 72020076 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ILA TOLUDAA |  |  |  | 85 | 15 | 0 | Preparing | 2021-05-27 | 2022-09-05 | 2021-12-09 |  |  |  |  | 329774500 | 57194200 | 386968700 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 257 | 01C11H01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ISIMU |  | 4 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 988932000 | 89009600 | 1077941600 | 1077941600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 256 | 01C11H01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ISIMU |  | 3 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 76000000 | 6840000 | 82840000 | 82840000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 255 | 01C11H01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ISIMU |  | 2 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 988932000 | 89009600 | 1077941600 | 1077941600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 253 | 01C11H01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ISIMU |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1668697000 | 150188400 | 1818885400 | 1818885400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 127 | 01C11H01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ISIMU |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2896/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0473/LG.320/DID-00000000/2021 | 2021-10-16 | 1574687200 | 142938200 | 1717625400 | 1717625400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 254 | 01C11H01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | ISIMU |  | 1 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1186697000 | 106808400 | 1293505400 | 1293505400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 273 | 01C11H01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | MARISA |  | 1 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 279286000 | 25137800 | 304423800 | 304423800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 272 | 01C11H01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | MARISA |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1066841900 | 119417500 | 1186259400 | 1186259400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 274 | 01C11H01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | GORONTALO | MARISA |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 652286000 | 58707800 | 710993800 | 710993800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 264 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | LUWUK | LUWUK |  | 3 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 84820000 | 7633000 | 92453000 | 92453000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 262 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | LUWUK | LUWUK |  | 1 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 988932000 | 89009600 | 1077941600 | 1077941600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 263 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | LUWUK | LUWUK |  | 2 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1261252000 | 113517600 | 1374769600 | 1374769600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 261 | 01C11H01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | LUWUK | LUWUK |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 2053998000 | 182743400 | 2236741400 | 2236741400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 248 | 01C11H01 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | AMURANG |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1101491800 | 97040800 | 1198532600 | 1198532600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 249 | 01C11H01 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | AMURANG |  | 1 |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1325864000 | 119339200 | 1445203200 | 1445203200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 314 | 01C11H01 | 019 | 72010018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | BUMBUNGAN |  |  |  | 85 |  |  |  | 2021-05-27 | 2022-09-05 | [5 empty] | 329774500 | 57194200 | 386968700 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 171 | 01C11H01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | KOTAMOBAGU |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.2126/LG.310/DID-B0400000/2022 | 2022-07-26 | TEL.1072/LG.320/DID-A0000000/2022 | 2022-07-26 | 745836040 | 67251600 | 813087640 | 813087640 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-29
12021150 | 12 | 258 | 01C11H01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | KOTAMOBAGU |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1101491800 | 97040800 | 1198532600 | 1198532600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 259 | 01C11H01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | KOTAMOBAGU |  | 1 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1325864000 | 119339200 | 1445203200 | 1445203200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 168 | 01C11H01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | KOTAMOBAGU |  |  |  | 85 | 15 | 0 | Preparing | 2021-05-27 | 2022-09-05 | 2021-12-09 |  |  |  |  | 282705400 | 26039400 | 308744800 | 0 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021150 | 12 | 260 | 01C11H01 | 019 | 72010055 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | LANGOAN |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1101491800 | 97040800 | 1198532600 | 1198532600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 128 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2896/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0473/LG.320/DID-00000000/2021 | 2021-10-16 | 1557262000 | 143330800 | 1700592800 | 1700592800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 22 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 623514500 | 51329900 | 674844400 | 674844400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 270 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  | 4 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 84820000 | 7633000 | 92453000 | 92453000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 269 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  | 3 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 997752000 | 89802600 | 1087554600 | 1087554600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 267 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1668697000 | 150188400 | 1818885400 | 1818885400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 266 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  | 1 |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 348320000 | 31348000 | 379668000 | 379668000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 265 | 01C11H01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | MANADO |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1284821000 | 115636700 | 1400457700 | 1400457700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 237 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  | 1 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 569376000 | 51245900 | 620621900 | 620621900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 243 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  | 5 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 348320000 | 31348000 | 379668000 | 379668000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 240 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  | 3 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 715877000 | 64434600 | 780311600 | 780311600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 242 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  | 4 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 997752000 | 89802600 | 1087554600 | 1087554600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 239 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 305876000 | 27530900 | 333406900 | 333406900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 244 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  | 6 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 997752000 | 89802600 | 1087554600 | 1087554600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 115 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-03 | 2021-05-21 | TEL.3303/LG.310/DID-B1060000/2021 | 2021-11-27 | TEL.0777/LG.320/DID-00000000/2021 | 2021-11-27 | 1458056400 | 131867400 | 1589923800 | 1589923800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 130 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2896/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0473/LG.320/DID-00000000/2021 | 2021-10-16 | 410122300 | 35108200 | 445230500 | 445230500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 25 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 1876764700 | 183397700 | 2060162400 | 2060162400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 233 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | PANIKI |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 2830907000 | 252662300 | 3083569300 | 3083569300 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 21 | 01C11H01 | 019 | 72010869 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | TTC PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 610047300 | 50117900 | 660165200 | 660165200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 290 | 01C11H01 | 019 | 72010283 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | TUTUYAN |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 988932000 | 89009600 | 1077941600 | 1077941600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 289 | 01C11H01 | 019 | 72010283 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | TUTUYAN |  | 1 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 739168000 | 66533700 | 805701700 | 805701700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 288 | 01C11H01 | 019 | 72010283 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | MANADO | TUTUYAN |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 2053998000 | 182743400 | 2236741400 | 2236741400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 46 | 01C11H01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | DONGGALA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 1421231000 | 127242000 | 1548473000 | 1548473000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 45 | 01C11H01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | PALU |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 2680873000 | 239272200 | 2920145200 | 2920145200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 275 | 01C11H01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | PARIGI |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1209988000 | 108907500 | 1318895500 | 1318895500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 276 | 01C11H01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | PARIGI |  | 1 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 297056000 | 26737900 | 323793900 | 323793900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 277 | 01C11H01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | PARIGI |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1209988000 | 108907500 | 1318895500 | 1318895500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 50 | 01C11H01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | PARIGI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 2888939100 | 260413500 | 3149352600 | 3149352600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 131 | 01C11H01 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | POSO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 2888939100 | 260413500 | 3149352600 | 3149352600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 281 | 01C11H01 | 019 | 72030069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | SANTIGI |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 2274506100 | 223558700 | 2498064800 | 2498064800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 282 | 01C11H01 | 019 | 72030069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | SANTIGI |  | 1 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2022-01-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1261252000 | 113517600 | 1374769600 | 1374769600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 283 | 01C11H01 | 019 | 72030069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | SANTIGI |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 84820000 | 7633000 | 92453000 | 92453000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 284 | 01C11H01 | 019 | 72030069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | SANTIGI |  | 3 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 988932000 | 89009600 | 1077941600 | 1077941600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 287 | 01C11H01 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PALU | TOLI-TOLI |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1101491800 | 97040800 | 1198532600 | 1198532600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 42 | 01C11H01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | ENREKANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-05-28 | 2021-05-21 | TEL.3588/LG.310/DID-B1060000/2021 | 2021-12-24 | TEL.0217/LG.320/DID-A0000000/2021 | 2021-12-24 | 1825163700 | 180649800 | 2005813500 | 2005813500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-28
12021150 | 12 | 41 | 01C11H01 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | MAKALE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-05-28 | 2021-05-21 | TEL.3588/LG.310/DID-B1060000/2021 | 2021-12-24 | TEL.0217/LG.320/DID-A0000000/2021 | 2021-12-24 | 1832279200 | 180955800 | 2013235000 | 2013235000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-28
12021150 | 12 | 132 | 01C11H01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | PALOPO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 2888939100 | 260413500 | 3149352600 | 3149352600 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 38 | 01C11H01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | PALOPO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-05-28 | 2021-05-21 | TEL.3588/LG.310/DID-B1060000/2021 | 2021-12-24 | TEL.0217/LG.320/DID-A0000000/2021 | 2021-12-24 | 632276100 | 69023600 | 701299700 | 701299700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-28
12021150 | 12 | 44 | 01C11H01 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-05-28 | 2021-05-21 | TEL.3588/LG.310/DID-B1060000/2021 | 2021-12-24 | TEL.0217/LG.320/DID-A0000000/2021 | 2021-12-24 | 629254900 | 53493000 | 682747900 | 682747900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-28
12021150 | 12 | 133 | 01C11H01 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 2319360000 | 223742400 | 2543102400 | 2543102400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 40 | 01C11H01 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | RANTEPAO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-05-28 | 2021-05-21 | TEL.3588/LG.310/DID-B1060000/2021 | 2021-12-24 | TEL.0217/LG.320/DID-A0000000/2021 | 2021-12-24 | 1086417400 | 106698300 | 1193115700 | 1193115700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-28
12021150 | 12 | 43 | 01C11H01 | 019 | 72040158 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | PARE-PARE | SIDRAP |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-05-28 | 2021-05-21 | TEL.3588/LG.310/DID-B1060000/2021 | 2021-12-24 | TEL.0217/LG.320/DID-A0000000/2021 | 2021-12-24 | 1111858200 | 107391700 | 1219249900 | 1219249900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-28
12021150 | 12 | 278 | 01C11H01 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | POSO | POSO |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1209988000 | 108907500 | 1318895500 | 1318895500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 280 | 01C11H01 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | POSO | POSO |  | 2 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1209988000 | 108907500 | 1318895500 | 1318895500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 279 | 01C11H01 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | POSO | POSO |  | 1 |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 297056000 | 26737900 | 323793900 | 323793900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021150 | 12 | 114 | 01C11H01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-03 | 2021-05-21 | TEL.3303/LG.310/DID-B1060000/2021 | 2021-11-27 | TEL.0777/LG.320/DID-00000000/2021 | 2021-11-27 | 1458056400 | 131867400 | 1589923800 | 1589923800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 23 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 1110406200 | 99936500 | 1210342700 | 1210342700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 48 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 1019461600 | 92160500 | 1111622100 | 1111622100 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 125 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2895/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0472/LG.320/DID-00000000/2021 | 2021-10-16 | 136882500 | 12319400 | 149201900 | 149201900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 228 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1484/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0974/LG.320/DID-A0000000/2022 | 2022-05-26 | 2619580500 | 235770700 | 2855351200 | 2855351200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 218 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1482/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0972/LG.320/DID-A0000000/2022 | 2022-05-26 | 4240926000 | 381700200 | 4622626200 | 4622626200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 222 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | BALAIKOTA |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1483/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0973/LG.320/DID-A0000000/2022 | 2022-05-26 | 2756463000 | 248090100 | 3004553100 | 3004553100 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 108 | 01C11H01 | 019 | 72080996 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | MAKASAR BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2894/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0471/LG.320/DID-00000000/2021 | 2021-10-16 | 631882500 | 56869400 | 688751900 | 688751900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 135 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 487882500 | 43909400 | 531791900 | 531791900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 27 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 2102423600 | 209004500 | 2311428100 | 2311428100 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 117 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-03 | 2021-05-21 | TEL.3303/LG.310/DID-B1060000/2021 | 2021-11-27 | TEL.0777/LG.320/DID-00000000/2021 | 2021-11-27 | 1623297400 | 153068000 | 1776365400 | 1776365400 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 217 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1482/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0972/LG.320/DID-A0000000/2022 | 2022-05-26 | 4240926000 | 381700200 | 4622626200 | 4622626200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 223 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  | 1 |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1483/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0973/LG.320/DID-A0000000/2022 | 2022-05-26 | 3114401500 | 280307400 | 3394708900 | 3394708900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 221 | 01C11H01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PENGAYOMAN |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1483/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0973/LG.320/DID-A0000000/2022 | 2022-05-26 | 2756463000 | 248090100 | 3004553100 | 3004553100 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 134 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 1887422500 | 169868000 | 2057290500 | 2057290500 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 225 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1483/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0973/LG.320/DID-A0000000/2022 | 2022-05-26 | 3114401500 | 280307400 | 3394708900 | 3394708900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 230 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1484/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0974/LG.320/DID-A0000000/2022 | 2022-05-26 | 2619580500 | 235770700 | 2855351200 | 2855351200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 216 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1482/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0972/LG.320/DID-A0000000/2022 | 2022-05-26 | 4240926000 | 381700200 | 4622626200 | 4622626200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 26 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 160406200 | 14436500 | 174842700 | 174842700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 111 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2894/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0471/LG.320/DID-00000000/2021 | 2021-10-16 | 2333882500 | 210049400 | 2543931900 | 2543931900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 123 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2895/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0472/LG.320/DID-00000000/2021 | 2021-10-16 | 578062500 | 52025600 | 630088100 | 630088100 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 227 | 01C11H01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | SUDIANG |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1484/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0974/LG.320/DID-A0000000/2022 | 2022-05-26 | 2619580500 | 235770700 | 2855351200 | 2855351200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 229 | 01C11H01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | SUDIANG |  | 1 |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1484/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0974/LG.320/DID-A0000000/2022 | 2022-05-26 | 2619580500 | 235770700 | 2855351200 | 2855351200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 224 | 01C11H01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | SUDIANG |  |  |  | 85 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-09-05 | 2021-12-09 | TEL.1482/LG.310/DID-B0400000/2022 | 2022-05-26 | TEL.0972/LG.320/DID-A0000000/2022 | 2022-05-26 | 4240926000 | 381700200 | 4622626200 | 4622626200 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021150 | 12 | 24 | 01C11H01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-12-17 | 2021-05-21 | TEL.3321/LG.310/DID-B1060000/2021 | 2021-11-28 | TEL.0773/LG.320/DID-00000000/2021 | 2021-11-28 | 1117139800 | 100542500 | 1217682300 | 1217682300 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021150 | 12 | 49 | 01C11H01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2892/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0476/LG.320/DID-00000000/2021 | 2021-10-16 | 98882500 | 8899400 | 107781900 | 107781900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 129 | 01C11H01 | 019 | 72080999 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | TELING |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2896/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0473/LG.320/DID-00000000/2021 | 2021-10-16 | 1188753300 | 106773600 | 1295526900 | 1295526900 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 112 | 01C11H01 | 019 | 72081012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | TTC PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2894/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0471/LG.320/DID-00000000/2021 | 2021-10-16 | 2737246600 | 246761100 | 2984007700 | 2984007700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 113 | 01C11H01 | 019 | 72080523 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | TTC SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2894/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0471/LG.320/DID-00000000/2021 | 2021-10-16 | 2737246600 | 246761100 | 2984007700 | 2984007700 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 122 | 01C11H01 | 019 | 72080523 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | TTC SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-05-27 | 2021-10-17 | 2021-05-21 | TEL.2895/LG.310/DID-B1060000/2021 | 2021-10-16 | TEL.0472/LG.320/DID-00000000/2021 | 2021-10-16 | 624765000 | 56228800 | 680993800 | 680993800 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-10-30
12021150 | 12 | 316 | 01C11H01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002662/HK.810/OPS-10000000/2021 | Kontrak DWDM Platform Nokia | 2021-05-21 | 2022-08-22 | DWDM ALU | UJUNGPANDANG | WATAMPONE |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-05-27 | 2022-08-22 | 2021-12-09 | TEL.1856/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.1008/LG.320/DID-A0000000/2022 | 2022-06-30 | 1104046000 | 97242000 | 1201288000 | 1201288000 | 4500429297 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-07-22
12021156 | 18 | 85 | 01C11I04 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | AMBON | AMBON |  | STO AMBON REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | TEL.235/AMC/MML/05102020 | 2021-05-25 | TEL.0216/LG.320/DID-00000000/2021 | 2021-05-25 | 3595658534 | 0 | 3595658534 | 3595658534 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2021-09-24
12021156 | 18 | 134 | 01C11I04 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | AMBON | AMBON |  | Duplikat Ke-1 |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 244 | 01C11I04 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | AMBON | AMBON |  | STO AMBON REKON-02 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_AMBON_2 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 222978660 | 0 | 222978660 | 222978660 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 201 | 01C11I04 | 019 | 74010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | BIAK | BIAK |  | STO BIAK REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-07-05 | 049/BIK/MML/PRIM-02062021 | 2021-07-05 | TEL.1047/LG.320/DID-A0000000/2022 | 2021-07-05 | 522068458 | 0 | 522068458 | 522068458 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-07-28
12021156 | 18 | 301 | 01C11I04 | 019 | 74010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | BIAK | BIAK |  | Duplikat Ke-1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 90 | 01C11I04 | 019 | 72020071 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | GORONTALO CENTRUM |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 250 | 01C11I04 | 019 | 72020071 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | GORONTALO CENTRUM |  | STO GORONTALO CENTRUM REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_GORONTALO_CENTRUM_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 561141000 | 0 | 561141000 | 561141000 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 87 | 01C11I04 | 019 | 72020023 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | LIMBOTO |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 252 | 01C11I04 | 019 | 72020023 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | LIMBOTO |  | STO LIMBOTO REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_LIMBOTO_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 48913890 | 0 | 48913890 | 48913890 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 88 | 01C11I04 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | MARISA |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 255 | 01C11I04 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | MARISA |  | STO MARISA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_MARISA_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 26349300 | 0 | 26349300 | 26349300 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 86 | 01C11I04 | 019 | 72020038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | TELAGA |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 260 | 01C11I04 | 019 | 72020038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | GORONTALO | TELAGA |  | STO TELAGA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_TELAGA_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 24697890 | 0 | 24697890 | 24697890 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 101 | 01C11I04 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | ABEPURA |  | STO ABEPURA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2022-07-14 | 2021-05-25 | LAMPIRAN_STO_ABEPURA_1 | 2021-05-25 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 87628420 | 0 | 87628420 | 87628420 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 292 | 01C11I04 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | ABEPURA |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 99 | 01C11I04 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | JAYAPURA-1 |  | STO JAYAPURA-1 REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2022-07-14 | 2022-03-26 | LAMPIRAN_STO_JAYAPURA1_1 | 2022-03-26 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 133319990 | 0 | 133319990 | 133319990 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 289 | 01C11I04 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | JAYAPURA-1 |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 290 | 01C11I04 | 019 | 74030034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | JAYAPURA-2 |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 100 | 01C11I04 | 019 | 74030034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | JAYAPURA-2 |  | STO JAYAPURA-2 REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2022-07-14 | 2021-05-25 | LAMPIRAN_STO_JAYAPURA2_1 | 2021-05-25 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 72609920 | 0 | 72609920 | 72609920 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 202 | 01C11I04 | 019 | 74030168 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | KAIMANA |  | STO KAIMANA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-10-11 | LAMPIRAN_STO_KAIMANA_1 | 2021-10-11 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 31980000 | 0 | 31980000 | 31980000 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 296 | 01C11I04 | 019 | 74030168 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | KAIMANA |  | Duplikat Ke-1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 203 | 01C11I04 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | NABIRE |  | STO NABIRE REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-09-30 | LAMPIRAN_STO_NABIRE_1 | 2021-09-30 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 21140000 | 0 | 21140000 | 21140000 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 295 | 01C11I04 | 019 | 74030176 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | NABIRE |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 102 | 01C11I04 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | SENTANI |  | STO SENTANI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2022-07-14 | 2021-05-25 | LAMPIRAN_STO_SENTANI_1 | 2021-05-25 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 92415310 | 0 | 92415310 | 92415310 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 291 | 01C11I04 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | SENTANI |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 103 | 01C11I04 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | TIMIKA |  | STO TIMIKA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2022-07-14 | 2022-03-31 | LAMPIRAN_STO_TIMIKA_1 | 2022-03-31 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 18185550 | 0 | 18185550 | 18185550 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 293 | 01C11I04 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | JAYAPURA | TIMIKA |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 247 | 01C11I04 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | KENDARI | BAU-BAU |  | STO BAU-BAU REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_BAU_BAU_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 368104440 | 0 | 368104440 | 368104440 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 91 | 01C11I04 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | KENDARI | BAU-BAU |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 245 | 01C11I04 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | MANADO | AMURANG |  | STO AMURANG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_AMURANG_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 46111320 | 0 | 46111320 | 46111320 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 92 | 01C11I04 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | MANADO | AMURANG |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 288 | 01C11I04 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | MANOKWARI | MANOKWARI |  | Duplikat Ke-1 |  | 0 | 0 |  | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 204 | 01C11I04 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | MANOKWARI | MANOKWARI |  | STO MANOKWARI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-09-28 | 134/TEL/MML-0206/2021 | 2021-09-28 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 738977565 | 0 | 738977565 | 738977565 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 104 | 01C11I04 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | MERAUKE | MERAUKE |  | STO MERAUKE REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2022-07-14 | 2022-04-27 | LAMPIRAN_STO_MERAUKE_1 | 2022-04-27 | TEL.0849/LG.320/DID-A0000000/2022 | 2022-04-27 | 47970050 | 0 | 47970050 | 47970050 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-06-29
12021156 | 18 | 294 | 01C11I04 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | MERAUKE | MERAUKE |  | Duplikat Ke-1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 0 | 0 | 0 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 153 | 01C11I04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PALU | PALU-1 |  | STO PALU-1 REKON-02 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_PALU1_2 | 2021-05-25 | TEL.0150/LG.320/DID-A0000000/2021 | 2021-05-25 | 381869910 | 0 | 381869910 | 381869910 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2021-12-27
12021156 | 18 | 93 | 01C11I04 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PALU | PALU-1 |  | STO PALU-1 REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | TEL.067/PL-A/MML/PRIM-19032021 | 2021-05-25 | TEL.0425/LG.320/DID-00000000/2021 | 2021-05-25 | 2443508501 | 0 | 2443508501 | 2443508501 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2021-10-27
12021156 | 18 | 94 | 01C11I04 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PALU | POSO |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 95 | 01C11I04 | 019 | 72040044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | CANGADI |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 248 | 01C11I04 | 019 | 72040044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | CANGADI |  | STO CANGADI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_CANGADI_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 17661920 | 0 | 17661920 | 17661920 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 253 | 01C11I04 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | MAKALE |  | STO MAKALE REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_MAKALE_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 126363640 | 0 | 126363640 | 126363640 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 96 | 01C11I04 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | MAKALE |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 97 | 01C11I04 | 019 | 72040195 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | POLEWALI |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 256 | 01C11I04 | 019 | 72040195 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | POLEWALI |  | STO POLEWALI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_POLEWALI_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 384299840 | 0 | 384299840 | 384299840 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 98 | 01C11I04 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | SENGKANG |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 257 | 01C11I04 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | PARE-PARE | SENGKANG |  | STO SENGKANG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_SENGKANG_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 136818940 | 0 | 136818940 | 136818940 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 258 | 01C11I04 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | SORONG | SERUI |  | STO SERUI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-05-25 | LAMPIRAN_STO_SERUI_1 | 2021-05-25 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 20372630 | 0 | 20372630 | 20372630 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021156 | 18 | 105 | 01C11I04 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | SORONG | SERUI |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 106 | 01C11I04 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | SORONG | SORONG |  |  |  | 100 | 90 | 0 | Siap UT | 2021-05-25 | 2021-12-21 | 2021-05-25 |  |  |  |  | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI
12021156 | 18 | 259 | 01C11I04 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002768/HK.810/OPS-10000000/2021 | Surat Pesanan-2 (SP#2) Penjualan Barang Scrap Telkom | 2021-05-25 | 2022-06-30 | PELOLOSAN | SORONG | SORONG |  | STO SORONG REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-05-25 | 2021-12-21 | 2021-10-30 | LAMPIRAN_STO_SORONG_1 | 2021-10-30 | TEL.0454/LG.320/DID-A0000000/2022 | 2021-10-30 | 323423810 | 0 | 323423810 | 323423810 | 0000000000 |  |  |  |  | MUKTI MANDIRI LESTARI | 2022-04-25
12021161 | 9 | 81 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002937/HK.810/OPS-10000000/2021 | SP#1 Ekspan PE Transit Platform Huawei | 2021-05-31 | 2021-12-10 | Ekspan PE Transit | AMBON | AMBON |  | PE-D7-AB1-TRANSIT |  | 90 | 100 | 100 | BAST-1 | 2021-05-31 | 2021-12-10 | 2021-05-31 | TEL.2133/LG.310/PND.B1050000/2021 | 2021-12-09 | TEL.0165/LG.320/DID-A0000000/2021 | 2021-12-09 | 38172000 | 3817200 | 41989200 | 41989200 | 4500430132 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-27
12021161 | 9 | 15 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002937/HK.810/OPS-10000000/2021 | SP#1 Ekspan PE Transit Platform Huawei | 2021-05-31 | 2021-12-10 | Ekspan PE Transit | JAYAPURA | JAYAPURA |  | PE-D7-JAP-TRANSIT |  | 100 | 100 | 100 | BAST-1 | 2021-05-31 | 2021-09-27 | 2021-05-31 | TEL.960/LG.310/PND-B1050000/2021 | 2021-06-25 | TEL.0757/LG.320/PND-A1000000/2021 | 2021-06-25 | 1014957000 | 101495700 | 1116452700 | 1116452700 | 4500430132 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-06-30
12021161 | 9 | 36 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002937/HK.810/OPS-10000000/2021 | SP#1 Ekspan PE Transit Platform Huawei | 2021-05-31 | 2021-12-10 | Ekspan PE Transit | MANADO | MANADO |  | PE-D7-MDO-Transit |  | 100 | 100 | 100 | BAST-1 | 2021-05-31 | 2021-09-27 | 2021-05-31 | TEL.962/LG.310/PND-B1050000/2021 | 2021-06-25 | TEL.0759/LG.320/PND-A1000000/2021 | 2021-06-25 | 0 | 83616000 | 83616000 | 83616000 | 4500430132 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-06-30
12021161 | 9 | 14 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002937/HK.810/OPS-10000000/2021 | SP#1 Ekspan PE Transit Platform Huawei | 2021-05-31 | 2021-12-10 | Ekspan PE Transit | MANADO | PANIKI |  | PE-D7-PNK-TRANSIT |  | 100 | 100 | 100 | BAST-1 | 2021-05-31 | 2021-09-27 | 2021-05-31 | TEL.960/LG.310/PND-B1050000/2021 | 2021-06-25 | TEL.0757/LG.320/PND-A1000000/2021 | 2021-06-25 | 1014957000 | 101495700 | 1116452700 | 1116452700 | 4500430132 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-06-30
12021161 | 9 | 79 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002937/HK.810/OPS-10000000/2021 | SP#1 Ekspan PE Transit Platform Huawei | 2021-05-31 | 2021-12-10 | Ekspan PE Transit | MANADO | PANIKI |  | PE-D7-PNK-TRANSIT |  | 90 | 100 | 100 | BAST-1 | 2021-05-31 | 2021-12-10 | 2021-05-31 | TEL.2133/LG.310/PND.B1050000/2021 | 2021-12-09 | TEL.0165/LG.320/DID-A0000000/2021 | 2021-12-09 | 577042000 | 57704200 | 634746200 | 634746200 | 4500430132 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-27
G2021116 | 2 | 6 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan Feeder Branching 1 LOP Area Witel Maluku | 2021-06-02 | 2021-08-30 | OSP-FO Feeder | AMBON | AMBON |  | NORMALISASI FEEDER JMP |  | 100 | 100 | 100 | BAST-1 | 2021-06-03 | 2021-08-12 | 2021-06-02 | TEL.959/LG.310/DR7-12700000/2022 | 2022-06-12 | TEL.0089/LG.320/DR7-10400000/2022 | 2022-06-12 | 306268656 | 74843973 | 381112629 | 381112629 | 4500430217 |  |  |  |  | TELKOM AKSES | 2022-06-15
12021163 | 7 | 281 | 01C11I01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | AMBON | PASSO |  |  |  | 95 | 100 | 100 | BAST-1 | 2021-09-20 | 2022-01-05 | 2021-12-27 | TEL.0094/LG.310/DID-C0200000/2021 | 2021-12-28 23:09 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 77224015 | 18009667 | 95233682 | 95233682 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 81 | 01C11I01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | GORONTALO | GORONTALO |  | Bundled cord |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-08 | 2021-08-01 | TEL.1410/LG.310/PND-C1030000/2021 | 2021-12-08 20:17 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 63219442 | 44580234 | 107799676 | 107799676 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 80 | 01C11I01 | 019 | 72020023 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | GORONTALO | LIMBOTO |  | Bundled cord |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-08 | 2021-08-01 | TEL.1410/LG.310/PND-C1030000/2021 | 2021-12-08 20:17 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 92489501 | 24386537 | 116876038 | 116876038 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 79 | 01C11I01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | GORONTALO | MARISA |  | Bundled cord |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-08 | 2021-08-01 | TEL.1410/LG.310/PND-C1030000/2021 | 2021-12-08 20:17 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 19279198 | 5184607 | 24463805 | 24463805 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 78 | 01C11I01 | 019 | 72020038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | GORONTALO | TELAGA |  | Bundled cord |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-08 | 2021-08-01 | TEL.1410/LG.310/PND-C1030000/2021 | 2021-12-08 20:17 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 22727686 | 7732633 | 30460319 | 30460319 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 77 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | KENDARI | MANDONGA |  | Expand FTM |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-06 | 2021-08-01 | TEL.1399/LG.310/PND-C1030000/2021 | 2021-12-06 16:25 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 18695881 | 1045511 | 19741392 | 19741392 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 74 | 01C11I01 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | MANADO | AIR MADIDI |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-29 | 2021-08-01 | TEL.0089/LG.310/DID-C0200000/2021 | 2021-12-28 17:24 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 81937309 | 16383012 | 98320321 | 98320321 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 75 | 01C11I01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | MANADO | BITUNG |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-29 | 2021-08-01 | TEL.0089/LG.310/DID-C0200000/2021 | 2021-12-28 17:24 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 106090593 | 23043874 | 129134467 | 129134467 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 76 | 01C11I01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | MANADO | TONDANO |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-29 | 2021-08-01 | TEL.0102/LG.310/DID-C0200000/2021 | 2021-12-29 12:05 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 72866499 | 14205226 | 87071725 | 87071725 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 71 | 01C11I01 | 019 | 72030124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | PALU | BUNTA |  | Bundled cord |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-28 | 2021-08-01 | TEL.0076/LG.310/DID-C0200000/2021 | 2021-12-28 05:39 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 38558396 | 11141498 | 49699894 | 49699894 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 72 | 01C11I01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | PALU | LUWUK |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-28 | 2021-08-01 | TEL.0076/LG.310/DID-C0200000/2021 | 2021-12-28 05:39 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 40445521 | 2539275 | 42984796 | 42984796 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 70 | 01C11I01 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | PALU | PALU-2 |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-28 | 2021-08-01 | TEL.0070/LG.310/DID-C0200000/2021 | 2021-12-26 14:10 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 117277185 | 21048718 | 138325903 | 138325903 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 73 | 01C11I01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | PALU | TAWAELI |  | Bundled cord |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-28 | 2021-08-01 | TEL.0070/LG.310/DID-C0200000/2021 | 2021-12-26 14:10 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 68183058 | 24925647 | 93108705 | 93108705 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 68 | 01C11I01 | 019 | 72040275 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | PARE-PARE | AJANGALE |  | New FTM |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-14 | 2021-08-01 | TEL.0011/LG.310/DID-C0200000/2021 | 2021-12-14 14:48 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 169325694 | 22993588 | 192319282 | 192319282 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 69 | 01C11I01 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | PARE-PARE | MAKALE |  | Bundled cord |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-14 | 2021-08-01 | TEL.0011/LG.310/DID-C0200000/2021 | 2021-12-14 14:48 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 47754364 | 18442298 | 66196662 | 66196662 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 87 | 01C11I01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | TERNATE | TERNATE |  | Expand FTM |  | 100 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-29 | 2021-08-01 | TEL.0071/LG.310/DID-C0200000/2021 | 2021-12-27 12:39 | TEL.0295/LG.320/DID-A0000000/2021 | 2021-12-29 | 68936395 | 1388125 | 70324520 | 70324520 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-12-30
12021163 | 7 | 89 | 01C11I01 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | UJUNGPANDANG | MATTOANGIN |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-05 | 2021-08-01 | TEL.1210/LG.310/PND-C1030000/2021 | 2021-11-15 11:22 | TEL.0684/LG.320/DID-00000000/2021 | 2021-11-15 | 67989743 | 2415016 | 70404759 | 70404759 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-11-29
12021163 | 7 | 88 | 01C11I01 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003006/HK.810/OPS-10040000/2021 | Kontrak Fiber Termination Management (FTM) | 2021-06-02 | 2021-12-29 | FTM | UJUNGPANDANG | TAMALANREA |  | Expand FTM |  | 95 | 100 | 100 | BAST-1 | 2021-07-07 | 2021-12-05 | 2021-08-01 | TEL.1210/LG.310/PND-C1030000/2021 | 2021-11-15 11:22 | TEL.0684/LG.320/DID-00000000/2021 | 2021-11-15 | 25859930 | 2467888 | 28327818 | 28327818 | 4500429619 |  |  |  |  | BANGTELINDO | 2021-11-29
G2021117 | 3 | 6 | 01E07V04 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.003022/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring 5 LOP Area Witel Maluku & Papua Barat | 2021-06-03 | 2021-09-05 | PALAPA RING | AMBON | DOBO |  | PALAPA RING DOBO |  | 100 | 100 | 100 | BAST-1 | 2021-06-03 | 2021-09-05 | 2021-12-01 | TEL.728/LG.310/DR7-12700000/2022 | 2022-03-23 | TEL.0039/LG.320/DR7-10400000/2022 | 2022-03-23 | 713357592 | 721232381 | 1434589973 | 1434589973 | 4500430349 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-25
G2021117 | 3 | 7 | 01E07V04 | 007 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.003022/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring 5 LOP Area Witel Maluku & Papua Barat | 2021-06-03 | 2021-09-05 | PALAPA RING | AMBON | SAUMLAKI |  | PALAPA RING SAUMLAKI |  | 100 | 100 | 100 | BAST-1 | 2021-06-03 | 2021-09-05 | 2021-12-01 | TEL.2093/LG.310/DR7-12700000/2021 | 2021-12-22 | TEL.0231/LG.320/DR7-10400000/2021 | 2021-12-22 | 184822053 | 251437674 | 436259727 | 436259727 | 4500430349 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-28
G2021117 | 3 | 11 | 01E07V04 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.003022/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring 5 LOP Area Witel Maluku & Papua Barat | 2021-06-03 | 2021-09-05 | PALAPA RING | SORONG | NABIRE |  | R7 PPB PRTIMNOC KIGAMANI - ENT008 |  | 100 | 100 | 100 | BAST-1 | 2021-06-03 | 2021-09-05 | 2021-12-01 | TEL.2096/LG.310/DR7-12700000/2021 | 2021-12-22 | TEL.0231/LG.320/DR7-10400000/2021 | 2021-12-22 | 122511685 | 33739447 | 156251132 | 156251132 | 4500430349 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-28
G2021117 | 3 | 10 | 01E07V04 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.003022/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring 5 LOP Area Witel Maluku & Papua Barat | 2021-06-03 | 2021-09-05 | PALAPA RING | SORONG | NABIRE |  | R7 PPB PRTIM NOC ENAROTALI - ENT002 |  | 100 | 100 | 100 | BAST-1 | 2021-06-03 | 2021-09-05 | 2021-12-01 | TEL.2095/LG.310/DR7-12700000/2021 | 2021-12-22 | TEL.0231/LG.320/DR7-10400000/2021 | 2021-12-22 | 388635600 | 103239562 | 491875162 | 491875162 | 4500430349 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-28
G2021117 | 3 | 9 | 01E07V04 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.003022/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring 5 LOP Area Witel Maluku & Papua Barat | 2021-06-03 | 2021-09-05 | PALAPA RING | SORONG | NABIRE |  | R7 PPB PRTIM NOC TIGI-ENT010 |  | 100 | 100 | 100 | BAST-1 | 2021-06-03 | 2021-09-05 | 2021-12-01 | TEL.2094/LG.310/DR7-12700000/2021 | 2021-12-22 | TEL.0231/LG.320/DR7-10400000/2021 | 2021-12-22 | 168899922 | 45700322 | 214600244 | 214600244 | 4500430349 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-28
12021186 | 10 | 130 | 01C11J02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | JAYAPURA | TIMIKA |  | MMU Timika SP 1 (dhTimika Satuan Pemukiman 1) |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4999000 | 17870000 | 17870000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 24 | 01C11J02 | 019 | 70000265 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | KANTOR DIVRE VII | KTI AREA |  | TREG-7 |  | 100 | 20 | 0 | Preparing | 2021-06-22 | 2022-06-20 | 2021-08-25 |  |  |  |  | 530000000 | 132526000 | 662526000 | 0 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021186 | 10 | 124 | 01C11J02 | 019 | 72050069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | KENDARI | TINANGGEA |  | MMU Tinanggea |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 129 | 01C11J02 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | MANADO | AMURANG |  | Amurang |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4810000 | 17681000 | 17681000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 128 | 01C11J02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | MANADO | MANADO |  | Manado Toar |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4810000 | 17681000 | 17681000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 122 | 01C11J02 | 019 | 72030167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | PALU | MOROWALI |  | Morowali Bahadopi |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 126 | 01C11J02 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | PALU | TENTENA |  | MMU Tentena |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 133 | 01C11J02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | SORONG | SORONG |  | MMU Sorong Aimas |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4999000 | 17870000 | 17870000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 131 | 01C11J02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | SORONG | SORONG |  | MMU Sorong Pasar Boswezen |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4999000 | 17870000 | 17870000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 132 | 01C11J02 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | SORONG | SORONG |  | MMU Sorong Klasaman |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4999000 | 17870000 | 17870000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 125 | 01C11J02 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | TERNATE | TERNATE |  | MMU Ternate Bastiong |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4716000 | 17587000 | 17587000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 120 | 01C11J02 | 019 | 72080023 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | BONE |  | MMU Masamba |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 123 | 01C11J02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | MAKASAR |  | SME Makassar Kartini |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 119 | 01C11J02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | MAKASAR |  | MMU Belopa |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 117 | 01C11J02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | MAKASAR |  | MMU Siwa |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 121 | 01C11J02 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | MAKASSAR |  | MMU Malili |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-03-17 | 2021-11-28 | TEL.0002/LG.310/DID-B0200000/2021 | 2021-12-30 09:05 | TEL.0365/LG.320/DID-A0000000/2021 | 2021-12-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021186 | 10 | 127 | 01C11J02 | 019 | 72080125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | TANETTE |  | MMU Bulukumba Tanete |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2021-12-10 | 2021-11-28 | TEL.0230/LG.310/PND-C1050000/2021 | 2021-11-30 08:17 | TEL.0767/LG.320/DID-00000000/2021 | 2021-11-30 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-11-30
12021186 | 10 | 302 | 01C11J02 | 019 | 72080135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | WIRELESS PROJECT MANAGEMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003381/HK.810/OPS-10050000/2021 | SP#1 SD-WAN VMware VeloCloud | 2021-06-14 | 2022-06-13 | SD-WAN | UJUNGPANDANG | UJUNG PANDANG |  | MMU Makasar Paccerakkang |  | 100 | 100 | 100 | BAST-1 | 2021-06-22 | 2022-04-25 | 2022-02-26 | TEL.0191/LG.310/DID-C0200000/2022 | 2022-02-27 10:46 | TEL.0196/LG.320/DID-A0000000/2022 | 2022-02-27 | 12871000 | 4527000 | 17398000 | 17398000 | 4500430405 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-27
12021187 | 13 | 107 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | AMBON | AMBON |  | P-D7-AB1 |  | 90 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-04-29 | 2021-12-06 | TEL.2196/LG.310/PND-B1050000/2021 | 2021-12-28 | TEL.0227/LG.320/DID-A0000000/2021 | 2021-12-28 | 2273538000 | 169972000 | 2443510000 | 2443510000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-12-29
12021187 | 13 | 119 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | AMBON | AMBON |  | P-D7-AB1 |  | 90 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-04-29 | 2021-12-06 | TEL.311/LG.310/DID-B0300000/2022 | 2022-03-22 | TEL.0266/LG.320/DID-A0000000/2022 | 2022-03-22 | 1006656000 | 75264000 | 1081920000 | 1081920000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-03-25
12021187 | 13 | 73 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | MANADO | PANIKI |  | P-D7-PNK |  | 100 | 100 | 100 | BAST-1 | 2021-10-04 | 2021-12-21 | 2021-10-13 | TEL.1831/LG.310/PND-B1050000/2021 | 2021-10-27 | TEL.0548/LG.320/DID-00000000/2021 | 2021-10-27 | 3280194000 | 245236000 | 3525430000 | 3525430000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-10-31
12021187 | 13 | 94 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | PALU | PALU-1 |  | P-D7-PAL |  | 100 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-01-27 | 2021-12-06 | TEL.0035/LG.310/DID-B0300000/2022 | 2022-01-26 | TEL.0267/LG.320/DID-A0000000/2022 | 2022-01-26 | 15000000 | 121200000 | 136200000 | 136200000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-03-25
12021187 | 13 | 74 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | PALU | PALU-1 |  | P-D7-PAL |  | 100 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-01-27 | 2021-10-13 | TEL.0036/LG.310/DID-B0300000/2022 | 2022-01-26 | TEL.0268/LG.320/DID-A0000000/2022 | 2022-01-26 | 120000000 | 129600000 | 249600000 | 249600000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-03-25
12021187 | 13 | 124 | 01C11B01 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | PALU | PALU-2 |  | P-D7-PAL2 |  | 50 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-05-29 | 2021-12-06 | K.TEL.764/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0765/LG.320/DID-A0000000/2022 | 2022-05-28 | 0 | 500000000 | 500000000 | 500000000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-05-31
12021187 | 13 | 108 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | TERNATE | TERNATE |  | P-D7-TNT |  | 90 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-04-29 | 2021-12-06 | TEL.2196/LG.310/PND-B1050000/2021 | 2021-12-28 | TEL.0227/LG.320/DID-A0000000/2021 | 2021-12-28 | 2273538000 | 169972000 | 2443510000 | 2443510000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-12-29
12021187 | 13 | 120 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | TERNATE | TERNATE |  | P-D7-TNT |  | 90 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-04-29 | 2021-12-06 | TEL.311/LG.310/DID-B0300000/2022 | 2022-03-22 | TEL.0266/LG.320/DID-A0000000/2022 | 2022-03-22 | 1006656000 | 75264000 | 1081920000 | 1081920000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-03-25
12021187 | 13 | 71 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | BALAIKOTA |  | P-D7-BAL |  | 100 | 100 | 100 | BAST-1 | 2021-10-04 | 2021-12-21 | 2021-10-13 | TEL.1832/LG.310/PND-B1050000/2021 | 2021-10-27 | TEL.0549/LG.320/DID-00000000/2021 | 2021-10-27 | 47959400 | 3593600 | 51553000 | 51553000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-10-31
12021187 | 13 | 17 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | BALAIKOTA |  | P-D7-BAL |  | 100 | 100 | 100 | BAST-1 | 2021-06-15 | 2021-10-12 | 2021-06-15 | TEL.1548/LG.310/PND-B1050000/2021 | 2021-09-17 | TEL.0218/LG.320/DID-00000000/2021 | 2021-09-17 | 6560388000 | 490472000 | 7050860000 | 7050860000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-09-24
12021187 | 13 | 76 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | PETTARANI |  | P-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-06-15 | 2022-01-27 | 2021-12-06 | TEL.0035/LG.310/DID-B0300000/2022 | 2022-01-26 | TEL.0267/LG.320/DID-A0000000/2022 | 2022-01-26 | 3000000 | 24240000 | 27240000 | 27240000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-03-25
12021187 | 13 | 72 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | PETTARANI |  | P-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-10-04 | 2021-12-21 | 2021-10-13 | TEL.1832/LG.310/PND-B1050000/2021 | 2021-10-27 | TEL.0549/LG.320/DID-00000000/2021 | 2021-10-27 | 47959400 | 3593600 | 51553000 | 51553000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-10-31
12021187 | 13 | 18 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003386/HK.810/OPS-10000000/2021 | SP#1 Ekspan IP Backbone Platform Cisco | 2021-06-15 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | PETTARANI |  | P-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-06-15 | 2021-10-12 | 2021-06-15 | TEL.1548/LG.310/PND-B1050000/2021 | 2021-09-17 | TEL.0218/LG.320/DID-00000000/2021 | 2021-09-17 | 6560388000 | 490472000 | 7050860000 | 7050860000 | 4500430941 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-09-24
12021223 | 8 | 90 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 24 Port DC |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-03-31 | 2021-12-29 | TEL.59/LG.235/DID-C1030000/2022 | 2022-02-23 | TEL.0188/LG.320/DID-A0000000/2022 | 2022-02-23 | 49351584 | 1599800 | 50951384 | 50951384 | 4500431408 |  |  |  |  | PINS INDONESIA | 2022-02-27
12021223 | 8 | 91 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 8 Port DC |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-03-31 | 2021-12-29 | TEL.59/LG.235/DID-C1030000/2022 | 2022-02-23 | TEL.0188/LG.320/DID-A0000000/2022 | 2022-02-23 | 4359496 | 299950 | 4659446 | 4659446 | 4500431408 |  |  |  |  | PINS INDONESIA | 2022-02-27
12021223 | 8 | 58 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch DC Support 10 G NON POE 24 Port Combo |  | 100 | 100 | 100 | BAST-1 | 2021-07-06 | 2021-12-22 | 2021-07-06 | TEL.3301/LG.000/PND-C1030000/2021 | 2021-12-21 | TEL.0258/LG.320/DID-A0000000/2021 | 2021-12-21 | 139460800 | 2000000 | 141460800 | 141460800 | 4500431408 |  |  |  |  | PINS INDONESIA | 2021-12-29
12021223 | 8 | 94 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch DC Support 10 G NON POE 24 Port SFP |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-03-31 | 2021-12-29 | TEL.59/LG.235/DID-C1030000/2022 | 2022-02-23 | TEL.0188/LG.320/DID-A0000000/2022 | 2022-02-23 | 102866544 | 1500000 | 104366544 | 104366544 | 4500431408 |  |  |  |  | PINS INDONESIA | 2022-02-27
12021223 | 8 | 53 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 8 Port DC |  | 100 | 100 | 100 | BAST-1 | 2021-07-06 | 2021-12-22 | 2021-07-06 | TEL.3301/LG.000/PND-C1030000/2021 | 2021-12-21 | TEL.0258/LG.320/DID-A0000000/2021 | 2021-12-21 | 8718992 | 599900 | 9318892 | 9318892 | 4500431408 |  |  |  |  | PINS INDONESIA | 2021-12-29
12021223 | 8 | 56 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch AC Support 10 G NON POE 24 Port SFP |  | 100 | 100 | 100 | BAST-1 | 2021-07-06 | 2021-12-22 | 2021-07-06 | TEL.3301/LG.000/PND-C1030000/2021 | 2021-12-21 | TEL.0258/LG.320/DID-A0000000/2021 | 2021-12-21 | 65440960 | 1000000 | 66440960 | 66440960 | 4500431408 |  |  |  |  | PINS INDONESIA | 2021-12-29
12021223 | 8 | 93 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch DC Support 10 G NON POE 24 Port Combo |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-03-31 | 2021-12-29 | TEL.59/LG.235/DID-C1030000/2022 | 2022-02-23 | TEL.0188/LG.320/DID-A0000000/2022 | 2022-02-23 | 348652000 | 5000000 | 353652000 | 353652000 | 4500431408 |  |  |  |  | PINS INDONESIA | 2022-02-27
12021223 | 8 | 80 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | L2 Switch 24 Port DC |  | 100 | 100 | 100 | BAST-1 | 2021-07-06 | 2021-12-22 | 2021-07-06 | TEL.3301/LG.000/PND-C1030000/2021 | 2021-12-21 | TEL.0258/LG.320/DID-A0000000/2021 | 2021-12-21 | 12337896 | 399950 | 12737846 | 12737846 | 4500431408 |  |  |  |  | PINS INDONESIA | 2021-12-29
12021223 | 8 | 57 | 01C11I03 | 019 | 70000014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-2 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003973/HK.810/OPS-10050000/2021 | Surat Pesanan-6 (SP#6) Pengadaan dan Pemasangan L2 Switch 2021 | 2021-07-05 | 2022-03-30 | L2 Switch | KANTOR DIVRE VII | KANTOR DIVRE VII |  | Switch DC Support 10 G NON POE 24 Port SFP |  | 100 | 100 | 100 | BAST-1 | 2021-07-06 | 2021-12-22 | 2021-07-06 | TEL.3301/LG.000/PND-C1030000/2021 | 2021-12-21 | TEL.0258/LG.320/DID-A0000000/2021 | 2021-12-21 | 34288848 | 500000 | 34788848 | 34788848 | 4500431408 |  |  |  |  | PINS INDONESIA | 2021-12-29
12021224 | 18 | 270 | 01C11I04 | 019 | 72030124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | BUNTA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 186 | 01C11I04 | 019 | 72030124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | BUNTA |  | STO BUNTA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-07-05 | 2022-01-14 | 2021-07-05 | LAMPIRAN_STO_BUNTA_1 | 2021-07-05 | TEL.0627/LG.320/DID-00000000/2021 | 2021-07-05 | 751500 | 0 | 751500 | 751500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-11-27
12021224 | 18 | 271 | 01C11I04 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | DONGGALA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 187 | 01C11I04 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | DONGGALA |  | STO DONGGALA REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-07-05 | 2022-01-14 | 2021-07-05 | LAMPIRAN_STO_DONGGALA_1 | 2021-07-05 | TEL.0627/LG.320/DID-00000000/2021 | 2021-07-05 | 16990500 | 0 | 16990500 | 16990500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-11-27
12021224 | 18 | 188 | 01C11I04 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | TINOMBO |  | STO TINOMBO REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-07-05 | 2022-01-14 | 2021-07-05 | LAMPIRAN_STO_TINOMBO_1 | 2021-07-05 | TEL.0627/LG.320/DID-00000000/2021 | 2021-07-05 | 463500 | 0 | 463500 | 463500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-11-27
12021224 | 18 | 287 | 01C11I04 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | TINOMBO |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 189 | 01C11I04 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | TOLI-TOLI |  | STO TOLI-TOLI REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-07-05 | 2022-01-14 | 2021-07-05 | LAMPIRAN_STO_TOLI_TOLI_1 | 2021-07-05 | TEL.0627/LG.320/DID-00000000/2021 | 2021-07-05 | 48091000 | 0 | 48091000 | 48091000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-11-27
12021224 | 18 | 288 | 01C11I04 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PALU | TOLI-TOLI |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 480 | 01C11I04 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PARE-PARE | MASAMBA |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 190 | 01C11I04 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PARE-PARE | MASAMBA |  | STO MASAMBA REKON-01 |  | 90 | 100 | 100 | BAST-1 | 2021-07-05 | 2023-01-14 | 2022-03-30 | LAMPIRAN_STO_MASAMBA_1 | 2022-03-30 | TEL.0836/LG.320/DID-A0000000/2022 | 2022-03-30 | 20454000 | 0 | 20454000 | 20454000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2022-06-29
12021224 | 18 | 390 | 01C11I04 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PARE-PARE | PALOPO |  | STO PALOPO REKON-02 |  | 90 | 100 | 100 | BAST-1 | 2021-07-05 | 2023-01-14 | 2022-03-30 | LAMPIRAN__STO__PALOPO__2 | 2022-03-30 | TEL.0836/LG.320/DID-A0000000/2022 | 2022-03-30 | 142147500 | 0 | 142147500 | 142147500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2022-06-29
12021224 | 18 | 481 | 01C11I04 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PARE-PARE | PALOPO |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 337 | 01C11I04 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | PARE-PARE | PALOPO |  | STO PALOPO REKON-01 |  | 90 | 100 | 100 | BAST-1 | 2021-07-05 | 2023-01-14 | 2021-07-05 | LAMPIRAN_STO_PALOPO_1 | 2021-07-05 | TEL.0093/LG.320/DID-A0000000/2022 | 2021-07-05 | 131751000 | 0 | 131751000 | 131751000 | 0000000000 |  |  |  |  | TELKOM AKSES | 2022-02-22
12021224 | 18 | 276 | 01C11I04 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | MATTOANGIN |  | Duplikat Ke-1 |  | 90 | 0 | 0 | Preparing | 2021-07-05 | 2023-01-14 | [5 empty] | 10000000 | 0 | 10000000 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
12021224 | 18 | 185 | 01C11I04 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003991/HK.810/OPS-10000000/2021 | SP#37 Granular Modenization - Pelolosan, Pembongkaran dan Penjualan Kabel Tembaga Primer dan Barang Scrap | 2021-07-05 | 2022-12-31 | PELOLOSAN | UJUNGPANDANG | MATTOANGIN |  | STO MATTOANGIN REKON-01 |  | 100 | 100 | 100 | BAST-1 | 2021-07-05 | 2022-01-14 | 2021-07-05 | LAMPIRAN_STO_MATTOANGIN_1 | 2021-07-05 | TEL.0627/LG.320/DID-00000000/2021 | 2021-07-05 | 435096500 | 0 | 435096500 | 435096500 | 0000000000 |  |  |  |  | TELKOM AKSES | 2021-11-27
12021230 | 7 | 70 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-12-15 | TEL.15953/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0080/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 110000000 | 110000000 | 110000000 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 58 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-12-15 | TEL.13501/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0081/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 151030400 | 151030400 | 151030400 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 65 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-12-15 | TEL.15952/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0082/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 229000000 | 229000000 | 229000000 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 67 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-12-15 | TEL.15951/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0083/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 4200000 | 4200000 | 4200000 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 17 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 90 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-01 | 2021-09-17 | TEL.26763/LG.320/PND-10320000/2021 | 2021-10-14 | TEL.0406/LG.320/DID-00000000/2021 | 2021-10-14 | 4555304412 | 515290788 | 5070595200 | 5070595200 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-10-22
12021230 | 7 | 22 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 90 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-01 | 2021-09-17 | TEL.26789/LG.320/PND-10320000/2021 | 2021-10-14 | TEL.0407/LG.320/DID-00000000/2021 | 2021-10-14 | 2061638422 | 284352738 | 2345991160 | 2345991160 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-10-22
12021230 | 7 | 64 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-12-15 | TEL.13301/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0079/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 11600000 | 11600000 | 11600000 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 19 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-09-21 | TEL.27570/LG.320/PND-10320000/2021 | 2021-12-20 | TEL.0073/LG.320/DID-A0000000/2021 | 2021-12-20 | 1125428254 | 140514406 | 1265942660 | 1265942660 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 20 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-09-22 | TEL.27465/LG.320/PND-10320000/2021 | 2021-12-20 | TEL.0074/LG.320/DID-A0000000/2021 | 2021-12-20 | 3788486975 | 460161011 | 4248647986 | 4248647986 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 77 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-12-15 | TEL.13302/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0075/LG.320/DID-A0000000/2021 | 2021-12-20 | 73600000 | 6400000 | 80000000 | 80000000 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 21 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-01 | 2021-09-17 | TEL.27566/LG.320/PND-10320000/2021 | 2021-10-26 | TEL.0076/LG.320/DID-A0000000/2021 | 2021-10-26 | 5938964730 | 712675854 | 6651640584 | 6651640584 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 23 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-09-22 | TEL.15202/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0077/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 3354000000 | 3354000000 | 3354000000 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 24 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 100 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-21 | 2021-09-21 | TEL.13652/LG.320/DID-A1043000/2021 | 2021-12-20 | TEL.0078/LG.320/DID-A0000000/2021 | 2021-12-20 | 0 | 2939191390 | 2939191390 | 2939191390 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-23
12021230 | 7 | 18 | 01C11J04 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | WIRELESS ACCESS DEPLOYMENT | DATA & INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004204/HK.810/OPS-10050000/2021 | Kontrak ISP Support PON Papua | 2021-07-13 | 2021-12-30 | ISP Support PON Papua | JAYAPURA | PAPUA |  | TREG-7 |  | 90 | 100 | 100 | BAST-1 | 2021-08-20 | 2021-12-01 | 2021-09-17 | TEL.27562/LG.320/PND-10320000/2021 | 2021-10-26 | TEL.0427/LG.320/DID-00000000/2021 | 2021-10-26 | 2663281068 | 404945100 | 3068226168 | 3068226168 | 4500432401 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-10-28
12021235 | 7 | 71 | 01C11I01 | 019 | 73010122 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | AMBON | LABUHA |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 272102479 | 22164468 | 294266947 | 294266947 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 425 | 01C11I01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | GORONTALO | GORONTALO |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 393736800 | 7678490 | 401415290 | 401415290 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 214 | 01C11I01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | GORONTALO | ISIMU |  | ASPARAGA 1 & 2 SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 215154856 | 27906856 | 243061712 | 243061712 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 216 | 01C11I01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | GORONTALO | ISIMU |  | PARIS SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 215154856 | 27906856 | 243061712 | 243061712 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 426 | 01C11I01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | GORONTALO | MARISA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0284/LG.320/DID-A0000000/2021 | 2021-12-28 | 173094720 | 3071396 | 176166116 | 176166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 215 | 01C11I01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | GORONTALO | MARISA |  | DULUPI SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 128607496 | 26371158 | 154978654 | 154978654 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 427 | 01C11I01 | 019 | 72020038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | GORONTALO | TELAGA |  | SS#3 GPON CARD |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0284/LG.320/DID-A0000000/2021 | 2021-12-28 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 248 | 01C11I01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | BAU-BAU |  | EREKE SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 434019132 | 46473660 | 480492792 | 480492792 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 251 | 01C11I01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | BAU-BAU |  | MAWASANGKA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 225959566 | 28600427 | 254559993 | 254559993 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 443 | 01C11I01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | BAU-BAU |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-18 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 367736800 | 7678490 | 375415290 | 375415290 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 219 | 01C11I01 | 019 | 72050084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | BULUKUMBA |  | PALAMPANG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 212959566 | 28595833 | 241555399 | 241555399 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 250 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | MANDONGA |  | MASAGENA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 444 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | MANDONGA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-18 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 220642080 | 4607094 | 225249174 | 225249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 286 | 01C11I01 | 019 | 72050082 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | POMAALA |  | TANGKETADA SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 445 | 01C11I01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | RAHA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-18 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 249 | 01C11I01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | RAHA |  | LAWA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 27060135 | 153472341 | 153472341 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 252 | 01C11I01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | UNAAHA |  | MOWEWE SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.1252/LG.310/PND-C1030000/2021 | 2021-11-26 07:40 | TEL.0672/LG.320/DID-00000000/2021 | 2021-11-26 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 254 | 01C11I01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | UNAAHA |  | POLIPOLIA SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.1252/LG.310/PND-C1030000/2021 | 2021-11-26 07:40 | TEL.0672/LG.320/DID-00000000/2021 | 2021-11-26 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 253 | 01C11I01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | UNAAHA |  | ONEMBUTE SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 446 | 01C11I01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | UNAAHA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-18 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 406736800 | 7678490 | 414415290 | 414415290 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 247 | 01C11I01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | UNAAHA |  | LASOLO SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-16 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 447 | 01C11I01 | 019 | 72050074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | KENDARI | WANCI |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-18 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 263 | 01C11I01 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | AIR MADIDI |  | PERUM VIOLA GAHARU MAUMBI SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-28 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 26366564 | 156978770 | 156978770 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 450 | 01C11I01 | 019 | 72010258 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | BEO |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-14 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 259642080 | 4607094 | 264249174 | 264249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 268 | 01C11I01 | 019 | 72010267 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | HULU SIAU |  | KOMPLEK BANDARA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 26361970 | 152774176 | 152774176 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 258 | 01C11I01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | KOTAMOBAGU |  | KOSIO SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-28 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 215154856 | 27906856 | 243061712 | 243061712 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 262 | 01C11I01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | KOTAMOBAGU |  | PEMKAB BOLSEL SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 212959566 | 27897668 | 240857234 | 240857234 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 449 | 01C11I01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | KOTAMOBAGU |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-23 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 173094720 | 3071396 | 176166116 | 176166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 269 | 01C11I01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | KOTAMOBAGU |  | BOROKO SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-28 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 217159566 | 27902262 | 245061828 | 245061828 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 451 | 01C11I01 | 019 | 72010055 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | LANGOAN |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-14 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 173094720 | 3071396 | 176166116 | 176166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 448 | 01C11I01 | 019 | 72010077 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | MOLIBAGU |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-23 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 452 | 01C11I01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | PANIKI |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-23 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 261 | 01C11I01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | PANIKI |  | PANDU SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-28 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 212383496 | 15379302 | 227762798 | 227762798 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 267 | 01C11I01 | 019 | 72010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | TAHUNA |  | TAMAKO SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 123962206 | 13839010 | 137801216 | 137801216 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 264 | 01C11I01 | 019 | 72010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | TAHUNA |  | PETA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 26361970 | 152774176 | 152774176 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 260 | 01C11I01 | 019 | 72010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | TAHUNA |  | MANGANITU SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 26361970 | 152774176 | 152774176 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 259 | 01C11I01 | 019 | 72010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | TAHUNA |  | KUMA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 26361970 | 152774176 | 152774176 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 73 | 01C11I01 | 019 | 72010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | MANADO | TAHUNA |  | SS#1 BIG OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 178787119 | 20388770 | 199175889 | 199175889 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 66 | 01C11I01 | 019 | 72030159 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | AMPANA |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 175896119 | 19835070 | 195731189 | 195731189 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 436 | 01C11I01 | 019 | 72030159 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | AMPANA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-23 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 67 | 01C11I01 | 019 | 72030124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | BUNTA |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-27 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 173226119 | 19649270 | 192875389 | 192875389 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 437 | 01C11I01 | 019 | 72030013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | BUOL |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-08 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 438 | 01C11I01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | KOLONODALE |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-23 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 173094720 | 3071396 | 176166116 | 176166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 65 | 01C11I01 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | KOTARAYA |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 256057479 | 20907672 | 276965151 | 276965151 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 69 | 01C11I01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | LUWUK |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 258280479 | 21241968 | 279522447 | 279522447 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 439 | 01C11I01 | 019 | 72030050 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | MOUTONG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-08 | TEL.1145/LG.310/PND-C1030000/2021 | 2021-10-28 09:18 | TEL.0439/LG.320/DID-00000000/2021 | 2021-10-28 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-10-29
12021235 | 7 | 440 | 01C11I01 | 019 | 72030103 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | PALU A |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-08 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 160094720 | 3071396 | 163166116 | 163166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 441 | 01C11I01 | 019 | 72030092 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | PALU B |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-05 | TEL.1145/LG.310/PND-C1030000/2021 | 2021-10-28 09:18 | TEL.0439/LG.320/DID-00000000/2021 | 2021-10-28 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-10-29
12021235 | 7 | 245 | 01C11I01 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | POSO |  | TAMBARANA SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 212959566 | 28595833 | 241555399 | 241555399 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 442 | 01C11I01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | TAWAELI |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-05 | TEL.1145/LG.310/PND-C1030000/2021 | 2021-10-28 09:18 | TEL.0439/LG.320/DID-00000000/2021 | 2021-10-28 | 294189440 | 6142792 | 300332232 | 300332232 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-10-29
12021235 | 7 | 243 | 01C11I01 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | TENTENA |  | PADANJAYA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 128286136 | 27064729 | 155350865 | 155350865 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 244 | 01C11I01 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | TENTENA |  | PENDOLO SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 214833496 | 28600427 | 243433923 | 243433923 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 68 | 01C11I01 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | TINOMBO |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 171275119 | 19660470 | 190935589 | 190935589 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 70 | 01C11I01 | 019 | 72030126 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | TOILI |  | SS#1 BIG OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 354497839 | 23914966 | 378412805 | 378412805 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 468 | 01C11I01 | 019 | 72030083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PALU | TOLAY |  | SS#3 GPON CARD |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-05 | TEL.1145/LG.310/PND-C1030000/2021 | 2021-10-28 09:18 | TEL.0439/LG.320/DID-00000000/2021 | 2021-10-28 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-10-29
12021235 | 7 | 428 | 01C11I01 | 019 | 72040044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | CANGADI |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-22 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 239 | 01C11I01 | 019 | 72040044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | CANGADI |  | TAKKALALA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-20 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 429 | 01C11I01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | ENREKANG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-22 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 220642080 | 4607094 | 225249174 | 225249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 241 | 01C11I01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | ENREKANG |  | CAKKE SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-20 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 19204904 | 158617110 | 158617110 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 236 | 01C11I01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MAJENE |  | PAMBOANG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 238 | 01C11I01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MAJENE |  | SENDANA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 234 | 01C11I01 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MAKALE |  | MATANA (MLE019) SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-20 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 128162206 | 13843604 | 142005810 | 142005810 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 62 | 01C11I01 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MAKALE |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-11-22 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 170235119 | 19500470 | 189735589 | 189735589 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 235 | 01C11I01 | 019 | 72040082 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MALILI |  | ONGKONA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 430 | 01C11I01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MAMUJU |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 232 | 01C11I01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MAMUJU |  | KAROSSA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-20 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 225959566 | 28600427 | 254559993 | 254559993 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 240 | 01C11I01 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | MASAMBA |  | TOMONI SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 431 | 01C11I01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | PALOPO |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-18 | TEL.1250/LG.310/PND-C1030000/2021 | 2021-11-26 07:40 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 220642080 | 4607094 | 225249174 | 225249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 233 | 01C11I01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | PALOPO |  | LAROMPONG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 237 | 01C11I01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | PALOPO |  | PATTEDONG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-23 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 27064729 | 166476935 | 166476935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 432 | 01C11I01 | 019 | 72040135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | RAPPANG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-22 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 61 | 01C11I01 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | SENGKANG |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-11-22 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 264879479 | 21658268 | 286537747 | 286537747 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 63 | 01C11I01 | 019 | 72040160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | SIWA |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-11-22 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 173487119 | 19800470 | 193287589 | 193287589 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 434 | 01C11I01 | 019 | 72040174 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | TANRUTEDONG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-22 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 220642080 | 4607094 | 225249174 | 225249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 64 | 01C11I01 | 019 | 72040280 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | TOPOYO |  | SS#1 BIG OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-12-07 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 254283479 | 20618268 | 274901747 | 274901747 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 435 | 01C11I01 | 019 | 72040186 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | PARE-PARE | WATANSOPPENG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-11-22 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 256 | 01C11I01 | 019 | 73020013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | LABUHA |  | BABANG & WAYAMIGA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-26 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 128286136 | 19204904 | 147491040 | 147491040 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 72 | 01C11I01 | 019 | 73020032 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | SANANA |  | SS#1 BIG OLT |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-11-26 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 266097729 | 21780108 | 287877837 | 287877837 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 266 | 01C11I01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | SOFIFI |  | SUBAIM SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-18 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 217159566 | 27902262 | 245061828 | 245061828 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 453 | 01C11I01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | TERNATE |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-13 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 220642080 | 4607094 | 225249174 | 225249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 265 | 01C11I01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | TERNATE |  | PULAU HIRI SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-26 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 139412206 | 26366564 | 165778770 | 165778770 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 454 | 01C11I01 | 019 | 73020044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | TOBELO |  | SS#3 GPON CARD |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-14 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0284/LG.320/DID-A0000000/2021 | 2021-12-28 | 173094720 | 3071396 | 176166116 | 176166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 257 | 01C11I01 | 019 | 73020044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | TERNATE | TOBELO |  | BANDARA KAO SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-18 | TEL.0095/LG.310/DID-C0200000/2021 | 2021-12-29 08:18 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 212959566 | 27897668 | 240857234 | 240857234 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 455 | 01C11I01 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | ANTANG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 456 | 01C11I01 | 019 | 72080009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | BANTAENG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 457 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 160094720 | 3071396 | 163166116 | 163166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 230 | 01C11I01 | 019 | 72080054 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | JENEPONTO |  | TONRO KASSI TIMUR SS#2 MINI OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 128286136 | 27064729 | 155350865 | 155350865 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 458 | 01C11I01 | 019 | 72080054 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | JENEPONTO |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 60 | 01C11I01 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | MAROS |  | SS#1 BIG OLT |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-28 | 2021-11-12 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0282/LG.320/DID-A0000000/2021 | 2021-12-28 | 260034479 | 21336168 | 281370647 | 281370647 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 220 | 01C11I01 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | MAROS |  | BOSOWA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-12 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 128286136 | 27064729 | 155350865 | 155350865 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 459 | 01C11I01 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | MAROS |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 466 | 01C11I01 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | PANAKUKANG |  | SS#3 GPON CARD |  | 90 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 220642080 | 4607094 | 225249174 | 225249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 460 | 01C11I01 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | PANGKEP |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 86547360 | 1535698 | 88083058 | 88083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 461 | 01C11I01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SELAYAR |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 73547360 | 1535698 | 75083058 | 75083058 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 221 | 01C11I01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SELAYAR |  | TILE-TILE SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 27060135 | 153472341 | 153472341 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 229 | 01C11I01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SELAYAR |  | BONTOMANAI SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 27060135 | 153472341 | 153472341 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 462 | 01C11I01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SINJAI |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 222 | 01C11I01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SINJAI |  | LAPPEATA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-07 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 123962206 | 21698835 | 145661041 | 145661041 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 223 | 01C11I01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SINJAI |  | TONRA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-07 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 123962206 | 21698835 | 145661041 | 145661041 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 224 | 01C11I01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUDIANG |  | TANRALILI SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-11-12 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 130612206 | 27064729 | 157676935 | 157676935 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 463 | 01C11I01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUDIANG |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 147094720 | 3071396 | 150166116 | 150166116 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 226 | 01C11I01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUNGGUMINASA |  | LIMBUNG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-22 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 213280926 | 28600427 | 241881353 | 241881353 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 225 | 01C11I01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUNGGUMINASA |  | GRIYA PATTALLASSANG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-22 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 217159566 | 28600427 | 245759993 | 245759993 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 464 | 01C11I01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUNGGUMINASA |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 294189440 | 6142792 | 300332232 | 300332232 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021235 | 7 | 227 | 01C11I01 | 019 | 72080120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | TAKALAR |  | BONTORITA SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-24 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 27060135 | 153472341 | 153472341 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 228 | 01C11I01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | WATAMPONE |  | KAWERANG SS#2 MINI OLT |  | 85 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-31 | 2021-12-07 | TEL.0086/LG.310/DID-C0200000/2021 | 2021-12-28 16:50 | TEL.0283/LG.320/DID-A0000000/2021 | 2021-12-29 | 126412206 | 27060135 | 153472341 | 153472341 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-12-30
12021235 | 7 | 465 | 01C11I01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004379/HK.810/OPS-10000000/2021 | SP#2 GPON-XGPON-XGSPON Platform Fiberhome | 2021-07-19 | 2022-01-14 | GPON-XGPON-XGSPON | UJUNGPANDANG | WATAMPONE |  | SS#3 GPON CARD |  | 80 | 100 | 100 | BAST-1 | 2021-07-19 | 2022-01-20 | 2021-10-04 | TEL.1242/LG.310/PND-C1030000/2021 | 2021-11-25 15:52 | TEL.0673/LG.320/DID-00000000/2021 | 2021-11-26 | 259642080 | 4607094 | 264249174 | 264249174 | 4500432400 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI | 2021-11-29
12021276 | 14 | 125 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | AMBON | AMBON |  | ME2-D7-AMB |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.1851/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0563/LG.320/DID-00000000/2021 | 2021-10-30 | 416643500 | 41664350 | 458307850 | 458307850 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 127 | 01C11B01 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | AMBON | MASOHI |  | ME-D7-MSH |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.1851/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0563/LG.320/DID-00000000/2021 | 2021-10-30 | 518543300 | 51854330 | 570397630 | 570397630 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 151 | 01C11B01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | AMBON | PASSO |  | ME-D7-PAO |  | 100 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-03-31 | 2022-01-04 | TEL.302/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0431/LG.320/DID-A0000000/2022 | 2022-03-25 | 621313240 | 62131324 | 683444564 | 683444564 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021276 | 14 | 147 | 01C11B01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | AMBON | PASSO |  | ME-D7-PAO |  | 50 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-08-20 | 2022-01-10 | TEL.1178/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1149/LG.320/DID-A0000000/2022 | 2022-07-27 | 282501600 | 17450160 | 299951760 | 299951760 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021276 | 14 | 149 | 01C11B01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | GORONTALO | ISIMU |  | ME-D7-IMU |  | 50 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-08-20 | 2022-01-10 | TEL.1178/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1149/LG.320/DID-A0000000/2022 | 2022-07-27 | 282501600 | 17450160 | 299951760 | 299951760 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021276 | 14 | 53 | 01C11B01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | ABEPURA |  | ME-D7-ABE |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.2141/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0033/LG.320/DID-A0000000/2021 | 2021-12-10 | 0 | 75000000 | 75000000 | 75000000 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-22
12021276 | 14 | 36 | 01C11B01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | ABEPURA |  | ME-D7-ABE |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-11-10 | 2021-08-26 | TEL.1850/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0562/LG.320/DID-00000000/2021 | 2021-10-30 | 2372621680 | 226462168 | 2599083848 | 2599083848 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 52 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | JAYAPURA |  | ME2-D7-JAP |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.2141/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0033/LG.320/DID-A0000000/2021 | 2021-12-10 | 0 | 30000000 | 30000000 | 30000000 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-22
12021276 | 14 | 33 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | JAYAPURA |  | ME-D7-JAP |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 1032967000 | 103296700 | 1136263700 | 1136263700 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 31 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | JAYAPURA |  | ME2-D7-JAP |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.2044/LG.310/PND-B1050000/2021 | 2021-11-26 | TEL.0756/LG.320/DID-00000000/2021 | 2021-11-26 | 584428640 | 58442864 | 642871504 | 642871504 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-11-30
12021276 | 14 | 34 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | JAYAPURA |  | ME3-D7-JAP |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 1032967000 | 103296700 | 1136263700 | 1136263700 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 32 | 01C11B01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | SENTANI |  | ME-D7-STN |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 187739440 | 18773944 | 206513384 | 206513384 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 35 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | TIMIKA |  | ME-D7-TMK |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 536985600 | 53698560 | 590684160 | 590684160 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 38 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | TIMIKA |  | ME9-D7-TMK |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.2140/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0032/LG.320/DID-A0000000/2021 | 2021-12-10 | 3473477180 | 336532928 | 3810010108 | 3810010108 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-22
12021276 | 14 | 55 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | JAYAPURA | TIMIKA |  | ME9-D7-TMK |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.2141/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0033/LG.320/DID-A0000000/2021 | 2021-12-10 | 0 | 75000000 | 75000000 | 75000000 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-22
12021276 | 14 | 148 | 01C11B01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | KENDARI | BAU-BAU |  | ME-D7-BAU |  | 50 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-08-20 | 2022-01-10 | TEL.1178/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1149/LG.320/DID-A0000000/2022 | 2022-07-27 | 282501600 | 17450160 | 299951760 | 299951760 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021276 | 14 | 150 | 01C11B01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | MANADO | KOTAMOBAGU |  | ME-D7-KTG |  | 50 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-08-20 | 2022-01-10 | TEL.1178/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1149/LG.320/DID-A0000000/2022 | 2022-07-27 | 282501600 | 17450160 | 299951760 | 299951760 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021276 | 14 | 30 | 01C11B01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | MANOKWARI | MANOKWARI |  | ME-D7-MWR |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.2044/LG.310/PND-B1050000/2021 | 2021-11-26 | TEL.0756/LG.320/DID-00000000/2021 | 2021-11-26 | 186227440 | 18622744 | 204850184 | 204850184 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-11-30
12021276 | 14 | 123 | 01C11B01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | MERAUKE | MERAUKE |  | ME-D7-MRK |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.2044/LG.310/PND-B1050000/2021 | 2021-11-26 | TEL.0756/LG.320/DID-00000000/2021 | 2021-11-26 | 184715440 | 18471544 | 203186984 | 203186984 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-11-30
12021276 | 14 | 37 | 01C11B01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | MERAUKE | MERAUKE |  | ME-D7-MRK |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-11-10 | 2021-08-26 | TEL.1850/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0562/LG.320/DID-00000000/2021 | 2021-10-30 | 1320684680 | 121268468 | 1441953148 | 1441953148 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 54 | 01C11B01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | MERAUKE | MERAUKE |  | ME-D7-MRK |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.2141/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0033/LG.320/DID-A0000000/2021 | 2021-12-10 | 0 | 75000000 | 75000000 | 75000000 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-22
12021276 | 14 | 48 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | SORONG | SORONG |  | ME-D7-SRG |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.2141/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0033/LG.320/DID-A0000000/2021 | 2021-12-10 | 0 | 30000000 | 30000000 | 30000000 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-22
12021276 | 14 | 28 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | SORONG | SORONG |  | ME-D7-SRG |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 805050190 | 80505019 | 885555209 | 885555209 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 29 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | SORONG | SORONG |  | ME2-D7-SRG |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.2044/LG.310/PND-B1050000/2021 | 2021-11-26 | TEL.0756/LG.320/DID-00000000/2021 | 2021-11-26 | 907523350 | 90752335 | 998275685 | 998275685 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-11-30
12021276 | 14 | 126 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | TERNATE | TERNATE |  | ME3-D7-TNT |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-20 | 2021-08-26 | TEL.1851/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0563/LG.320/DID-00000000/2021 | 2021-10-30 | 518543300 | 51854330 | 570397630 | 570397630 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 26 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | UJUNGPANDANG | BALAIKOTA |  | ME3-D7-BAL |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 50504000 | 5050400 | 55554400 | 55554400 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021276 | 14 | 27 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005353/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-1 2021 | 2021-08-26 | 2022-08-20 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME3-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-08-26 | 2021-12-10 | 2021-08-26 | TEL.1849/LG.310/PND-B1050000/2021 | 2021-10-30 | TEL.0561/LG.320/DID-00000000/2021 | 2021-10-30 | 50504000 | 5050400 | 55554400 | 55554400 | 4500435595 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-10-31
12021284 | 6 | 14 | 01C11H06 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | ABEPURA |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-09-03 | TEL.2992/LG.310/DID-B1060000/2021 | 2021-10-26 | TEL.0430/LG.320/DID-00000000/2021 | 2021-10-26 | 1396953400 | 132384396 | 1529337796 | 1529337796 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 19 | 01C11H06 | 019 | 74030165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | CLS TIMIKA |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2982/LG.310/DID-B1060000/2021 | 2021-10-25 | TEL.0431/LG.320/DID-00000000/2021 | 2021-10-25 | 1216699300 | 104108996 | 1320808296 | 1320808296 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 15 | 01C11H06 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | JAYAPURA-1 |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-09-03 | TEL.2992/LG.310/DID-B1060000/2021 | 2021-10-26 | TEL.0430/LG.320/DID-00000000/2021 | 2021-10-26 | 1200090046 | 106912358 | 1307002404 | 1307002404 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 18 | 01C11H06 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | KUALA KENCANA |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2982/LG.310/DID-B1060000/2021 | 2021-10-25 | TEL.0431/LG.320/DID-00000000/2021 | 2021-10-25 | 92239568 | 6899628 | 99139196 | 99139196 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 12 | 01C11H06 | 019 | 74030171 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | NGN JAYAPURA - STO JAYAPURA-1 |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2992/LG.310/DID-B1060000/2021 | 2021-10-26 | TEL.0430/LG.320/DID-00000000/2021 | 2021-10-26 | 1191808470 | 116343897 | 1308152367 | 1308152367 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 13 | 01C11H06 | 019 | 74030184 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | STO SENTANI |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2992/LG.310/DID-B1060000/2021 | 2021-10-26 | TEL.0430/LG.320/DID-00000000/2021 | 2021-10-26 | 436012700 | 45800499 | 481813199 | 481813199 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 17 | 01C11H06 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | TIMIKA |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2982/LG.310/DID-B1060000/2021 | 2021-10-25 | TEL.0431/LG.320/DID-00000000/2021 | 2021-10-25 | 174516736 | 13060958 | 187577694 | 187577694 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 20 | 01C11H06 | 019 | 74030131 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | TIMIKA TTC |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2982/LG.310/DID-B1060000/2021 | 2021-10-25 | TEL.0431/LG.320/DID-00000000/2021 | 2021-10-25 | 1459381204 | 122267286 | 1581648490 | 1581648490 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
12021284 | 6 | 11 | 01C11H06 | 019 | 74030179 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.005536/HK.810/OPS-10000000/2021 | SP#8 DWDM dan OTN Platform ZTE - OLO, Trunk Metro & IPBB | 2021-09-03 | 2022-01-30 | DWDM & OTN | JAYAPURA | TTC JAYAPURA |  |  |  | 45 | 100 | 100 | BAST-1 | 2021-09-04 | 2022-02-08 | 2021-10-05 | TEL.2992/LG.310/DID-B1060000/2021 | 2021-10-26 | TEL.0430/LG.320/DID-00000000/2021 | 2021-10-26 | 860953600 | 90773998 | 951727598 | 951727598 | 4500435878 |  |  |  |  | ZTE INDONESIA | 2021-10-28
G2021202 | 3 | 6 | 01E07V06 | 007 | 74030162 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.005568/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Lastmile HEM Muara Tami Skouw Area Witel Papua | 2021-09-06 | 2022-02-06 | HEM | JAYAPURA | JAYAPURA |  | R7 JYP JAP HEM POS BATAS SKOUW |  | 100 | 100 | 100 | BAST-1 | 2021-09-06 | 2021-12-04 | 2021-12-01 | TEL.692/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0034/LG.320/DR7-10400000/2022 | 2022-03-04 | 2254743427 | 455768083 | 2710511510 | 2710511510 | 4500436486 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-12
G2021203 | 7 | 7 | 01E07V04 | 007 | 73010013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005662/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan NIQE 5 LOP Area Witel Maluku | 2021-09-09 | 2022-03-31 | BACKBONE NIQE | AMBON | BULA |  | R7 AMB BUL NAMTO KELAPA SAWIT |  | 100 | 100 | 100 | BAST-1 | 2021-09-09 | 2021-12-07 | 2021-12-01 | TEL.006/LG.310/DR7-12700000/2022 | 2022-01-12 | TEL.0002/LG.320/DR7-10400000/2022 | 2022-01-12 | 87252035 | 17389726 | 104641761 | 104641761 | 4500436681 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021203 | 7 | 6 | 01E07V04 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005662/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan NIQE 5 LOP Area Witel Maluku | 2021-09-09 | 2022-03-31 | BACKBONE NIQE | AMBON | MASOHI |  | R7 AMB MSH KM 84-90 |  | 100 | 100 | 100 | BAST-1 | 2021-09-09 | 2021-12-07 | 2021-12-01 | TEL.1095/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0119/LG.320/DR7-10400000/2022 | 2022-07-07 | 382459479 | 69560214 | 452019693 | 452019693 | 4500436681 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-26
G2021203 | 7 | 9 | 01E07V04 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005662/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan NIQE 5 LOP Area Witel Maluku | 2021-09-09 | 2022-03-31 | BACKBONE NIQE | AMBON | MASOHI |  | R7 AMB MSH TALA |  | 100 | 100 | 100 | BAST-1 | 2021-09-09 | 2021-12-07 | 2021-12-01 | TEL.007/LG.310/DR7-12700000/2022 | 2022-01-12 | TEL.0002/LG.320/DR7-10400000/2022 | 2022-01-12 | 240564754 | 41654732 | 282219486 | 282219486 | 4500436681 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021203 | 7 | 12 | 01E07V04 | 007 | 73010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005662/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan NIQE 5 LOP Area Witel Maluku | 2021-09-09 | 2022-03-31 | BACKBONE NIQE | AMBON | NAMROLE |  | R7 AMB NMR NAMROLE KM 53 |  | 100 | 100 | 100 | BAST-1 | 2021-09-09 | 2021-12-07 | 2021-12-01 | TEL.009/LG.310/DR7-12700000/2022 | 2022-01-12 | TEL.0002/LG.320/DR7-10400000/2022 | 2022-01-12 | 24531540 | 7493544 | 32025084 | 32025084 | 4500436681 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021203 | 7 | 11 | 01E07V04 | 007 | 73010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005662/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan NIQE 5 LOP Area Witel Maluku | 2021-09-09 | 2022-03-31 | BACKBONE NIQE | AMBON | NAMROLE |  | R7 AMB NMR NAMROLE KM 35 |  | 100 | 100 | 100 | BAST-1 | 2021-09-09 | 2021-12-07 | 2021-12-01 | TEL.008/LG.310/DR7-12700000/2022 | 2022-01-12 | TEL.0002/LG.320/DR7-10400000/2022 | 2022-01-12 | 480340206 | 84392142 | 564732348 | 564732348 | 4500436681 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021208 | 2 | 11 | 01E07V04 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005871/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 5 LoP Area Witel Makassar & Sulselbar | 2021-09-17 | 2022-01-28 | BACKBONE NIQE | PARE-PARE | MALILI |  | R7 PRE MLI MALILI LATOWU KM 56-57 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2021-11-28 | 2022-01-01 | TEL.565/LG.310/DR7-12700000/2022 | 2022-01-18 | TEL.0009/LG.320/DR7-10400000/2022 | 2022-01-18 | 28715645 | 10397330 | 39112975 | 39112975 | 4500437282 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-01-28
G2021208 | 2 | 10 | 01E07V04 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005871/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 5 LoP Area Witel Makassar & Sulselbar | 2021-09-17 | 2022-01-28 | BACKBONE NIQE | PARE-PARE | MALILI |  | R7 PRE MLI MALILI LATOWU KM 52-54 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2021-11-28 | 2022-01-01 | TEL.564/LG.310/DR7-12700000/2022 | 2022-01-18 | TEL.0009/LG.320/DR7-10400000/2022 | 2022-01-18 | 140017402 | 24911489 | 164928891 | 164928891 | 4500437282 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-01-28
G2021208 | 2 | 9 | 01E07V04 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005871/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 5 LoP Area Witel Makassar & Sulselbar | 2021-09-17 | 2022-01-28 | BACKBONE NIQE | PARE-PARE | MALILI |  | R7 PRE MLI MALILI LATOWU KM 49-50 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2021-11-28 | 2022-01-01 | TEL.563/LG.310/DR7-12700000/2022 | 2022-01-18 | TEL.0009/LG.320/DR7-10400000/2022 | 2022-01-18 | 103655607 | 20134308 | 123789915 | 123789915 | 4500437282 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-01-28
G2021208 | 2 | 7 | 01E07V04 | 007 | 72080075 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005871/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 5 LoP Area Witel Makassar & Sulselbar | 2021-09-17 | 2022-01-28 | BACKBONE NIQE | UJUNGPANDANG | MALINO |  | R7 MKS MAL PAKATTO MALINO KM 19-21 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2021-11-28 | 2022-01-01 | TEL.561/LG.310/DR7-12700000/2022 | 2022-01-18 | TEL.0009/LG.320/DR7-10400000/2022 | 2022-01-18 | 167463648 | 28398041 | 195861689 | 195861689 | 4500437282 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-01-28
G2021208 | 2 | 8 | 01E07V04 | 007 | 72080075 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005871/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 5 LoP Area Witel Makassar & Sulselbar | 2021-09-17 | 2022-01-28 | BACKBONE NIQE | UJUNGPANDANG | MALINO |  | R7 MKS MAL PAKATTO MALINO KM 29-30 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2021-11-28 | 2022-01-01 | TEL.562/LG.310/DR7-12700000/2022 | 2022-01-18 | TEL.0009/LG.320/DR7-10400000/2022 | 2022-01-18 | 61408238 | 12330081 | 73738319 | 73738319 | 4500437282 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-01-28
G2021209 | 2 | 13 | 01E07V04 | 007 | 72030099 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | KOTARAYA |  | SANTIGI-KOTARAYA |  | 100 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-01-06 | 2021-12-22 | TEL.011/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 46283687 | 11374400 | 57658087 | 57658087 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 8 | 01E07V04 | 007 | 72030125 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | PAGIMANA |  | PAGIMANA - LUWUK |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2022-01-04 | 2021-10-01 | TEL.012/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 774039181 | 94957820 | 868997001 | 868997001 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 9 | 01E07V04 | 007 | 72030058 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | PALU |  | ASAM - TAWANJU |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2022-01-04 | 2021-10-01 | TEL.013/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 60925705 | 14898913 | 75824618 | 75824618 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 7 | 01E07V04 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | PARIGI |  | PALU- PARIGI |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2022-01-03 | 2021-10-01 | TEL.014/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 1367296170 | 145215466 | 1512511636 | 1512511636 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 10 | 01E07V04 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | PARIGI |  | PARIGI - SAU JT11 - JT15 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2022-01-04 | 2021-10-01 | TEL.015/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 350981167 | 54805687 | 405786854 | 405786854 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 11 | 01E07V04 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | PARIGI |  | SANTIGI JT01-JT06 |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2022-01-04 | 2021-10-01 | TEL.016/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 288713672 | 35935482 | 324649154 | 324649154 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 6 | 01E07V04 | 007 | 72030139 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | TENTENA |  | TENTENA - SAMPURAGA |  | 100 | 100 | 100 | BAST-1 | 2021-09-17 | 2022-01-04 | 2021-10-01 | TEL.017/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 456372222 | 52950042 | 509322264 | 509322264 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021209 | 2 | 12 | 01E07V04 | 007 | 72030084 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005872/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 6 LoP Area Witel Sulteng | 2021-09-17 | 2022-02-03 | BACKBONE NIQE | PALU | TOLI-TOLI |  | KOTARAYA-TOLITOLI |  | 100 | 100 | 100 | BAST-1 | 2021-12-06 | 2022-01-10 | 2021-12-22 | TEL.018/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0012/LG.320/DR7-10400000/2022 | 2022-01-14 | 375121662 | 43092094 | 418213756 | 418213756 | 4500437283 |  |  |  |  | PERKONSUMA | 2022-01-31
G2021213 | 1 | 6 | 01E07V04 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005952/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring Timur TR-7 2 LoP Area Witel Papua Barat | 2021-09-21 | 2021-10-20 | PALAPA RING | SORONG | NABIRE |  | LASTMILE STO-SB NABIRE |  | 100 | 100 | 100 | BAST-1 | 2021-09-21 | 2021-10-18 | 2021-12-01 | TEL.002/LG.310/DR7-12700000/2021 | 2022-01-06 | TEL.0003/LG.320/DR7-10400000/2022 | 2022-01-06 | 5885121 | 3317722 | 9202843 | 9202843 | 4500437542 |  |  |  |  | TELKOM AKSES | 2022-01-27
G2021213 | 1 | 7 | 01E07V04 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.005952/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP Palapa Ring Timur TR-7 2 LoP Area Witel Papua Barat | 2021-09-21 | 2021-10-20 | PALAPA RING | SORONG | SORONG |  | LASTMILE STO TO MSC (SB SORC) |  | 100 | 100 | 100 | BAST-1 | 2021-09-21 | 2021-10-19 | 2021-12-01 | TEL.003/LG.310/DR7-12700000/2021 | 2022-01-06 | TEL.0003/LG.320/DR7-10400000/2022 | 2022-01-06 | 17226820 | 11036514 | 28263334 | 28263334 | 4500437542 |  |  |  |  | TELKOM AKSES | 2022-01-27
12021302 | 10 | 128 | 01C11H04 | 019 | 72020072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006167/HK.810/OPS-10000000/2021 | Kontrak OSP FO Backbone, RMJ dan Last Mile | 2021-09-27 | 2022-10-31 | OSP FO Backbone | GORONTALO | BULUWATU |  |  |  | 55 | 69 | 0 | Instalasi | 2021-11-01 | 2022-09-19 | 2021-11-01 |  |  |  |  | 4295370359 | 3930666737 | 8226037096 | 0 | 4500436282 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021302 | 10 | 131 | 01C11H04 | 019 | 72020075 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006167/HK.810/OPS-10000000/2021 | Kontrak OSP FO Backbone, RMJ dan Last Mile | 2021-09-27 | 2022-10-31 | OSP FO Backbone | GORONTALO | HULUBALANG |  |  |  | 55 | 64.5 | 0 | Instalasi | 2021-11-01 | 2022-11-02 | 2021-11-01 |  |  |  |  | 4030474120 | 5391504439 | 9421978559 | 0 | 4500436282 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021302 | 10 | 127 | 01C11H04 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006167/HK.810/OPS-10000000/2021 | Kontrak OSP FO Backbone, RMJ dan Last Mile | 2021-09-27 | 2022-10-31 | OSP FO Backbone | GORONTALO | ISIMU |  |  |  | 55 | 64.5 | 0 | Instalasi | 2021-11-01 | 2022-10-19 | 2021-11-01 |  |  |  |  | 5466909297 | 6055982498 | 11522891795 | 0 | 4500436282 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021302 | 10 | 129 | 01C11H04 | 019 | 72020073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006167/HK.810/OPS-10000000/2021 | Kontrak OSP FO Backbone, RMJ dan Last Mile | 2021-09-27 | 2022-10-31 | OSP FO Backbone | GORONTALO | KASIA |  |  |  | 55 | 64.5 | 0 | Instalasi | 2021-11-01 | 2022-09-23 | 2021-11-01 |  |  |  |  | 2912430357 | 3764243697 | 6676674054 | 0 | 4500436282 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021302 | 10 | 130 | 01C11H04 | 019 | 72020074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006167/HK.810/OPS-10000000/2021 | Kontrak OSP FO Backbone, RMJ dan Last Mile | 2021-09-27 | 2022-10-31 | OSP FO Backbone | GORONTALO | TOULINGGULA |  |  |  | 55 | 64.5 | 0 | Instalasi | 2021-11-01 | 2022-09-23 | 2021-11-01 |  |  |  |  | 3870423405 | 5056657411 | 8927080816 | 0 | 4500436282 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021302 | 10 | 132 | 01C11H04 | 019 | 72030173 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006167/HK.810/OPS-10000000/2021 | Kontrak OSP FO Backbone, RMJ dan Last Mile | 2021-09-27 | 2022-10-31 | OSP FO Backbone | PALU | GADUNG |  |  |  | 55 | 64.5 | 0 | Instalasi | 2021-11-01 | 2022-11-02 | 2021-11-01 |  |  |  |  | 3917021877 | 3984936423 | 7901958300 | 0 | 4500436282 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
G2021219 | 4 | 14 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006257/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan QE RELOKASI 6 LoP Periode Agustus Area Witel Makassar - PT. TELKOM AKSES | 2021-09-29 | 2021-11-27 | QE RELOKASI | UJUNGPANDANG | BALAIKOTA |  | RELOKASI JARINGAN KABEL DEPAN AURI PERINTIS |  | 100 | 100 | 100 | BAST-1 | 2021-11-01 | 2021-11-18 | 2021-11-01 | TEL.395/LG310/R7W-7A330000/2021 | 2021-11-09 | TEL.0037/LG.320/R7W-7A100000/2021 | 2021-11-09 | 89589405 | 92109594 | 181698999 | 181698999 | 4500438505 |  |  |  |  | TELKOM AKSES | 2021-12-27
G2021219 | 4 | 10 | 01E07J04 | 007 | 72080054 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006257/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan QE RELOKASI 6 LoP Periode Agustus Area Witel Makassar - PT. TELKOM AKSES | 2021-09-29 | 2021-11-27 | QE RELOKASI | UJUNGPANDANG | JENEPONTO |  | RELOKASI ALPRO JALAN POROS JENEPONTO |  | 100 | 100 | 100 | BAST-1 | 2021-11-01 | 2021-11-21 | 2021-11-01 | TEL.396/LG310/R7W-7A330000/2021 | 2021-11-09 | TEL.0037/LG.320/R7W-7A100000/2021 | 2021-11-09 | 9288800 | 5612038 | 14900838 | 14900838 | 4500438505 |  |  |  |  | TELKOM AKSES | 2021-12-27
G2021219 | 4 | 8 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006257/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan QE RELOKASI 6 LoP Periode Agustus Area Witel Makassar - PT. TELKOM AKSES | 2021-09-29 | 2021-11-27 | QE RELOKASI | UJUNGPANDANG | KIMA |  | RELOKASI JARINGAN KABEL DEPAN AURI PERINTIS |  | 100 | 100 | 100 | BAST-1 | 2021-10-02 | 2021-10-22 | 2021-10-01 | TEL.391/LG310/R7W-7A330000/2021 | 2021-10-18 | TEL.0033/LG.320/R7W-7A100000/2021 | 2021-10-18 | 16947700 | 12568199 | 29515899 | 29515899 | 4500438505 |  |  |  |  | TELKOM AKSES | 2021-11-12
G2021219 | 4 | 13 | 01E07J04 | 007 | 72080075 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006257/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan QE RELOKASI 6 LoP Periode Agustus Area Witel Makassar - PT. TELKOM AKSES | 2021-09-29 | 2021-11-27 | QE RELOKASI | UJUNGPANDANG | MALINO |  | RELOKASI ALPRO PARIGI -MALINO - KANREAPIA |  | 100 | 100 | 100 | BAST-1 | 2021-11-01 | 2021-11-21 | 2021-11-01 | TEL.397/LG310/R7W-7A330000/2021 | 2021-11-09 | TEL.0037/LG.320/R7W-7A100000/2021 | 2021-11-09 | 65634725 | 55714399 | 121349124 | 121349124 | 4500438505 |  |  |  |  | TELKOM AKSES | 2021-12-27
G2021219 | 4 | 9 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006257/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan QE RELOKASI 6 LoP Periode Agustus Area Witel Makassar - PT. TELKOM AKSES | 2021-09-29 | 2021-11-27 | QE RELOKASI | UJUNGPANDANG | MAROS |  | RELOKASI UTILITAS MANDAI |  | 100 | 100 | 100 | BAST-1 | 2021-11-01 | 2021-11-21 | 2021-11-01 | TEL.398/LG310/R7W-7A330000/2021 | 2021-11-09 | TEL.0037/LG.320/R7W-7A100000/2021 | 2021-11-09 | 27390120 | 12308923 | 39699043 | 39699043 | 4500438505 |  |  |  |  | TELKOM AKSES | 2021-12-27
G2021219 | 4 | 11 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.006257/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan QE RELOKASI 6 LoP Periode Agustus Area Witel Makassar - PT. TELKOM AKSES | 2021-09-29 | 2021-11-27 | QE RELOKASI | UJUNGPANDANG | MAROS |  | MAROS 2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-01 | 2021-11-22 | 2021-11-01 | TEL.399/LG310/R7W-7A330000/2021 | 2021-11-09 | TEL.0037/LG.320/R7W-7A100000/2021 | 2021-11-09 | 47141970 | 53320808 | 100462778 | 100462778 | 4500438505 |  |  |  |  | TELKOM AKSES | 2021-12-27
12021321 | 10 | 57 | 01C11H01 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | FAK-FAK | FAK-FAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3563/LG.310/PND-B1060000/2021 | 2021-12-21 | TEL.0141/LG.320/DID-A0000000/2021 | 2021-12-21 | 628802900 | 100301920 | 729104820 | 729104820 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 59 | 01C11H01 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | FAK-FAK | FAK-FAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3564/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0142/LG.320/DID-A0000000/2021 | 2021-12-22 | 240711480 | 121614740 | 362326220 | 362326220 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 81 | 01C11H01 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | FAK-FAK | FAK-FAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3631/LG.310/PND-B1060000/2021 | 2021-12-27 | TEL.0318/LG.320/DID-A0000000/2021 | 2021-12-27 | 163928190 | 197276380 | 361204570 | 361204570 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 55 | 01C11H01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3563/LG.310/PND-B1060000/2021 | 2021-12-21 | TEL.0141/LG.320/DID-A0000000/2021 | 2021-12-21 | 704761380 | 112961670 | 817723050 | 817723050 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 78 | 01C11H01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3631/LG.310/PND-B1060000/2021 | 2021-12-27 | TEL.0318/LG.320/DID-A0000000/2021 | 2021-12-27 | 9465900 | 87998430 | 97464330 | 97464330 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 58 | 01C11H01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3564/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0142/LG.320/DID-A0000000/2021 | 2021-12-22 | 240711480 | 121614740 | 362326220 | 362326220 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 133 | 01C11H01 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | JAYAPURA | SARMI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3655/LG.310/DID-B106000/2021 | 2021-12-29 | TEL.0321/LG.320/DID-A0000000/2021 | 2021-12-29 | 710520510 | 109552050 | 820072560 | 820072560 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 120 | 01C11H01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | JAYAPURA | SENTANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3632/LG.310/PND-B1060000/2021 | 2021-12-27 | TEL.0319/LG.320/DID-A0000000/2021 | 2021-12-27 | 188177160 | 117074300 | 305251460 | 305251460 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 80 | 01C11H01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | JAYAPURA | TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3631/LG.310/PND-B1060000/2021 | 2021-12-27 | TEL.0318/LG.320/DID-A0000000/2021 | 2021-12-27 | 188177160 | 114637520 | 302814680 | 302814680 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 46 | 01C11H01 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | MANADO | MANADO CENTRUM |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3562/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0140/LG.320/DID-A0000000/2021 | 2021-12-22 | 188177160 | 114637520 | 302814680 | 302814680 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 152 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3567/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0136/LG.320/DID-A0000000/2021 | 2021-12-22 | 1276070770 | 385685110 | 1661755880 | 1661755880 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 136 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3570/LG.310/DID-B106000/2021 | 2021-12-22 | TEL.0322/LG.320/DID-A0000000/2021 | 2021-12-22 | 2004221800 | 682705430 | 2686927230 | 2686927230 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 56 | 01C11H01 | 019 | 74060085 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | SORONG | SAOKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3563/LG.310/PND-B1060000/2021 | 2021-12-21 | TEL.0141/LG.320/DID-A0000000/2021 | 2021-12-21 | 2148286210 | 347351510 | 2495637720 | 2495637720 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 132 | 01C11H01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3655/LG.310/DID-B106000/2021 | 2021-12-29 | TEL.0321/LG.320/DID-A0000000/2021 | 2021-12-29 | 676805640 | 104192480 | 780998120 | 780998120 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 119 | 01C11H01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3632/LG.310/PND-B1060000/2021 | 2021-12-27 | TEL.0319/LG.320/DID-A0000000/2021 | 2021-12-27 | 188177160 | 117074300 | 305251460 | 305251460 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 79 | 01C11H01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3631/LG.310/PND-B1060000/2021 | 2021-12-27 | TEL.0318/LG.320/DID-A0000000/2021 | 2021-12-27 | 18931800 | 175996860 | 194928660 | 194928660 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 151 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3567/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0136/LG.320/DID-A0000000/2021 | 2021-12-22 | 1276070770 | 385685110 | 1661755880 | 1661755880 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 126 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-27 | 2021-10-05 | TEL.1152/LG.310/DID-B0400000/2022 | 2022-04-25 | TEL.0560/LG.320/DID-A0000000/2022 | 2022-04-25 | 1667049560 | 269749290 | 1936798850 | 1936798850 | 4500438655 |  |  |  |  | NEC INDONESIA | 2022-04-28
12021321 | 10 | 71 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3572/LG.310/DID-B106000/2021 | 2021-12-22 | TEL.0323/LG.320/DID-A0000000/2021 | 2021-12-22 | 1168577900 | 365744410 | 1534322310 | 1534322310 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 118 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3568/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0137/LG.320/DID-A0000000/2021 | 2021-12-22 | 43180770 | 93358000 | 136538770 | 136538770 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 44 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3562/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0140/LG.320/DID-A0000000/2021 | 2021-12-22 | 43180770 | 45739810 | 88920580 | 88920580 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 134 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3570/LG.310/DID-B106000/2021 | 2021-12-22 | TEL.0322/LG.320/DID-A0000000/2021 | 2021-12-22 | 2643402900 | 786421587 | 3429824487 | 3429824487 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-30
12021321 | 10 | 74 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3565/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0132/LG.320/DID-A0000000/2021 | 2021-12-22 | 62112570 | 269354860 | 331467430 | 331467430 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 127 | 01C11H01 | 019 | 72081006 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | KALUKUBODO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-27 | 2021-10-05 | TEL.1152/LG.310/DID-B0400000/2022 | 2022-04-25 | TEL.0560/LG.320/DID-A0000000/2022 | 2022-04-25 | 535363950 | 90620470 | 625984420 | 625984420 | 4500438655 |  |  |  |  | NEC INDONESIA | 2022-04-28
12021321 | 10 | 150 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-04-16 | 2021-10-05 | TEL.3567/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0136/LG.320/DID-A0000000/2021 | 2021-12-22 | 1349848770 | 400266240 | 1750115010 | 1750115010 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021321 | 10 | 49 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006443/HK.810/OPS-10000000/2021 | Kontrak Ekspan ISP SKKL Transport PoP Platform NEC | 2021-10-05 | 2022-06-20 | SKKL | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-05 | 2022-03-04 | 2021-10-05 | TEL.3562/LG.310/DID-B1060000/2021 | 2021-12-22 | TEL.0140/LG.320/DID-A0000000/2021 | 2021-12-22 | 1470596190 | 506621400 | 1977217590 | 1977217590 | 4500438655 |  |  |  |  | NEC INDONESIA | 2021-12-26
12021328 | 7 | 22 | 01C11H06 | 019 | 74010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | BIAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.3633/LG.310/DID-B1060000/2021 | 2021-12-27 | TEL.0317/LG.320/DID-A0000000/2021 | 2021-12-27 | 1971256784 | 0 | 1971256784 | 1971256784 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2021-12-30
12021328 | 7 | 26 | 01C11I07 | 019 | 74010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | BIAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.356/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0622/LG.320/DID-A0000000/2022 | 2022-03-09 | 634169207 | 337694487 | 971863694 | 971863694 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-28
12021328 | 7 | 27 | 01C11I07 | 019 | 74010026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | MOKMER |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.356/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0622/LG.320/DID-A0000000/2022 | 2022-03-09 | 1219661634 | 486890702 | 1706552336 | 1706552336 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-28
12021328 | 7 | 29 | 01C11I07 | 019 | 74010061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | RUNI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.356/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0622/LG.320/DID-A0000000/2022 | 2022-03-09 | 771654846 | 486890702 | 1258545548 | 1258545548 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-28
12021328 | 7 | 31 | 01C11I07 | 019 | 74010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | WAINDU DMT |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-10-13 | 2022-09-08 | 2021-10-13 |  |  |  |  | 190921009 | 337694487 | 528615496 | 0 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021328 | 7 | 30 | 01C11I07 | 019 | 74010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | WAINDU DMT |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.356/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0622/LG.320/DID-A0000000/2022 | 2022-03-09 | 190921009 | 337694487 | 528615496 | 528615496 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-28
12021328 | 7 | 28 | 01C11I07 | 019 | 74010045 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | BIAK | WUNDI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.356/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0622/LG.320/DID-A0000000/2022 | 2022-03-09 | 1161467674 | 298392430 | 1459860104 | 1459860104 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-28
12021328 | 7 | 36 | 01C11I07 | 019 | 74030188 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | APAWER |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.357/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0436/LG.320/DID-A0000000/2022 | 2022-03-09 | 381842018 | 675388974 | 1057230992 | 1057230992 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-14
12021328 | 7 | 38 | 01C11I07 | 019 | 74030189 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | BAGAISEWAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.357/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0436/LG.320/DID-A0000000/2022 | 2022-03-09 | 580733837 | 149196215 | 729930052 | 729930052 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-14
12021328 | 7 | 32 | 01C11I07 | 019 | 74030185 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | INDOMBA |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-10-13 | 2022-09-08 | 2021-10-13 |  |  |  |  | 771654846 | 486890702 | 1258545548 | 0 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021328 | 7 | 37 | 01C11I07 | 019 | 74030190 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | MARTEWAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.357/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0436/LG.320/DID-A0000000/2022 | 2022-03-09 | 771654846 | 486890702 | 1258545548 | 1258545548 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-14
12021328 | 7 | 33 | 01C11I07 | 019 | 74030186 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | TAMAKURI |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-10-13 | 2022-09-08 | 2021-10-13 |  |  |  |  | 1161467674 | 298392430 | 1459860104 | 0 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021328 | 7 | 35 | 01C11I07 | 019 | 74030187 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | TEBA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-13 | 2022-03-13 | 2021-10-13 | TEL.357/LG.310/DID-B1060000/2022 | 2022-03-09 | TEL.0436/LG.320/DID-A0000000/2022 | 2022-03-09 | 385827423 | 243445351 | 629272774 | 629272774 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-04-14
12021328 | 7 | 34 | 01C11I07 | 019 | 74030187 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006585/HK.810/OPS-10050000/2021 | Kontrak Ekspan Radio IP Long Haul Support PON XX Papua | 2021-10-13 | 2022-09-07 | RADIO IP | JAYAPURA | TEBA |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-10-13 | 2022-09-08 | 2021-10-13 |  |  |  |  | 385827423 | 243445351 | 629272774 | 0 | 4500438788 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021344 | 3 | 5 | 01C11H01 | 019 | 72081029 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006785/HK.910/OPS-10000000/2021 | Kontrak Cable Spare Material Nexans | 2021-10-22 | 2022-07-18 | SKKL | UJUNGPANDANG | DEPO KABEL MAKASSAR |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-23 | 2021-10-22 | TEL.1311/LG.310/DID-B1060000/2022 | 2022-05-07 | TEL.0634/LG.320/DID-A0000000/2022 | 2022-05-07 | 32879989800 | 15965472600 | 48845462400 | 48845462400 | 4500437529 |  |  |  |  | NEXANS NORWAY AS | 2022-05-19
12021349 | 10 | 132 | 01C11H06 | 019 | 73010167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | AMBON PATIMURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.561/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0222/LG.320/DID-A0000000/2022 | 2022-02-25 | 247179400 | 32899300 | 280078700 | 280078700 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 243 | 01C11H06 | 019 | 73010167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | AMBON PATIMURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1167/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0614/LG.320/DID-A0000000/2022 | 2022-04-26 | 1268773900 | 114832000 | 1383605900 | 1383605900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 209 | 01C11H06 | 019 | 73010167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | AMBON PATIMURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1166/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0613/LG.320/DID-A0000000/2022 | 2022-04-26 | 1588505900 | 156376000 | 1744881900 | 1744881900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 362 | 01C11H06 | 019 | 73010167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | AMBON PATIMURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1179/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0610/LG.320/DID-A0000000/2022 | 2022-04-26 | 1116273900 | 101107000 | 1217380900 | 1217380900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 348 | 01C11H06 | 019 | 73010167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | AMBON PATIMURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1175/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0606/LG.320/DID-A0000000/2022 | 2022-04-26 | 1116273900 | 101107000 | 1217380900 | 1217380900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 127 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  | 3R |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 6935975400 | 642099000 | 7578074400 | 7578074400 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 126 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 22475600 | 4496600 | 26972200 | 26972200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 228 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1169/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0600/LG.320/DID-A0000000/2022 | 2022-04-26 | 2103747800 | 191035000 | 2294782800 | 2294782800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 206 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1165/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0612/LG.320/DID-A0000000/2022 | 2022-04-26 | 4788479800 | 445429000 | 5233908800 | 5233908800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 355 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1177/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0608/LG.320/DID-A0000000/2022 | 2022-04-26 | 2853222700 | 272260500 | 3125483200 | 3125483200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 352 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1176/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0607/LG.320/DID-A0000000/2022 | 2022-04-26 | 2408747800 | 218485000 | 2627232800 | 2627232800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 129 | 01C11H06 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.561/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0222/LG.320/DID-A0000000/2022 | 2022-02-25 | 4512495600 | 409520000 | 4922015600 | 4922015600 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 131 | 01C11H06 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | FAK-FAK | FAK-FAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.561/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0222/LG.320/DID-A0000000/2022 | 2022-02-25 | 247179400 | 32899300 | 280078700 | 280078700 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 122 | 01C11H06 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | FAK-FAK | FAK-FAK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 154 | 01C11H06 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | GORONTALO | GORONTALO |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 2238359400 | 231746700 | 2470106100 | 2470106100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 386 | 01C11H06 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | GORONTALO | GORONTALO |  |  |  | 90 |  | 0 |  | 2021-10-26 | 2022-11-30 | [5 empty] | 90576900 | 4641700 | 95218600 | 0 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021349 | 10 | 155 | 01C11H06 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | GORONTALO | ISIMU |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 1866639400 | 198255900 | 2064895300 | 2064895300 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 385 | 01C11H06 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | GORONTALO | ISIMU |  |  |  | 90 |  |  |  | 2021-10-26 | 2022-11-30 | [5 empty] | 94472000 | 4976700 | 99448700 | 0 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021349 | 10 | 383 | 01C11H06 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | GORONTALO | MARISA |  |  |  | 90 |  |  |  | 2021-10-26 | 2022-11-30 | [5 empty] | 46741200 | 4020000 | 50761200 | 0 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021349 | 10 | 354 | 01C11H06 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | KENDARI | MANDONGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1177/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0608/LG.320/DID-A0000000/2022 | 2022-04-26 | 1522279800 | 151058000 | 1673337800 | 1673337800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 358 | 01C11H06 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | KENDARI | MANDONGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1178/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0609/LG.320/DID-A0000000/2022 | 2022-04-26 | 1202547800 | 109514000 | 1312061800 | 1312061800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 124 | 01C11H06 | 019 | 72010045 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | KAUDITAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 22475600 | 4496600 | 26972200 | 26972200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 99 | 01C11H06 | 019 | 72010045 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | KAUDITAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 210519400 | 33045600 | 243565000 | 243565000 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 231 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3669/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0368/LG.320/DID-A0000000/2021 | 2021-12-29 | 1289679900 | 107109300 | 1396789200 | 1396789200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 220 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  | 1 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1168/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0615/LG.320/DID-A0000000/2022 | 2022-04-26 | 240051900 | 22614800 | 262666700 | 262666700 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 117 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 172547800 | 16814000 | 189361800 | 189361800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 219 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1168/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0615/LG.320/DID-A0000000/2022 | 2022-04-26 | 200934600 | 18743200 | 219677800 | 219677800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 246 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3673/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0372/LG.320/DID-A0000000/2021 | 2021-12-29 | 109300000 | 10046100 | 119346100 | 119346100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 227 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1169/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0600/LG.320/DID-A0000000/2022 | 2022-04-26 | 1522279800 | 151058000 | 1673337800 | 1673337800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 241 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3672/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0371/LG.320/DID-A0000000/2021 | 2021-12-29 | 699777900 | 58609000 | 758386900 | 758386900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 156 | 01C11H06 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 2238359400 | 201746700 | 2440106100 | 2440106100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 96 | 01C11H06 | 019 | 72010062 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | MANADO 2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 870630500 | 88293700 | 958924200 | 958924200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 212 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-29 | 2021-10-26 | TEL.1851/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.0971/LG.320/DID-A0000000/2022 | 2022-06-30 | 665903000 | 60055100 | 725958100 | 725958100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 97 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 919346700 | 93096400 | 1012443100 | 1012443100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 130 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.561/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0222/LG.320/DID-A0000000/2022 | 2022-02-25 | 172547800 | 16814000 | 189361800 | 189361800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 232 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3669/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0368/LG.320/DID-A0000000/2021 | 2021-12-29 | 1289679900 | 107109300 | 1396789200 | 1396789200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 356 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1177/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0608/LG.320/DID-A0000000/2022 | 2022-04-26 | 1202547800 | 109514000 | 1312061800 | 1312061800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 245 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3673/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0372/LG.320/DID-A0000000/2021 | 2021-12-29 | 109300000 | 10046100 | 119346100 | 119346100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 207 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1165/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0612/LG.320/DID-A0000000/2022 | 2022-04-26 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 217 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1168/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0615/LG.320/DID-A0000000/2022 | 2022-04-26 | 200934600 | 18743200 | 219677800 | 219677800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 242 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1167/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0614/LG.320/DID-A0000000/2022 | 2022-04-26 | 1268773900 | 114832000 | 1383605900 | 1383605900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 238 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3671/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0370/LG.320/DID-A0000000/2021 | 2021-12-29 | 699777900 | 58609000 | 758386900 | 758386900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 120 | 01C11H06 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 237 | 01C11H06 | 019 | 72010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | TELLING |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3671/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0370/LG.320/DID-A0000000/2021 | 2021-12-29 | 699777900 | 58609000 | 758386900 | 758386900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 213 | 01C11H06 | 019 | 72010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | TELLING |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-29 | 2021-10-26 | TEL.1851/LG.310/DID-B0400000/2022 | 2022-06-30 | TEL.0971/LG.320/DID-A0000000/2022 | 2022-06-30 | 665903000 | 60055100 | 725958100 | 725958100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 240 | 01C11H06 | 019 | 72010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | TELLING |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3672/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0371/LG.320/DID-A0000000/2021 | 2021-12-29 | 699777900 | 58609000 | 758386900 | 758386900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 218 | 01C11H06 | 019 | 72010125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | MANADO | TELLING |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1168/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0615/LG.320/DID-A0000000/2022 | 2022-04-26 | 240051900 | 22614800 | 262666700 | 262666700 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 107 | 01C11H06 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | DONGGALA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 920602000 | 82854300 | 1003456300 | 1003456300 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 349 | 01C11H06 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | DONGGALA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1174/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0605/LG.320/DID-A0000000/2022 | 2022-04-26 | 1767203000 | 159048300 | 1926251300 | 1926251300 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 168 | 01C11H06 | 019 | 72030171 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | ILA TARIPA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 267835200 | 24302200 | 292137400 | 292137400 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 336 | 01C11H06 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | PALU |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1173/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0604/LG.320/DID-A0000000/2022 | 2022-04-26 | 1467101000 | 132075100 | 1599176100 | 1599176100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 343 | 01C11H06 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | PALU |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1174/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0605/LG.320/DID-A0000000/2022 | 2022-04-26 | 305101000 | 27495100 | 332596100 | 332596100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 166 | 01C11H06 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | PALU-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 305101000 | 27495100 | 332596100 | 332596100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 106 | 01C11H06 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | PALU-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 1425502000 | 128331200 | 1553833200 | 1553833200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 101 | 01C11H06 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | PARIGI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 448802000 | 40392200 | 489194200 | 489194200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 337 | 01C11H06 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | PARIGI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1173/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0604/LG.320/DID-A0000000/2022 | 2022-04-26 | 1128802000 | 101592200 | 1230394200 | 1230394200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 338 | 01C11H06 | 019 | 72030101 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | POSO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1173/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0604/LG.320/DID-A0000000/2022 | 2022-04-26 | 448802000 | 40392200 | 489194200 | 489194200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 384 | 01C11H06 | 019 | 72030069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PALU | SANTIGI |  |  |  | 90 |  |  |  | 2021-10-26 | 2022-11-30 | [5 empty] | 46741200 | 4020000 | 50761200 | 0 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021349 | 10 | 161 | 01C11H06 | 019 | 72040193 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | BARRU |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 1038957800 | 108765500 | 1147723300 | 1147723300 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 169 | 01C11H06 | 019 | 72040310 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | ILA SAMPURAGA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 252254800 | 22962200 | 275217000 | 275217000 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 378 | 01C11H06 | 019 | 72040082 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | MALILI |  |  |  | 90 |  |  |  | 2021-10-26 | 2022-11-30 | [5 empty] | 933580000 | 86364100 | 1019944100 | 0 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021349 | 10 | 171 | 01C11H06 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | MASAMBA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 1098580600 | 112669500 | 1211250100 | 1211250100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 103 | 01C11H06 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PALOPO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 448802000 | 40392200 | 489194200 | 489194200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 150 | 01C11H06 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PALOPO |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 1128802000 | 101592200 | 1230394200 | 1230394200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 160 | 01C11H06 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PALOPO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 473012000 | 42571100 | 515583100 | 515583100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 339 | 01C11H06 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PALOPO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1173/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0604/LG.320/DID-A0000000/2022 | 2022-04-26 | 448802000 | 40392200 | 489194200 | 489194200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 151 | 01C11H06 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PARE-PARE |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 1128802000 | 101592200 | 1230394200 | 1230394200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 341 | 01C11H06 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1173/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0604/LG.320/DID-A0000000/2022 | 2022-04-26 | 448802000 | 40392200 | 489194200 | 489194200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 104 | 01C11H06 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 448802000 | 40392200 | 489194200 | 489194200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 162 | 01C11H06 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | PARE-PARE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 1355365000 | 122239100 | 1477604100 | 1477604100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 379 | 01C11H06 | 019 | 72040161 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | PARE-PARE | SOROWAKO |  |  |  | 90 |  |  |  | 2021-10-26 | 2022-11-30 | [5 empty] | 962940900 | 86924100 | 1049865000 | 0 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021349 | 10 | 149 | 01C11H06 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | POSO | POSO |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 305101000 | 27495100 | 332596100 | 332596100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 157 | 01C11H06 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | POSO | POSO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 436111000 | 39250000 | 475361000 | 475361000 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 102 | 01C11H06 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | POSO | POSO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 1610802000 | 144972200 | 1755774200 | 1755774200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 158 | 01C11H06 | 019 | 72070020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | POSO | TENTENA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 1060304300 | 94683500 | 1154987800 | 1154987800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 361 | 01C11H06 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | TERNATE | TERNATE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1179/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0610/LG.320/DID-A0000000/2022 | 2022-04-26 | 1268773900 | 114832000 | 1383605900 | 1383605900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 118 | 01C11H06 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | TERNATE | TERNATE |  | 1 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 119 | 01C11H06 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | TERNATE | TERNATE |  | 2 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 1268773900 | 114832000 | 1383605900 | 1383605900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 363 | 01C11H06 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | TERNATE | TERNATE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1176/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0607/LG.320/DID-A0000000/2022 | 2022-04-26 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 235 | 01C11H06 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3670/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0369/LG.320/DID-A0000000/2021 | 2021-12-29 | 720902000 | 64989200 | 785891200 | 785891200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 112 | 01C11H06 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.825/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0424/LG.320/DID-A0000000/2022 | 2022-03-23 | 787101000 | 70875100 | 857976100 | 857976100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 128 | 01C11H06 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BALAIKOTA |  | 1 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.561/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0222/LG.320/DID-A0000000/2022 | 2022-02-25 | 172547800 | 16814000 | 189361800 | 189361800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 121 | 01C11H06 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 1268773900 | 114832000 | 1383605900 | 1383605900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 210 | 01C11H06 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1167/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0614/LG.320/DID-A0000000/2022 | 2022-04-26 | 264701000 | 23823100 | 288524100 | 288524100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 153 | 01C11H06 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BALAIKOTA |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 985101000 | 88695100 | 1073796100 | 1073796100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 159 | 01C11H06 | 019 | 72080024 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | BONEPOTE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 1053188800 | 94377500 | 1147566300 | 1147566300 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 164 | 01C11H06 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PANGKEP |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 1038957800 | 108765500 | 1147723300 | 1147723300 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 208 | 01C11H06 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1166/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0613/LG.320/DID-A0000000/2022 | 2022-04-26 | 1116273900 | 101107000 | 1217380900 | 1217380900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 205 | 01C11H06 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PENGAYOMAN |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1165/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0612/LG.320/DID-A0000000/2022 | 2022-04-26 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 351 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1176/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0607/LG.320/DID-A0000000/2022 | 2022-04-26 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 111 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.825/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0424/LG.320/DID-A0000000/2022 | 2022-03-23 | 787101000 | 70875100 | 857976100 | 857976100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 163 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.826/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0425/LG.320/DID-A0000000/2022 | 2022-03-23 | 473024900 | 42572300 | 515597200 | 515597200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 152 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-08-13 | 2021-10-26 | TEL.1183/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0969/LG.320/DID-A0000000/2022 | 2022-04-26 | 1128802000 | 101592200 | 1230394200 | 1230394200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-06-30
12021349 | 10 | 359 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1178/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0609/LG.320/DID-A0000000/2022 | 2022-04-26 | 1355047800 | 123239000 | 1478286800 | 1478286800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 116 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  | 2 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 172547800 | 16814000 | 189361800 | 189361800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 234 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.3670/LG.310/DID-B1060000/2021 | 2021-12-29 | TEL.0369/LG.320/DID-A0000000/2021 | 2021-12-29 | 720902000 | 64989200 | 785891200 | 785891200 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2021-12-30
12021349 | 10 | 123 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  | 4 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 86273900 | 8407000 | 94680900 | 94680900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 229 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1169/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0600/LG.320/DID-A0000000/2022 | 2022-04-26 | 1522279800 | 151058000 | 1673337800 | 1673337800 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 347 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1175/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0606/LG.320/DID-A0000000/2022 | 2022-04-26 | 1116273900 | 101107000 | 1217380900 | 1217380900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 340 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1173/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0604/LG.320/DID-A0000000/2022 | 2022-04-26 | 305101000 | 27495100 | 332596100 | 332596100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 115 | 01C11H06 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI |  | 1 |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.560/LG.310/DID-B1060000/2022 | 2022-02-25 | TEL.0221/LG.320/DID-A0000000/2022 | 2022-02-25 | 1116273900 | 101107000 | 1217380900 | 1217380900 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-02-28
12021349 | 10 | 167 | 01C11H06 | 019 | 72081036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | PETTARANI-3 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 305101000 | 27495100 | 332596100 | 332596100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021349 | 10 | 211 | 01C11H06 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | SUDIANG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-05-15 | 2021-10-26 | TEL.1167/LG.310/DID-B0400000/2022 | 2022-04-26 | TEL.0614/LG.320/DID-A0000000/2022 | 2022-04-26 | 1426701000 | 128403100 | 1555104100 | 1555104100 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-04-28
12021349 | 10 | 98 | 01C11H06 | 019 | 72080999 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | OPTICAL TRANSPORT DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006848/HK.810/OPS-10000000/2021 | Perjanjian Pengadaan dan Pemasangan DWDM Platform Nokia Pemenuhan Kebutuhan OLO, IPBB, Trunk Metro dan SMPCS Paket-1 | 2021-10-26 | 2022-11-23 | DWDM | UJUNGPANDANG | TELING |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-10-26 | 2022-03-31 | 2021-10-26 | TEL.824/LG.310/DID-B0400000/2022 | 2022-03-23 | TEL.0423/LG.320/DID-A0000000/2022 | 2022-03-23 | 144934400 | 27352200 | 172286600 | 172286600 | 4500439995 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-03-31
12021353 | 12 | 65 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | AMBON | AMBON |  | dsl-sgtera14-amb-01 |  | 100 | 100 | 100 | BAST-1 | 2022-02-24 | 2022-05-30 | 2022-05-01 | TEL.746/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0785/LG.320/DID-A0000000/2022 | 2022-05-28 | 0 | 56150000 | 56150000 | 56150000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-05-31
12021353 | 12 | 40 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | AMBON | AMBON |  | ABN |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-02 | TEL.44/LG.310/DID-B0300000/2022 | 2022-01-27 | TEL.0032/LG.320/DID-A0000000/2022 | 2022-01-27 | 143070000 | 29345000 | 172415000 | 172415000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-01-31
12021353 | 12 | 67 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-05-30 | 2022-05-01 | TEL.746/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0785/LG.320/DID-A0000000/2022 | 2022-05-28 | 0 | 56150000 | 56150000 | 56150000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-05-31
12021353 | 12 | 43 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | JAYAPURA | JAYAPURA |  | JAP |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-04 | TEL.44/LG.310/DID-B0300000/2022 | 2022-01-27 | TEL.0032/LG.320/DID-A0000000/2022 | 2022-01-27 | 605070000 | 52445000 | 657515000 | 657515000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-01-31
12021353 | 12 | 44 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | JAYAPURA | TIMIKA |  | TIM |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-05 | TEL.2254/LG310/PND-B1050000/2021 | 2021-12-27 | TEL.0177/LG.320/DID-A0000000/2021 | 2021-12-27 | 3079120000 | 172295000 | 3251415000 | 3251415000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2021-12-27
12021353 | 12 | 78 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | PALU | PALU-1 |  | dsl-sg9700B-palu-01 |  | 100 | 100 | 100 | BAST-1 | 2022-02-24 | 2022-05-30 | 2022-04-01 | TEL.407/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0489/LG.320/DID-A0000000/2022 | 2022-04-26 | 2171520000 | 126915000 | 2298435000 | 2298435000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-04-27
12021353 | 12 | 90 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | PALU | PALU-1 |  | dsl-sg9700b-pal1-01 |  | 50 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-07-25 | 2022-07-01 | TEL.1168/LG.310/DID-B0300000/2022 | 2022-07-25 | TEL.1052/LG.320/DID-A0000000/2022 | 2022-07-25 | 34000000 | 40300000 | 74300000 | 74300000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-07-29
12021353 | 12 | 79 | 01C11B01 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | PALU | PALU-2 |  | dsl-sg9700B-palu-02 |  | 100 | 100 | 100 | BAST-1 | 2022-02-24 | 2022-05-30 | 2022-04-01 | TEL.407/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0489/LG.320/DID-A0000000/2022 | 2022-04-26 | 2171520000 | 126915000 | 2298435000 | 2298435000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-04-27
12021353 | 12 | 91 | 01C11B01 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | PALU | PALU-2 |  | dsl-sg9700B-pal2-01 |  | 50 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-07-25 | 2022-07-01 | TEL.1168/LG.310/DID-B0300000/2022 | 2022-07-25 | TEL.1052/LG.320/DID-A0000000/2022 | 2022-07-25 | 523165000 | 64745000 | 587910000 | 587910000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-07-29
12021353 | 12 | 42 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | SORONG | SORONG |  | dsl-sgtera14-son-01 |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-05-30 | 2021-11-04 | TEL.746/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0785/LG.320/DID-A0000000/2022 | 2022-05-28 | 146070000 | 65645000 | 211715000 | 211715000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-05-31
12021353 | 12 | 41 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | TERNATE | TERNATE |  | TNT |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-04 | TEL.44/LG.310/DID-B0300000/2022 | 2022-01-27 | TEL.0032/LG.320/DID-A0000000/2022 | 2022-01-27 | 788570000 | 61620000 | 850190000 | 850190000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-01-31
12021353 | 12 | 66 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | TERNATE | TERNATE |  | dsl-sgtera14-tnt-01 |  | 100 | 100 | 100 | BAST-1 | 2022-02-24 | 2022-05-30 | 2022-05-01 | TEL.746/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0785/LG.320/DID-A0000000/2022 | 2022-05-28 | 0 | 56150000 | 56150000 | 56150000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-05-31
12021353 | 12 | 64 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | UJUNGPANDANG | BALAIKOTA |  | dsl-sgtera14-bal-01 |  | 100 | 100 | 100 | BAST-1 | 2022-02-23 | 2022-05-30 | 2022-04-01 | TEL.396/LG.310/DID-B1050000/2022 | 2022-04-11 | TEL.0488/LG.320/DID-A0000000/2022 | 2022-04-11 | 92570000 | 3220000 | 95790000 | 95790000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-04-27
12021353 | 12 | 39 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | UJUNGPANDANG | BALAIKOTA |  | BAL |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-02 | TEL.2059/LG310/PND-B1050000/2021 | 2021-11-29 | TEL.0695/LG.320/DID-00000000/2021 | 2021-11-29 | 66375000 | 83060000 | 149435000 | 149435000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2021-11-30
12021353 | 12 | 13 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | UJUNGPANDANG | PETTARANI |  | PTR |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-04 | TEL.2255/LG310/PND-B1050000/2021 | 2021-12-27 | TEL.0178/LG.320/DID-A0000000/2021 | 2021-12-27 | 256300000 | 12815000 | 269115000 | 269115000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2021-12-27
12021353 | 12 | 38 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | UJUNGPANDANG | PETTARANI |  | PTR |  | 100 | 100 | 100 | BAST-1 | 2021-10-28 | 2022-02-24 | 2021-11-04 | TEL.2059/LG310/PND-B1050000/2021 | 2021-11-29 | TEL.0695/LG.320/DID-00000000/2021 | 2021-11-29 | 84375000 | 83960000 | 168335000 | 168335000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2021-11-30
12021353 | 12 | 63 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.006906/HK.810/OPS-10000000/2021 | SP#1 Ekspan PCEF Platform Allot | 2021-10-28 | 2022-07-25 | PCEF | UJUNGPANDANG | PETTARANI |  | dsl-sgtera14-ptr-01 |  | 100 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-05-30 | 2022-04-01 | TEL.396/LG.310/DID-B1050000/2022 | 2022-04-11 | TEL.0488/LG.320/DID-A0000000/2022 | 2022-04-11 | 92570000 | 3220000 | 95790000 | 95790000 | 4500440263 |  |  |  |  | ANDES LASEA KREASINDO | 2022-04-27
12021361 | 4 | 71 | 01C11I04 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007033/HK.810/OPS-10050000/2021 | Surat Pesanan-5 (SP#5) Pengadaan dan Pemasangan Ekspan PE VPN Cisco - SDWAN Hermina | 2021-11-02 | 2022-06-29 | SD-WAN | AMBON | AMBON |  | RSH Ambon |  | 100 |  |  |  | 2022-04-05 | 2022-07-06 | [5 empty] | 17868000 | 99328680 | 117196680 | 0 | 4500440284 |  |  |  |  | SISINDOKOM LINTASBUANA
12021361 | 4 | 74 | 01C11I04 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007033/HK.810/OPS-10050000/2021 | Surat Pesanan-5 (SP#5) Pengadaan dan Pemasangan Ekspan PE VPN Cisco - SDWAN Hermina | 2021-11-02 | 2022-06-29 | SD-WAN | KENDARI | KENDARI |  | RSH Kendari |  | 100 | 100 | 100 | BAST-1 | 2022-04-05 | 2022-07-06 | 2022-06-27 | TEL.0660/LG.310/DID-C0200000/2022 | 2022-06-28 18:11 | TEL.0854/LG.320/DID-A0000000/2022 | 2022-06-28 | 17868000 | 9328680 | 27196680 | 27196680 | 4500440284 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-06-29
12021361 | 4 | 73 | 01C11I04 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007033/HK.810/OPS-10050000/2021 | Surat Pesanan-5 (SP#5) Pengadaan dan Pemasangan Ekspan PE VPN Cisco - SDWAN Hermina | 2021-11-02 | 2022-06-29 | SD-WAN | MANADO | MANADO |  | RSH Manado |  | 100 | 100 | 100 | BAST-1 | 2022-04-05 | 2022-07-06 | 2022-06-27 | TEL.0660/LG.310/DID-C0200000/2022 | 2022-06-28 18:11 | TEL.0854/LG.320/DID-A0000000/2022 | 2022-06-28 | 17868000 | 9328680 | 27196680 | 27196680 | 4500440284 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-06-29
12021361 | 4 | 72 | 01C11I04 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS STRATEGIC DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007033/HK.810/OPS-10050000/2021 | Surat Pesanan-5 (SP#5) Pengadaan dan Pemasangan Ekspan PE VPN Cisco - SDWAN Hermina | 2021-11-02 | 2022-06-29 | SD-WAN | UJUNGPANDANG | MAKASAR |  | RSH Makasar |  | 100 |  |  |  | 2022-04-05 | 2022-07-06 | [5 empty] | 17868000 | 9328680 | 27196680 | 0 | 4500440284 |  |  |  |  | SISINDOKOM LINTASBUANA
G2021239 | 7 | 13 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007057/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 5 LOP Area Witel Maluku | 2021-11-03 | 2022-02-23 | OSP FTTH PT-3 2021 | AMBON | AMBON |  | R7 AMB ABO PT3 ARBES |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-31 | 2021-11-05 | TEL.779/LG.310/DR7-12700000/2022 | 2022-04-12 | TEL.0045/LG.320/DR7-10400000/2022 | 2022-04-12 | 633114409 | 160628208 | 793742617 | 793742617 | 4500441116 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-04-21
G2021239 | 7 | 11 | 01E07V01 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007057/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 5 LOP Area Witel Maluku | 2021-11-03 | 2022-02-23 | OSP FTTH PT-3 2021 | AMBON | MASOHI |  | R7 AMB MSH PT3 LATU |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-31 | 2021-11-12 | TEL.1770/LG.310/DR7-12700000/2021 | 2021-11-26 | TEL.0182/LG.320/DR7-10400000/2021 | 2021-11-26 | 228632286 | 44861688 | 273493974 | 273493974 | 4500441116 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-07
G2021239 | 7 | 12 | 01E07V01 | 007 | 73010046 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007057/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 5 LOP Area Witel Maluku | 2021-11-03 | 2022-02-23 | OSP FTTH PT-3 2021 | AMBON | NAMLEA |  | R7 AMB NML PT3 POHON DURIAN |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-31 | 2021-12-20 | TEL.2011/LG.310/DR7-12700000/2021 | 2021-12-21 | TEL.0217/LG.320/DR7-10400000/2021 | 2021-12-21 | 114730865 | 22654434 | 137385299 | 137385299 | 4500441116 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-24
G2021239 | 7 | 10 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007057/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 5 LOP Area Witel Maluku | 2021-11-03 | 2022-02-23 | OSP FTTH PT-3 2021 | AMBON | PASSO |  | R7 AMB PAO PT3 VILA INDAH PASSO |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-31 | 2021-12-12 | TEL.2010/LG.310/DR7-12700000/2021 | 2021-12-21 | TEL.0217/LG.320/DR7-10400000/2021 | 2021-12-21 | 203245566 | 60499680 | 263745246 | 263745246 | 4500441116 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-24
G2021239 | 7 | 14 | 01E07V01 | 007 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007057/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 5 LOP Area Witel Maluku | 2021-11-03 | 2022-02-23 | OSP FTTH PT-3 2021 | AMBON | PIRU |  | R7 AMB PIR PT3 PELITA JAYA |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-31 | 2021-11-10 | TEL.1771/LG.310/DR7-12700000/2021 | 2021-11-26 | TEL.0182/LG.320/DR7-10400000/2021 | 2021-11-26 | 207203231 | 58391355 | 265594586 | 265594586 | 4500441116 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-07
12021370 | 8 | 201 | 01C11I02 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | AMBON | MALUKU |  | PT2-Jl. Pelabuhan Labuha Halsel |  | 100 |  | 0 |  | 2021-11-03 | 2022-03-04 | [5 empty] | 8644230 | 1591969 | 10236199 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 198 | 01C11I02 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | AMBON | MALUKU |  | PT2-Jl. Trans Yamdena |  | 100 | 90 | 0 | Siap UT | 2021-11-03 | 2022-03-04 | 2022-02-14 |  |  |  |  | 34774839 | 6879163 | 41654002 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 200 | 01C11I02 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | AMBON | MALUKU |  | PT2-Jl. Halong Tanah Merah |  | 100 | 30 | 0 | Mat. Delivery | 2021-11-03 | 2022-03-04 | 2022-02-14 |  |  |  |  | 36639444 | 10742449 | 47381893 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 202 | 01C11I02 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | AMBON | MALUKU |  | PT2-Kec. Malifut Kab. Halmahera Utara |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-27 | 2022-02-16 | TEL.0242/LG.310/DID-C0200000/2022 | 2022-03-26 07:05 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 80974888 | 24481653 | 105456541 | 105456541 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 364 | 01C11I02 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | GORONTALO | GORONTALO |  | PT3-Jl. Trans Sulawesi, Ds Maleo Kec. Popayato |  | 100 |  | 0 |  | 2021-11-03 | 2022-03-04 | [5 empty] | 180727096 | 42649013 | 223376109 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 365 | 01C11I02 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | GORONTALO | GORONTALO |  | PT2-Jl. Trans Sulawesi Kel. Libuwo Kec. |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 101623118 | 32068441 | 133691559 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 367 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | MANADO |  | PT3-Jl. J.W Lasut, Desa Sawangan, K |  | 100 |  | 0 |  | 2021-11-03 | 2022-03-04 | [5 empty] | 108261913 | 29413197 | 137675110 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 368 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | MANADO |  | PT2-Jl. Raya Tomohon Desa Matani Satu |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 4441177 | 511421 | 4952598 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 366 | 01C11I02 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | MANADO |  | PT3-Jl. Yos Sudarso Nomor 28, Kel. Kair |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 4972320 | 1282161 | 6254481 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 185 | 01C11I02 | 019 | 72010825 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | STO MANADO |  | PT3-Jl. Raya Desa Tuyat Kec.Lolak |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-25 | 2022-02-17 | TEL.0239/LG.310/DID-C0200000/2022 | 2022-03-24 20:16 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 178132437 | 35710871 | 213843308 | 213843308 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 184 | 01C11I02 | 019 | 72010825 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | STO MANADO |  | PT3-Jl. Trans Sulawesi Desa Batu Lintik |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-25 | 2022-02-17 | TEL.0239/LG.310/DID-C0200000/2022 | 2022-03-24 20:16 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 95465299 | 23904217 | 119369516 | 119369516 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 183 | 01C11I02 | 019 | 72010825 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | STO MANADO |  | PT2-Jl. Trans Halmahera Kampung Baru Bu |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 2820057 | 344637 | 3164694 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 182 | 01C11I02 | 019 | 72010825 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | STO MANADO |  | PT2-Jl. Raya Sonder Kel. Kolongan Atas |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-25 | 2022-02-16 | TEL.0239/LG.310/DID-C0200000/2022 | 2022-03-24 20:16 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 26024705 | 7667255 | 33691960 | 33691960 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 181 | 01C11I02 | 019 | 72010825 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | MANADO | STO MANADO |  | PT2-Jl. Trans Sulawesi Desa Kapitu |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-25 | 2022-02-17 | TEL.0239/LG.310/DID-C0200000/2022 | 2022-03-24 20:16 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 8213031 | 1475715 | 9688746 | 9688746 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 376 | 01C11I02 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | PALU | SULTENG |  | PT3-Jl.Parigi-Palu Kel. Toboli Barat, Kec. Parigi Utara |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 111803151 | 33397031 | 145200182 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 377 | 01C11I02 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | PARE-PARE | PARE-PARE |  | PT3-Jl. Poros Parepare - Pinrang |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-28 | 2022-02-12 | TEL.0240/LG.310/DID-C0200000/2022 | 2022-03-26 07:04 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 162398115 | 45962135 | 208360250 | 208360250 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 374 | 01C11I02 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | PARE-PARE | PARE-PARE |  | PT2-Jl.A.P.Pettarani Kel.Lalebata, Kec. Panca Rijang |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-28 | 2022-02-12 | TEL.0240/LG.310/DID-C0200000/2022 | 2022-03-26 07:04 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 27790075 | 7840996 | 35631071 | 35631071 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 375 | 01C11I02 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | PARE-PARE | PARE-PARE |  | PT4-Dusun Bungadidi, Kel. Bone Bone, Kec. Tana Lili |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-05-28 | 2022-03-21 | TEL.0499/LG.310/DID-C0200000/2022 | 2022-05-27 08:47 | TEL.0654/LG.320/DID-A0000000/2022 | 2022-05-27 | 215718956 | 38231026 | 253949982 | 253949982 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-05-30
12021370 | 8 | 373 | 01C11I02 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | PARE-PARE | PARE-PARE |  | PT2-Masamba Jl. Trans Sulawesi |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-05-28 | 2022-03-15 | TEL.0499/LG.310/DID-C0200000/2022 | 2022-05-27 08:47 | TEL.0654/LG.320/DID-A0000000/2022 | 2022-05-27 | 110968414 | 29613590 | 140582004 | 140582004 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-05-30
12021370 | 8 | 371 | 01C11I02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | MAKASAR |  | PT3-Jl. Poros Sinjai Makassar |  | 100 |  | 0 |  | 2021-11-03 | 2022-03-04 | [5 empty] | 55735922 | 12765245 | 68501167 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 370 | 01C11I02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | MAKASAR |  | PT3-Jl. Poros Bulukumba Bira Kec. Bonto Bahari |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 80529470 | 23826212 | 104355682 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 191 | 01C11I02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | MAKASAR |  | PT2-Jl. Poros Maros-Bone (Kec. Camba) |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-15 | 2022-02-14 | TEL.0213/LG.310/DID-C0200000/2022 | 2022-03-14 21:55 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 6676759 | 830473 | 7507232 | 7507232 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 372 | 01C11I02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | MAKASAR |  | PT2-Jl. Mallombassang |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 3436398 | 684425 | 4120823 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 369 | 01C11I02 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | MAKASAR |  | PT3-Jl Persatuan Raya Sinjai Selatan |  | 100 |  | 0 |  | 2021-11-03 | 2022-03-04 | [5 empty] | 91134583 | 17875747 | 109010330 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021370 | 8 | 193 | 01C11I02 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | SULSELBAR |  | PT2-Jl. Ds Kajuara Kec.Tanete Riaja. Kab. Barru |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-28 | 2022-02-12 | TEL.0240/LG.310/DID-C0200000/2022 | 2022-03-26 07:04 | TEL.0319/LG.320/DID-A0000000/2022 | 2022-03-26 | 14567058 | 3988750 | 18555808 | 18555808 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-03-30
12021370 | 8 | 194 | 01C11I02 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | SULSELBAR |  | PT3-Kec. Ponrang Padang Sappa |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-05-02 | 2022-02-14 | TEL.0469/LG.310/DID-C0200000/2022 | 2022-05-01 08:00 | TEL.0654/LG.320/DID-A0000000/2022 | 2022-05-27 | 43869909 | 15781455 | 59651364 | 59651364 | 4500439945 |  |  |  |  | TELKOM AKSES | 2022-05-30
12021370 | 8 | 195 | 01C11I02 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007079/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Granular Modernization - OSP FO Pelanggan Enterprise dan HRB TREG-2 | 2021-11-03 | 2022-05-31 | GRANULAR | UJUNGPANDANG | SULSELBAR |  | PT3-Desa Polohu |  | 100 | 0 | 0 | Preparing | 2021-11-03 | 2022-03-04 | [5 empty] | 3217599 | 415401 | 3633000 | 0 | 4500439945 |  |  |  |  | TELKOM AKSES
12021371 | 13 | 65 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | AMBON | AMBON |  | ME2-D7-AMB |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2244/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0211/LG.320/DID-A0000000/2021 | 2021-12-24 | 761400500 | 76140050 | 837540550 | 837540550 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 159 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | AMBON | AMBON |  | ME2-D7-AMB |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 518543300 | 51854330 | 570397630 | 570397630 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 140 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | AMBON | AMBON |  | ME2-D7-AMB |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.164/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0135/LG.320/DID-A0000000/2022 | 2022-02-17 | 483796200 | 48379620 | 532175820 | 532175820 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 228 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | AMBON | AMBON |  | ME2-D7-AMB |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2022-02-07 | TEL.980/LG.310/DID-B0300000/2022 | 2022-06-27 | TEL.0928/LG.320/DID-A0000000/2022 | 2022-06-27 | 890992850 | 89099285 | 980092135 | 980092135 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-30
12021371 | 13 | 189 | 01C11B01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | AMBON | PASSO |  | ME-D7-PAO |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-02 | TEL.1180/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1099/LG.320/DID-A0000000/2022 | 2022-07-27 | 1871475430 | 187140148 | 2058615578 | 2058615578 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 198 | 01C11B01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | AMBON | PASSO |  | ME-D7-PAO |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-01 | TEL.1181/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1100/LG.320/DID-A0000000/2022 | 2022-07-27 | 43200000 | 79320000 | 122520000 | 122520000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 191 | 01C11B01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | GORONTALO | ISIMU |  | ME-D7-IMU |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-01 | TEL.1180/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1099/LG.320/DID-A0000000/2022 | 2022-07-27 | 2762468280 | 276239433 | 3038707713 | 3038707713 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 201 | 01C11B01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | GORONTALO | ISIMU |  | ME-D7-IMU |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-01 | TEL.1181/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1100/LG.320/DID-A0000000/2022 | 2022-07-27 | 43200000 | 79320000 | 122520000 | 122520000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 63 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | JAYAPURA | JAYAPURA |  | ME3-D7-JAP |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.164/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0135/LG.320/DID-A0000000/2022 | 2022-02-17 | 1582904480 | 158290448 | 1741194928 | 1741194928 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 84 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | JAYAPURA | JAYAPURA |  | ME3-D7-JAP |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.333/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0376/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 30000000 | 30000000 | 30000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 66 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | JAYAPURA | TIMIKA |  | ME9-D7-TMK |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2244/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0211/LG.320/DID-A0000000/2021 | 2021-12-24 | 1350117250 | 135011725 | 1485128975 | 1485128975 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 168 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | JAYAPURA | TIMIKA |  | ME-D7-TMK |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.334/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0371/LG.320/DID-A0000000/2022 | 2022-03-28 | 279741800 | 27974180 | 307715980 | 307715980 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 199 | 01C11B01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | KENDARI | BAU-BAU |  | ME-D7-BAU |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-01 | TEL.1181/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1100/LG.320/DID-A0000000/2022 | 2022-07-27 | 43200000 | 79320000 | 122520000 | 122520000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 200 | 01C11B01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | KENDARI | BAU-BAU |  | ME-D7-BAU |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-01 | TEL.1180/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1099/LG.320/DID-A0000000/2022 | 2022-07-27 | 2762468280 | 276239433 | 3038707713 | 3038707713 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 80 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | KENDARI | KENDARI |  | ME-D7-KDR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.333/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0376/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 30000000 | 30000000 | 30000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 42 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | KENDARI | KENDARI |  | ME-D7-KDR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 1560930200 | 156093020 | 1717023220 | 1717023220 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 139 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | KENDARI | KENDARI |  | ME-D7-KDR |  | 90 | 20 | 0 | Preparing | 2021-11-03 | 2022-08-25 | 2021-11-08 |  |  |  |  | 238801500 | 23880150 | 262681650 | 0 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT
12021371 | 13 | 164 | 01C11B01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | KENDARI | MANDONGA |  | ME-D7-MDG |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 891496850 | 89149685 | 980646535 | 980646535 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 192 | 01C11B01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | MANADO | KOTAMOBAGU |  | ME2-D7-KTG |  | 80 | 50 | 0 | Mat. Delivery | 2021-12-13 | 2022-08-25 | 2021-12-01 |  |  |  |  | 2762468280 | 276239433 | 3038707713 | 0 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT
12021371 | 13 | 202 | 01C11B01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | MANADO | KOTAMOBAGU |  | ME2-D7-KTG |  | 80 | 90 | 0 | Siap UT | 2021-12-13 | 2022-08-25 | 2021-12-01 |  |  |  |  | 43200000 | 79320000 | 122520000 | 0 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT
12021371 | 13 | 165 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | MANADO | MANADO |  | ME2-D7-MDO |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 779842800 | 77984280 | 857827080 | 857827080 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 160 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | MANADO | PANIKI |  | ME2-D7-PIK |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 761400500 | 76140050 | 837540550 | 837540550 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 107 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | PALU |  | ME9-D7-PAL |  | 90 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-08-25 | 2021-11-08 | TEL.976/LG.310/DID-B0300000/2022 | 2022-06-27 | TEL.0930/LG.320/DID-A0000000/2022 | 2022-06-27 | 2560015180 | 245186728 | 2805201908 | 2805201908 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-30
12021371 | 13 | 108 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | PALU |  | ME9-D7-PAL2 |  | 90 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-08-25 | 2021-11-08 | TEL.976/LG.310/DID-B0300000/2022 | 2022-06-27 | TEL.0930/LG.320/DID-A0000000/2022 | 2022-06-27 | 2560015180 | 245186728 | 2805201908 | 2805201908 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-30
12021371 | 13 | 113 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | PALU |  | ME9-D7-PAL2 |  | 90 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-08-25 | 2021-11-08 | TEL.1179/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1101/LG.320/DID-A0000000/2022 | 2022-07-27 | 0 | 75000000 | 75000000 | 75000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 96 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | PALU |  | ME-D7-PAL |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.160/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0131/LG.320/DID-A0000000/2022 | 2022-02-17 | 538759400 | 53875940 | 592635340 | 592635340 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 172 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | PALU |  | ME2-D7-PAL |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.168/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0128/LG.320/DID-A0000000/2022 | 2022-02-17 | 500101000 | 50010100 | 550111100 | 550111100 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 112 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | PALU |  | ME9-D7-PAL |  | 90 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-08-25 | 2021-11-08 | TEL.1179/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1101/LG.320/DID-A0000000/2022 | 2022-07-27 | 0 | 75000000 | 75000000 | 75000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021371 | 13 | 226 | 01C11B01 | 019 | 72030069 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PALU | SANTIGI |  | ME-D7-STG |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2022-02-07 | TEL.978/LG.310/DID-B0300000/2022 | 2022-06-27 | TEL.0925/LG.320/DID-A0000000/2022 | 2022-06-27 | 204669740 | 20466974 | 225136714 | 225136714 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-30
12021371 | 13 | 43 | 01C11B01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PARE-PARE | MAMUJU |  | ME-D7-MAM |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.160/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0131/LG.320/DID-A0000000/2022 | 2022-02-17 | 510082300 | 51008230 | 561090530 | 561090530 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 45 | 01C11B01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PARE-PARE | PALOPO |  | ME-D7-PLP |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 751038400 | 75103840 | 826142240 | 826142240 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 46 | 01C11B01 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PARE-PARE | PARE-PARE |  | ME-D7-PRE |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 1041793980 | 104179398 | 1145973378 | 1145973378 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 47 | 01C11B01 | 019 | 72040158 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | PARE-PARE | SIDRAP |  | ME-D7-SID |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 763538000 | 76353800 | 839891800 | 839891800 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 41 | 01C11B01 | 019 | 74060038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | SORONG | FAKFAK |  | ME-D7-FFA |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.160/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0131/LG.320/DID-A0000000/2022 | 2022-02-17 | 474049440 | 47404944 | 521454384 | 521454384 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 161 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | SORONG | SORONG |  | ME2-D7-SRG |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 244994700 | 24499470 | 269494170 | 269494170 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 167 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | SORONG | SORONG |  | ME-D7-SRG |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 244994700 | 24499470 | 269494170 | 269494170 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 125 | 01C11B01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | TERNATE | SOFIFI |  | ME-D7-SFI |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.160/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0131/LG.320/DID-A0000000/2022 | 2022-02-17 | 724515900 | 72451590 | 796967490 | 796967490 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 162 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | TERNATE | TERNATE |  | ME2-D7-TNT |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.167/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0126/LG.320/DID-A0000000/2022 | 2022-02-17 | 518543300 | 51854330 | 570397630 | 570397630 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 171 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | TERNATE | TERNATE |  | ME2-D7-TNT |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-31 | 2021-12-01 | TEL.168/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0128/LG.320/DID-A0000000/2022 | 2022-02-17 | 728790900 | 72879090 | 801669990 | 801669990 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 97 | 01C11B01 | 019 | 73030018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | TUAL | TUAL |  | ME-D7-TUL |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 704770740 | 70477074 | 775247814 | 775247814 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 204 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | BALAIKOTA |  | ME-D7-BAL, ME2-D7-BAL, ME3-D7-BAL |  | 80 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-08-25 | 2021-12-01 | TEL.981/LG.310/DID-B0300000/2022 | 2022-06-27 | TEL.0929/LG.320/DID-A0000000/2022 | 2022-06-27 | 43200000 | 229320000 | 272520000 | 272520000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-30
12021371 | 13 | 75 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | BALAIKOTA |  | ME9-D7-BAL |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-06-30 | 2021-11-08 | TEL.757/LG.310/DID-B0300000/2022 | 2022-05-27 | TEL.0774/LG.320/DID-A0000000/2022 | 2022-05-27 | 0 | 75000000 | 75000000 | 75000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-05-31
12021371 | 13 | 217 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | BALAIKOTA |  | ME9-D7-BAL |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-04-30 | 2022-02-01 | TEL.539/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0626/LG.320/DID-A0000000/2022 | 2022-04-26 | 760262000 | 76026200 | 836288200 | 836288200 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-04-28
12021371 | 13 | 61 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | BALAIKOTA |  | ME9-D7-BAL |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.332/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0375/LG.320/DID-A0000000/2022 | 2022-03-28 | 6391304330 | 628315643 | 7019619973 | 7019619973 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 44 | 01C11B01 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | MATTOANGIN |  | ME-D7-MAT |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 1796269760 | 179626976 | 1975896736 | 1975896736 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 81 | 01C11B01 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | MATTOANGIN |  | ME-D7-MAT |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.333/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0376/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 30000000 | 30000000 | 30000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 126 | 01C11B01 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PANAKUKANG |  | ME-D7-PAN |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.164/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0135/LG.320/DID-A0000000/2022 | 2022-02-17 | 269379700 | 26937970 | 296317670 | 296317670 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 124 | 01C11B01 | 019 | 72080998 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PENGAYOMAN |  | HRB-D7-PGY-TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2241/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0208/LG.320/DID-A0000000/2021 | 2021-12-24 | 667886140 | 66788614 | 734674754 | 734674754 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 62 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME9-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.332/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0375/LG.320/DID-A0000000/2022 | 2022-03-28 | 6391304330 | 628315643 | 7019619973 | 7019619973 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 85 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.333/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0376/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 30000000 | 30000000 | 30000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-03-31
12021371 | 13 | 76 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME9-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-04-30 | 2021-11-08 | TEL.540/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0627/LG.320/DID-A0000000/2022 | 2022-04-26 | 0 | 75000000 | 75000000 | 75000000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-04-28
12021371 | 13 | 205 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME-D7-PTR, ME3-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-04-30 | 2021-12-01 | TEL.543/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0625/LG.320/DID-A0000000/2022 | 2022-04-26 | 43200000 | 154320000 | 197520000 | 197520000 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-04-28
12021371 | 13 | 64 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-01-31 | 2021-11-08 | TEL.2244/LG.310/PND-B1050000/2021 | 2021-12-24 | TEL.0211/LG.320/DID-A0000000/2021 | 2021-12-24 | 1327478480 | 132747848 | 1460226328 | 1460226328 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2021-12-28
12021371 | 13 | 219 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME9-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-04-30 | 2022-02-01 | TEL.541/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0623/LG.320/DID-A0000000/2022 | 2022-04-26 | 1490191400 | 149019140 | 1639210540 | 1639210540 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-04-28
12021371 | 13 | 40 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | PETTARANI |  | ME2-D7-PTR |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.160/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0131/LG.320/DID-A0000000/2022 | 2022-02-17 | 1309720720 | 130972072 | 1440692792 | 1440692792 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
12021371 | 13 | 48 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007083/HK.810/OPS-10000000/2021 | Kontrak Ekspan Kapasitas L3 Aggregation Metro Ethernet Platform Huawei Tahap-2 2021 | 2021-11-03 | 2022-08-25 | Metro Ethernet | UJUNGPANDANG | SUDIANG |  | ME-D7-SUD |  | 100 | 100 | 100 | BAST-1 | 2021-11-03 | 2022-03-31 | 2021-11-08 | TEL.160/LG.310/DID-B0300000/2022 | 2022-02-17 | TEL.0131/LG.320/DID-A0000000/2022 | 2022-02-17 | 1368487980 | 136848798 | 1505336778 | 1505336778 | 4500440579 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-26
G2021244 | 8 | 10 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | BIAK |  | R7 SON BIA PT3 BINTARO |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1663/LG.310/DR7-12700000/2021 | 2021-11-24 | TEL.0170/LG.320/DR7-10400000/2021 | 2021-11-24 | 176868316 | 44431786 | 221300102 | 221300102 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-11-25
G2021244 | 8 | 9 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | BIAK |  | R7 SON BIA PT3 RAYA MARAW |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1666/LG.310/DR7-12700000/2021 | 2021-11-23 | TEL.0170/LG.320/DR7-10400000/2021 | 2021-11-24 | 198685253 | 52330479 | 251015732 | 251015732 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-11-25
G2021244 | 8 | 11 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | BIAK |  | R7 SON BIA PT3 ANGKASA SUMBEKER |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1662/LG.310/DR7-12700000/2021 | 2021-11-23 | TEL.0170/LG.320/DR7-10400000/2021 | 2021-11-24 | 229164122 | 56447667 | 285611789 | 285611789 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-11-25
G2021244 | 8 | 12 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | BIAK |  | R7 SON BIA PT3 PETRUS KAFIAR |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1664/LG.310/DR7-12700000/2021 | 2021-11-23 | TEL.0170/LG.320/DR7-10400000/2021 | 2021-11-24 | 85767479 | 25588930 | 111356409 | 111356409 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-11-25
G2021244 | 8 | 13 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | BIAK |  | R7 SON BIA PT3 YAFDAS |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1667/LG.310/DR7-12700000/2021 | 2021-11-24 | TEL.0170/LG.320/DR7-10400000/2021 | 2021-11-24 | 91188266 | 26343715 | 117531981 | 117531981 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-11-25
G2021244 | 8 | 14 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | BIAK |  | R7 SON BIA PT3 RAYA DOLOG |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1665/LG.310/DR7-12700000/2021 | 2021-11-24 | TEL.0170/LG.320/DR7-10400000/2021 | 2021-11-24 | 114337159 | 33637844 | 147975003 | 147975003 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-11-25
G2021244 | 8 | 17 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | NABIRE |  | R7 SON NAB PT3 ODC-NAB-FK |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-22 | TEL.1934/LG.310/DR7-12700000/2021 | 2021-12-11 | TEL.0187/LG.320/DR7-10400000/2021 | 2021-12-11 | 41006729 | 8989727 | 49996456 | 49996456 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-13
G2021244 | 8 | 18 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | NABIRE |  | R7 SON NAB PT3 RE MARTADINATA |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-23 | TEL.1933/LG.310/DR7-12700000/2021 | 2021-12-11 | TEL.0187/LG.320/DR7-10400000/2021 | 2021-12-11 | 223667283 | 54057951 | 277725234 | 277725234 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-13
G2021244 | 8 | 15 | 01E07V01 | 007 | 74060049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | RAJA AMPAT |  | R7 SON RJA PT3 DEPAN GEREJA WCBLESSING |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-12-10 | TEL.035/LG.310/DR7-12700000/2021 | 2022-01-26 | TEL.0010/LG.320/DR7-10400000/2022 | 2022-01-26 | 377072874 | 94142299 | 471215173 | 471215173 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-28
G2021244 | 8 | 16 | 01E07V01 | 007 | 74060049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | RAJA AMPAT |  | R7 SON RJA PT3 BMH |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-12-10 | TEL.034/LG.310/DR7-12700000/2021 | 2022-01-26 | TEL.0010/LG.320/DR7-10400000/2022 | 2022-01-26 | 155301357 | 43242324 | 198543681 | 198543681 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-28
G2021244 | 8 | 6 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | SORONG |  | R7 SON SON PT3 SP 2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.2092/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0228/LG.320/DR7-10400000/2021 | 2021-12-24 | 1158300767 | 295204603 | 1453505370 | 1453505370 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021244 | 8 | 7 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | SORONG |  | R7 SON SON PT3 ODC-SON-FSA DS 6 |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.1935/LG.310/DR7-12700000/2021 | 2021-12-11 | TEL.0187/LG.320/DR7-10400000/2021 | 2021-12-11 | 181272013 | 45465820 | 226737833 | 226737833 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-13
G2021244 | 8 | 8 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007095/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 13 LOP Area Witel Papua Barat | 2021-11-04 | 2022-01-18 | OSP FTTH PT-3 2021 | SORONG | SORONG |  | R7 SON SON PT3 KLAMONO |  | 100 | 100 | 100 | BAST-1 | 2021-11-04 | 2022-01-02 | 2021-11-12 | TEL.2091/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0228/LG.320/DR7-10400000/2021 | 2021-12-24 | 582147683 | 142375014 | 724522697 | 724522697 | 4500441216 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021245 | 3 | 6 | 01E07V04 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007127/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP NIQE Lokasi Sentani Area Witel Papua | 2021-11-05 | 2022-03-22 | BACKBONE NIQE | JAYAPURA | SENTANI |  | SENTANI - BMH AMAI |  | 100 |  | 0 |  | 2021-11-05 | 2021-12-19 | 2021-12-01 |  |  |  |  | 332797838 | 392781910 | 725579748 | 0 | 4500441188 |  |  |  |  | TRANSDATA SATKOMINDO
12021379 | 9 | 88 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | AMBON | AMBON |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.990/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0882/LG.320/DID-A0000000/2022 | 2022-06-28 | 14000000 | 30000000 | 44000000 | 44000000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-06-29
12021379 | 9 | 93 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.990/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0882/LG.320/DID-A0000000/2022 | 2022-06-28 | 7000000 | 15000000 | 22000000 | 22000000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-06-29
12021379 | 9 | 68 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.1035/LG.310/DID-B0300000/2022 | 2022-07-06 | TEL.1150/LG.320/DID-A0000000/2022 | 2022-07-06 | 205250000 | 17825000 | 223075000 | 223075000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-07-29
12021379 | 9 | 69 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.1035/LG.310/DID-B0300000/2022 | 2022-07-06 | TEL.1150/LG.320/DID-A0000000/2022 | 2022-07-06 | 205250000 | 17825000 | 223075000 | 223075000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-07-29
12021379 | 9 | 30 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | MANADO | PANIKI |  | PNK |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-03-08 | 2021-11-09 | TEL.1923/LG.310/PND-B1050000/2021 | 2021-12-10 | TEL.0105/LG.320/DID-A0000000/2021 | 2021-12-10 | 405405000 | 123310000 | 528715000 | 528715000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2021-12-24
12021379 | 9 | 89 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | SORONG | SORONG |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.990/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0882/LG.320/DID-A0000000/2022 | 2022-06-28 | 7000000 | 15000000 | 22000000 | 22000000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-06-29
12021379 | 9 | 85 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.1036/LG.310/DID-B0300000/2022 | 2022-07-06 | TEL.1151/LG.320/DID-A0000000/2022 | 2022-07-06 | 13550000 | 1084000 | 14634000 | 14634000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-07-29
12021379 | 9 | 29 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | UJUNGPANDANG | PETTARANI |  | PTR |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-03-08 | 2021-11-09 | TEL.489/LG.310/DID-B0300000/2022 | 2022-03-08 | TEL.0001/LG.320/DID-00000000/2022 | 2022-03-08 | 949700000 | 212145000 | 1161845000 | 1161845000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-04-26
12021379 | 9 | 84 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007219/HK.810/OPS-10000000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-11-09 | 2022-10-05 | CACHE & DNS | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-07-06 | 2021-11-09 | TEL.1036/LG.310/DID-B0300000/2022 | 2022-07-06 | TEL.1151/LG.320/DID-A0000000/2022 | 2022-07-06 | 13550000 | 1084000 | 14634000 | 14634000 | 4500441263 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-07-29
G2021259 | 1 | 6 | 01E07R05 | 007 | 73020035 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | NETWORK AREA | TELKOM REGIONAL VII | K.TEL.007250/HK.810/R7W-7F100000/2021 | PENGADAAN DAN PEMASANGAN OSP FO NIQE 3 LOP WITEL SULUT MALUT | 2021-11-09 | 2022-01-07 | BACKBONE NIQE | TERNATE | SOFIFI |  | R7 MDO TOB NIQE SOFIFI |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-01-07 | 2021-12-01 | TEL.334/LG.300/R7W-7F100000/2022 | 2022-03-31 | TEL.0001/LG.320/R7W-7F100000/2022 | 2022-03-31 | 153425257 | 30659562 | 184084819 | 184084819 | 4500441532 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-05-18
G2021259 | 1 | 8 | 01E07R05 | 007 | 73020043 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | NETWORK AREA | TELKOM REGIONAL VII | K.TEL.007250/HK.810/R7W-7F100000/2021 | PENGADAAN DAN PEMASANGAN OSP FO NIQE 3 LOP WITEL SULUT MALUT | 2021-11-09 | 2022-01-07 | BACKBONE NIQE | TERNATE | TETEWANG |  | R7 MDO TOB NIQE TETEWANG |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-01-07 | 2021-12-01 | TEL.335/LG.300/R7W-7F100000/2022 | 2022-03-31 | TEL.0001/LG.320/R7W-7F100000/2022 | 2022-03-31 | 43293916 | 13368522 | 56662438 | 56662438 | 4500441532 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-05-18
G2021259 | 1 | 7 | 01E07R05 | 007 | 73020044 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | NETWORK AREA | TELKOM REGIONAL VII | K.TEL.007250/HK.810/R7W-7F100000/2021 | PENGADAAN DAN PEMASANGAN OSP FO NIQE 3 LOP WITEL SULUT MALUT | 2021-11-09 | 2022-01-07 | BACKBONE NIQE | TERNATE | TOBELO |  | R7 MDO TOB NIQE TOBELO |  | 100 | 100 | 100 | BAST-1 | 2021-11-09 | 2022-01-07 | 2021-12-01 | TEL.336/LG.300/R7W-7F100000/2022 | 2022-03-31 | TEL.0001/LG.320/R7W-7F100000/2022 | 2022-03-31 | 150258654 | 30411922 | 180670576 | 180670576 | 4500441532 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-05-18
G2021260 | 3 | 9 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | JAILOLO |  | R7 MDO JLL PT3 SOAKONOR |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2063/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 48840902 | 8446009 | 57286911 | 57286911 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 11 | 01E07V01 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | LABUHA |  | R7 MDO LBH PT3 PASAR BARU |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2068/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 81835512 | 17620511 | 99456023 | 99456023 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 12 | 01E07V01 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | LABUHA |  | R7 MDO LBH PT3 TOMORI ATAS |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2069/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 104234171 | 21223620 | 125457791 | 125457791 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 10 | 01E07V01 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | LABUHA |  | R7 MDO LBH PT3 MARABOSE |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2065/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 329443206 | 65824476 | 395267682 | 395267682 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 13 | 01E07V01 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | LABUHA |  | R7 MDO LBH PT3 TOMORI BAWAH |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2064/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 102145678 | 21169751 | 123315429 | 123315429 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 6 | 01E07V01 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | LABUHA |  | R7 MDO LBH PT3 MANDAWONG |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2066/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 78543053 | 15359706 | 93902759 | 93902759 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 7 | 01E07V01 | 007 | 73020057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | MANGOLE |  | R7 MDO MGL PT3 TALIABU |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2164/LG.310/DR7-12700000/2021 | 2021-12-30 | TEL.0001/LG.320/DR7-10400000/2022 | 2021-12-30 | 379122536 | 76931363 | 456053899 | 456053899 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-01-04
G2021260 | 3 | 14 | 01E07V01 | 007 | 73020032 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | SANANA |  | R7 MDO SNN PT3 VALAHU |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2165/LG.310/DR7-12700000/2021 | 2021-12-30 | TEL.0001/LG.320/DR7-10400000/2022 | 2021-12-30 | 257777476 | 55366837 | 313144313 | 313144313 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-01-04
G2021260 | 3 | 15 | 01E07V01 | 007 | 73020032 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | SANANA |  | R7 MDO SNN PT3 VAGULU |  | 90 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2067/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 105651356 | 23620971 | 129272327 | 129272327 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021260 | 3 | 8 | 01E07V01 | 007 | 73020032 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007259/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 10 LOP Area Witel Sulut Malut | 2021-11-10 | 2022-01-13 | FTTH BATCH-3 | TERNATE | SANANA |  | R7 MDO SNN PT3 VACEI |  | 66 | 100 | 100 | BAST-1 | 2021-11-10 | 2022-01-13 | 2021-11-10 | TEL.2070/LG.310/DR7-12700000/2021 | 2021-12-23 | TEL.0225/LG.320/DR7-10400000/2021 | 2021-12-23 | 155564849 | 46606461 | 202171310 | 202171310 | 4500441603 |  |  |  |  | SOLUSI AKSES MANDIRI | 2021-12-27
G2021262 | 6 | 13 | 01E07V01 | 007 | 72010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BAHU |  | R7 MDO BAH PT3 PURI INDAH MALALAYANG |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2131/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 43659683 | 8487776 | 52147459 | 52147459 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 12 | 01E07V01 | 007 | 72010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BAHU |  | R7 MDO BAH PT3 MALALAYANG SATU |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2130/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 40909283 | 11705941 | 52615224 | 52615224 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 15 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | R7 MDO BIT PT3 JALUR KU TOWER TENDEKI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2138/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 48053653 | 9654921 | 57708574 | 57708574 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 14 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | R7 MDO BIT PT3 PESANTREN TENDEKI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2137/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 39663836 | 7836829 | 47500665 | 47500665 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 11 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | GERBANG INDAH AER UJANG |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2022-02-01 | TEL.729/LG.310/DR7-12700000/2022 | 2022-03-26 | TEL.0040/LG.320/DR7-10400000/2022 | 2022-03-26 | 147062611 | 27439746 | 174502357 | 174502357 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021262 | 6 | 16 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | R7 MDO BIT PT3 PERUM JL. DUA SAUDARA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2139/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 7185260 | 1149783 | 8335043 | 8335043 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 17 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | R7 MDO BIT PT3 KOMP. GMIM MAUMALONDO |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2140/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 15197642 | 3375928 | 18573570 | 18573570 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 18 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | R7 MDO BIT PT3 AERTEMBAGA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2141/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 3420859 | 861141 | 4282000 | 4282000 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 19 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | R7 MDO BIT PT3 PERUM BCL |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2142/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 181428705 | 33141213 | 214569918 | 214569918 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 10 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | BITUNG |  | PERUM DANOWUDU |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2022-02-01 | TEL.730/LG.310/DR7-12700000/2022 | 2022-03-26 | TEL.0040/LG.320/DR7-10400000/2022 | 2022-03-26 | 180863105 | 34551918 | 215415023 | 215415023 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021262 | 6 | 20 | 01E07V01 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | KOTAMOBAGU |  | R7 MDO KTG PT3 LOBONG PERUM GPI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2133/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 150756659 | 29381064 | 180137723 | 180137723 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 41 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 SUMOMPO |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2132/LG.310/DR7-12700000/2021 | 2021-12-25 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 27295752 | 5275464 | 32571216 | 32571216 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 21 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 MALENDENG_1 |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2116/LG.310/DR7-12700000/2021 | 2021-12-25 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 24907242 | 4429432 | 29336674 | 29336674 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 22 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 PERUM KOKA ASRI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2120/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 200474271 | 55127317 | 255601588 | 255601588 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 23 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 ASPOL TUMINTING |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2121/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 84421187 | 19235835 | 103657022 | 103657022 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 24 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 KAMPUNG TALI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2122/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 43502866 | 9813665 | 53316531 | 53316531 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 29 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 KHARISMA KOKA 2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2129/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 85679000 | 17534354 | 103213354 | 103213354 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 27 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 CAMAR PERKAMIL |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2126/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 4848770 | 580147 | 5428917 | 5428917 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 28 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 DALUGA KOMBOS |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2127/LG.310/DR7-12700000/2021 | 2021-12-27 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 6391275 | 763554 | 7154829 | 7154829 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 25 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 PERUM SIMPONI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2123/LG.310/DR7-12700000/2021 | 2021-12-25 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 51765090 | 10845437 | 62610527 | 62610527 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 26 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | MANADO |  | R7 MDO MDO PT3 BUMI NYIUR |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2124/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 115679273 | 25365136 | 141044409 | 141044409 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 34 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 DEPAN POS GPI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2119/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 33124669 | 5897036 | 39021705 | 39021705 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 33 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 SAMPING BALITKA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2118/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 31755393 | 5623347 | 37378740 | 37378740 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 32 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 PERUM COZY HOME & PERUM BALE LUHUR |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2117/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 120753942 | 24714848 | 145468790 | 145468790 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 31 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 LAPANGAN MAPANGET |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2115/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 50154142 | 11725044 | 61879186 | 61879186 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 35 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 BUHA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2125/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 86630067 | 20650258 | 107280325 | 107280325 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 30 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 KIMA ATAS PANIKI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2114/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 149004817 | 28795397 | 177800214 | 177800214 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 36 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 KAIRAGI PERMAI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2128/LG.310/DR7-12700000/2021 | 2021-12-26 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 85509107 | 19740432 | 105249539 | 105249539 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 37 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | PANIKI |  | R7 MDO PIK PT3 PALM HILL |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-12-01 | TEL.644/LG.310/DR7-12700000/2021 | 2022-01-27 | TEL.0014/LG.320/DR7-10400000/2022 | 2022-01-27 | 193380174 | 52388827 | 245769001 | 245769001 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-07
G2021262 | 6 | 38 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | TOMOHON |  | R7 MDO TMH PT3 WAILAN |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2135/LG.310/DR7-12700000/2021 | 2021-12-25 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 75463635 | 14549106 | 90012741 | 90012741 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 40 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | TONDANO |  | R7 MDO TDN PT3 GREEN KAWANGKOAN |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2136/LG.310/DR7-12700000/2021 | 2021-12-25 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 181900771 | 35118358 | 217019129 | 217019129 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021262 | 6 | 39 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007290/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 32 LOP Area Witel Sulut Malut | 2021-11-11 | 2022-03-31 | FTTH BATCH-3 | MANADO | TONDANO |  | R7 MDO TDN PT3 PUSAT KOTA TONDANO |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-02-08 | 2021-11-11 | TEL.2134/LG.310/DR7-12700000/2021 | 2021-12-25 | TEL.0241/LG.320/DR7-10400000/2021 | 2021-12-27 | 109595621 | 23850642 | 133446263 | 133446263 | 4500441677 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-30
G2021264 | 6 | 7 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 ENTROP ASRI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.724/LG.310/DR7-12700000/2022 | 2022-02-25 | TEL.0038/LG.320/DR7-10400000/2022 | 2022-02-26 | 20866204 | 5784803 | 26651007 | 26651007 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021264 | 6 | 6 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 BHAYANGKARA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.2084/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0226/LG.320/DR7-10400000/2021 | 2021-12-24 | 164629813 | 44953406 | 209583219 | 209583219 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021264 | 6 | 10 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 DWI KOALA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.2083/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0226/LG.320/DR7-10400000/2021 | 2021-12-24 | 276930989 | 61294933 | 338225922 | 338225922 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021264 | 6 | 9 | 01E07V01 | 007 | 74030072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | JAYAPURA | WAENA |  | R7 JYP WAE PT3 GRAHA YOTEFA WAENA |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.725/LG.310/DR7-12700000/2022 | 2022-02-26 | TEL.0038/LG.320/DR7-10400000/2022 | 2022-02-26 | 102925056 | 29698515 | 132623571 | 132623571 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021264 | 6 | 8 | 01E07V01 | 007 | 74030072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | JAYAPURA | WAENA |  | R7 JYP WAE PT3 PERUM PURI LESTARI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.726/LG.310/DR7-12700000/2022 | 2022-02-26 | TEL.0038/LG.320/DR7-10400000/2022 | 2022-02-26 | 114179287 | 31137260 | 145316547 | 145316547 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021264 | 6 | 12 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 SPADEM |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.2082/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0226/LG.320/DR7-10400000/2021 | 2021-12-24 | 621895577 | 152860851 | 774756428 | 774756428 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021264 | 6 | 13 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 JLN. NOWARI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.2080/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0226/LG.320/DR7-10400000/2021 | 2021-12-24 | 489993079 | 130417305 | 620410384 | 620410384 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021264 | 6 | 17 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 PERUM GRAHA SIMPATI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-12-01 | TEL.2081/LG.310/DR7-12700000/2021 | 2021-12-24 | TEL.0226/LG.320/DR7-10400000/2021 | 2021-12-24 | 609468141 | 153478775 | 762946916 | 762946916 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-27
G2021264 | 6 | 14 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 KOREM |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-11-12 | TEL.1766/LG.310/DR7-12700000/2021 | 2021-11-26 | TEL.0180/LG.320/DR7-10400000/2021 | 2021-11-26 | 112708337 | 23673496 | 136381833 | 136381833 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-04
G2021264 | 6 | 15 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 PAYUM ASRI |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-11-12 | TEL.1768/LG.310/DR7-12700000/2021 | 2021-11-26 | TEL.0180/LG.320/DR7-10400000/2021 | 2021-11-26 | 61679037 | 12920422 | 74599459 | 74599459 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-04
G2021264 | 6 | 18 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 MARGA MULYA2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-11-12 | TEL.1767/LG.310/DR7-12700000/2021 | 2021-11-26 | TEL.0180/LG.320/DR7-10400000/2021 | 2021-11-26 | 205561166 | 44590446 | 250151612 | 250151612 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-04
G2021264 | 6 | 16 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007298/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 13 LoP Area Witel Papua | 2021-11-11 | 2022-01-26 | OSP FTTH PT-3 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 WASUR |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-01-09 | 2021-11-12 | TEL.1769/LG.310/DR7-12700000/2021 | 2021-11-26 | TEL.0180/LG.320/DR7-10400000/2021 | 2021-11-26 | 337116697 | 77955702 | 415072399 | 415072399 | 4500441738 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-04
12021384 | 7 | 66 | 01C11B01 | 019 | 74060063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007302/HK.810/OPS-10000000/2021 | SP#6 Ekspan PE-VPN Cisco | 2021-11-11 | 2022-04-15 | Ekspan PE-VPN Cisco | SORONG | SORONG-1 |  | sr-sorong.1-new |  | 80 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-04-15 | 2021-12-13 | TEL.337/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0354/LG.320/DID-A0000000/2022 | 2022-03-28 | 3448868300 | 258785300 | 3707653600 | 3707653600 | 4500441425 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021384 | 7 | 67 | 01C11B01 | 019 | 74060060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007302/HK.810/OPS-10000000/2021 | SP#6 Ekspan PE-VPN Cisco | 2021-11-11 | 2022-04-15 | Ekspan PE-VPN Cisco | SORONG | SORONG-2 |  | sr-sorong.2-new |  | 80 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-04-15 | 2021-12-13 | TEL.337/LG.310/DID-B0300000/2022 | 2022-03-28 | TEL.0354/LG.320/DID-A0000000/2022 | 2022-03-28 | 3448868300 | 258785300 | 3707653600 | 3707653600 | 4500441425 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021384 | 7 | 32 | 01C11B01 | 019 | 72081028 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007302/HK.810/OPS-10000000/2021 | SP#6 Ekspan PE-VPN Cisco | 2021-11-11 | 2022-04-15 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG 2 |  | sr-sudiang.2-new |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-03-10 | 2021-11-15 | TEL.2247/LG.310.PND-B1050000/2021 | 2021-12-28 | TEL.0241/LG.320/DID-A0000000/2021 | 2021-12-28 | 1150533600 | 86020800 | 1236554400 | 1236554400 | 4500441425 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021384 | 7 | 24 | 01C11B01 | 019 | 72081028 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007302/HK.810/OPS-10000000/2021 | SP#6 Ekspan PE-VPN Cisco | 2021-11-11 | 2022-04-15 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG 2 |  | sr-sudiang.2-new |  | 100 | 100 | 100 | BAST-1 | 2021-11-11 | 2022-03-10 | 2021-11-15 | TEL.2245/LG.310.PND-B1050000/2021 | 2021-12-28 | TEL.0239/LG.320/DID-A0000000/2021 | 2021-12-28 | 2729784800 | 205022300 | 2934807100 | 2934807100 | 4500441425 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021385 | 7 | 10 | 01C11B02 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE AGGREGATION CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007320/HK.810/OPS-10050000/2021 | Kontrak Ekspan IMS Platform ZTE | 2021-11-11 | 2022-03-10 | IMS | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-03-13 | 2021-12-03 | TEL.220/LG.310/DID-B0300000/2022 | 2022-03-09 | TEL.0255/LG.320/DID-A0000000/2022 | 2022-03-09 | 2726606470 | 256123298 | 2982729768 | 2982729768 | 4500441426 |  |  |  |  | ZTE INDONESIA | 2022-03-23
12021385 | 7 | 13 | 01C11B02 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE AGGREGATION CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007320/HK.810/OPS-10050000/2021 | Kontrak Ekspan IMS Platform ZTE | 2021-11-11 | 2022-03-10 | IMS | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-03-13 | 2021-12-03 | TEL.220/LG.310/DID-B0300000/2022 | 2022-03-09 | TEL.0255/LG.320/DID-A0000000/2022 | 2022-03-09 | 2726606470 | 256123298 | 2982729768 | 2982729768 | 4500441426 |  |  |  |  | ZTE INDONESIA | 2022-03-23
12021388 | 8 | 40 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | MANADO |  | RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 63 | 01C11B01 | 019 | 72010061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | MANADO 1 |  | ASBR] ex PALEMBANG CENTRUM [ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2276/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0261/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 530963300 | 590963300 | 590963300 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 36 | 01C11B01 | 019 | 72010061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | MANADO 1 |  | ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 37 | 01C11B01 | 019 | 72010062 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | MANADO 2 |  | - TLG [ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 64 | 01C11B01 | 019 | 72010062 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | MANADO 2 |  | - TLG [ASBR] ex PALEMBANG CENTRUM - DLD [ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2276/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0261/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 689362400 | 749362400 | 749362400 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 29 | 01C11B01 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | MANADO CENTRUM |  | RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2274/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0259/LG.320/DID-A0000000/2021 | 2021-12-29 | 798785200 | 62416900 | 861202100 | 861202100 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 30 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI |  | RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2274/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0259/LG.320/DID-A0000000/2021 | 2021-12-29 | 798785200 | 62416900 | 861202100 | 861202100 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 44 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI |  | CENTRUM [RR] |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 41 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI |  | RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 73 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI |  | RR] ex TALANGKELAPA [RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2275/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0260/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 62416900 | 122416900 | 122416900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 23 | 01C11B01 | 019 | 72010874 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.1 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2277/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0262/LG.320/DID-A0000000/2021 | 2021-12-29 | 6306376500 | 474821100 | 6781197600 | 6781197600 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 65 | 01C11B01 | 019 | 72010874 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.1 |  | ASBR] ex TALANG KELAPA.1[ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2276/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0261/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 468844200 | 528844200 | 528844200 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 49 | 01C11B01 | 019 | 72010874 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.1 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.299/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0356/LG.320/DID-A0000000/2022 | 2022-03-25 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 32 | 01C11B01 | 019 | 72010874 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.1 |  | MR-TTC TSEL] ex JATINEGARA [STANDBY UNIT |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.298/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0355/LG.320/DID-A0000000/2022 | 2022-03-25 | 60000000 | 283746300 | 343746300 | 343746300 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 38 | 01C11B01 | 019 | 72010874 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.1 |  | RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 26 | 01C11B01 | 019 | 72010874 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.1 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2278/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0263/LG.320/DID-A0000000/2021 | 2021-12-29 | 2013433800 | 150536400 | 2163970200 | 2163970200 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 34 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL] ex MARPOYAN.1 [CORE-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.298/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0355/LG.320/DID-A0000000/2022 | 2022-03-25 | 60000000 | 57863200 | 117863200 | 117863200 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 24 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2277/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0262/LG.320/DID-A0000000/2021 | 2021-12-29 | 4840422900 | 364639100 | 5205062000 | 5205062000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 52 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.299/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0356/LG.320/DID-A0000000/2022 | 2022-03-25 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 75 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL] ex HR MUHAMMAD.1[SR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.298/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0355/LG.320/DID-A0000000/2022 | 2022-03-25 | 0 | 203722300 | 203722300 | 203722300 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 27 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2278/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0263/LG.320/DID-A0000000/2021 | 2021-12-29 | 2013433800 | 150536400 | 2163970200 | 2163970200 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 66 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | ASBR] ex TALANG KELAPA.2 [ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2276/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0261/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 468844200 | 528844200 | 528844200 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 74 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL] ex BATAM CENTRUM.2[SR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.298/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0355/LG.320/DID-A0000000/2022 | 2022-03-25 | 0 | 101351900 | 101351900 | 101351900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 33 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | MR-TTC TSEL] ex BATAM CENTRUM.1[SR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-25 | 2021-11-15 | TEL.298/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0355/LG.320/DID-A0000000/2022 | 2022-03-25 | 0 | 21505200 | 21505200 | 21505200 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-03-30
12021388 | 8 | 39 | 01C11B01 | 019 | 72010875 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | PANIKI.2 |  | -PNKC [ASBR] |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 57 | 01C11B01 | 019 | 72010853 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | TSEL TELING |  | RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 58 | 01C11B01 | 019 | 72010853 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | MANADO | TSEL TELING |  | RR] ex DEMANG LEBAR DAUN [RR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2275/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0260/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 62416900 | 122416900 | 122416900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 21 | 01C11B01 | 019 | 72081034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | UJUNGPANDANG | TELING.1 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2277/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0262/LG.320/DID-A0000000/2021 | 2021-12-29 | 5488172400 | 411675500 | 5899847900 | 5899847900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 42 | 01C11B01 | 019 | 72081034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | UJUNGPANDANG | TELING.1 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 67 | 01C11B01 | 019 | 72081034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | UJUNGPANDANG | TELING.1 |  | MR-TTC TSEL] ex MEDAN CENTRUM [ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2279/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0264/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 468386900 | 528386900 | 528386900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 43 | 01C11B01 | 019 | 72081035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | UJUNGPANDANG | TELING.2 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2280/LG.310.PND-B1050000/2021 | 2021-12-29 | TEL.0265/LG.320/DID-A0000000/2021 | 2021-12-29 | 0 | 290050000 | 290050000 | 290050000 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 13 | 01C11B01 | 019 | 72081035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | UJUNGPANDANG | TELING.2 |  | MR-TTC TSEL |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2277/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0262/LG.320/DID-A0000000/2021 | 2021-12-29 | 5488172400 | 411675500 | 5899847900 | 5899847900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021388 | 8 | 68 | 01C11B01 | 019 | 72081035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007340/HK.810/OPS-10050000/2021 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan Ekspan PE VPN Cisco | 2021-11-12 | 2022-07-25 | Ekspan PE-VPN Cisco | UJUNGPANDANG | TELING.2 |  | MR-TTC TSEL] ex MEDAN CENTRUM2 - AHZ [ASBR |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-03-11 | 2021-11-15 | TEL.2279/LG.310/PND-B1050000/2021 | 2021-12-29 | TEL.0264/LG.320/DID-A0000000/2021 | 2021-12-29 | 60000000 | 468386900 | 528386900 | 528386900 | 4500441927 |  |  |  |  | SISINDOKOM LINTASBUANA | 2021-12-29
12021389 | 8 | 49 | 01C11H04 | 019 | 73010122 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | AMBON | LABUHA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-05-12 | 2021-11-12 | TEL.3621/LG.310/DID-B1060000/2021 | 2021-12-27 | TEL.0306/LG.320/DID-A0000000/2021 | 2021-12-27 | 3251436502 | 762203588 | 4013640090 | 4013640090 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2021-12-30
12021389 | 8 | 52 | 01C11H04 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE TERRESTRIAL DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | JAYAPURA | SARMI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-05-12 | 2021-11-12 | TEL.3634/LG.310/DID-B1060000/2021 | 2021-12-27 | TEL.0305/LG.320/DID-A0000000/2021 | 2021-12-27 | 1618148000 | 0 | 1618148000 | 1618148000 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2021-12-30
12021389 | 8 | 27 | 01C11I07 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | AMBON | AMBON |  |  |  | 35 | 35 | 0 | Mat. Delivery | 2021-11-12 | 2022-11-08 | 2021-11-12 |  |  |  |  | 654403318 | 153838156 | 808241474 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021389 | 8 | 28 | 01C11I07 | 019 | 73010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | AMBON | BANDA NEIRA |  |  |  | 50 | 35 | 0 | Mat. Delivery | 2021-11-12 | 2022-09-09 | 2021-11-12 |  |  |  |  | 821395018 | 222838156 | 1044233174 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021389 | 8 | 41 | 01C11I07 | 019 | 73010031 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | AMBON | KAYU TIGA |  |  |  | 50 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-09-09 | 2021-11-12 | TEL.334/LG.310/DID-B1060000/2022 | 2022-07-23 | TEL.1075/LG.320/DID-A0000000/2022 | 2022-07-23 | 0 | 103717980 | 103717980 | 103717980 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-07-29
12021389 | 8 | 39 | 01C11I07 | 019 | 74030185 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | JAYAPURA | INDOMBA |  |  |  | 35 | 50 | 0 | Mat. Delivery | 2021-11-12 | 2022-11-08 | 2021-11-12 |  |  |  |  | 401174176 | 69667832 | 470842008 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021389 | 8 | 45 | 01C11I07 | 019 | 72050074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | KENDARI | WANCI |  |  |  | 50 | 35 | 0 | Mat. Delivery | 2021-11-12 | 2022-09-09 | 2021-11-12 |  |  |  |  | 1143428594 | 152586398 | 1296014992 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021389 | 8 | 43 | 01C11I07 | 019 | 72050074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | KENDARI | WANCI |  |  |  | 50 | 35 | 0 | Mat. Delivery | 2021-11-12 | 2022-09-09 | 2021-11-12 |  |  |  |  | 844403318 | 152586398 | 996989716 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021389 | 8 | 61 | 01C11I07 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | MANOKWARI | MANOKWARI |  |  |  | 90 | 100 | 100 | BAST-1 | 2021-11-12 | 2022-08-04 | 2021-11-12 | TEL.1060/LG.310/DID-B1060000/2022 | 2022-06-21 | TEL.1076/LG.320/DID-A0000000/2022 | 2022-06-21 | 1627160920 | 467365512 | 2094526432 | 2094526432 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA | 2022-07-29
12021389 | 8 | 30 | 01C11I07 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | SORONG | SORONG |  |  |  | 50 | 35 | 0 | Mat. Delivery | 2021-11-12 | 2022-09-09 | 2021-11-12 |  |  |  |  | 603623318 | 172812890 | 776436208 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
12021389 | 8 | 29 | 01C11I07 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | WIRELESS DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007342/HK.810/OPS-10000000/2021 | Kontrak Radio IP Long Haul 2021 | 2021-11-12 | 2022-12-18 | RADIO IP | SORONG | SORONG |  |  |  | 50 | 35 | 0 | Mat. Delivery | 2021-11-12 | 2022-09-09 | 2021-11-12 |  |  |  |  | 795203318 | 172812890 | 968016208 | 0 | 4500441142 |  |  |  |  | MULTIREKA PRIMA UTAMA
G2021274 | 3 | 12 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB305 STP MCP Dinas kelautan |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1783/LG.310/DR7-12700000/2021 | 2021-12-06 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 4256243 | 1936205 | 6192448 | 6192448 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 13 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB371 Anugerah Kusu-Kusu Sere Atas |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1785/LG.310/DR7-12700000/2021 | 2021-12-06 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 5746501 | 2367313 | 8113814 | 8113814 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 14 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB038 DMT Vihara Gunung Nona |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1788/LG.310/DR7-12700000/2021 | 2021-12-06 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3981909 | 1826691 | 5808600 | 5808600 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 11 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB288 DMT Mangga Dua Ambon |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1782/LG.310/DR7-12700000/2021 | 2021-12-06 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 4344553 | 1922605 | 6267158 | 6267158 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 8 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB176 MCR Jalan Listrik |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.629/LG.310/DR7-12700000/2021 | 2022-01-27 | TEL.0013/LG.320/DR7-10400000/2022 | 2022-01-27 | 2386987 | 978000 | 3364987 | 3364987 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-31
G2021274 | 3 | 9 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB037 ERI |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1776/LG.310/DR7-12700000/2021 | 2021-12-06 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 20268545 | 6799487 | 27068032 | 27068032 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 10 | 01E07V06 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | AMBON |  | R7 AMB ABO AMB082 WMI SKIP |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1777/LG.310/DR7-12700000/2021 | 2021-12-06 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3238271 | 1593053 | 4831324 | 4831324 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 7 | 01E07V06 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | MASOHI |  | R7 AMB MSH MSH391 TBG Waimital Kairatu |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1789/LG.310/DR7-12700000/2021 | 2021-12-08 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 8724453 | 2539609 | 11264062 | 11264062 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 6 | 01E07V06 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | MASOHI |  | R7 AMB MSH MSH007 Latu |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1772/LG.310/DR7-12700000/2021 | 2021-12-08 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 274197075 | 49569351 | 323766426 | 323766426 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 19 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB267 STP MCP Split Wayame |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1780/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3768589 | 1770271 | 5538860 | 5538860 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 20 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB329 TBG STO Passo |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1784/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3939245 | 1815407 | 5754652 | 5754652 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 21 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB143 Split Lateri Sec 2&3 |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1787/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3491273 | 1696925 | 5188198 | 5188198 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 22 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB302 Dmt Desa Hatu |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1790/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 8065725 | 3054627 | 11120352 | 11120352 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 26 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB229 DMT Perumnas Waiheru |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1779/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3152943 | 1570485 | 4723428 | 4723428 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 27 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB271 DMT Tawiri Airport 2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1781/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3366263 | 1626905 | 4993168 | 4993168 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 28 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB276 MCR Halong Baru |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1786/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 1982665 | 1224007 | 3206672 | 3206672 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 29 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB066 Protelindo Liliboi |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1791/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 22222143 | 7427055 | 29649198 | 29649198 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 18 | 01E07V06 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | PASSO |  | R7 AMB PAO AMB168 TELUK AMBON |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1778/LG.310/DR7-12700000/2021 | 2021-12-07 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 2832963 | 1485855 | 4318818 | 4318818 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 17 | 01E07V06 | 007 | 73010172 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | TIAKUR |  | R7 AMB TIA SML017 MOALAKOR(DMT) |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1775/LG.310/DR7-12700000/2021 | 2021-12-09 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 3494255 | 1660757 | 5155012 | 5155012 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 16 | 01E07V06 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | TUAL |  | R7 AMB TUL COK223 COMBATPELABUHANTUAL |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1773/LG.310/DR7-12700000/2021 | 2021-12-09 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 22579053 | 6005139 | 28584192 | 28584192 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 15 | 01E07V06 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | TUAL |  | R7 AMB TUL TUL025 Protelindo Pasir Panjang |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.1774/LG.310/DR7-12700000/2021 | 2021-12-09 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 722674754 | 131144059 | 853818813 | 853818813 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021274 | 3 | 30 | 01E07V06 | 007 | 73010089 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007464/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE-B 22 LOP Area Witel Maluku | 2021-11-18 | 2022-01-31 | FIMO NODE-B 2021 | AMBON | WAHAI |  | R7 AMB WHA MSH120 Tbg Morokay |  | 100 | 100 | 100 | BAST-1 | 2021-11-18 | 2022-01-31 | 2021-12-01 | TEL.2012/LG.310/DR7-12700000/2021 | 2021-12-21 | TEL.0215/LG.320/DR7-10400000/2021 | 2021-12-21 | 759729387 | 136950887 | 896680274 | 896680274 | 4500442467 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-23
G2021280 | 7 | 8 | 01E07V04 | 007 | 73010071 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | AMBON | SAPARUA |  | R7 AMB TIA NIQE Frekedel - Saparua |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-02-19 | 2021-12-01 | TEL.2153/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0244/LG.320/DR7-10400000/2021 | 2021-12-29 | 104247136 | 28431308 | 132678444 | 132678444 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-31
G2021280 | 7 | 7 | 01E07V04 | 007 | 73010172 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | AMBON | TIAKUR |  | R7 AMB TIA NIQE STO TIAKUR - PRT TIAKUR |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-02-19 | 2021-12-01 | TEL.1050/LG.310/DR7-12700000/2022 | 2022-06-18 | TEL.0112/LG.320/DR7-10400000/2022 | 2022-06-18 | 1028307603 | 181667483 | 1209975086 | 1209975086 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-01
G2021280 | 7 | 15 | 01E07V04 | 007 | 74010053 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | BIAK | WAROPEN |  | R7 SON WRP NIQE SITE BOTAWA - RNC BOTAWA |  | 100 | 0 | 0 | Preparing | 2021-11-22 | 2022-02-19 | 2021-12-01 |  |  |  |  | 49655401 | 57710508 | 107365909 | 0 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO
G2021280 | 7 | 13 | 01E07V04 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | MANOKWARI | BINTUNI |  | R7 SON BTI NIQE STO BINTUNI - PRT BINTUNI |  | 100 | 0 | 0 | Preparing | 2021-11-22 | 2022-02-19 | 2021-12-01 |  |  |  |  | 415365690 | 599622236 | 1014987926 | 0 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO
G2021280 | 7 | 14 | 01E07V04 | 007 | 74040033 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | MANOKWARI | REISE |  | R7 SON WSR NIQE SITE REISEI - PRT REISEI |  | 100 | 0 | 0 | Preparing | 2021-11-22 | 2022-02-19 | 2021-12-01 |  |  |  |  | 619412406 | 631822332 | 1251234738 | 0 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO
G2021280 | 7 | 9 | 01E07V04 | 007 | 74060078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | SORONG | KAIMANA |  | R7 SON KMN NIQE STO KAIMANA- KMN002 |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-02-19 | 2021-12-01 | TEL.2154/LG.310/DR7-12700000/2021 | 2021-12-29 | TEL.0244/LG.320/DR7-10400000/2021 | 2021-12-29 | 715305670 | 161094856 | 876400526 | 876400526 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-31
G2021280 | 7 | 10 | 01E07V04 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | SORONG | NABIRE |  | R7 SON NAB NIQE STO NABIRE- PRT NABIRE |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-02-19 | 2021-12-01 | TEL.948/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0087/LG.320/DR7-10400000/2022 | 2022-05-11 | 331338938 | 403405699 | 734744637 | 734744637 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2021280 | 7 | 11 | 01E07V04 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | SORONG | SERUI |  | R7 SON SRU NIQE STOSERUI - PRT SERUI |  | 100 | 0 | 0 | Preparing | 2021-11-22 | 2022-02-19 | 2021-12-01 |  |  |  |  | 369241507 | 1904569523 | 2273811030 | 0 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO
G2021280 | 7 | 12 | 01E07V04 | 007 | 74060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007565/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 9 LOP Area Witel Maluku dan Papua Barat | 2021-11-22 | 2022-03-26 | OSP-FO | SORONG | TEMINABUAN |  | R7 SONTMB NIQE STO TEMINAMBUAN - PRT TEMINABUAN |  | 100 | 50 | 0 | Mat. Delivery | 2021-11-22 | 2022-02-19 | 2021-12-01 |  |  |  |  | 102707576 | 121642069 | 224349645 | 0 | 4500442668 |  |  |  |  | TRANSDATA SATKOMINDO
G2021281 | 3 | 6 | 01E07V04 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007567/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 4 LOP Area Witel Sultra | 2021-11-22 | 2022-05-07 | OSP-FO Feeder | KENDARI | KENDARI |  | R7 KDI MDG NIQE STO MANDONGA - MH KDI 04/15 |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-03-21 | 2021-12-01 | TEL.803/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0052/LG.320/DR7-10400000/2022 | 2022-04-25 | 250121739 | 43971352 | 294093091 | 294093091 | 4500442669 |  |  |  |  | INNANDA INDAH | 2022-05-04
G2021281 | 3 | 7 | 01E07V04 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007567/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 4 LOP Area Witel Sultra | 2021-11-22 | 2022-05-07 | OSP-FO Feeder | KENDARI | KOLAKA |  | R7 KDI UNH NIQE UNAHA - KOLAKA |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-03-21 | 2021-12-01 | TEL.806/LG.310/DR7-12700000/2022 | 2022-04-25 | TEL.0052/LG.320/DR7-10400000/2022 | 2022-04-25 | 200390009 | 31562875 | 231952884 | 231952884 | 4500442669 |  |  |  |  | INNANDA INDAH | 2022-05-04
G2021281 | 3 | 8 | 01E07V04 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007567/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 4 LOP Area Witel Sultra | 2021-11-22 | 2022-05-07 | OSP-FO Feeder | KENDARI | KOLAKA |  | R7 KDI KKA NIQE KOLAKA KOTA |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-03-21 | 2021-12-01 | TEL.805/LG.310/DR7-12700000/2022 | 2022-04-25 | TEL.0052/LG.320/DR7-10400000/2022 | 2022-04-25 | 94054207 | 19106874 | 113161081 | 113161081 | 4500442669 |  |  |  |  | INNANDA INDAH | 2022-05-04
G2021281 | 3 | 9 | 01E07V04 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007567/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP NIQE 4 LOP Area Witel Sultra | 2021-11-22 | 2022-05-07 | OSP-FO Feeder | KENDARI | KOLAKA |  | R7 KDI KKA NIQE KOLAKA - BATULAKI |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2022-03-21 | 2021-12-01 | TEL.804/LG.310/DR7-12700000/2022 | 2022-04-25 | TEL.0052/LG.320/DR7-10400000/2022 | 2022-04-25 | 105457459 | 19319768 | 124777227 | 124777227 | 4500442669 |  |  |  |  | INNANDA INDAH | 2022-05-04
G2021285 | 2 | 20 | 01E07T02 | 007 | 74010058 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | BIAK | SUPIORI |  | BIA059 - R7 PPB SUPIORI BIA059 TBG Supiori Raya |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1058/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 6133326 | 2319295 | 8452621 | 8452621 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 21 | 01E07T02 | 007 | 74010053 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | BIAK | WAROPEN |  | BTW003 - R7 PPB WAROPEN BTW003 DMT Khemon Waropen |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1059/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 413010616 | 110711640 | 523722256 | 523722256 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 13 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | BINTUNI |  | COK220 - R7 PPB BINTUNI COK220 Combat Pasar Sentral Bintuni |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1065/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 6110933 | 2312481 | 8423414 | 8423414 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 16 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | BINTUNI |  | BTI023 - R7 PPB BINTUNI BTI023 Protelindo KM.9 Bintuni |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1062/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 79028106 | 29912928 | 108941034 | 108941034 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 15 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | BINTUNI |  | BTI010 - R7 PPB BINTUNI BTI010 Polres Bintuni DCS |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1061/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 7384205 | 2744551 | 10128756 | 10128756 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 14 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | BINTUNI |  | BTI024 - R7 PPB BINTUNI BTI024 Telecode Isat Bintuni |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1063/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 8343975 | 3081225 | 11425200 | 11425200 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 12 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | BINTUNI |  | BTI028 - R7 PPB BINTUNI BTI028 TBG RAYA BINTUNI |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1064/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 6133326 | 2319295 | 8452621 | 8452621 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 17 | 01E07T02 | 007 | 74040005 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | MANOKWARI |  | MWR025 - R7 PPB MANOKWARI MWR025 TBGMCPPOLSEKTRIKORAMANOKWARI |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1060/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 5618037 | 2601061 | 8219098 | 8219098 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 18 | 01E07T02 | 007 | 74040009 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | MANOKWARI | PRAFI |  | MWR007 - R7 PPB PRAFI MWR007 Prafi 2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.80/LG000/R7W-7H100000/2022 | 2022-02-09 | TEL.0002/LG.320/R7W-7H100000/2022 | 2022-02-09 | 505259193 | 108563691 | 613822884 | 613822884 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-11
G2021285 | 2 | 10 | 01E07T02 | 007 | 74060035 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | SORONG | BIAK |  | BIA031 - R7 PPB BIAK BIA031 Mokmer |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1056/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 4303108 | 2111691 | 6414799 | 6414799 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021285 | 2 | 19 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.007640/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 12 LOP AREA WITEL PAPUA BARAT | 2021-11-22 | 2021-12-21 | FIMO NODE-B 2021 | SORONG | SORONG |  | SON188 - R7 PPB SORONG SON188 Komp BP2IP Sorong |  | 100 | 100 | 100 | BAST-1 | 2021-11-22 | 2021-12-21 | 2021-12-01 | TEL.1057/LG000/R7W-7H100000/2021 | 2021-12-11 | TEL.0022/LG.320/R7W-7H100000/2021 | 2021-12-11 | 163895217 | 51597627 | 215492844 | 215492844 | 4500442708 |  |  |  |  | TRANSDATA SATKOMINDO | 2021-12-16
G2021289 | 5 | 13 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ARSO 2 |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1946/LG.310/DR7-12700000/2021 | 2021-12-16 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 2061778945 | 457311183 | 2519090128 | 2519090128 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 12 | 01E07V01 | 007 | 74030026 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | JAYAPURA B |  | R7 JYP SRM PT3 DOK 8 SOSIAL |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1938/LG.310/DR7-12700000/2021 | 2021-12-15 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 105371345 | 31741297 | 137112642 | 137112642 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 11 | 01E07V01 | 007 | 74030060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SARMI |  | R7 JYP SRM PT3 SARMI KOTA |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1956/LG.310/DR7-12700000/2021 | 2021-12-16 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 287921441 | 76801289 | 364722730 | 364722730 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 10 | 01E07V01 | 007 | 74030060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SARMI |  | R7 JYP SRM PT3 NEW ODC-SRM-FD |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1937/LG.310/DR7-12700000/2021 | 2021-12-16 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 933443777 | 248746973 | 1182190750 | 1182190750 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 16 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 BTN MARWAH INDAH & CITRA BUANA |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1940/LG.310/DR7-12700000/2021 | 2021-12-16 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 139824729 | 35696255 | 175520984 | 175520984 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 19 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 PERUM BERINGIN |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1947/LG.310/DR7-12700000/2021 | 2021-12-15 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 66714419 | 17684863 | 84399282 | 84399282 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 15 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 BTN GRAHA BINTANG TIMUR |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1939/LG.310/DR7-12700000/2021 | 2021-12-15 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 120526477 | 32573619 | 153100096 | 153100096 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 18 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 BTN GAJAH MADA |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1958/LG.310/DR7-12700000/2021 | 2021-12-15 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 148377567 | 35643294 | 184020861 | 184020861 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 20 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 HAWAII |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2022-01-01 | TEL.021/LG.310/DR7-12700000/2022 | 2022-01-19 | TEL.0017/LG.320/DR7-10400000/2022 | 2022-01-19 | 361576827 | 90346807 | 451923634 | 451923634 | 4500442860 |  |  |  |  | TELKOM AKSES | 2022-02-18
G2021289 | 5 | 17 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 BTN MATOA |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1941/LG.310/DR7-12700000/2021 | 2021-12-15 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 111770256 | 27782156 | 139552412 | 139552412 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 22 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 SP1 |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2022-01-01 | TEL.723/LG.310/DR7-12700000/2022 | 2022-03-12 | TEL.0035/LG.320/DR7-10400000/2022 | 2022-03-12 | 1227198072 | 318434538 | 1545632610 | 1545632610 | 4500442860 |  |  |  |  | TELKOM AKSES | 2022-03-16
G2021289 | 5 | 14 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | MERAUKE | MERAUKE |  | R7 JYP JPB PT3 YASA MULYA |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1978/LG.310/DR7-12700000/2021 | 2021-12-20 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 986716880 | 237817453 | 1224534333 | 1224534333 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021289 | 5 | 21 | 01E07V01 | 007 | 74050022 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.007722/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 13 LoP Area Witel Papua | 2021-11-23 | 2022-01-21 | FTTH BATCH-2 | MERAUKE | TANAH MERAH |  | R7 JYP TMR PT3 ODC-TMR-FB |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-15 | 2021-11-23 | TEL.1979/LG.310/DR7-12700000/2021 | 2021-12-20 | TEL.0211/LG.320/DR7-10400000/2021 | 2021-12-20 | 786942342 | 190127325 | 977069667 | 977069667 | 4500442860 |  |  |  |  | TELKOM AKSES | 2021-12-22
G2021290 | 1 | 10 | 01E07V04 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.007730/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP NIQE Palapa Ring Timur Merauke Area Witel Papua | 2021-11-23 | 2022-01-06 | PALAPA RING | MERAUKE | MERAUKE |  | R7 JYP MRK NIQE RUTE 2 NOC MERAUKE |  | 100 | 100 | 100 | BAST-1 | 2021-11-23 | 2021-12-20 | 2022-01-01 | TEL.001/LG.310/DR7-12700000/2021 | 2022-01-06 | TEL.0004/LG.320/DR7-10400000/2022 | 2022-01-06 | 181344501 | 53181388 | 234525889 | 234525889 | 4500442880 |  |  |  |  | TELKOM AKSES | 2022-01-27
12021402 | 6 | 125 | 01C11B03 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007894/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (GSD) | 2021-11-24 | 2022-11-30 | Modernisasi ME | PARE-PARE | RANTEPAO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-24 | 2022-05-22 | 2022-03-18 | TEL.743/LG.310/DID-B0300000/2022 | 2022-05-22 | TEL.0708/LG.320/DID-A0000000/2022 | 2022-05-22 | 823227504 | 107873560 | 931101064 | 931101064 | 4500442055 |  |  |  |  | GRAHA SARANA DUTA | 2022-05-31
12021402 | 6 | 140 | 01C11B03 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.007894/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (GSD) | 2021-11-24 | 2022-11-30 | Modernisasi ME | PARE-PARE | RANTEPAO |  |  |  | 77 | 50 | 0 | Mat. Delivery | 2021-11-24 | 2022-08-08 | 2021-12-01 |  |  |  |  | 773633915 | 78223458 | 851857373 | 0 | 4500442055 |  |  |  |  | GRAHA SARANA DUTA
12021403 | 6 | 60 | 01C11B03 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-04-29 | 2022-02-14 | TEL.741/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0710/LG.320/DID-A0000000/2022 | 2022-04-26 | 1603973442 | 176458200 | 1780431642 | 1780431642 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-05-31
12021403 | 6 | 63 | 01C11B03 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-05-19 | 2021-11-29 | TEL.537/LG.310/DID-B0300000/2022 | 2022-04-26 | TEL.0003/LG.320/DID-00000000/2022 | 2022-04-26 | 1123598976 | 235748285 | 1359347261 | 1359347261 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-04-28
12021403 | 6 | 38 | 01C11B03 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-02-08 | 2021-12-01 | TEL.340/LG.310/DID-B0300000/2022 | 2022-02-05 | TEL.0409/LG.320/DID-A0000000/2022 | 2022-02-05 | 1333343801 | 218542508 | 1551886309 | 1551886309 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-03-31
12021403 | 6 | 41 | 01C11B03 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | PALU | PALU-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-02-08 | 2021-12-13 | TEL.340/LG.310/DID-B0300000/2022 | 2022-02-05 | TEL.0409/LG.320/DID-A0000000/2022 | 2022-02-05 | 1633427354 | 178033111 | 1811460465 | 1811460465 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-03-31
12021403 | 6 | 26 | 01C11B03 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | PALU | PALU-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-03-24 | 2022-01-05 | TEL.339/LG.310/DID-B0300000/2022 | 2022-03-21 | TEL.0407/LG.320/DID-A0000000/2022 | 2022-03-21 | 1005802077 | 226356809 | 1232158886 | 1232158886 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-03-31
12021403 | 6 | 27 | 01C11B03 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | PALU | PALU-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-03-24 | 2022-01-05 | TEL.339/LG.310/DID-B0300000/2022 | 2022-03-21 | TEL.0407/LG.320/DID-A0000000/2022 | 2022-03-21 | 878347799 | 214762212 | 1093110011 | 1093110011 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-03-31
12021403 | 6 | 42 | 01C11B03 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | PALU | PALU-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-02-08 | 2021-12-13 | TEL.340/LG.310/DID-B0300000/2022 | 2022-02-05 | TEL.0409/LG.320/DID-A0000000/2022 | 2022-02-05 | 1379188519 | 176458200 | 1555646719 | 1555646719 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-03-31
12021403 | 6 | 68 | 01C11B03 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | PARE-PARE | RANTEPAO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-04-30 | 2022-02-18 | TEL.742/LG.310/DID-B0300000/2022 | 2022-04-29 | TEL.0711/LG.320/DID-A0000000/2022 | 2022-04-29 | 697695579 | 56906497 | 754602076 | 754602076 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-05-31
12021403 | 6 | 32 | 01C11B03 | 019 | 74060052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | SORONG | WAISAI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-11-25 | 2022-03-24 | 2022-01-04 | TEL.339/LG.310/DID-B0300000/2022 | 2022-03-21 | TEL.0407/LG.320/DID-A0000000/2022 | 2022-03-21 | 677153579 | 98185628 | 775339207 | 775339207 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA | 2022-03-31
12021403 | 6 | 25 | 01C11B03 | 019 | 72081037 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008028/HK.810/OPS-10000000/2021 | Pengadaan Sipil Support POP & CLS 2021 | 2021-11-25 | 2022-10-31 | sipil support | UJUNGPANDANG | CLS NEW MAKASSAR |  |  |  | 40 | 59 | 0 | Instalasi | 2021-11-25 | 2022-10-05 | 2022-01-05 |  |  |  |  | 2957883710 | 705090488 | 3662974198 | 0 | 4500439779 |  |  |  |  | GRAHA SARANA DUTA
12021407 | 9 | 121 | 01C11G01 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | JAYAPURA | SARMI |  | SMI015 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.1049/LG.310/DID-C0300000/2022 | 2022-03-23 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 3650001354 | 837067775 | 4487069129 | 4487069129 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 135 | 01C11G01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | MANADO | TONDANO |  | TDO090 | TDO090 | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0898/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 30308345 | 7848877 | 38157222 | 38157222 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 136 | 01C11G01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | MANADO | TONDANO |  | TDO042 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0897/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 380885090 | 448012264 | 828897354 | 828897354 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 142 | 01C11G01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | MANOKWARI | MANOKWARI |  | MWR083 |  | 90 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-08-29 | 2022-01-01 | TEL.1717/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0659/LG.320/DID-A0000000/2022 | 2022-05-23 | 1947124745 | 480387565 | 2427512310 | 2427512310 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-05-30
12021407 | 9 | 141 | 01C11G01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | MANOKWARI | MANOKWARI |  | MWR028 |  | 90 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-08-29 | 2022-01-01 | TEL.1716/LG.310/DID-C0300000/2022 | 2022-05-23 | TEL.0659/LG.320/DID-A0000000/2022 | 2022-05-23 | 6955883 | 2484938 | 9440821 | 9440821 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-05-30
12021407 | 9 | 95 | 01C11G01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAJENE |  | MAJ039 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0900/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 13479472 | 2691304 | 16170776 | 16170776 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 96 | 01C11G01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAJENE |  | MAJ024 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-02-01 | TEL.0505/LG.310/DID-C0300000/2022 | 2022-02-17 | TEL.0191/LG.320/DID-A0000000/2022 | 2022-02-18 | 37423395 | 7240373 | 44663768 | 44663768 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021407 | 9 | 97 | 01C11G01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAJENE |  | MAJ050 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-02-01 | TEL.0506/LG.310/DID-C0300000/2022 | 2022-02-17 | TEL.0191/LG.320/DID-A0000000/2022 | 2022-02-18 | 51111577 | 10646921 | 61758498 | 61758498 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021407 | 9 | 92 | 01C11G01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAJENE |  | MAJ023 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0899/LG.310/DID-C0300000/2022 | 2022-03-24 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 521754763 | 99908388 | 621663151 | 621663151 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 99 | 01C11G01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAJENE |  | MAJ011 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-02-01 | TEL.1335/LG.310/DID-C0300000/2022 | 2022-04-23 | TEL.0587/LG.320/DID-A0000000/2022 | 2022-04-23 | 9374026 | 2125082 | 11499108 | 11499108 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-04-28
12021407 | 9 | 98 | 01C11G01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAJENE |  | MAJ006 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-02-01 | TEL.1334/LG.310/DID-C0300000/2022 | 2022-04-23 | TEL.0587/LG.320/DID-A0000000/2022 | 2022-04-23 | 1365154165 | 251969106 | 1617123271 | 1617123271 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-04-28
12021407 | 9 | 100 | 01C11G01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAMUJU |  | MAM011 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0924/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 1203339 | 785982 | 1989321 | 1989321 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 93 | 01C11G01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAMUJU |  | MAM025 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0923/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 1385240399 | 281010375 | 1666250774 | 1666250774 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 101 | 01C11G01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | MAMUJU |  | MAM075 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-03-22 | TEL.0922/LG.310/DID-C0300000/2022 | 2022-03-25 | TEL.0382/LG.320/DID-A0000000/2022 | 2022-03-25 | 1203339 | 785982 | 1989321 | 1989321 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-03-31
12021407 | 9 | 94 | 01C11G01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | PARE-PARE | PASANG KAYU |  | DGL111 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-01-01 | TEL.0519/LG.310/DID-C0300000/2022 | 2022-02-18 | TEL.0191/LG.320/DID-A0000000/2022 | 2022-02-18 | 1016907657 | 189094051 | 1206001708 | 1206001708 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021407 | 9 | 102 | 01C11G01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SINJAI |  | SIN006 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-01-01 | TEL.0503/LG.310/DID-C0300000/2022 | 2022-02-17 | TEL.0191/LG.320/DID-A0000000/2022 | 2022-02-18 | 101596157 | 18022449 | 119618606 | 119618606 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021407 | 9 | 105 | 01C11G01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SINJAI |  | SIN023 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-01-01 | TEL.0504/LG.310/DID-C0300000/2022 | 2022-02-17 | TEL.0191/LG.320/DID-A0000000/2022 | 2022-02-18 | 66881412 | 15549011 | 82430423 | 82430423 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021407 | 9 | 104 | 01C11G01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SINJAI |  | SIN014 |  | 100 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-05-13 | 2022-01-01 | TEL.0518/LG.310/DID-C0300000/2022 | 2022-02-18 | TEL.0191/LG.320/DID-A0000000/2022 | 2022-02-18 | 630629073 | 111735644 | 742364717 | 742364717 | 4500443632 |  |  |  |  | TELKOM AKSES | 2022-02-27
12021407 | 9 | 137 | 01C11G01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SUNGGUMINASA |  | SNS361 |  | 90 | 50 | 0 | Mat. Delivery | 2021-12-01 | 2022-08-29 | 2022-01-01 |  |  |  |  | 3706994 | 3087556 | 6794550 | 0 | 4500443632 |  |  |  |  | TELKOM AKSES
12021407 | 9 | 106 | 01C11G01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SUNGGUMINASA |  | SNS003 |  | 90 | 50 | 0 | Mat. Delivery | 2021-12-01 | 2022-08-29 | 2022-01-01 |  |  |  |  | 245996957 | 75933345 | 321930302 | 0 | 4500443632 |  |  |  |  | TELKOM AKSES
12021407 | 9 | 103 | 01C11G01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008613/HK.810/OPS-10000000/2021 | SP#4 OSP FO Node-B Telkomsel Tahap-2 | 2021-12-01 | 2022-08-15 | Node-B 2021 (DID) | UJUNGPANDANG | SUNGGUMINASA |  | SNS036 |  | 90 | 50 | 0 | Mat. Delivery | 2021-12-01 | 2022-08-29 | 2022-01-01 |  |  |  |  | 430200287 | 546703053 | 976903340 | 0 | 4500443632 |  |  |  |  | TELKOM AKSES
G2021316 | 1 | 7 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | ABEPURA |  | R7 JYP ABE JAP495 MCR BPD Furia- MCR BPD Furia |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.50/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 7260832 | 3277286 | 10538118 | 10538118 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 8 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | ABEPURA |  | R7 JYP ABE JAP479 DMT MCP SMP 2- DMT MCP SMP 2 |  | 65 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.51/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 3623289 | 1991916 | 5615205 | 5615205 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 6 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | ABEPURA |  | R7 JYPABE JAP294 MCR Wahno Furia-MCR Wahno Furia |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.49/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 5632651 | 2254032 | 7886683 | 7886683 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 13 | 01E07L12 | 007 | 74030162 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | JAYAPURA |  | R7 JYP JAP JAP543 TBG MCP Lapangan Hamadi- TBG MCP Lapangan Hamadi |  | 65 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.53/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 5117612 | 2097310 | 7214922 | 7214922 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 16 | 01E07L12 | 007 | 74030043 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | KUALA KENCANA |  | R7 JYP KKU TIM029 Kuala Kencana City- KUALA KENCANA CITY |  | 75 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.60/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 201382503 | 197537136 | 398919639 | 398919639 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 19 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | SENTANI |  | R7 JYP SNI JAP024 DMT Koramil Hawai- DMT Koramil Hawai |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.59/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 34788701 | 11016067 | 45804768 | 45804768 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 18 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | SENTANI |  | R7 JTP SNI JAP463 TBG Hawai Raya- TBG Hawai Raya |  | 65 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.58/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 3848002 | 1971983 | 5819985 | 5819985 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 17 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | SENTANI |  | R7 JYP SNI JAP225 DMT Nendali 1- DMT Nendali 1 |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.57/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 7668068 | 2829705 | 10497773 | 10497773 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 9 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM225 TBG Nenas SP2 Timika- TBG Nenas SP2 Timika |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.55/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 33401293 | 11131612 | 44532905 | 44532905 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 10 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | TIMIKA |  | R7 JYP TIM TIM147 TBG Desa Sempang- TBG Desa Sempang |  | 65 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.56/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 4540514 | 1804622 | 6345136 | 6345136 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 12 | 01E07L12 | 007 | 74030072 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | JAYAPURA | WAENA |  | R7 JYP WAE JAP468 TBG Jakale- TBG Jakele |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.52/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 9331690 | 2751868 | 12083558 | 12083558 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021316 | 1 | 15 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.008621/HK.810/R7W-7B100000/2021 | Pengadaan Pekerjaan FIMO Node B 14 LOP Area Witel Papua | 2021-12-01 | 2022-02-28 | FIMO NODE-B 2021 | MERAUKE | MERAUKE |  | R7 JYP MRK MRK092 DMT Gang Rawa- DMT Gang Rawa |  | 70 | 100 | 100 | BAST-1 | 2021-12-01 | 2022-02-28 | 2021-12-01 | TEL.54/LG270/R7W-7B100000/2022 | 2022-01-21 | TEL.0001/LG.320/R7W-7B100000/2022 | 2022-01-21 | 3799304 | 2090100 | 5889404 | 5889404 | 4500443896 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-02-24
G2021319 | 1 | 10 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.008683/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Plus Batch 3 Tahun 2021 Area Witel Maluku | 2021-12-02 | 2022-03-01 | PT2 | AMBON | AMBON |  | R7 ABO PT3 BTN KECE |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-10 | 2021-12-03 | TEL.651/LG.310/DR7-12700000/2022 | 2022-03-01 | TEL.0028/LG.320/DR7-10400000/2022 | 2022-03-01 | 134609993 | 40798307 | 175408300 | 175408300 | 4500444053 |  |  |  |  | TELKOM AKSES | 2022-03-10
G2021319 | 1 | 11 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.008683/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Plus Batch 3 Tahun 2021 Area Witel Maluku | 2021-12-02 | 2022-03-01 | PT2 | AMBON | AMBON |  | R7 AMB ABO PT3 HATALAI |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-10 | 2021-12-03 | TEL.652/LG.310/DR7-12700000/2022 | 2022-03-01 | TEL.0028/LG.320/DR7-10400000/2022 | 2022-03-01 | 328787094 | 64238503 | 393025597 | 393025597 | 4500444053 |  |  |  |  | TELKOM AKSES | 2022-03-10
G2021319 | 1 | 12 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.008683/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Plus Batch 3 Tahun 2021 Area Witel Maluku | 2021-12-02 | 2022-03-01 | PT2 | AMBON | PASSO |  | R7 AMB PAO PT3 LAHA |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-10 | 2021-12-03 | TEL.653/LG.310/DR7-12700000/2022 | 2022-03-01 | TEL.0028/LG.320/DR7-10400000/2022 | 2022-03-01 | 484240653 | 127323323 | 611563976 | 611563976 | 4500444053 |  |  |  |  | TELKOM AKSES | 2022-03-10
G2021319 | 1 | 13 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.008683/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Plus Batch 3 Tahun 2021 Area Witel Maluku | 2021-12-02 | 2022-03-01 | PT2 | AMBON | PASSO |  | R7 AMB PAO PT3 POKA |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-10 | 2021-12-03 | TEL.654/LG.310/DR7-12700000/2022 | 2022-03-01 | TEL.0028/LG.320/DR7-10400000/2022 | 2022-03-01 | 302931100 | 78201740 | 381132840 | 381132840 | 4500444053 |  |  |  |  | TELKOM AKSES | 2022-03-10
G2021319 | 1 | 14 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.008683/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Plus Batch 3 Tahun 2021 Area Witel Maluku | 2021-12-02 | 2022-03-01 | PT2 | AMBON | PASSO |  | R7 AMB PAO PT3 WAITATIRI |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-10 | 2021-12-03 | TEL.655/LG.310/DR7-12700000/2022 | 2022-03-01 | TEL.0028/LG.320/DR7-10400000/2022 | 2022-03-01 | 737395032 | 173576561 | 910971593 | 910971593 | 4500444053 |  |  |  |  | TELKOM AKSES | 2022-03-10
12021409 | 11 | 195 | 01C11H01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008686/HK.810/OPS-10000000/2021 | SP#9 DWDM dan OTN Platform ZTE - CNOP NARU, HEM dan OLO | 2021-12-02 | 2022-07-19 | DWDM & OTN | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-02 | 2022-05-04 | 2022-01-27 | TEL.302/LG.310/DID-B1060000/2022 | 2022-01-31 | TEL.0069/LG.320/DID-A0000000/2022 | 2022-01-31 | 748105500 | 69915798 | 818021298 | 818021298 | 4500444006 |  |  |  |  | ZTE INDONESIA | 2022-01-31
12021409 | 11 | 194 | 01C11H01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008686/HK.810/OPS-10000000/2021 | SP#9 DWDM dan OTN Platform ZTE - CNOP NARU, HEM dan OLO | 2021-12-02 | 2022-07-19 | DWDM & OTN | JAYAPURA | SENTANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-02 | 2022-05-04 | 2022-01-27 | TEL.302/LG.310/DID-B1060000/2022 | 2022-01-31 | TEL.0069/LG.320/DID-A0000000/2022 | 2022-01-31 | 748105500 | 69915798 | 818021298 | 818021298 | 4500444006 |  |  |  |  | ZTE INDONESIA | 2022-01-31
12021409 | 11 | 120 | 01C11H01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008686/HK.810/OPS-10000000/2021 | SP#9 DWDM dan OTN Platform ZTE - CNOP NARU, HEM dan OLO | 2021-12-02 | 2022-07-19 | DWDM & OTN | JAYAPURA | TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-02 | 2022-05-04 | 2021-12-27 | TEL.301/LG.310/DID-B1060000/2022 | 2022-01-31 | TEL.0068/LG.320/DID-A0000000/2022 | 2022-01-31 | 601163000 | 51513999 | 652676999 | 652676999 | 4500444006 |  |  |  |  | ZTE INDONESIA | 2022-01-31
12021409 | 11 | 193 | 01C11H01 | 019 | 74030179 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008686/HK.810/OPS-10000000/2021 | SP#9 DWDM dan OTN Platform ZTE - CNOP NARU, HEM dan OLO | 2021-12-02 | 2022-07-19 | DWDM & OTN | JAYAPURA | TTC JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-02 | 2022-05-04 | 2022-01-27 | TEL.302/LG.310/DID-B1060000/2022 | 2022-01-31 | TEL.0069/LG.320/DID-A0000000/2022 | 2022-01-31 | 1489390700 | 139320096 | 1628710796 | 1628710796 | 4500444006 |  |  |  |  | ZTE INDONESIA | 2022-01-31
12021409 | 11 | 121 | 01C11H01 | 019 | 74030178 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.008686/HK.810/OPS-10000000/2021 | SP#9 DWDM dan OTN Platform ZTE - CNOP NARU, HEM dan OLO | 2021-12-02 | 2022-07-19 | DWDM & OTN | JAYAPURA | TTC TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-02 | 2022-05-04 | 2021-12-27 | TEL.301/LG.310/DID-B1060000/2022 | 2022-01-31 | TEL.0068/LG.320/DID-A0000000/2022 | 2022-01-31 | 601163000 | 51513999 | 652676999 | 652676999 | 4500444006 |  |  |  |  | ZTE INDONESIA | 2022-01-31
G2021321 | 6 | 6 | 01E07V04 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.008764/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 2 LoP Area Witel Sulselbar | 2021-12-03 | 2022-05-20 | NIQE | PARE-PARE | RANTEPAO |  | R7 PRE RTP NIQE MLE004-STO.RTP |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-27 | 2022-03-01 | TEL.868/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0061/LG.320/DR7-10400000/2022 | 2022-05-18 | 45064437 | 10424746 | 55489183 | 55489183 | 4500444197 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-05-21
G2021321 | 6 | 7 | 01E07V04 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | NETWORK DEPLOYMENT & PROJECT SUPERVISION | TELKOM REGIONAL VII | K.TEL.008764/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan NIQE 2 LoP Area Witel Sulselbar | 2021-12-03 | 2022-05-20 | NIQE | PARE-PARE | RANTEPAO |  | R7 PRE RTP NIQE JT46-STO.RTP |  | 100 | 100 | 100 | BAST-1 | 2021-12-03 | 2022-01-21 | 2022-03-01 | TEL.867/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0061/LG.320/DR7-10400000/2022 | 2022-05-18 | 84266889 | 30235637 | 114502526 | 114502526 | 4500444197 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-05-21
G2021327 | 2 | 12 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009153/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH Lokasi IKK Enarotali dan Tigi Tahun 2021 Area Witel Papua Barat | 2021-12-09 | 2022-07-31 | FTTH BATCH-3 | SORONG | NABIRE |  | R7 SON NAB PT3 ENAROTALI FB |  | 100 | 100 | 100 | BAST-1 | 2021-12-09 | 2022-03-08 | 2022-01-01 | TEL.1107/LG.310/DR7-12700000/2022 | 2022-07-23 | TEL.0125/LG.320/DR7-10400000/2022 | 2022-07-23 | 228246000 | 48549458 | 276795458 | 276795458 | 4500444819 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-30
G2021327 | 2 | 10 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009153/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH Lokasi IKK Enarotali dan Tigi Tahun 2021 Area Witel Papua Barat | 2021-12-09 | 2022-07-31 | FTTH BATCH-3 | SORONG | NABIRE |  | R7 SON NAB PT3 TIGI |  | 100 | 100 | 100 | BAST-1 | 2021-12-09 | 2022-03-08 | 2022-01-01 | TEL.1106/LG.310/DR7-12700000/2022 | 2022-07-22 | TEL.0125/LG.320/DR7-10400000/2022 | 2022-07-23 | 272614158 | 56645599 | 329259757 | 329259757 | 4500444819 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-30
G2021334 | 1 | 12 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MAMUJU |  | MAM037 - R7 PRE MAM MAM037 Ampalas |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-20 | TEL.1002/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 12820424 | 3247775 | 16068199 | 16068199 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021334 | 1 | 10 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MAMUJU |  | MAM031 - R7 PRE MAM MAM031 DMT LemoLemo |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-20 | TEL.1000/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 266513879 | 52410948 | 318924827 | 318924827 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021334 | 1 | 11 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MAMUJU |  | MAJ045 - R7 PRE MAM MAJ045 DMT Lembang |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-20 | TEL.1001/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 4750093 | 1814078 | 6564171 | 6564171 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021334 | 1 | 13 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MASAMBA |  | MAS118 - R7 PRE MAS MAS118 Tete Induk sec 2 |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-20 | TEL.1003/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 505183566 | 94223993 | 599407559 | 599407559 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021334 | 1 | 14 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MASAMBA |  | MAS121 - R7 PRE MAS MAS121 Sabbang sec 2 |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-18 | TEL.1004/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 144398956 | 37592079 | 181991035 | 181991035 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021334 | 1 | 16 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MASAMBA |  | MAS003 - R7 PRE MAS MAS003 Wotu |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-20 | TEL.1006/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 28281762 | 7763069 | 36044831 | 36044831 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021334 | 1 | 15 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009274/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 7 LOP Area Witel Sulselbar | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MASAMBA |  | MAS001 - R7 PRE MAS MAS001 Masamba |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2021-12-20 | TEL.1005/LG.320/R7W-7D100000/2021 | 2022-01-01 | TEL.0001/LG.320/R7W-7D100000/2022 | 2022-01-01 | 16840251 | 5395798 | 22236049 | 22236049 | 4500444835 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-31
G2021336 | 1 | 8 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009276/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 3 LOP Area Witel Sulselbar. | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | MASAMBA |  | R7 PRE MAS MLI097 TBG MANTADULU ANGKONA |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-23 | 2022-02-14 | TEL.43/LG.320/R7W-7D100000/2022 | 2022-02-16 | TEL.0003/LG.320/R7W-7D100000/2022 | 2022-02-16 | 677521506 | 118269746 | 795791252 | 795791252 | 4500444833 |  |  |  |  | INATEL NUSANTARA | 2022-03-01
G2021336 | 1 | 6 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009276/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 3 LOP Area Witel Sulselbar. | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | PALOPO |  | PLP008 - R7 PRE PLP PLP008 Lamasi |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-02 | 2021-12-28 | TEL.42/LG.320/R7W-7D100000/2022 | 2022-02-16 | TEL.0003/LG.320/R7W-7D100000/2022 | 2022-02-16 | 12192513 | 2596837 | 14789350 | 14789350 | 4500444833 |  |  |  |  | INATEL NUSANTARA | 2022-03-01
G2021336 | 1 | 7 | 01E07P02 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009276/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan Fimo Node B 3 LOP Area Witel Sulselbar. | 2021-12-10 | 2022-01-23 | FIMO NODE-B 2021 | PARE-PARE | SOROWAKO |  | R7 PRE SRK MLI082 DMT ASULI WAWONDULA |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-01-02 | 2021-12-28 | TEL.44/LG.320/R7W-7D100000/2022 | 2022-02-16 | TEL.0003/LG.320/R7W-7D100000/2022 | 2022-02-16 | 4797074 | 1552431 | 6349505 | 6349505 | 4500444833 |  |  |  |  | INATEL NUSANTARA | 2022-03-01
12021423 | 14 | 724 | 01C11I02 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | JAYAPURA |  | R7JYP HEM HOTEL SWISSBELL JAP OKT 21 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0513/LG.310/DID-C0200000/2022 | 2022-05-28 19:25 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 19933714 | 6146795 | 26080509 | 26080509 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 725 | 01C11I02 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | JAYAPURA |  | R7JYP HEM HOTEL SAHID OKT 21 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0513/LG.310/DID-C0200000/2022 | 2022-05-28 19:25 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 20439567 | 6033929 | 26473496 | 26473496 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 726 | 01C11I02 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | JAYAPURA |  | R7JYP HEM TVRI NBC JAP OKT 21 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0513/LG.310/DID-C0200000/2022 | 2022-05-28 19:25 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 56128166 | 21184668 | 77312834 | 77312834 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 727 | 01C11I02 | 019 | 74030027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | JAYAPURA 2 REP. |  | R7JYP HEM TVRI NBC JPB OKT 21 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0513/LG.310/DID-C0200000/2022 | 2022-05-28 19:25 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 13621956 | 4324527 | 17946483 | 17946483 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 728 | 01C11I02 | 019 | 74030027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | JAYAPURA 2 REP. |  | R7JYP HEM HOTEL SUNNI OKT 21 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0513/LG.310/DID-C0200000/2022 | 2022-05-28 19:25 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 124329247 | 38844059 | 163173306 | 163173306 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 729 | 01C11I02 | 019 | 74030027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | JAYAPURA 2 REP. |  | R7JYP HEM HOTEL SWISSBELL JPB OKT 21 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0513/LG.310/DID-C0200000/2022 | 2022-05-28 19:25 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 26647268 | 8304520 | 34951788 | 34951788 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 736 | 01C11I02 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | SENTANI |  | NON COMPETITION VENUE WISMA ATLIT PANAHAN SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 35159557 | 7812899 | 42972456 | 42972456 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 739 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | TIMIKA |  | NON COMPETITION VENUE MES GKI MARTHEN LUTHER SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 18665692 | 7083207 | 25748899 | 25748899 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 740 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | TIMIKA |  | NON COMPETITION VENUE MES TARUNA SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 51408166 | 18268902 | 69677068 | 69677068 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 741 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | TIMIKA |  | NON COMPETITION VENUE SENTRA PENDIDIKAN TIMIKA SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 68333330 | 14027010 | 82360340 | 82360340 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 737 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | TIMIKA |  | BRIGIF TIMIKA TIM SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0393/LG.310/DID-C0200000/2022 | 2022-04-05 13:15 | TEL.0523/LG.320/DID-A0000000/2022 | 2022-04-05 | 314378964 | 101924114 | 416303078 | 416303078 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-04-27
12021423 | 14 | 738 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | TIMIKA |  | KAVALERI 3 KAVALERI 3 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0393/LG.310/DID-C0200000/2022 | 2022-04-05 13:15 | TEL.0523/LG.320/DID-A0000000/2022 | 2022-04-05 | 153892997 | 51771721 | 205664718 | 205664718 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-04-27
12021423 | 14 | 742 | 01C11I02 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | TIMIKA |  | UPLINK MINI OLT MAPURU SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-04-07 | TEL.0580/LG.310/DID-C0200000/2022 | 2022-05-31 10:22 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 23532223 | 7978379 | 31510602 | 31510602 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 746 | 01C11I02 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | WAENA |  | NON COMPETITION VENUE TELUK BAYUR INDAH HOTEL SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 7733799 | 2343571 | 10077370 | 10077370 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 745 | 01C11I02 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | WAENA |  | ASRAMA SMANKOR WAENA WAE SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0393/LG.310/DID-C0200000/2022 | 2022-04-05 13:15 | TEL.0523/LG.320/DID-A0000000/2022 | 2022-04-05 | 19629341 | 6060745 | 25690086 | 25690086 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-04-27
12021423 | 14 | 743 | 01C11I02 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | WAENA |  | ASRAMA IAIN FATAHUL MULUK PAPUA WAE SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0393/LG.310/DID-C0200000/2022 | 2022-04-05 13:15 | TEL.0523/LG.320/DID-A0000000/2022 | 2022-04-05 | 45842938 | 13475798 | 59318736 | 59318736 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-04-27
12021423 | 14 | 744 | 01C11I02 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | JAYAPURA | WAENA |  | PONDOK PESANTREN AT-MUTTAQIN WAE SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0393/LG.310/DID-C0200000/2022 | 2022-04-05 13:15 | TEL.0523/LG.320/DID-A0000000/2022 | 2022-04-05 | 14290888 | 4795524 | 19086412 | 19086412 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-04-27
12021423 | 14 | 732 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | MERAUKE | MERAUKE |  | NON COMPETITION VENUE RUSUN PONPES AN-NAJA MERAUKE SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 32678432 | 12061151 | 44739583 | 44739583 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 734 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | MERAUKE | MERAUKE |  | NON COMPETITION VENUE KEBUN COKLAT SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 54490352 | 12593609 | 67083961 | 67083961 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 735 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | MERAUKE | MERAUKE |  | NON COMPETITION VENUE MUSAMUS SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 78193335 | 27651291 | 105844626 | 105844626 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 731 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | MERAUKE | MERAUKE |  | NON COMPETITION VENUE RUSUN BWS PAPUA MERAUKE SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 9240878 | 3858323 | 13099201 | 13099201 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 733 | 01C11I02 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | MERAUKE | MERAUKE |  | NON COMPETITION VENUE ASRAMA KOREM 174 TANAH MIRING SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2022-03-28 | TEL.0471/LG.310/DID-C0200000/2022 | 2022-05-12 09:09 | TEL.0762/LG.320/DID-A0000000/2022 | 2022-05-31 | 25384319 | 6601806 | 31986125 | 31986125 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-05-31
12021423 | 14 | 717 | 01C11I02 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | UJUNGPANDANG | ANTANG |  | PT. PLN - Sektor Tello SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 |  | 0 |  | 2021-12-10 | 2022-06-21 | [5 empty] | 16824944 | 3788282 | 20613226 | 0 | 4500444893 |  |  |  |  | TELKOM AKSES
12021423 | 14 | 718 | 01C11I02 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | UJUNGPANDANG | MATTOANGIN |  | ARTA BOGA CEMERLANG,HOTEL COLONIAL ,IN101064054,IN101585106,OCTAVIANUS GAUTAMA SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2021-12-29 | TEL.0054/LG.310/DID-C0200000/2022 | 2022-01-31 13:58 | TEL.0060/LG.320/DID-A0000000/2022 | 2022-01-31 | 134518920 | 26873705 | 161392625 | 161392625 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021423 | 14 | 719 | 01C11I02 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | UJUNGPANDANG | PANAKUKANG |  | KANTOR KEUANGAN SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 |  | 0 |  | 2021-12-10 | 2022-06-21 | [5 empty] | 32613016 | 8443390 | 41056406 | 0 | 4500444893 |  |  |  |  | TELKOM AKSES
12021423 | 14 | 720 | 01C11I02 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | UJUNGPANDANG | SUDIANG |  | MIGRASI FO LANUD HASANUDDIN SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2022-06-21 | 2021-12-29 | TEL.0054/LG.310/DID-C0200000/2022 | 2022-01-31 13:58 | TEL.0060/LG.320/DID-A0000000/2022 | 2022-01-31 | 294696261 | 69484923 | 364181184 | 364181184 | 4500444893 |  |  |  |  | TELKOM AKSES | 2022-01-31
12021423 | 14 | 722 | 01C11I02 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | UJUNGPANDANG | SUNGGUMINASA |  | TAENG SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 | 90 | 0 | Siap UT | 2021-12-10 | 2022-06-21 | 2022-03-07 |  |  |  |  | 178445123 | 37232424 | 215677547 | 0 | 4500444893 |  |  |  |  | TELKOM AKSES
12021423 | 14 | 723 | 01C11I02 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | FIBER EXPANSION & MODERN DEPLOY AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009293/HK.810/OPS-10000000/2021 | SP#5 Granular Modernization - OSP FO FTTH & Migrasi T-Cloud Tahap-2 | 2021-12-10 | 2022-12-23 | Granular Modernization | UJUNGPANDANG | WATAMPONE |  | UPLINK MINI CAMBA 2 SS#2 DISTRIBUSI [DISTRIBUSI SS2] |  | 100 |  | 0 |  | 2021-12-10 | 2022-06-21 | [5 empty] | 571194760 | 203385639 | 774580399 | 0 | 4500444893 |  |  |  |  | TELKOM AKSES
12021425 | 4 | 12 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.009340/HK.810/OPS-10000000/2021 | Surat Pesanan-9 (SP#9) Pengadaan ONT dan STB Platform ZTE - ONT | 2021-12-10 | 2022-04-10 | ONT dan STB | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-10 | 2021-12-21 | 2021-12-10 | C.TEL2465/LG300/12800000/2021 | 2021-12-20 | TEL.0214/LG.320/COP-F3000000/2021 | 2021-12-20 | 4680000000 | 0 | 4680000000 | 4680000000 | 4500445029 |  |  |  |  | ZTE INDONESIA | 2021-12-22
12021425 | 4 | 21 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.009340/HK.810/OPS-10000000/2021 | Surat Pesanan-9 (SP#9) Pengadaan ONT dan STB Platform ZTE - ONT | 2021-12-10 | 2022-04-10 | ONT dan STB | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-16 | 2022-03-02 | C.TEL90/LG300/DR7-1280000/2022 | 2022-03-24 | TEL.0046/LG.320/COP-F3000000/2022 | 2022-03-24 | 1620000000 | 0 | 1620000000 | 1620000000 | 4500445029 |  |  |  |  | ZTE INDONESIA | 2022-03-28
G2021340 | 4 | 10 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009387/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan NIQE 1 LOP Area Witel Gorontalo | 2021-12-13 | 2022-06-02 | NIQE | GORONTALO | ISIMU |  | R7 GTO ISM NIQE RUAS SIPATTAN LAMU |  | 100 | 50 | 0 | Mat. Delivery | 2021-12-13 | 2022-04-11 | 2022-03-01 |  |  |  |  | 352279522 | 279115260 | 631394782 | 0 | 4500445090 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2021344 | 7 | 53 | 01E07V01 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | BIAK | BIAK |  | R7 SON BIA PT2 DM067127 SAIPUDDIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.711/LG.310/DR7-12700000/2022 | 2022-03-10 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 6018675 | 1782229 | 7800904 | 7800904 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 49 | 01E07V01 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | BIAK | BIAK |  | R7 SON BIA PT2 DM069351 SHERLY |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.710/LG.310/DR7-12700000/2022 | 2022-03-10 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 51 | 01E07V01 | 007 | 74020026 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 JL. MAMBRUK |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.771/LG.310/DR7-12700000/2022 | 2022-04-09 | TEL.0043/LG.320/DR7-10400000/2022 | 2022-04-09 | 89644349 | 25076168 | 114720517 | 114720517 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-04-12
G2021344 | 7 | 48 | 01E07V01 | 007 | 74020026 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 WAGOM UTARA |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.772/LG.310/DR7-12700000/2022 | 2022-04-09 | TEL.0043/LG.320/DR7-10400000/2022 | 2022-04-09 | 83807378 | 22419867 | 106227245 | 106227245 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-04-12
G2021344 | 7 | 30 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FH/037 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.762/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 11591685 | 3027858 | 14619543 | 14619543 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 10 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 Masjid asakinah manokwari |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.759/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 11 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 Depan rays bakery |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.758/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 13 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 Depan kios kampus mbak mar |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.757/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 14 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 SDIT |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.756/LG.310/DRT-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 11602738 | 3448430 | 15051168 | 15051168 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 32 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 JL MARUNI |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.705/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 352365263 | 80773757 | 433139020 | 433139020 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 8 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FG/053 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.764/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 15 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 Jl. Merdeka manokwari |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.698/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 5215412 | 720146 | 5935558 | 5935558 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 19 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FF/11 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.693/LG.310/DR7-12700000/2022 | 2022-03-10 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 20 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FF/050 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.694/LG.310/DR7-12700000/2022 | 2022-03-10 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 7535504 | 1045435 | 8580939 | 8580939 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 25 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FH/19,20,06 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.695/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 7535504 | 1045435 | 8580939 | 8580939 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 28 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FG/02,06 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.696/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 5215412 | 720146 | 5935558 | 5935558 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 9 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 BOSTON CITY |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.760/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 12 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 Lorong SMK N 1 Manokwari |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.697/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 26 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FB/55,53,51 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.763/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2451440 | 390325 | 2841765 | 2841765 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 24 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FA/32 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.765/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 22 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FA/051 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.766/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 31 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FJ/028 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.761/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 18 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FA/052 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.753/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 7291947 | 2214299 | 9506246 | 9506246 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 21 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FB/76 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.752/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 17 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FE/15 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.754/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 16 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT2 ODP-MWR-FE/041 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-11 | 2022-01-01 | TEL.755/LG.310/DR7-12700000/2022 | 2022-03-28 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 52 | 01E07V01 | 007 | 74060078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | KAIMANA |  | R7 SON KIN PT2 POLRES KAIMANA |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.750/LG.310/DR7-12700000/2022 | 2022-03-27 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 73368714 | 23619005 | 96987719 | 96987719 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 47 | 01E07V01 | 007 | 74060078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | KAIMANA |  | R7 SON KIN PT2 KILO NOL |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.751/LG.310/DR7-12700000/2022 | 2022-03-27 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 12750916 | 1765581 | 14516497 | 14516497 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 55 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 Jl.Padat karya Serui |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.713/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 42486932 | 9325786 | 51812718 | 51812718 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 56 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 Jl. Moh yamin Serui |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.714/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 5215412 | 720146 | 5935558 | 5935558 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 57 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 Warari jln kuburan Serui |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.715/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 33945999 | 7219190 | 41165189 | 41165189 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 58 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 JL Hasanudin SD inpres 10 |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.716/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 27630054 | 5130676 | 32760730 | 32760730 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 59 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 Hotel Klapa 2 naik Serui |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.717/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 61 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 Lorong Rakha Ponsel Serui |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.718/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 22412118 | 5173515 | 27585633 | 27585633 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 50 | 01E07V01 | 007 | 74060041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SERUI |  | R7 SON SRU PT2 Jl.samratulangi Serui |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.712/LG.310/DR7-12700000/2022 | 2022-03-05 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 10294349 | 2376987 | 12671336 | 12671336 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 46 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 RS. Angkatan Laut |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.701/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 33 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 Depan tembok berlin |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.699/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 34 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 Sorpus |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.700/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 35 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 Belakang Bosowa (citra) |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.703/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 36 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 JL TRIKORA |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.704/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 345727233 | 99511691 | 445238924 | 445238924 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 45 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | PT2 KEDIAMAN PANGLIMA ARMADA |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.749/LG.310/DR7-12700000/2022 | 2022-03-27 | TEL.0041/LG.320/DR7-10400000/2022 | 2022-03-28 | 16399930 | 16754367 | 33154297 | 33154297 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-30
G2021344 | 7 | 39 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 Komp. perumnas |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.719/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 163139233 | 45174080 | 208313313 | 208313313 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 41 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 Lorong bakso berkah rahma |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.702/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 2895320 | 394857 | 3290177 | 3290177 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 42 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 PERUM BERDIKARI |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.706/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 11529343 | 2269597 | 13798940 | 13798940 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 43 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 DM078745 MARGARETHA |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.707/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 6354820 | 1445951 | 7800771 | 7800771 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 44 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 DM082843 VITALIS C |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.709/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 6556357 | 1507277 | 8063634 | 8063634 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
G2021344 | 7 | 37 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009419/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan PT2 Q4 Area Witel Papua Barat | 2021-12-13 | 2022-03-27 | PT2 | SORONG | SORONG |  | R7 SON SON PT2 DM076763 HAMKA RUSTAM |  | 100 | 100 | 100 | BAST-1 | 2021-12-13 | 2022-03-12 | 2022-01-01 | TEL.708/LG.310/DR7-12700000/2022 | 2022-03-03 | TEL.0036/LG.320/DR7-10400000/2022 | 2022-03-10 | 18029103 | 3849514 | 21878617 | 21878617 | 4500445139 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-18
12021428 | 6 | 34 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009494/HK.810/OPS-10050000/2021 | SP#2 Ekspan PCEF Platform Allot | 2021-12-14 | 2022-05-30 | Ekspan PCEF | JAYAPURA | JAYAPURA |  | dsl-sgtera14-jap-01 |  | 100 | 100 | 100 | BAST-1 | 2021-12-14 | 2022-04-12 | 2021-12-16 | TEL.187/LG.310/DID-B0300000/2022 | 2022-02-24 | TEL.0161/LG.320/DID-A0000000/2022 | 2022-02-24 | 248000000 | 12400000 | 260400000 | 260400000 | 4500445109 |  |  |  |  | ANDES LASEA KREASINDO | 2022-02-27
12021428 | 6 | 33 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009494/HK.810/OPS-10050000/2021 | SP#2 Ekspan PCEF Platform Allot | 2021-12-14 | 2022-05-30 | Ekspan PCEF | TERNATE | TERNATE |  | dsl-sgtera14-tnt-02 |  | 100 | 100 | 100 | BAST-1 | 2021-12-14 | 2022-04-12 | 2021-12-16 | TEL.187/LG.310/DID-B0300000/2022 | 2022-02-24 | TEL.0161/LG.320/DID-A0000000/2022 | 2022-02-24 | 248000000 | 12400000 | 260400000 | 260400000 | 4500445109 |  |  |  |  | ANDES LASEA KREASINDO | 2022-02-27
12021428 | 6 | 38 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009494/HK.810/OPS-10050000/2021 | SP#2 Ekspan PCEF Platform Allot | 2021-12-14 | 2022-05-30 | Ekspan PCEF | UJUNGPANDANG | BALAIKOTA |  | wag-sg9700-bal-01 |  | 100 | 100 | 100 | BAST-1 | 2021-12-14 | 2022-04-12 | 2022-02-17 | TEL.398/LG.310/DID-B1050000/2022 | 2022-04-11 | TEL.0468/LG.320/DID-A0000000/2022 | 2022-04-11 | 31000000 | 46300000 | 77300000 | 77300000 | 4500445109 |  |  |  |  | ANDES LASEA KREASINDO | 2022-04-26
12021428 | 6 | 26 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009494/HK.810/OPS-10050000/2021 | SP#2 Ekspan PCEF Platform Allot | 2021-12-14 | 2022-05-30 | Ekspan PCEF | UJUNGPANDANG | PETTARANI |  | wag-sg9700-ptr-01 |  | 100 | 100 | 100 | BAST-1 | 2021-12-14 | 2022-04-12 | 2021-12-15 | TEL.2286/LG310/PND-B1050000/2021 | 2021-12-30 | TEL.0367/LG.320/DID-A0000000/2021 | 2021-12-30 | 792100000 | 39605000 | 831705000 | 831705000 | 4500445109 |  |  |  |  | ANDES LASEA KREASINDO | 2021-12-30
12021438 | 6 | 24 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.448/LG.310/DID-B0300000/2022 | 2022-04-13 | TEL.0483/LG.320/DID-A0000000/2022 | 2022-04-13 | 1238890000 | 145913000 | 1384803000 | 1384803000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-04-26
12021438 | 6 | 35 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.447/LG.310/DID-B0300000/2022 | 2022-04-13 | TEL.0482/LG.320/DID-A0000000/2022 | 2022-04-13 | 14000000 | 30000000 | 44000000 | 44000000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-04-26
12021438 | 6 | 25 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.448/LG.310/DID-B0300000/2022 | 2022-04-13 | TEL.0483/LG.320/DID-A0000000/2022 | 2022-04-13 | 1238890000 | 145913000 | 1384803000 | 1384803000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-04-26
12021438 | 6 | 36 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.320/LG.310/PND-B0300000/2022 | 2022-03-08 | TEL.0311/LG.320/DID-A0000000/2022 | 2022-03-08 | 7000000 | 30000000 | 37000000 | 37000000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-03-30
12021438 | 6 | 39 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | TERNATE | TERNATE |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.320/LG.310/PND-B0300000/2022 | 2022-03-08 | TEL.0311/LG.320/DID-A0000000/2022 | 2022-03-08 | 7000000 | 15000000 | 22000000 | 22000000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-03-30
12021438 | 6 | 55 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.138/LG.310/DID-B0300000/2022 | 2022-02-09 | TEL.0097/LG.320/DID-A0000000/2022 | 2022-02-09 | 556752000 | 124342000 | 681094000 | 681094000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-02-23
12021438 | 6 | 54 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.009653/HK.810/OPS-10050000/2021 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2021-12-15 | 2022-04-13 | CACHE & DNS | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-15 | 2022-04-13 | 2021-12-17 | TEL.138/LG.310/DID-B0300000/2022 | 2022-02-09 | TEL.0097/LG.320/DID-A0000000/2022 | 2022-02-09 | 556752000 | 124342000 | 681094000 | 681094000 | 4500445094 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK | 2022-02-23
G2021361 | 2 | 9 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009759/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 4 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-17 | 2022-01-15 | PT2 | UJUNGPANDANG | TAKALAR |  | PT2-TKA-SIRAJUDDIN DG TUTU-82187820391--KENDALA |  | 100 | 100 | 100 | BAST-1 | 2021-12-17 | 2022-01-15 | 2022-01-01 | TEL.4/LG310/R7W-7A330000/2022 | 2022-01-12 | TEL.0001/LG.320/R7W-7A1O0000/2022 | 2022-01-12 | 2898163 | 662217 | 3560380 | 3560380 | 4500445831 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-01-15
G2021361 | 2 | 8 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009759/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 4 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-17 | 2022-01-15 | PT2 | UJUNGPANDANG | TAKALAR |  | PT2-TKA-MARIATI---KENDALA |  | 100 | 100 | 100 | BAST-1 | 2021-12-17 | 2022-01-15 | 2022-01-01 | TEL.3/LG310/R7W-7A330000/2022 | 2022-01-12 | TEL.0001/LG.320/R7W-7A1O0000/2022 | 2022-01-12 | 2775277 | 631683 | 3406960 | 3406960 | 4500445831 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-01-15
G2021361 | 2 | 7 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009759/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 4 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-17 | 2022-01-15 | PT2 | UJUNGPANDANG | TAKALAR |  | PT2-TKA-HADRAWATI SPd ---KENDALA |  | 100 | 100 | 100 | BAST-1 | 2021-12-17 | 2022-01-15 | 2022-01-01 | TEL.2/LG310/R7W-7A330000/2022 | 2022-01-12 | TEL.0001/LG.320/R7W-7A1O0000/2022 | 2022-01-12 | 6067200 | 1143934 | 7211134 | 7211134 | 4500445831 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-01-15
G2021361 | 2 | 6 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009759/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 4 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-17 | 2022-01-15 | PT2 | UJUNGPANDANG | TAKALAR |  | ARIFUDDIN ANSHAR |  | 100 | 100 | 100 | BAST-1 | 2021-12-17 | 2022-01-15 | 2022-01-01 | TEL.1/LG310/R7W-7A330000/2022 | 2022-01-12 | TEL.0001/LG.320/R7W-7A1O0000/2022 | 2022-01-12 | 5045808 | 1184322 | 6230130 | 6230130 | 4500445831 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-01-15
G2021362 | 2 | 8 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009760/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 5 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2021-12-17 | 2022-01-15 | PT2 | UJUNGPANDANG | PANGKEP |  | PT2-PKN-MASNUR ZAMAN-082291934808 / 082190627256-KENDALA |  | 100 | 100 | 100 | BAST-1 | 2021-12-17 | 2022-01-04 | 2021-12-17 | 7/LG310/R7W-7A330000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7A1O0000/2022 | 2022-01-13 | 13232919 | 3563471 | 16796390 | 16796390 | 4500445833 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-01-18
G2021362 | 2 | 7 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009760/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 5 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2021-12-17 | 2022-01-15 | PT2 | UJUNGPANDANG | PANGKEP |  | PT2-PKN-JUMRIA-83135462917-KENDALA |  | 100 | 100 | 100 | BAST-1 | 2021-12-17 | 2022-01-04 | 2021-12-17 | 8/LG310/R7W-7A330000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7A1O0000/2022 | 2022-01-13 | 9439094 | 2220923 | 11660017 | 11660017 | 4500445833 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-01-18
G2021372 | 1 | 10 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009909/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH Lokasi Gayaman Permai - Dulomo Area Witel Gorontalo | 2021-12-20 | 2022-02-02 | FTTH BATCH-3 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 GAMAYAN PERMAI-DULOMO |  | 82 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-02 | 2021-12-20 | TEL.005/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0006/LG.320/DR7-10400000/2022 | 2022-01-14 | 153691024 | 33098090 | 186789114 | 186789114 | 4500446066 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-01-28
G2021373 | 1 | 15 | 01E07V01 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009913/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 5 LoP Area Witel Makassar | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT3 TAMANGAPA RY III & PESONA PRIMA GRIYA |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2021-12-28 | 2021-12-20 | TEL.659/LG.310/DR7-12700000/2022 | 2022-01-30 | TEL.0022/LG.320/DR7-10400000/2022 | 2022-02-16 | 202704099 | 45000930 | 247705029 | 247705029 | 4500446082 |  |  |  |  | TELKOM AKSES | 2022-03-01
G2021373 | 1 | 11 | 01E07V01 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009913/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 5 LoP Area Witel Makassar | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | UJUNGPANDANG | MAROS |  | R7 MKS MAR PT3 PENAMBAHAN NUSA IDAMAN |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2021-12-29 | 2021-12-20 | TEL.656/LG.310/DR7-12700000/2022 | 2022-01-29 | TEL.0022/LG.320/DR7-10400000/2022 | 2022-02-16 | 327698645 | 69086878 | 396785523 | 396785523 | 4500446082 |  |  |  |  | TELKOM AKSES | 2022-03-01
G2021373 | 1 | 12 | 01E07V01 | 007 | 72080112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009913/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 5 LoP Area Witel Makassar | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | UJUNGPANDANG | SELAYAR |  | R7 MKS SLY PT3 INNER SELAYAR |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2021-12-28 | 2021-12-20 | TEL.657/LG.310/DR7-12700000/2022 | 2022-01-30 | TEL.0022/LG.320/DR7-10400000/2022 | 2022-02-16 | 377528470 | 98042449 | 475570919 | 475570919 | 4500446082 |  |  |  |  | TELKOM AKSES | 2022-03-01
G2021373 | 1 | 14 | 01E07V01 | 007 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009913/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 5 LoP Area Witel Makassar | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | UJUNGPANDANG | SINJAI |  | R7 MKS SIN PT3 SINJAI INNER 2 |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2021-12-29 | 2021-12-20 | TEL.658/LG.310/DR7-12700000/2022 | 2022-01-29 | TEL.0022/LG.320/DR7-10400000/2022 | 2022-02-16 | 955869563 | 211025043 | 1166894606 | 1166894606 | 4500446082 |  |  |  |  | TELKOM AKSES | 2022-03-01
G2021373 | 1 | 10 | 01E07V01 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009913/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 5 LoP Area Witel Makassar | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA PT3 DIST-1 PELANGI |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2021-12-28 | 2021-12-20 | TEL.662/LG.310/DR7-12700000/2022 | 2022-02-16 | TEL.0022/LG.320/DR7-10400000/2022 | 2022-02-16 | 153641595 | 29708857 | 183350452 | 183350452 | 4500446082 |  |  |  |  | TELKOM AKSES | 2022-03-01
G2021374 | 1 | 6 | 01E07V01 | 007 | 74030162 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009915/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-3 Lokasi Kloofkamp Kodam Area Witel Papua | 2021-12-20 | 2022-02-02 | FTTH BATCH-3 | JAYAPURA | JAYAPURA |  | R7 JYP JAP PT3 KLOOFKAMP KODAM |  | 60 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-02 | 2022-01-01 | TEL.10/LG.310/DR7-12700000/2022 | 2022-01-14 | TEL.0007/LG.320/DR7-10400000/2022 | 2022-01-14 | 151924333 | 46415294 | 198339627 | 198339627 | 4500446084 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-28
G2021375 | 2 | 7 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009916/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 3 LoP Periode Q4 Tahun 2021 Area Witel Makassar - KOPKAR SIPORENNU | 2021-12-20 | 2022-01-18 | PT2 | UJUNGPANDANG | BALAIKOTA |  | PT2-BAL-syarifuddin-082337034311-MYIR-10312140240001 |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-17 | 2022-01-01 | TEL.380/LG310/R7W-7A1C0000/2022 | 2022-02-24 | TEL.0007/LG.320/R7W-7A1O0000/2022 | 2022-02-24 | 3533074 | 819976 | 4353050 | 4353050 | 4500446089 |  |  |  |  | KOPKAR SIPORENNU | 2022-03-19
G2021375 | 2 | 6 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009916/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 3 LoP Periode Q4 Tahun 2021 Area Witel Makassar - KOPKAR SIPORENNU | 2021-12-20 | 2022-01-18 | PT2 | UJUNGPANDANG | BALAIKOTA |  | PT2-BAL-Miftahulreski;085399782021-MYIR-10324350490001 |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-17 | 2022-01-01 | TEL.379/LG310/R7W-7A1C0000/2022 | 2022-02-24 | TEL.0007/LG.320/R7W-7A1O0000/2022 | 2022-02-24 | 3021049 | 692751 | 3713800 | 3713800 | 4500446089 |  |  |  |  | KOPKAR SIPORENNU | 2022-03-19
G2021375 | 2 | 8 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009916/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 3 LoP Periode Q4 Tahun 2021 Area Witel Makassar - KOPKAR SIPORENNU | 2021-12-20 | 2022-01-18 | PT2 | UJUNGPANDANG | BALAIKOTA |  | TITI DARMAYANTI |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-17 | 2022-01-01 | TEL.381/LG310/R7W-7A1C0000/2022 | 2022-02-24 | TEL.0007/LG.320/R7W-7A1O0000/2022 | 2022-02-24 | 4121297 | 1032801 | 5154098 | 5154098 | 4500446089 |  |  |  |  | KOPKAR SIPORENNU | 2022-03-19
G2021376 | 3 | 6 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009918/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 2 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. BAKTI SARANA PRATAMA | 2021-12-20 | 2022-01-18 | PT2 | UJUNGPANDANG | MATTOANGIN |  | PT2 MAT Jerry Elvano Thio |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-18 | 2021-12-20 | TEL360/LG.310/R7W-7A1C0000/2022 | 2022-01-15 | TEL.0004/LG.320/R7W-7A1O0000/2022 | 2022-01-15 | 4311355 | 968496 | 5279851 | 5279851 | 4500446091 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-01-24
G2021376 | 3 | 7 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.009918/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 2 LoP Periode Q4 Tahun 2021 Area Witel Makassar - PT. BAKTI SARANA PRATAMA | 2021-12-20 | 2022-01-18 | PT2 | UJUNGPANDANG | MATTOANGIN |  | PT2 MAT ZUL FAHMI NOOR |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-18 | 2021-12-20 | TEL359/LG.310/R7W-7A1C0000/2022 | 2022-01-15 | TEL.0004/LG.320/R7W-7A1O0000/2022 | 2022-01-15 | 4121297 | 1032801 | 5154098 | 5154098 | 4500446091 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-01-24
G2021378 | 1 | 10 | 01E07V01 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009953/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH BATCH 3 5 LOP Area Witel Sulut Malut | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | MANADO | AMURANG |  | R7 MDO AMR PT3 LOPAN & PINALING |  | 80 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-11 | 2021-12-20 | TEL.630/LG.310/DR7-12700000/2022 | 2022-01-29 | TEL.0015/LG.320/DR7-10400000/2022 | 2022-01-30 | 685172485 | 134711573 | 819884058 | 819884058 | 4500446185 |  |  |  |  | TELKOM AKSES | 2022-02-07
G2021378 | 1 | 11 | 01E07V01 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009953/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH BATCH 3 5 LOP Area Witel Sulut Malut | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | MANADO | KOTAMOBAGU |  | R7 MDO KTG PT3 MARIRI BARU |  | 80 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-11 | 2021-12-20 | TEL.631/LG.310/DR7-12700000/2022 | 2022-01-29 | TEL.0015/LG.320/DR7-10400000/2022 | 2022-01-30 | 217556212 | 56728131 | 274284343 | 274284343 | 4500446185 |  |  |  |  | TELKOM AKSES | 2022-02-07
G2021378 | 1 | 13 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009953/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH BATCH 3 5 LOP Area Witel Sulut Malut | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | MANADO | TOMOHON |  | R7 MDO TMH PT3 PASLATEN 2 |  | 80 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-11 | 2021-12-20 | TEL.633/LG.310/DR7-12700000/2022 | 2022-01-30 | TEL.0015/LG.320/DR7-10400000/2022 | 2022-01-30 | 164325877 | 32286092 | 196611969 | 196611969 | 4500446185 |  |  |  |  | TELKOM AKSES | 2022-02-07
G2021378 | 1 | 14 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009953/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH BATCH 3 5 LOP Area Witel Sulut Malut | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | MANADO | TOMOHON |  | R7 MDO TMH PT3 KAMASI PASLATEN |  | 80 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-11 | 2021-12-20 | TEL.632/LG.310/DR7-12700000/2022 | 2022-01-30 | TEL.0015/LG.320/DR7-10400000/2022 | 2022-01-30 | 258975893 | 60430810 | 319406703 | 319406703 | 4500446185 |  |  |  |  | TELKOM AKSES | 2022-02-07
G2021378 | 1 | 12 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009953/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH BATCH 3 5 LOP Area Witel Sulut Malut | 2021-12-20 | 2022-02-17 | FTTH BATCH-3 | MANADO | TONDANO |  | R7 MDO TDN PT3 TATAARAN 2 |  | 80 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-02-11 | 2021-12-20 | TEL.634/LG.310/DR7-12700000/2022 | 2022-01-30 | TEL.0015/LG.320/DR7-10400000/2022 | 2022-01-30 | 206866408 | 48768962 | 255635370 | 255635370 | 4500446185 |  |  |  |  | TELKOM AKSES | 2022-02-07
G2021380 | 1 | 10 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | BARRU |  | R7 PRE BAR PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.11/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 4421184 | 619845 | 5041029 | 5041029 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 11 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | MAJENE |  | R7 PRE MAJ PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.12/LG320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 247551002 | 64408056 | 311959058 | 311959058 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 12 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.13/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 5147973 | 718764 | 5866737 | 5866737 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 13 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.10/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 14 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | PASANG KAYU |  | R7 PRE PKU PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.15/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 3431982 | 603622 | 4035604 | 4035604 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 15 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | PINRANG |  | R7 PRE PIN PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.16/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 16 | 01E07P02 | 007 | 72040135 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | RAPPANG |  | R7 PRE RPN PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.17/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 31136939 | 6206721 | 37343660 | 37343660 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 17 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.18/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 15417725 | 3032571 | 18450296 | 18450296 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 18 | 01E07P02 | 007 | 72040159 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | SIDENRENG RAPPANG |  | R7 PRE SID PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL.19/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021380 | 1 | 19 | 01E07P02 | 007 | 72040187 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.009959/HK.810/R7W-7D100000/2021 | Pengadaan Pekerjaan PT2 Tahap 11 Tahun 2021 10 LOP Area Witel Sulselbar | 2021-12-20 | 2022-01-18 | PT2 | PARE-PARE | WONOMULYO |  | R7 PRE WON PT2 NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-11 | TEL14/LG.320/R7W-7D100000/2022 | 2022-01-13 | TEL.0002/LG.320/R7W-7D100000/2022 | 2022-01-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500445840 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021381 | 1 | 12 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009962/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 4 LOP Area Witel Papua Barat | 2021-12-20 | 2022-03-19 | FTTH BATCH-3 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 APOTEK NURUL FARMA |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-19 | 2022-01-18 | TEL.032/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0011/LG.320/DR7-10400000/2022 | 2022-01-22 | 243100676 | 65138886 | 308239562 | 308239562 | 4500446190 |  |  |  |  | TELKOM AKSES | 2022-01-29
G2021381 | 1 | 13 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009962/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 4 LOP Area Witel Papua Barat | 2021-12-20 | 2022-03-19 | FTTH BATCH-3 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 ODC-BTI-FC WESIRI |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-19 | 2022-01-17 | TEL.033/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0011/LG.320/DR7-10400000/2022 | 2022-01-22 | 210718822 | 52968091 | 263686913 | 263686913 | 4500446190 |  |  |  |  | TELKOM AKSES | 2022-01-29
G2021381 | 1 | 10 | 01E07V01 | 007 | 74060078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009962/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 4 LOP Area Witel Papua Barat | 2021-12-20 | 2022-03-19 | FTTH BATCH-3 | SORONG | KAIMANA |  | R7 SON KIN PT3 KROY |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-19 | 2022-01-12 | TEL.030/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0011/LG.320/DR7-10400000/2022 | 2022-01-22 | 240951617 | 70130076 | 311081693 | 311081693 | 4500446190 |  |  |  |  | TELKOM AKSES | 2022-01-29
G2021381 | 1 | 11 | 01E07V01 | 007 | 74060078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.009962/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FTTH BATCH 3 4 LOP Area Witel Papua Barat | 2021-12-20 | 2022-03-19 | FTTH BATCH-3 | SORONG | KAIMANA |  | R7 SON KIN PT3 UTARUM |  | 100 | 100 | 100 | BAST-1 | 2021-12-20 | 2022-01-19 | 2022-01-13 | TEL.31/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0011/LG.320/DR7-10400000/2022 | 2022-01-22 | 161894089 | 51879199 | 213773288 | 213773288 | 4500446190 |  |  |  |  | TELKOM AKSES | 2022-01-29
12021441 | 4 | 20 | 01C11G04 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010044/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2021-12-20 | 2022-03-17 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#4 BHP-ISR |  | 90 | 100 | 100 | BAST-1 | 2022-02-01 | 2022-03-18 | 2022-03-01 | TEL.0657./LG310/DID-C0305000/2022 | 2022-03-09 | TEL.0247/LG.320/DID-A0000000/2022 | 2022-03-09 | 0 | 214330259 | 214330259 | 214330259 | 4500446227 |  |  |  |  | ERICSSON INDONESIA | 2022-03-14
12021441 | 4 | 19 | 01C11G04 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010044/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2021-12-20 | 2022-03-17 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#2 Upgrade Hardware |  | 90 | 100 | 100 | BAST-1 | 2022-02-01 | 2022-03-18 | 2022-03-01 | TEL.0652/LG310/DID-C0305000/2022 | 2022-03-09 | TEL.0247/LG.320/DID-A0000000/2022 | 2022-03-09 | 238572203 | 44062124 | 282634327 | 282634327 | 4500446227 |  |  |  |  | ERICSSON INDONESIA | 2022-03-14
12021441 | 4 | 18 | 01C11G04 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010044/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2021-12-20 | 2022-03-17 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#1 Redeploy |  | 90 | 100 | 100 | BAST-1 | 2022-02-01 | 2022-03-18 | 2022-03-01 | TEL.0651/LG310/DID-C0305000/2022 | 2022-03-09 | TEL.0247/LG.320/DID-A0000000/2022 | 2022-03-09 | 146175231 | 321308107 | 467483338 | 467483338 | 4500446227 |  |  |  |  | ERICSSON INDONESIA | 2022-03-14
12021446 | 1 | 64 | 01C11B08 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE & EDGE CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010170/HK.810/OPS-10000000/2021 | Pengadaan dan Pemasangan Expand and Enhancement NeuCentrIX 2.0 Tahun 2021 (GSD) | 2021-12-21 | 2022-08-31 | Enhancement NeuCentrIX | MANADO | PANIKI |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2022-02-21 | 2022-08-31 | 2022-02-21 |  |  |  |  | 495475341 | 169399082 | 664874423 | 0 | 4500446377 |  |  |  |  | GRAHA SARANA DUTA
12021446 | 1 | 58 | 01C11B08 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE & EDGE CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010170/HK.810/OPS-10000000/2021 | Pengadaan dan Pemasangan Expand and Enhancement NeuCentrIX 2.0 Tahun 2021 (GSD) | 2021-12-21 | 2022-08-31 | Enhancement NeuCentrIX | UJUNGPANDANG | MATTOANGIN |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-12-21 | 2022-08-31 | 2021-12-21 |  |  |  |  | 6526027537 | 1025431818 | 7551459355 | 0 | 4500446377 |  |  |  |  | GRAHA SARANA DUTA
12021446 | 1 | 63 | 01C11B08 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE & EDGE CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010170/HK.810/OPS-10000000/2021 | Pengadaan dan Pemasangan Expand and Enhancement NeuCentrIX 2.0 Tahun 2021 (GSD) | 2021-12-21 | 2022-08-31 | Enhancement NeuCentrIX | UJUNGPANDANG | MATTOANGIN |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2022-02-21 | 2022-08-31 | 2022-02-21 |  |  |  |  | 130201550 | 149360950 | 279562500 | 0 | 4500446377 |  |  |  |  | GRAHA SARANA DUTA
12021448 | 5 | 7 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010173/HK.810/OPS-10000000/2021 | SP#3 Ekspan IP Backbone Platform Cisco | 2021-12-21 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | AMBON | AMBON |  | P-D7-AB1 |  | 100 | 100 | 100 | BAST-1 | 2021-12-21 | 2022-04-19 | 2021-12-21 | TEL.2256/LG.310/PND-B1050000/2021 | 2021-12-27 | TEL.0198/LG.320/DID-A0000000/2021 | 2021-12-27 | 8661052700 | 652652000 | 9313704700 | 9313704700 | 4500446380 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-12-28
12021448 | 5 | 23 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010173/HK.810/OPS-10000000/2021 | SP#3 Ekspan IP Backbone Platform Cisco | 2021-12-21 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | AMBON | AMBON |  | P-D7-AB1 |  | 100 | 100 | 100 | BAST-1 | 2021-12-21 | 2022-05-30 | 2021-12-21 | TEL.765/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0795/LG.320/DID-A0000000/2022 | 2022-05-28 | 120000000 | 299650000 | 419650000 | 419650000 | 4500446380 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-05-31
12021448 | 5 | 9 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010173/HK.810/OPS-10000000/2021 | SP#3 Ekspan IP Backbone Platform Cisco | 2021-12-21 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | MANADO | PANIKI |  | P-D7-PNK |  | 80 | 100 | 100 | BAST-1 | 2021-12-21 | 2022-04-19 | 2021-12-21 | TEL.2257/LG.310/PND-B1050000/2021 | 2021-12-27 | TEL.0199/LG.320/DID-A0000000/2021 | 2021-12-27 | 6560388000 | 490472000 | 7050860000 | 7050860000 | 4500446380 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-12-28
12021448 | 5 | 8 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010173/HK.810/OPS-10000000/2021 | SP#3 Ekspan IP Backbone Platform Cisco | 2021-12-21 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | TERNATE | TERNATE |  | P-D7-TNT |  | 80 | 100 | 100 | BAST-1 | 2021-12-21 | 2022-04-19 | 2021-12-21 | TEL.2256/LG.310/PND-B1050000/2021 | 2021-12-27 | TEL.0198/LG.320/DID-A0000000/2021 | 2021-12-27 | 8661052700 | 652652000 | 9313704700 | 9313704700 | 4500446380 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2021-12-28
12021448 | 5 | 24 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010173/HK.810/OPS-10000000/2021 | SP#3 Ekspan IP Backbone Platform Cisco | 2021-12-21 | 2022-05-28 | Ekspan IP Backbone Platform Cisco | TERNATE | TERNATE |  | P-D7-TNT |  | 100 | 100 | 100 | BAST-1 | 2021-12-21 | 2022-04-19 | 2021-12-21 | K.TEL.503/LG.310/DID-B0300000/2022 | 2022-04-19 | TEL.0796/LG.320/DID-A0000000/2022 | 2022-04-19 | 0 | 290050000 | 290050000 | 290050000 | 4500446380 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-05-31
G2021385 | 1 | 7 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010178/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 2 LOP AREA WITEL PAPUA BARAT | 2021-12-21 | 2021-12-31 | FIMO NODE-B 2021 | SORONG | NABIRE |  | R7 SON NAB NODE B NAB109 |  | 100 | 100 | 100 | BAST-1 | 2021-12-21 | 2021-12-31 | 2022-01-01 | TEL.11/LG000/R7W-7H100000/2022 | 2022-01-08 | TEL.0001/LG.320/R7W-7H100000/2022 | 2022-01-08 | 76652887 | 2571139 | 79224026 | 79224026 | 4500446400 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021385 | 1 | 6 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010178/HK.810/R7W-7H100000/2021 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 2 LOP AREA WITEL PAPUA BARAT | 2021-12-21 | 2021-12-31 | FIMO NODE-B 2021 | SORONG | NABIRE |  | R7 SON NAB NODE B NAB108 |  | 100 | 100 | 100 | BAST-1 | 2021-12-21 | 2021-12-31 | 2022-01-01 | TEL.10/LG000/R7W-7H100000/2022 | 2022-01-08 | TEL.0001/LG.320/R7W-7H100000/2022 | 2022-01-08 | 329760824 | 4879800 | 334640624 | 334640624 | 4500446400 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021386 | 2 | 6 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010231/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH IKK Kigamani Area Witel Papua Barat | 2021-12-22 | 2022-07-31 | OSP FTTH PT-3 2021 | SORONG | NABIRE |  | R7 SON NAB PT3 KIGAMANI |  | 100 |  | 0 |  | 2021-12-22 | 2022-03-21 | 2022-01-01 |  |  |  |  | 154354255 | 58929099 | 213283354 | 0 | 4500446469 |  |  |  |  | TRANSDATA SATKOMINDO
G2021386 | 2 | 7 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010231/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH IKK Kigamani Area Witel Papua Barat | 2021-12-22 | 2022-07-31 | OSP FTTH PT-3 2021 | SORONG | SORONG |  | R7 SON SON PT3 JL. WORTEL AIMAS |  | 100 | 0 | 0 | Preparing | 2022-06-17 | 2022-07-31 | [5 empty] | 615683440 | 154292632 | 769976072 | 0 | 4500446469 |  |  |  |  | TRANSDATA SATKOMINDO
G2021387 | 1 | 6 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.010247/HK.810/R7W-7C100000/2021 | LASTMILE HEM EGBIS PY HYNC 1 LOP | 2021-12-22 | 2022-01-20 | HEM | PALU | BUNGKU |  | PT.HYNC |  | 100 | 100 | 100 | BAST-1 | 2021-12-22 | 2022-01-19 | 2022-01-01 | TEL.001/LG000/R7W-7C100000/2022 | 2022-01-18 | TEL.0001/LG.320/R7W-7C100000/2022 | 2022-01-18 | 123739483 | 26148693 | 149888176 | 149888176 | 4500446441 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-26
G2021390 | 2 | 6 | 01E07V01 | 007 | 74010053 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010358/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan Feeder Branching 1 LOP Area Witel Papua Barat | 2021-12-23 | 2022-03-22 | FEEDER BRANCHING | BIAK | WAROPEN |  | R7 SON WPN FE WAREN 1 |  | 100 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-03-08 | 2022-03-01 | TEL.839/LG.310/DR7-12700000/2022 | 2022-05-10 | TEL.0056/LG.320/DR7-10400000/2022 | 2022-05-10 | 389698256 | 109806336 | 499504592 | 499504592 | 4500446668 |  |  |  |  | TELKOM AKSES | 2022-05-15
G2021391 | 2 | 10 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010429/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 2 LOP Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2021-12-23 | 2022-01-21 | FIMO NODE-B 2021 | UJUNGPANDANG | MAROS |  | MRS058 - ODP-MAR-FD/105 |  | 100 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-01-07 | 2021-12-23 | TEL.5/LG310/R7W-7A330000/2022 | 2022-01-11 | TEL.0003/LG.320/R7W-7A1O0000/2022 | 2022-01-11 | 2403129 | 1308545 | 3711674 | 3711674 | 4500446727 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-01-21
G2021391 | 2 | 11 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010429/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 2 LOP Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2021-12-23 | 2022-01-21 | FIMO NODE-B 2021 | UJUNGPANDANG | TAKALAR |  | JNP078 - ODP-JNP-FAL/006 |  | 100 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-01-07 | 2021-12-23 | TEL.6/LG310/R7W-7A330000/2022 | 2022-01-11 | TEL.0003/LG.320/R7W-7A1O0000/2022 | 2022-01-11 | 19129627 | 4066250 | 23195877 | 23195877 | 4500446727 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-01-21
G2021392 | 1 | 18 | 01E07S02 | 007 | 72050009 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | BAU-BAU |  | R7 KDI BAU RHA033 DMT EREKE |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.017/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 10195525 | 2552155 | 12747680 | 12747680 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 9 | 01E07S02 | 007 | 72050009 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | BAU-BAU |  | R7 KDI BBU BAU106 DMT LABALAWA BAU BAU |  | 95 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-20 | 2022-01-01 | TEL.005/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 112572168 | 19988976 | 132561144 | 132561144 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 16 | 01E07S02 | 007 | 72050009 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | BAU-BAU |  | R7 KDI BBU BAU204 TBG MCP CEMARA |  | 95 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-20 | 2022-01-01 | TEL.018/TK.000/R7W-7G461000/2022 | 2022-02-02 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 4511679 | 1623299 | 6134978 | 6134978 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 17 | 01E07S02 | 007 | 72050009 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | BAU-BAU |  | R7 KDI RHA RHA005 KALISUSU |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.016/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 4598190 | 1643315 | 6241505 | 6241505 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 19 | 01E07S02 | 007 | 72050025 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | KENDARI |  | R7 KDI KDI KDI128 PROTELINDO 3G KOTA LAMA |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.008/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 8578460 | 2412680 | 10991140 | 10991140 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 11 | 01E07S02 | 007 | 72050025 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | KENDARI |  | R7 KDI KDI ADL273 DMT MM PUURUY MOROSI |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.007/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 14405912 | 2796539 | 17202451 | 17202451 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 14 | 01E07S02 | 007 | 72050041 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | LASUSUA |  | R7 KDI LSS KKA135 LSP SARUDONGKO |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.015/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 182975832 | 50637918 | 233613750 | 233613750 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 7 | 01E07S02 | 007 | 72050041 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | LASUSUA |  | R7 KDI LSS KKA179 API LELEHAO |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.014/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 13919999 | 3838435 | 17758434 | 17758434 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 13 | 01E07S02 | 007 | 72050093 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | MANDONGA |  | R7 KDI MDG KDI263 DMT POROS HOMBIS |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.009/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 85963447 | 35989123 | 121952570 | 121952570 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 12 | 01E07S02 | 007 | 72050093 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | MANDONGA |  | R7 KDI MDG ADL111 CMI MCP TAPUAHI |  | 95 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-20 | 2022-01-01 | TEL.006/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 6725556 | 1877733 | 8603289 | 8603289 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 6 | 01E07S02 | 007 | 72050093 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | MANDONGA |  | R7 KDI MDG ADL106 DMT LAMBUSA KONDA |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.019/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 74112241 | 21282433 | 95394674 | 95394674 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 10 | 01E07S02 | 007 | 72050057 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | RAHA |  | R7 KDI RHA RHA065 TBG OELONGKO MUNA |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.020/TK.000/R7W-7G461000/2022 | 2022-02-02 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 407928965 | 69041660 | 476970625 | 476970625 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 15 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | UNAAHA |  | R7 KDI UNH UNH051 DMT AHUA WATU |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.010/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 380368926 | 91079788 | 471448714 | 471448714 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 20 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | UNAAHA |  | R7 KDI UNH UNH058 WUKUSAOKENDARI |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.011/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 12236729 | 3087753 | 15324482 | 15324482 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 21 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | UNAAHA |  | R7 KDI UNH UNH067 Near_KDI022 |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.012/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 32738307 | 6295113 | 39033420 | 39033420 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021392 | 1 | 8 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010443/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 16 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | UNAAHA |  | R7 KDI UNH COI834 COMBAT BUPATI KONAWE UTARA |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.013/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0001/LG.320/R7W-7G100000/2022 | 2022-02-02 | 4539610 | 1595426 | 6135036 | 6135036 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 8 | 01E07S02 | 007 | 72050009 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | BAU-BAU |  | R7 KDI BBU NODE B BAU215 |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.026/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 30458150 | 7309382 | 37767532 | 37767532 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 11 | 01E07S02 | 007 | 72050050 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | POMALAA |  | R7 KDI PMA NODE B ADL117 |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.032/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 417526883 | 74042582 | 491569465 | 491569465 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 6 | 01E07S02 | 007 | 72050050 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | POMALAA |  | R7 KDI PMA NODE B ADL162 |  | 95 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-20 | 2022-01-01 | TEL.029/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 35583075 | 12224121 | 47807196 | 47807196 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 9 | 01E07S02 | 007 | 72050057 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | RAHA |  | R7 KDI RAH NODE B RHA143 |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.028/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 25378692 | 9387793 | 34766485 | 34766485 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 12 | 01E07S02 | 007 | 72050057 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | RAHA |  | R7 KDI RAH NODE B RHA130 |  | 95 | 100 | 100 | BAST-1 | 2021-12-23 | 2022-02-20 | 2022-01-01 | TEL.027/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 252264477 | 44702425 | 296966902 | 296966902 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 7 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | UNAAHA |  | R7 KDI UNH NODE B UNH061 |  | 95 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-20 | 2022-01-01 | TEL.031/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 208518932 | 46748879 | 255267811 | 255267811 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021393 | 1 | 10 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.010444/HK.810/R7W-7G100000/2021 | Pengadaan Pelaksanaan Pekerjaan FIMO Node B New Infra 7 LoP Area Witel Sultra | 2021-12-23 | 2022-02-20 | FIMO NODE-B 2021 | KENDARI | UNAAHA |  | R7 KDI UNH NODE B UNH057 |  | 95 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-20 | 2022-01-01 | TEL.030/TK.000/R7W-7G461000/2022 | 2022-02-01 | TEL.0002/LG.320/R7W-7G100000/2022 | 2022-02-01 | 8494227 | 2418682 | 10912909 | 10912909 | 0000000000 |  |  |  |  | INNANDA INDAH | 2022-02-18
G2021398 | 2 | 13 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010546/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 4 LOP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-24 | 2022-02-21 | FIMO NODE-B 2021 | UJUNGPANDANG | SINJAI |  | WTP232 - R7 MKS SIN NODE B WTP046 |  | 100 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-21 | 2022-01-01 | TEL.377/LG310/R7W-7A1C0000/2022 | 2022-02-17 | TEL.0004/LG.320/R7W-7A100000/2022 | 2022-02-17 | 31833380 | 9026016 | 40859396 | 40859396 | 4500446721 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-11
G2021398 | 2 | 12 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010546/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 4 LOP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-24 | 2022-02-21 | FIMO NODE-B 2021 | UJUNGPANDANG | SUNGGUMINASA |  | SNS236 - R7 MKS SUG NODE B SNS236 |  | 100 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-21 | 2022-01-01 | TEL.375/LG310/R7W-7A1C0000/2022 | 2022-02-17 | TEL.0004/LG.320/R7W-7A100000/2022 | 2022-02-17 | 43771007 | 9250433 | 53021440 | 53021440 | 4500446721 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-11
G2021398 | 2 | 11 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010546/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 4 LOP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-24 | 2022-02-21 | FIMO NODE-B 2021 | UJUNGPANDANG | WATAMPONE |  | WTP294 - R7 MKS WTP NODE B WTP294 |  | 100 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-21 | 2022-01-01 | TEL.378/LG310/R7W-7A1C0000/2022 | 2022-02-17 | TEL.0004/LG.320/R7W-7A100000/2022 | 2022-02-17 | 287698335 | 54895862 | 342594197 | 342594197 | 4500446721 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-11
G2021398 | 2 | 10 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010546/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 4 LOP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2021-12-24 | 2022-02-21 | FIMO NODE-B 2021 | UJUNGPANDANG | WATAMPONE |  | WTP046 - R7 MKS WTP NODE B WTP046 |  | 100 | 100 | 100 | BAST-1 | 2021-12-24 | 2022-02-21 | 2022-01-01 | TEL.376/LG310/R7W-7A1C0000/2022 | 2022-02-17 | TEL.0004/LG.320/R7W-7A100000/2022 | 2022-02-17 | 129208688 | 23454168 | 152662856 | 152662856 | 4500446721 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-11
G2021399 | 2 | 10 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2022-01-01 | 2021-12-25 | TEL.361/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 4017580 | 547055 | 4564635 | 4564635 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021399 | 2 | 11 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | MAROS |  | R7 MKS MAR PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2021-12-30 | 2021-12-25 | TEL.362/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 7553926 | 1330699 | 8884625 | 8884625 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021399 | 2 | 12 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2021-12-29 | 2021-12-25 | TEL.363/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 10650763 | 2763970 | 13414733 | 13414733 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021399 | 2 | 13 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2021-12-29 | 2021-12-25 | TEL.364/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 27008452 | 6872089 | 33880541 | 33880541 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021399 | 2 | 14 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2021-12-30 | 2021-12-25 | TEL.365/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 9295717 | 2120190 | 11415907 | 11415907 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021399 | 2 | 15 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2021-12-30 | 2021-12-25 | TEL.366/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 12772436 | 3213524 | 15985960 | 15985960 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021399 | 2 | 16 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010617/HK.810/R7W-7A1O0000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 7 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-25 | 2022-01-23 | PT2 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP PT2 NOV 2021 (7 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-25 | 2021-12-30 | 2021-12-25 | TEL.367/LG310/R7W-7A1C0000/2022 | 2022-01-17 | TEL.0005/LG.320/R7W-7A1O0000/2022 | 2022-01-17 | 4563573 | 901435 | 5465008 | 5465008 | 4500446888 |  |  |  |  | TELKOM AKSES | 2022-02-17
G2021400 | 1 | 10 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010647/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 5 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM PT SALT INTEGRA SOLUSI |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-27 | TEL.0638/LG.310/DR7-12700000/2022 | 2022-02-08 | TEL.0023/LG.320/DR7-10400000/2022 | 2022-02-08 | 13680638 | 3708051 | 17388689 | 17388689 | 4500446909 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021400 | 1 | 8 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010647/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 5 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM POLDA SULBAR |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-27 | TEL.0637/LG.310/DR7-12700000/2022 | 2022-02-08 | TEL.0023/LG.320/DR7-10400000/2022 | 2022-02-08 | 5897418 | 1540788 | 7438206 | 7438206 | 4500446909 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021400 | 1 | 7 | 01E07V06 | 007 | 72040117 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010647/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 5 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM KOMINFO PAREPARE |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-27 | TEL.0635/LG.310/DR7-12700000/2022 | 2022-02-08 | TEL.0023/LG.320/DR7-10400000/2022 | 2022-02-08 | 1715991 | 239588 | 1955579 | 1955579 | 4500446909 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021400 | 1 | 6 | 01E07V06 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010647/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 5 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | RANTEPAO |  | R7 PRE RTP HEM DISKOMINFO TORAJA UTARA |  | 100 | 100 | 100 | BAST-1 | 2022-01-02 | 2022-01-14 | 2022-01-01 | TEL.0636/LG.310/DR7-12700000/2022 | 2022-02-08 | TEL.0023/LG.320/DR7-10400000/2022 | 2022-02-08 | 36818634 | 6283414 | 43102048 | 43102048 | 4500446909 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021400 | 1 | 9 | 01E07V06 | 007 | 72040161 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010647/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 5 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | SOROWAKO |  | R7 PRE SRK HEM VALE (PONTADA-SALONSA) |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-27 | TEL.0639/LG.310/DR7-12700000/2022 | 2022-02-08 | TEL.0023/LG.320/DR7-10400000/2022 | 2022-02-08 | 202747019 | 49082217 | 251829236 | 251829236 | 4500446909 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021401 | 1 | 11 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM KANTOR CAMAT TOMONI |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.023/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 2121966 | 242973 | 2364939 | 2364939 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 10 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM SMKN 2 LUWU TIMUR |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.022/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 120185896 | 20701035 | 140886931 | 140886931 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 12 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM SMAN 8 LUWU TIMUR |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.024/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 23033221 | 3701471 | 26734692 | 26734692 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 13 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM PUSKESMAS KALAENA |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.025/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 23673858 | 3793986 | 27467844 | 27467844 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 14 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM KANTOR CAMAT KALAENA |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.026/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 19911900 | 3877302 | 23789202 | 23789202 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 15 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM KANTOR CAMAT MAGKUTANA |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.027/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 2121966 | 242973 | 2364939 | 2364939 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 17 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM DIN PERTANIAN LUWU UTARA |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.029/LG.310/DR7-12700000/2022 | 2022-01-16 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 41428683 | 8322432 | 49751115 | 49751115 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
G2021401 | 1 | 16 | 01E07V06 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010650/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 8 LoP Area Witel Sulselbar | 2021-12-27 | 2022-02-09 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM PUSKESMAS TOMONI TIMUR |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-09 | 2022-01-03 | TEL.028/LG.310/DR7-12700000/2022 | 2022-01-16 | TEL.0016/LG.320/DR7-10400000/2022 | 2022-01-16 | 561386545 | 119707946 | 681094491 | 681094491 | 4500446918 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-02-09
12021461 | 3 | 13 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.010697/HK.810/OPS-10060000/2021 | Surat Pesanan-3 (SP#3) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2021-12-27 | 2022-03-26 | Jasa Pekerjaan Penunjang | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2021-12-28 | 2021-12-27 | C.TEL2489/LG300/DR7-12800000/2021 | 2021-12-28 | TEL.0232/LG.320/COP-F3000000/2021 | 2021-12-28 | 0 | 597271000 | 597271000 | 597271000 | 4500446893 | 4500447833 |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2021-12-29
12021461 | 3 | 21 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.010697/HK.810/OPS-10060000/2021 | Surat Pesanan-3 (SP#3) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2021-12-27 | 2022-03-26 | Jasa Pekerjaan Penunjang | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-26 | 2022-01-04 | C.TEL27/LG300/DR7-12800000/2022 | 2022-01-25 | TEL.0004/LG.320/COP-F3000000/2022 | 2022-01-25 | 0 | 617120500 | 617120500 | 617120500 | 4500446893 | 4500447833 |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-01-26
12021461 | 3 | 29 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.010697/HK.810/OPS-10060000/2021 | Surat Pesanan-3 (SP#3) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2021-12-27 | 2022-03-26 | Jasa Pekerjaan Penunjang | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-26 | 2022-02-18 | 2022-01-26 | C.TEL49/LG300/DR7-12800000/2022 | 2022-02-17 | TEL.0021/LG.320/COP-F3000000/2022 | 2022-02-17 | 0 | 469579500 | 469579500 | 469579500 | 4500446893 | 4500447833 |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-02-18
G2021403 | 2 | 8 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010727/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH Lokasi IKK Enarotali dan Tigi Area Witel Papua Barat | 2021-12-27 | 2022-02-24 | OSP FTTH PT-3 2021 | SORONG | NABIRE |  | R7 SON NAB FE ENAROTALI ODC FB |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-24 | 2022-01-01 | TEL.1108/LG.310/DR7-12700000/2022 | 2022-07-23 | TEL.0122/LG.320/DR7-10400000/2022 | 2022-07-23 | 244183350 | 89186442 | 333369792 | 333369792 | 4500446997 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-29
G2021403 | 2 | 6 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010727/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan OSP FTTH Lokasi IKK Enarotali dan Tigi Area Witel Papua Barat | 2021-12-27 | 2022-02-24 | OSP FTTH PT-3 2021 | SORONG | NABIRE |  | R7 SON NAB FE TIGI |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-02-24 | 2022-01-01 | TEL.1109/LG.310/DR7-12700000/2022 | 2022-07-22 | TEL.0122/LG.320/DR7-10400000/2022 | 2022-07-23 | 47590259 | 29064473 | 76654732 | 76654732 | 4500446997 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-29
12021464 | 3 | 50 | 01C11B08 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE & EDGE CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010770/HK.810/OPS-10000000/2021 | Pengadaan dan Pemasangan Ekspand and Enhancement NeuCentrIX 2.0 Tahun 2021 (SIGMA) | 2021-12-27 | 2022-08-31 | Enhancement NeuCentrIX | UJUNGPANDANG | MATTOANGIN |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-12-27 | 2022-08-31 | 2021-12-27 |  |  |  |  | 10743540900 | 1572187600 | 12315728500 | 0 | 4500445919 |  |  |  |  | SIGMA CIPTA CARAKA
12021464 | 3 | 69 | 01C11B08 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | SERVICE & EDGE CLOUD DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010770/HK.810/OPS-10000000/2021 | Pengadaan dan Pemasangan Ekspand and Enhancement NeuCentrIX 2.0 Tahun 2021 (SIGMA) | 2021-12-27 | 2022-08-31 | Enhancement NeuCentrIX | UJUNGPANDANG | MATTOANGIN |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2021-12-27 | 2022-08-31 | 2021-12-27 |  |  |  |  | 204429600 | 24543500 | 228973100 | 0 | 4500445919 |  |  |  |  | SIGMA CIPTA CARAKA
G2021405 | 2 | 10 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010792/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-27 | 2022-02-24 | PT2 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT2 NOV 2021 (8 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-01-03 | 2021-12-27 | TEL368/LG310/R7W-7A1C0000/2022 | 2022-02-22 | TEL.0006/LG.320/R7W-7A1O0000/2022 | 2022-02-22 | 2816239 | 766307 | 3582546 | 3582546 | 4500446979 |  |  |  |  | TELKOM AKSES | 2022-03-09
G2021405 | 2 | 11 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010792/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-27 | 2022-02-24 | PT2 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 NOV 2021 (8 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-01-02 | 2021-12-27 | TEL369/LG310/R7W-7A1C0000/2022 | 2022-02-22 | TEL.0006/LG.320/R7W-7A1O0000/2022 | 2022-02-22 | 13577298 | 2479716 | 16057014 | 16057014 | 4500446979 |  |  |  |  | TELKOM AKSES | 2022-03-09
G2021405 | 2 | 12 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010792/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-27 | 2022-02-24 | PT2 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 NOV 2021 (8 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-01-04 | 2021-12-27 | TEL370/LG310/R7W-7A1C0000/2022 | 2022-02-22 | TEL.0006/LG.320/R7W-7A1O0000/2022 | 2022-02-22 | 1715991 | 239588 | 1955579 | 1955579 | 4500446979 |  |  |  |  | TELKOM AKSES | 2022-03-09
G2021405 | 2 | 13 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010792/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-27 | 2022-02-24 | PT2 | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK PT2 NOV 2021 (8 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-01-08 | 2021-12-27 | TEL371/LG310/R7W-7A1C0000/2022 | 2022-02-22 | TEL.0006/LG.320/R7W-7A1O0000/2022 | 2022-02-22 | 19318855 | 4884554 | 24203409 | 24203409 | 4500446979 |  |  |  |  | TELKOM AKSES | 2022-03-09
G2021405 | 2 | 15 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010792/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-27 | 2022-02-24 | PT2 | UJUNGPANDANG | TAKALAR |  | R7 MKS TKA PT2 NOV 2021 (8 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-01-09 | 2021-12-27 | TEL373/LG310/R7W-7A1C0000/2022 | 2022-02-22 | TEL.0006/LG.320/R7W-7A1O0000/2022 | 2022-02-22 | 6653043 | 1081994 | 7735037 | 7735037 | 4500446979 |  |  |  |  | TELKOM AKSES | 2022-03-09
G2021405 | 2 | 17 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010792/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode November Area Witel Makassar - PT. TELKOM AKSES | 2021-12-27 | 2022-02-24 | PT2 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP PT2 NOV 2021(8 LOP) |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-01-04 | 2021-12-27 | TEL374/LG310/R7W-7A1C0000/2022 | 2022-02-22 | TEL.0006/LG.320/R7W-7A1O0000/2022 | 2022-02-22 | 4402305 | 1169291 | 5571596 | 5571596 | 4500446979 |  |  |  |  | TELKOM AKSES | 2022-03-09
12021467 | 4 | 24 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010796/HK.810/OPS-10050000/2021 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Ekspan PE Platform Juniper | 2021-12-27 | 2022-06-24 | Ekspan PE Platform Juniper | JAYAPURA | JAYAPURA |  | PE-D7-JAP-HSI |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-02-11 | TEL.937/LG.310/DID-B0300000/2022 | 2022-06-22 | TEL.0832/LG.320/DID-A0000000/2022 | 2022-06-22 | 0 | 80000000 | 80000000 | 80000000 | 4500446965 |  |  |  |  | NEC INDONESIA | 2022-06-28
12021467 | 4 | 22 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010796/HK.810/OPS-10050000/2021 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Ekspan PE Platform Juniper | 2021-12-27 | 2022-06-24 | Ekspan PE Platform Juniper | UJUNGPANDANG | BALAIKOTA |  | PE-D7-BAL-HSI |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-17 | TEL.937/LG.310/DID-B0300000/2022 | 2022-06-22 | TEL.0832/LG.320/DID-A0000000/2022 | 2022-06-22 | 735554000 | 66754000 | 802308000 | 802308000 | 4500446965 |  |  |  |  | NEC INDONESIA | 2022-06-28
12021467 | 4 | 23 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010796/HK.810/OPS-10050000/2021 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Ekspan PE Platform Juniper | 2021-12-27 | 2022-06-24 | Ekspan PE Platform Juniper | UJUNGPANDANG | PETTARANI |  | PE-D7-PTR-HSI |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-02-08 | TEL.937/LG.310/DID-B0300000/2022 | 2022-06-22 | TEL.0832/LG.320/DID-A0000000/2022 | 2022-06-22 | 505554000 | 44624000 | 550178000 | 550178000 | 4500446965 |  |  |  |  | NEC INDONESIA | 2022-06-28
12021468 | 5 | 13 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010803/HK.810/OPS-10050000/2021 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2021-12-27 | 2022-04-25 | Ekspan PE Transit | JAYAPURA | JAYAPURA |  | PE-D7-JAP-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-04-25 | 2021-12-27 | TEL.32/LG.310/DID-B0300000/2022 | 2022-01-24 | TEL.0023/LG.320/DID-A0000000/2022 | 2022-01-24 | 577042000 | 57704200 | 634746200 | 634746200 | 4500446961 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-01-28
12021468 | 5 | 14 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010803/HK.810/OPS-10050000/2021 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2021-12-27 | 2022-04-25 | Ekspan PE Transit | SORONG | SORONG |  | PE-D7-SON-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-04-25 | 2021-12-27 | TEL.32/LG.310/DID-B0300000/2022 | 2022-01-24 | TEL.0023/LG.320/DID-A0000000/2022 | 2022-01-24 | 1014451000 | 131445100 | 1145896100 | 1145896100 | 4500446961 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-01-28
12021468 | 5 | 15 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010803/HK.810/OPS-10050000/2021 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2021-12-27 | 2022-04-25 | Ekspan PE Transit | TERNATE | TERNATE |  | PE-D7-TNT-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-04-25 | 2021-12-27 | TEL.190/LG.310/DID-B0300000/2022 | 2022-02-25 | TEL.0165/LG.320/DID-A0000000/2022 | 2022-02-25 | 10764159000 | 916415900 | 11680574900 | 11680574900 | 4500446961 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-02-27
12021469 | 9 | 130 | 01C11B03 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | AMBON | AMBON |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-03-26 | 2022-01-05 | TEL.338/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0362/LG.320/DID-A0000000/2022 | 2022-03-25 | 80851120 | 9832000 | 90683120 | 90683120 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-03-30
12021469 | 9 | 101 | 01C11B03 | 019 | 73010121 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | AMBON | AMBON CENTRUM |  |  |  | 70 | 85 | 0 | Instalasi | 2021-12-27 | 2022-08-09 | 2022-01-05 |  |  |  |  | 546032538 | 75443868 | 621476406 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 177 | 01C11B03 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | AMBON | PASSO |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-05-20 | 2022-01-05 | 761/LG.310/DID-B0300000/2022 | 2022-05-18 | TEL.0664/LG.320/DID-A0000000/2022 | 2022-05-18 | 40425560 | 4916000 | 45341560 | 45341560 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-05-31
12021469 | 9 | 178 | 01C11B03 | 019 | 73010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | AMBON | TERSILI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-05-20 | 2022-01-05 | 761/LG.310/DID-B0300000/2022 | 2022-05-18 | TEL.0664/LG.320/DID-A0000000/2022 | 2022-05-18 | 40425560 | 4916000 | 45341560 | 45341560 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-05-31
12021469 | 9 | 202 | 01C11B03 | 019 | 74030182 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | CLS CARGO DOCK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-07-18 | 2022-01-05 | TEL.1105/LG.310/DID-B0300000/2022 | 2022-07-16 | TEL.1175/LG.320/DID-A0000000/2022 | 2022-07-16 | 17453560 | 6341000 | 23794560 | 23794560 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-07-30
12021469 | 9 | 36 | 01C11B03 | 019 | 74030182 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | CLS CARGO DOCK |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.951/LG.310/DID-B0300000/2022 | 2022-06-24 | TEL.0916/LG.320/DID-A0000000/2022 | 2022-06-24 | 541717314 | 67767158 | 609484472 | 609484472 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 76 | 01C11B03 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | JAYAPURA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-03-26 | 2022-01-05 | TEL.338/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0362/LG.320/DID-A0000000/2022 | 2022-03-25 | 40425560 | 4916000 | 45341560 | 45341560 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-03-30
12021469 | 9 | 106 | 01C11B03 | 019 | 74030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | JAYAPURA-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.951/LG.310/DID-B0300000/2022 | 2022-06-24 | TEL.0916/LG.320/DID-A0000000/2022 | 2022-06-24 | 510627570 | 69018667 | 579646237 | 579646237 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 31 | 01C11B03 | 019 | 74030034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | JAYAPURA-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.951/LG.310/DID-B0300000/2022 | 2022-06-24 | TEL.0916/LG.320/DID-A0000000/2022 | 2022-06-24 | 360456700 | 39240748 | 399697448 | 399697448 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 176 | 01C11B03 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | SARMI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-05-20 | 2022-01-05 | 761/LG.310/DID-B0300000/2022 | 2022-05-18 | TEL.0664/LG.320/DID-A0000000/2022 | 2022-05-18 | 80851120 | 9832000 | 90683120 | 90683120 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-05-31
12021469 | 9 | 151 | 01C11B03 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | SARMI |  |  |  | 65 | 50 | 0 | Mat. Delivery | 2021-12-27 | 2022-08-13 | 2022-01-05 |  |  |  |  | 408570748 | 60370203 | 468940951 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 159 | 01C11B03 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | SARMI |  |  |  | 70 | 65 | 0 | Instalasi | 2021-12-27 | 2022-08-09 | 2022-01-05 |  |  |  |  | 271312535 | 48174166 | 319486701 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 208 | 01C11B03 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | SENTANI |  |  |  | 45 | 20 | 0 | Preparing | 2021-12-27 | 2022-09-30 | 2022-01-05 |  |  |  |  | 1371397560 | 138873420 | 1510270980 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 97 | 01C11B03 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | JAYAPURA | TIMIKA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.951/LG.310/DID-B0300000/2022 | 2022-06-24 | TEL.0916/LG.320/DID-A0000000/2022 | 2022-06-24 | 547091214 | 82147268 | 629238482 | 629238482 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 126 | 01C11B03 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANADO | MANADO CENTRUM |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-07-18 | 2022-01-05 | TEL.1105/LG.310/DID-B0300000/2022 | 2022-07-16 | TEL.1175/LG.320/DID-A0000000/2022 | 2022-07-16 | 1470595610 | 159128560 | 1629724170 | 1629724170 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-07-30
12021469 | 9 | 34 | 01C11B03 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANADO | MANADO CENTRUM |  |  |  | 70 | 65 | 0 | Instalasi | 2021-12-27 | 2022-08-09 | 2022-01-05 |  |  |  |  | 1409042673 | 168610801 | 1577653474 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 149 | 01C11B03 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANADO | MANADO CENTRUM |  |  |  | 65 | 55 | 0 | Instalasi | 2021-12-27 | 2022-08-13 | 2022-01-05 |  |  |  |  | 1325240274 | 156304705 | 1481544979 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 23 | 01C11B03 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANADO | PANIKI |  |  |  | 65 | 55 | 0 | Instalasi | 2021-12-27 | 2022-08-13 | 2022-01-05 |  |  |  |  | 700674867 | 82296738 | 782971605 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 42 | 01C11B03 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANADO | PANIKI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.951/LG.310/DID-B0300000/2022 | 2022-06-24 | TEL.0916/LG.320/DID-A0000000/2022 | 2022-06-24 | 925066313 | 132118017 | 1057184330 | 1057184330 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 163 | 01C11B03 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANOKWARI | MANOKWARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-03-26 | 2022-01-05 | TEL.338/LG.310/DID-B0300000/2022 | 2022-03-25 | TEL.0362/LG.320/DID-A0000000/2022 | 2022-03-25 | 17453560 | 6341000 | 23794560 | 23794560 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-03-30
12021469 | 9 | 179 | 01C11B03 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | MANOKWARI | MANOKWARI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-05-20 | 2022-01-05 | 761/LG.310/DID-B0300000/2022 | 2022-05-18 | TEL.0664/LG.320/DID-A0000000/2022 | 2022-05-18 | 17453560 | 6341000 | 23794560 | 23794560 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-05-31
12021469 | 9 | 64 | 01C11B03 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | PALU | PALU-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-07-18 | 2022-01-05 | TEL.1105/LG.310/DID-B0300000/2022 | 2022-07-16 | TEL.1175/LG.320/DID-A0000000/2022 | 2022-07-16 | 688398506 | 71678802 | 760077308 | 760077308 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-07-30
12021469 | 9 | 152 | 01C11B03 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | PALU | PALU-1 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.945/LG.310/DID-B0300000/2022 | 2022-06-23 | TEL.0915/LG.320/DID-A0000000/2022 | 2022-06-23 | 143423295 | 15066284 | 158489579 | 158489579 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 62 | 01C11B03 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | PALU | PALU-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-07-18 | 2022-01-05 | TEL.1105/LG.310/DID-B0300000/2022 | 2022-07-16 | TEL.1175/LG.320/DID-A0000000/2022 | 2022-07-16 | 713376326 | 74440282 | 787816608 | 787816608 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-07-30
12021469 | 9 | 25 | 01C11B03 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | PALU | PALU-2 |  |  |  | 65 | 55 | 0 | Instalasi | 2021-12-27 | 2022-08-13 | 2022-01-05 |  |  |  |  | 446621211 | 50801752 | 497422963 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 41 | 01C11B03 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | PALU | PALU-2 |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | TEL.951/LG.310/DID-B0300000/2022 | 2022-06-24 | TEL.0916/LG.320/DID-A0000000/2022 | 2022-06-24 | 566195750 | 77303769 | 643499519 | 643499519 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-06-30
12021469 | 9 | 102 | 01C11B03 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | TERNATE | TERNATE |  |  |  | 70 | 65 | 0 | Instalasi | 2021-12-27 | 2022-08-09 | 2022-01-05 |  |  |  |  | 488899530 | 61229656 | 550129186 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 153 | 01C11B03 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | TERNATE | TERNATE |  |  |  | 65 | 50 | 0 | Mat. Delivery | 2021-12-27 | 2022-08-13 | 2022-01-05 |  |  |  |  | 598256289 | 70086892 | 668343181 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 45 | 01C11B03 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | 762/LG.310/DID-B0300000/2022 | 2022-05-27 | TEL.0665/LG.320/DID-A0000000/2022 | 2022-05-27 | 1039462780 | 136909324 | 1176372104 | 1176372104 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-05-31
12021469 | 9 | 124 | 01C11B03 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | UJUNGPANDANG | BALAIKOTA |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-07-18 | 2022-01-05 | TEL.1105/LG.310/DID-B0300000/2022 | 2022-07-16 | TEL.1175/LG.320/DID-A0000000/2022 | 2022-07-16 | 344199253 | 35839401 | 380038654 | 380038654 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-07-30
12021469 | 9 | 125 | 01C11B03 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-07-18 | 2022-01-05 | TEL.1105/LG.310/DID-B0300000/2022 | 2022-07-16 | TEL.1175/LG.320/DID-A0000000/2022 | 2022-07-16 | 344199253 | 35839401 | 380038654 | 380038654 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-07-30
12021469 | 9 | 188 | 01C11B03 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | UJUNGPANDANG | PETTARANI |  |  |  | 65 | 50 | 0 | Mat. Delivery | 2021-12-27 | 2022-08-13 | 2022-01-05 |  |  |  |  | 905305298 | 141010182 | 1046315480 | 0 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12021469 | 9 | 107 | 01C11B03 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010805/HK.810/OPS-10000000/2021 | Pengadaan Modernisasi ME dan Ekspan ME Support PoP, OTN, dan SKKL 2021 (Telkominfra) | 2021-12-27 | 2022-11-30 | Modernisasi ME | UJUNGPANDANG | PETTARANI |  |  |  | 100 | 100 | 100 | BAST-1 | 2021-12-27 | 2022-06-24 | 2022-01-05 | 762/LG.310/DID-B0300000/2022 | 2022-05-27 | TEL.0665/LG.320/DID-A0000000/2022 | 2022-05-27 | 802741320 | 106792614 | 909533934 | 909533934 | 4500447050 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA | 2022-05-31
G2021406 | 5 | 7 | 01E07V01 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010876/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching STO Rantepao Area Witel Sulselbar | 2021-12-28 | 2022-06-21 | FEEDER BRANCHING | PARE-PARE | RANTEPAO |  | R7 PRE RTP FE RLK STO RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2021-12-28 | 2022-02-25 | 2022-01-03 | TEL.886/LG.310/DR7-12700000/2022 | 2022-05-25 | TEL.0095/LG.320/DR7-10400000/2022 | 2022-05-25 | 298699291 | 148285822 | 446985113 | 446985113 | 4500447176 |  |  |  |  | TELKOM AKSES | 2022-06-23
G2021407 | 1 | 6 | 01E07V06 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010903/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 2 LOP Area Witel Sulut Malut | 2021-12-28 | 2022-02-25 | HEM | TERNATE | LABUHA |  | R7 MDO LBH HEM HARITA PULAU OBI |  | 100 | 100 | 100 | BAST-1 | 2021-12-28 | 2022-02-25 | 2022-01-27 | TEL.660/LG.310/DR7-12700000/2022 | 2022-02-12 | TEL.0021/LG.320/DR7-10400000/2022 | 2022-02-12 | 593797867 | 110396358 | 704194225 | 704194225 | 4500447213 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-02-25
G2021407 | 1 | 7 | 01E07V06 | 007 | 73020013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010903/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 2 LOP Area Witel Sulut Malut | 2021-12-28 | 2022-02-25 | HEM | TERNATE | LABUHA |  | R7 MDO LBH HEM TOWER HARITA |  | 100 | 100 | 100 | BAST-1 | 2021-12-28 | 2022-02-25 | 2022-01-27 | TEL.661/LG.310/DR7-12700000/2022 | 2022-02-12 | TEL.0021/LG.320/DR7-10400000/2022 | 2022-02-12 | 221842099 | 40777358 | 262619457 | 262619457 | 4500447213 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-02-25
G2021408 | 1 | 6 | 01E07V06 | 007 | 72040049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010930/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 4 LoP Area Witel Sulselbar | 2021-12-28 | 2022-01-26 | HEM | PARE-PARE | ENREKANG |  | R7 PRE ENR HEM STKIP ENREKANG |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-28 | TEL.640/LG.310/DR7-12700000/2022 | 2022-01-26 | TEL.0026/LG.320/DR7-10400000/2022 | 2022-01-26 | 1715991 | 239588 | 1955579 | 1955579 | 4500447237 |  |  |  |  | TELKOM AKSES | 2022-03-08
G2021408 | 1 | 7 | 01E07V06 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010930/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 4 LoP Area Witel Sulselbar | 2021-12-28 | 2022-01-26 | HEM | PARE-PARE | MALILI |  | R7 PRE MLL HEM KOMINFO MALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-28 | TEL.641/LG.310/DR7-12700000/2022 | 2022-01-26 | TEL.0026/LG.320/DR7-10400000/2022 | 2022-01-26 | 33486299 | 6756175 | 40242474 | 40242474 | 4500447237 |  |  |  |  | TELKOM AKSES | 2022-03-08
G2021408 | 1 | 8 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010930/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 4 LoP Area Witel Sulselbar | 2021-12-28 | 2022-01-26 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KANTOR DINAS KB MAMUJU |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-28 | TEL.642/LG.310/DR7-12700000/2022 | 2022-01-26 | TEL.0026/LG.320/DR7-10400000/2022 | 2022-01-26 | 4978636 | 1279161 | 6257797 | 6257797 | 4500447237 |  |  |  |  | TELKOM AKSES | 2022-03-08
G2021408 | 1 | 9 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010930/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 4 LoP Area Witel Sulselbar | 2021-12-28 | 2022-01-26 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KTR DINAS PERPUSTAKAAN PEMPROV SULBAR |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2021-12-28 | TEL.643/LG.310/DR7-12700000/2022 | 2022-01-26 | TEL.0026/LG.320/DR7-10400000/2022 | 2022-01-26 | 9107414 | 2077545 | 11184959 | 11184959 | 4500447237 |  |  |  |  | TELKOM AKSES | 2022-03-08
12021470 | 4 | 19 | 01C11G04 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010933/HK.810/OPS-10050000/2021 | SP#1 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2021-12-28 | 2022-05-26 | RADIO IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#3 Upgrade Hardware Sumalpua |  | 90 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-06-09 | 2022-02-25 | TEL.0635/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0142/LG.320/DID-A0000000/2022 | 2022-02-26 | 725033290 | 119528604 | 844561894 | 844561894 | 4500446978 |  |  |  |  | NEC INDONESIA | 2022-02-26
12021470 | 4 | 20 | 01C11G04 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010933/HK.810/OPS-10050000/2021 | SP#1 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2021-12-28 | 2022-05-26 | RADIO IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#4 BHP ISR Sumalpua |  | 90 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-06-09 | 2022-02-25 | TEL.0637/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0142/LG.320/DID-A0000000/2022 | 2022-02-26 | 0 | 29967248 | 29967248 | 29967248 | 4500446978 |  |  |  |  | NEC INDONESIA | 2022-02-26
12021470 | 4 | 18 | 01C11G04 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010933/HK.810/OPS-10050000/2021 | SP#1 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2021-12-28 | 2022-05-26 | RADIO IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#2 Redeploy Sumalpua |  | 90 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-06-09 | 2022-02-25 | TEL.0634/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0142/LG.320/DID-A0000000/2022 | 2022-02-26 | 643503253 | 601298744 | 1244801997 | 1244801997 | 4500446978 |  |  |  |  | NEC INDONESIA | 2022-02-26
12021470 | 4 | 17 | 01C11G04 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO PROJECT INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.010933/HK.810/OPS-10050000/2021 | SP#1 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2021-12-28 | 2022-05-26 | RADIO IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#1 New Link Sumalpua |  | 90 | 100 | 100 | BAST-1 | 2022-02-25 | 2022-06-09 | 2022-02-25 | TEL.0630/LG.310/DID-C0300000/2022 | 2022-02-26 | TEL.0142/LG.320/DID-A0000000/2022 | 2022-02-26 | 128685061 | 47229734 | 175914795 | 175914795 | 4500446978 |  |  |  |  | NEC INDONESIA | 2022-02-26
G2021409 | 2 | 9 | 01E07V06 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | ANTANG |  | LME WIFI CONSUMER NURWAHYUNI STO ANTANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.530/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1314278 | 708241 | 2022519 | 2022519 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 8 | 01E07V06 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | ANTANG |  | LME WIFI CONSUMER DEWI ANGRENI STO ANTANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.530/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 10 | 01E07V06 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | ANTANG |  | LME WIFI CONSUMER SALMAN STO ANTANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.530/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 11 | 01E07V06 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | ANTANG |  | LME WIFI CONSUMER WARKOP BORONG 77 STO ANTANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.530/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1523003 | 786191 | 2309194 | 2309194 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 21 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER CAFÉ D'SEVEN STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1155647 | 648999 | 1804646 | 1804646 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 16 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER RUSLI STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1022063 | 599111 | 1621174 | 1621174 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 23 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER JAHJA HOSEA STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 846734 | 533633 | 1380367 | 1380367 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 24 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER PT. BANK MANDIRI (PERSERO) Tbk STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1356023 | 723831 | 2079854 | 2079854 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 25 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER WARKOP ALAMI 2 STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 26 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER LIONG HENDRA GUNAWAN STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1022063 | 599111 | 1621174 | 1621174 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 22 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER SUNARDI LIWONGTO STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1982198 | 957681 | 2939879 | 2939879 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 17 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER GUNTUR EKA P STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1464560 | 764365 | 2228925 | 2228925 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 18 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER RAHMAD RAHMAN STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 19 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER MUH. ALQIZHAZ FAIZAL MUSDA STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 20 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER A. AHMAD.SE STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1523003 | 786191 | 2309194 | 2309194 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 12 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER WAHYUDDIN 1 STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 14 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER MUCHLIS M STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 15 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | LME WIFI CONSUMER ASRINET STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.491/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 838385 | 530515 | 1368900 | 1368900 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 27 | 01E07V06 | 007 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | JENEPONTO |  | LME WIFI CONSUMER ISAWARA GAUTAMA UDIN STO JENEPONTO |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.560/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 997016 | 589757 | 1586773 | 1586773 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 29 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER AKHMAD KHAIRIL STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1205741 | 667707 | 1873448 | 1873448 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 30 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER FERDINAN T STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1748426 | 870377 | 2618803 | 2618803 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 31 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER WARKOP BAHAGIA STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1314278 | 708241 | 2022519 | 2022519 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 32 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER YUSTISIA P STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1356023 | 723831 | 2079854 | 2079854 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 33 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER AKHMAD AKBAR R,SE 1 STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 679754 | 471273 | 1151027 | 1151027 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 34 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER AKHMAD AKBAR R,SE 2 STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 679754 | 471273 | 1151027 | 1151027 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 37 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER ILHAM STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 35 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER BURHANUDDIN 1 STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 36 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MAROS |  | LME WIFI CONSUMER BURHANUDDIN 2 STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.534/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 47 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER DG. TENE STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 46 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER BUYUNG ADI SAPUTRA STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1673285 | 842315 | 2515600 | 2515600 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 45 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER HAMKA SYARIFUDDIN STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 955271 | 574167 | 1529438 | 1529438 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 38 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER CHANDRA MAYA SIREGAR STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 39 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER ULIL AMRI STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1523003 | 786191 | 2309194 | 2309194 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 40 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER IR SUMIATI STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 963620 | 577285 | 1540905 | 1540905 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 41 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER ADE ALFATIRA STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 997016 | 589757 | 1586773 | 1586773 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 42 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER TAUPIQ KADIR STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1397768 | 739421 | 2137189 | 2137189 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 48 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER RANDI KURNIAWAN STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 955271 | 574167 | 1529438 | 1529438 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 44 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER AMRUL STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1189043 | 661471 | 1850514 | 1850514 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 43 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | LME WIFI CONSUMER A.HAERUL UMAM STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-22 | 2022-01-01 | TEL.506/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 804989 | 518043 | 1323032 | 1323032 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 56 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER ZULKIFLI STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1982198 | 957681 | 2939879 | 2939879 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 54 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER AMINUDDIN (tirai) STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 913526 | 558577 | 1472103 | 1472103 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 53 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER NANDAR NET WICO 2.0 STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 846734 | 533633 | 1380367 | 1380367 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 52 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER A. ERLINA ARAS STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1523003 | 786191 | 2309194 | 2309194 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 51 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER MUH. ASDAR SYAM STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 838385 | 530515 | 1368900 | 1368900 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 50 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER ZULFAJRIN ANSARI STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 930224 | 564813 | 1495037 | 1495037 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 49 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER AKSAN SURYA WIJAYA STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2282762 | 1069929 | 3352691 | 3352691 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 55 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER AMINUDDIN (bambu) STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 72 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER RISMA SALBIYANI STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1280882 | 695769 | 1976651 | 1976651 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 71 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER ARHAM STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1748426 | 870377 | 2618803 | 2618803 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 70 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER SAKINAH INDAH PRATIWI STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1523003 | 786191 | 2309194 | 2309194 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 69 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER IHKSAN RAHMAN STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 68 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER KANTOR MILAGROS STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1356023 | 723831 | 2079854 | 2079854 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 67 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER HJ. ROSDIANA STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1748426 | 870377 | 2618803 | 2618803 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 66 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER A. BANGSAWAN STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1038761 | 605347 | 1644108 | 1644108 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 64 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER RAKUM MARSUDI STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1673285 | 842315 | 2515600 | 2515600 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 63 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER GARY ADRIAN WAHYUDI STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 62 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER RINDINI'S STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1673285 | 842315 | 2515600 | 2515600 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 61 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER SYARIF HIDAYATULLAH STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2942333 | 1316251 | 4258584 | 4258584 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 60 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER ANDI ARI DWI ADITYA ISHAK STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 59 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER MUH ILHAM SYAM STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 679754 | 471273 | 1151027 | 1151027 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 58 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER YUNUS STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1189043 | 661471 | 1850514 | 1850514 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 57 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | LME WIFI CONSUMER MUH.ADRIYANSYAH STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.467/LG.310/DR7-12700000/2022 | 2022-03-15 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 955271 | 574167 | 1529438 | 1529438 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 86 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER KTR LURAH LAIKANG STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1147298 | 645881 | 1793179 | 1793179 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 85 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER MUH TAUFIQ HIDAYAT STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 855083 | 536751 | 1391834 | 1391834 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 84 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER BURHAN STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 988667 | 586639 | 1575306 | 1575306 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 83 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER ZULVAIZ JOKO STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 855083 | 536751 | 1391834 | 1391834 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 82 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER IRWAN 1 STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 838385 | 530515 | 1368900 | 1368900 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 81 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER HASRULLAH STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1280882 | 695769 | 1976651 | 1976651 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 73 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER SULFADLY RAHMAN STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2282762 | 1069929 | 3352691 | 3352691 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 79 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER BAYU SATRIYO EPSA STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 78 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER AWALUDDIN ST STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 77 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER SARI AYU STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 76 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER ANDHIKA FAIZAL DANGGANG STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1230788 | 677061 | 1907849 | 1907849 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 75 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER NADIA RISKY AMALIA STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 688103 | 474391 | 1162494 | 1162494 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 74 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER UNGGUL BUDI PRABOWO STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1022063 | 599111 | 1621174 | 1621174 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 80 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUDIANG |  | LME WIFI CONSUMER DAHLIA STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.544/LG.310/DR7-12700000/2022 | 2022-03-17 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 123 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER NURUL EKA PUTRI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 122 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER SYAFRI ALI BETA STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 121 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HANNI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1464560 | 764365 | 2228925 | 2228925 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 120 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER MUSLIMIN STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1464560 | 764365 | 2228925 | 2228925 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 119 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HARPENDI UMAR SE STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1147298 | 645881 | 1793179 | 1793179 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 118 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RASIDUDDIN, S.SOS. I. MPD STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 3075917 | 1366139 | 4442056 | 4442056 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 117 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HAJRIAH STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 880130 | 546105 | 1426235 | 1426235 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 116 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HERMAN S.PD STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1022063 | 599111 | 1621174 | 1621174 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 115 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER SAHRA RAHAYU STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 688103 | 474391 | 1162494 | 1162494 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 114 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER SAMSUDIN T JALO STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1673285 | 842315 | 2515600 | 2515600 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 113 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER AMIN DANTO STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2942333 | 1316251 | 4258584 | 4258584 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 112 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER ACHMAD GOZALI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 111 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER TAMAN KANAK KANAK DHIFA STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 110 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RASDIANA PRATIWI R STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1314278 | 708241 | 2022519 | 2022519 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 109 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER ASRUL STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1189043 | 661471 | 1850514 | 1850514 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 108 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER ANJANI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 107 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER IRMAWATI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 905177 | 555459 | 1460636 | 1460636 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 106 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER MUH IMRAN ISMAIL STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1731728 | 864141 | 2595869 | 2595869 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 105 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER NURSYAMSI, ST STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1105553 | 630291 | 1735844 | 1735844 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 104 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER ANDI ISWHYARTIFRI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1673285 | 842315 | 2515600 | 2515600 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 103 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER MUHAMMAD AMIN, SHI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1982198 | 957681 | 2939879 | 2939879 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 102 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER SANGMANGAWARU STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2023943 | 973271 | 2997214 | 2997214 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 101 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER SITI UMMY RUSUNAH HARIS STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1147298 | 645881 | 1793179 | 1793179 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 100 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RIZKI ARIYANTI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 930224 | 564813 | 1495037 | 1495037 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 96 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER ASMA STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2023943 | 973271 | 2997214 | 2997214 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 95 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HASRI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 729848 | 489981 | 1219829 | 1219829 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 94 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER MUHAMMAD YUSRAN STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1731728 | 864141 | 2595869 | 2595869 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 93 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RAHMAWATI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 788291 | 511807 | 1300098 | 1300098 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 92 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER BURHANUDDIN STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1189043 | 661471 | 1850514 | 1850514 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 91 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER TAUFIK M. AKIB S.S STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1356023 | 723831 | 2079854 | 2079854 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 90 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RIZAL STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1255835 | 686415 | 1942250 | 1942250 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 89 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER BACHTIAR SALEH STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 838385 | 530515 | 1368900 | 1368900 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 87 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HASRAN STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2023943 | 973271 | 2997214 | 2997214 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 134 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER REZKY AMALIYAH B. DOLLAH STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1982198 | 957681 | 2939879 | 2939879 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 133 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER KANTOR LURAH MAWANG STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1147298 | 645881 | 1793179 | 1793179 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 132 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER IRWAN 2 STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 913526 | 558577 | 1472103 | 1472103 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 131 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER NURSYAIFULLAH STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1147298 | 645881 | 1793179 | 1793179 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 130 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER ALGIFARI ANANTA G STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1013714 | 595993 | 1609707 | 1609707 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 129 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER FADLY WIFI SUSAH SENANG STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 128 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER HERU PANGESTU STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1523003 | 786191 | 2309194 | 2309194 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 127 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RISMAWATI KADIR STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1013714 | 595993 | 1609707 | 1609707 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 126 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER AIR SEHAT ALFARABI STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1105553 | 630291 | 1735844 | 1735844 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 125 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER RISKA ANNITA RAHMA STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 955271 | 574167 | 1529438 | 1529438 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 124 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | LME WIFI CONSUMER MUH SYAHRUL R STO SUNGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.419/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1147298 | 645881 | 1793179 | 1793179 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 136 | 01E07V06 | 007 | 72080120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAKALAR |  | LME WIFI CONSUMER CHAERO INDRA PRYATMA STO TAKALAR |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.558/LG.310/DR7-12700000/2022 | 2022-03-18 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2942333 | 1316251 | 4258584 | 4258584 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 139 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER MUH. ARSYAD/WMS APPINK STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 140 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER TAJUDDIN NUR STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 2023943 | 973271 | 2997214 | 2997214 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 141 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER UMMI KULSUM DURHAN STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 963620 | 577285 | 1540905 | 1540905 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 142 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER ANDI ABDUL RAUF STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 997016 | 589757 | 1586773 | 1586773 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 143 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER ANDI SAHRUL RAMADHAN STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1982198 | 957681 | 2939879 | 2939879 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 144 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER M.AKBAR RAHMADI STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 688103 | 474391 | 1162494 | 1162494 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 145 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER VICKY STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1055459 | 611583 | 1667042 | 1667042 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 146 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER M. BASRI STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1982198 | 957681 | 2939879 | 2939879 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 147 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER HJ. HAJERAH STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 813338 | 521161 | 1334499 | 1334499 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 148 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER HASANUDDIN STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1063808 | 614701 | 1678509 | 1678509 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 149 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER MARK MAMANGKEY TJOST STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 688103 | 474391 | 1162494 | 1162494 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 137 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER ILHAM JAYA STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 1356023 | 723831 | 2079854 | 2079854 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021409 | 2 | 138 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010936/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan LME Wifi Consumer 142 LoP Area Witel Makassar | 2021-12-28 | 2022-01-26 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | LME WIFI CONSUMER ACHMAD RISWAN STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-24 | 2022-01-01 | TEL.517/LG.310/DR7-12700000/2022 | 2022-03-16 | TEL.0044/LG.320/DR7-10400000/2022 | 2022-03-18 | 596264 | 440093 | 1036357 | 1036357 | 4500447241 |  |  |  |  | RATI UTAMA KARYA | 2022-04-12
G2021410 | 1 | 10 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010944/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan Feeder Untuk Lokasi Mawasangka & Lasolo Area Witel Sultra | 2021-12-28 | 2022-02-10 | FEEDER BRANCHING | KENDARI | BAU-BAU |  | R7 KDI BBU FE MAWASANGKA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-02 | 2022-01-03 | TEL.646/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0018/LG.320/DR7-10400000/2022 | 2022-02-05 | 1400563 | 2642523 | 4043086 | 4043086 | 4500447244 |  |  |  |  | TELKOM AKSES | 2022-02-18
G2021410 | 1 | 11 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.010944/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan Feeder Untuk Lokasi Mawasangka & Lasolo Area Witel Sultra | 2021-12-28 | 2022-02-10 | FEEDER BRANCHING | KENDARI | KENDARI |  | R7KDI KDR FE LASOLO |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-02 | 2022-01-03 | TEL.647/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0018/LG.320/DR7-10400000/2022 | 2022-02-05 | 1113169 | 3370553 | 4483722 | 4483722 | 4500447244 |  |  |  |  | TELKOM AKSES | 2022-02-18
G2021411 | 1 | 66 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.195/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 78 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.186/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 79 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.188/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 6 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.191/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6771456 | 3113064 | 9884520 | 9884520 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 22 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.189/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 32 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.183/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 44 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.197/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 56 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.196/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 101 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.187/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 102 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.193/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 103 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.185/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 104 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.194/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 105 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.192/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 106 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.190/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 191 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.198/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 107 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | ANTANG |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.184/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 196 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.214/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 114 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.200/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7335744 | 3372486 | 10708230 | 10708230 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 113 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.206/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6771456 | 3113064 | 9884520 | 9884520 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 112 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.208/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 111 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.210/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 110 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.201/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9592896 | 4410174 | 14003070 | 14003070 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 109 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.209/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7900032 | 3631908 | 11531940 | 11531940 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 108 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.203/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9592896 | 4410174 | 14003070 | 14003070 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 95 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.204/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 61 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.212/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 12978624 | 5966706 | 18945330 | 18945330 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 49 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.213/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11850048 | 5447862 | 17297910 | 17297910 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 37 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.199/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 18057216 | 8301504 | 26358720 | 26358720 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 27 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.205/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 18057216 | 8301504 | 26358720 | 26358720 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 10 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.207/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 13542912 | 6226128 | 19769040 | 19769040 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 83 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.202/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 10721472 | 4929018 | 15650490 | 15650490 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 71 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.211/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 14107200 | 6485550 | 20592750 | 20592750 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 19 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BULUKUMBA |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.216/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 100 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | BULUKUMBA |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.215/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 88 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.219/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 77 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-15 | 2022-01-01 | TEL.225/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 168 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.223/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 169 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.218/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 171 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.222/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 172 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.227/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 43 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.217/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 17 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.221/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 65 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.226/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 31 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-20 | 2022-01-01 | TEL.220/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 170 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | KIMA |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.224/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 150 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.236/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 151 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.229/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 152 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.234/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 153 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.240/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 12 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.235/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 149 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.231/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 73 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.237/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 85 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.230/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 63 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.238/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 97 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.232/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 39 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.228/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 51 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-19 | 2022-01-01 | TEL.239/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 29 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MAROS |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.233/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 48 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-14 | 2022-01-01 | TEL.255/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11850048 | 5447862 | 17297910 | 17297910 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 36 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-14 | 2022-01-01 | TEL.241/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 13542912 | 6226128 | 19769040 | 19769040 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 142 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.242/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7900032 | 3631908 | 11531940 | 11531940 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 141 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.248/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 140 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.250/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6207168 | 2853642 | 9060810 | 9060810 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 139 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.252/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 138 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.243/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9592896 | 4410174 | 14003070 | 14003070 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 137 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.251/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6207168 | 2853642 | 9060810 | 9060810 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 136 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.245/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9028608 | 4150752 | 13179360 | 13179360 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 195 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.256/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9028608 | 4150752 | 13179360 | 13179360 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 94 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.246/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 60 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-12 | 2022-01-20 | 2022-01-01 | TEL.254/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 12414336 | 5707284 | 18121620 | 18121620 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 82 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.244/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 10157184 | 4669596 | 14826780 | 14826780 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 70 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-12 | 2022-01-19 | 2022-01-01 | TEL.253/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 10157184 | 4669596 | 14826780 | 14826780 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 26 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-21 | 2022-01-28 | 2022-01-01 | TEL.247/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 10721472 | 4929018 | 15650490 | 15650490 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 9 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-12 | 2022-01-19 | 2022-01-01 | TEL.249/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 15800064 | 7263816 | 23063880 | 23063880 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 35 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 0 | 100 | 100 | BAST-1 | 2022-03-01 | 2022-03-14 | 2022-01-01 | TEL.257/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 16364352 | 7523238 | 23887590 | 23887590 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 59 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-19 | 2022-01-25 | 2022-01-01 | TEL.270/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 13542912 | 6226128 | 19769040 | 19769040 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 47 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-19 | 2022-01-26 | 2022-01-01 | TEL.271/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 14671488 | 6744972 | 21416460 | 21416460 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 194 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.272/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6771456 | 3113064 | 9884520 | 9884520 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 129 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.261/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 12414336 | 5707284 | 18121620 | 18121620 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 130 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.267/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11285760 | 5188440 | 16474200 | 16474200 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 8 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-13 | 2022-01-19 | 2022-01-01 | TEL.265/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 20314368 | 9339192 | 29653560 | 29653560 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 131 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.259/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 25 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-05 | 2022-01-12 | 2022-01-01 | TEL.263/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 15800064 | 7263816 | 23063880 | 23063880 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 132 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.268/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6771456 | 3113064 | 9884520 | 9884520 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 69 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-01-28 | 2022-01-01 | TEL.269/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 16364352 | 7523238 | 23887590 | 23887590 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 133 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.266/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11285760 | 5188440 | 16474200 | 16474200 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 81 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.260/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9028608 | 4150752 | 13179360 | 13179360 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 134 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.264/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 135 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.258/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 93 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.262/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11850048 | 5447862 | 17297910 | 17297910 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 157 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.282/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 158 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.275/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 159 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.283/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 160 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.281/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 173 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.274/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 174 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.287/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 13 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-12 | 2022-01-18 | 2022-01-01 | TEL.280/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 30 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-01-28 | 2022-01-01 | TEL.279/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 74 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-08 | 2022-01-16 | 2022-01-01 | TEL.284/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 52 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 90 | 100 | 100 | BAST-1 | 2022-01-26 | 2022-02-02 | 2022-01-01 | TEL.286/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 64 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-11 | 2022-01-01 | TEL.285/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 86 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.276/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 98 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.278/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 156 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.277/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 40 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | PANGKEP |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-12 | 2022-01-19 | 2022-01-01 | TEL.273/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 178 | 01E07J04 | 007 | 72080112 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SELAYAR |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.288/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 20 | 01E07J04 | 007 | 72080112 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SELAYAR |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-22 | 2022-01-30 | 2022-01-01 | TEL.289/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 185 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SINJAI |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.290/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 177 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SINJAI |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.292/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 55 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SINJAI |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-15 | 2022-01-23 | 2022-01-01 | TEL.293/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 16 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SINJAI |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-15 | 2022-01-22 | 2022-01-01 | TEL.291/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 193 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.309/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 128 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.295/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 34 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-14 | 2022-01-01 | TEL.294/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 46 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-05 | 2022-01-12 | 2022-01-01 | TEL.308/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7335744 | 3372486 | 10708230 | 10708230 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 21 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-13 | 2022-01-01 | TEL.302/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 12978624 | 5966706 | 18945330 | 18945330 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 24 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-18 | 2022-01-01 | TEL.300/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 68 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-12 | 2022-01-01 | TEL.306/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7900032 | 3631908 | 11531940 | 11531940 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 80 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.297/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7900032 | 3631908 | 11531940 | 11531940 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 58 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-12 | 2022-01-01 | TEL.307/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6771456 | 3113064 | 9884520 | 9884520 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 92 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.299/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 122 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.298/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 123 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.304/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 124 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.296/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 125 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.305/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 126 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.303/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 127 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUDIANG |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.301/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 84 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.312/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11850048 | 5447862 | 17297910 | 17297910 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 188 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.310/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7335744 | 3372486 | 10708230 | 10708230 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 72 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-02 | 2022-01-10 | 2022-01-01 | TEL.322/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 10157184 | 4669596 | 14826780 | 14826780 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 143 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.313/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 50 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-05 | 2022-01-11 | 2022-01-01 | TEL.324/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9592896 | 4410174 | 14003070 | 14003070 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 62 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-10 | 2022-01-01 | TEL.323/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 9592896 | 4410174 | 14003070 | 14003070 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 11 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-12 | 2022-01-01 | TEL.318/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 12414336 | 5707284 | 18121620 | 18121620 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 96 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.314/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 144 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.320/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7335744 | 3372486 | 10708230 | 10708230 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 38 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-10 | 2022-01-01 | TEL.315/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5642880 | 2594220 | 8237100 | 8237100 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 145 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.311/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6207168 | 2853642 | 9060810 | 9060810 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 146 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.321/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 28 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-11 | 2022-01-01 | TEL.316/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 11850048 | 5447862 | 17297910 | 17297910 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 147 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.319/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 189 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.325/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 7900032 | 3631908 | 11531940 | 11531940 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 148 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.317/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6771456 | 3113064 | 9884520 | 9884520 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 42 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAKALAR |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-10 | 2022-01-01 | TEL.326/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 18 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAKALAR |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-13 | 2022-01-01 | TEL.328/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 76 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAKALAR |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-12 | 2022-01-01 | TEL.330/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 89 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAKALAR |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.327/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 181 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAKALAR |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.329/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 182 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAKALAR |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.331/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 121 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.333/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 45 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-11 | 2022-01-01 | TEL.346/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5642880 | 2594220 | 8237100 | 8237100 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 119 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.341/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 118 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.343/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 117 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.334/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 116 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.342/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 115 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.336/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 6207168 | 2853642 | 9060810 | 9060810 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 91 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.337/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 90 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.335/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 67 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-19 | 2022-01-26 | 2022-01-01 | TEL.344/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 23 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-05 | 2022-01-11 | 2022-01-01 | TEL.338/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 57 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-11 | 2022-01-19 | 2022-01-01 | TEL.345/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 192 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.347/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 33 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-02 | 2022-01-09 | 2022-01-01 | TEL.332/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 7 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-13 | 2022-01-01 | TEL.340/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 5078592 | 2334798 | 7413390 | 7413390 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 120 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | Instalasi AP WiFi.id Consumer Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.339/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 41 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-04 | 2022-01-09 | 2022-01-01 | TEL.348/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 99 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.352/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 87 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.350/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1128576 | 518844 | 1647420 | 1647420 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 54 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2021-12-28 | 2022-01-06 | 2022-01-01 | TEL.357/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 53 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-14 | 2022-01-01 | TEL.358/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 8464320 | 3891330 | 12355650 | 12355650 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 161 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.351/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 15 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode JUNI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-06 | 2022-01-13 | 2022-01-01 | TEL.354/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 14 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-13 | 2022-01-19 | 2022-01-01 | TEL.353/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 1692864 | 778266 | 2471130 | 2471130 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 163 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.349/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 162 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-14 | 2022-01-01 | TEL.355/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021411 | 1 | 75 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010955/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan AP WIFI 176 LOP Periode Juni 2020 - September 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | AP WIFI | UJUNGPANDANG | WATAMPONE |  | Instalasi AP WiFi.id Consumer Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-09 | 2022-01-01 | TEL.356/LG310/R7W-7A330000/2022 | 2022-01-20 | TEL.0001/LG.320/R7W-7A100000/2022 | 2022-01-20 | 564288 | 259422 | 823710 | 823710 | 4500447073 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 19 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.89/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5480248 | 0 | 5480248 | 5480248 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 18 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.90/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 7443110 | 0 | 7443110 | 7443110 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 17 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.81/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8220372 | 0 | 8220372 | 8220372 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 16 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.85/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5480248 | 0 | 5480248 | 5480248 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 10 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.84/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 12080554 | 3215 | 12083769 | 12083769 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 14 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.88/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 4794186 | 0 | 4794186 | 4794186 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 13 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.82/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5480248 | 0 | 5480248 | 5480248 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 12 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.87/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 4566186 | 0 | 4566186 | 4566186 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 11 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.83/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 10046434 | 0 | 10046434 | 10046434 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 15 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.86/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 3036524 | 0 | 3036524 | 3036524 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 25 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.96/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 10960496 | 0 | 10960496 | 10960496 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 29 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.99/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 24020654 | 0 | 24020654 | 24020654 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 28 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.100/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 20984130 | 0 | 20984130 | 20984130 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 27 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.91/LG310/R7W-7A3300000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 18722806 | 0 | 18722806 | 18722806 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 26 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.95/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 16946904 | 0 | 16946904 | 16946904 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 20 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.94/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 14299136 | 6430 | 14305566 | 14305566 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 24 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.98/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 7306310 | 0 | 7306310 | 7306310 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 23 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.92/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 24718334 | 0 | 24718334 | 24718334 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 22 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.97/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 20870130 | 0 | 20870130 | 20870130 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 21 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.93/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 27399178 | 0 | 27399178 | 27399178 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 30 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | BULUKUMBA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.101/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 35 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.106/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 34 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.103/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 31 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.104/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 4110186 | 0 | 4110186 | 4110186 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 32 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.102/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 33 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.105/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 36 | 01E07J04 | 007 | 72080075 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MALINO |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.107/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 38 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.109/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 13470558 | 0 | 13470558 | 13470558 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 39 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.112/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1598062 | 0 | 1598062 | 1598062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 40 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.108/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5022186 | 0 | 5022186 | 5022186 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 42 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.111/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 4110186 | 0 | 4110186 | 4110186 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 43 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.115/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 3196124 | 0 | 3196124 | 3196124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 44 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.114/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5022186 | 0 | 5022186 | 5022186 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 37 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.110/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 12998270 | 9645 | 13007915 | 13007915 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 41 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.113/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 45 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.119/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 14071136 | 6430 | 14077566 | 14077566 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 46 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.118/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 26350378 | 0 | 26350378 | 26350378 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 47 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.122/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 16805544 | 0 | 16805544 | 16805544 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 48 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.117/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 23655854 | 0 | 23655854 | 23655854 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 49 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.123/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 21006930 | 0 | 21006930 | 21006930 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 50 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.121/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 15982682 | 0 | 15982682 | 15982682 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 51 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.120/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 7078310 | 0 | 7078310 | 7078310 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 52 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.116/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 19956068 | 0 | 19956068 | 19956068 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 54 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.124/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8220372 | 0 | 8220372 | 8220372 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 53 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.125/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 22422592 | 0 | 22422592 | 22422592 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 57 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.132/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 28541240 | 0 | 28541240 | 28541240 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 58 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.127/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 20550930 | 0 | 20550930 | 20550930 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 59 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.133/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 17170344 | 0 | 17170344 | 17170344 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 60 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.131/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 28085240 | 0 | 28085240 | 28085240 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 64 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.134/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 22376992 | 0 | 22376992 | 22376992 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 62 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.126/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 21462930 | 0 | 21462930 | 21462930 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 63 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.135/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 17580744 | 0 | 17580744 | 17580744 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 56 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.128/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 31372564 | 0 | 31372564 | 31372564 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 55 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.129/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 37400872 | 28935 | 37429807 | 37429807 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 61 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.130/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 9590434 | 0 | 9590434 | 9590434 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 65 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.139/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1826062 | 0 | 1826062 | 1826062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 66 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.138/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5617048 | 0 | 5617048 | 5617048 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 67 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.143/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 68 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.136/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1598062 | 0 | 1598062 | 1598062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 69 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.140/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 2740124 | 0 | 2740124 | 2740124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 70 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.142/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 3241724 | 0 | 3241724 | 3241724 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 71 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.137/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1598062 | 0 | 1598062 | 1598062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 72 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.141/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 3196124 | 0 | 3196124 | 3196124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 73 | 01E07J04 | 007 | 72080112 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SELAYAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.144/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 3560924 | 0 | 3560924 | 3560924 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 74 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SINJAI |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.146/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 75 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SINJAI |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.145/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 84 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.148/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8220372 | 0 | 8220372 | 8220372 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 76 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.150/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 6150022 | 9645 | 6159667 | 6159667 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 77 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.149/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 9132372 | 0 | 9132372 | 9132372 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 78 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.155/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8813172 | 0 | 8813172 | 8813172 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 79 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.156/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 13288158 | 0 | 13288158 | 13288158 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 80 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.147/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 10046434 | 0 | 10046434 | 10046434 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 81 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.151/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8448372 | 0 | 8448372 | 8448372 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 82 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.152/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8813172 | 0 | 8813172 | 8813172 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 83 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.154/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5480248 | 0 | 5480248 | 5480248 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 85 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.153/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 12556496 | 0 | 12556496 | 12556496 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 94 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.166/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 20548868 | 0 | 20548868 | 20548868 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 93 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.157/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 18193846 | 0 | 18193846 | 18193846 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 95 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.165/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 10912834 | 0 | 10912834 | 10912834 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 86 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.160/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 8818888 | 6430 | 8825318 | 8825318 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 92 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.161/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 17722104 | 0 | 17722104 | 17722104 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 88 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.163/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 19406806 | 0 | 19406806 | 19406806 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 89 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.158/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 16119482 | 0 | 16119482 | 16119482 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 90 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.164/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 13652958 | 0 | 13652958 | 13652958 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 91 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.162/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 11867936 | 0 | 11867936 | 11867936 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 87 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.159/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 11416496 | 0 | 11416496 | 11416496 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 97 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAKALAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.168/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 96 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAKALAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.167/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 2740124 | 0 | 2740124 | 2740124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 105 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Mei 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.176/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5936248 | 0 | 5936248 | 5936248 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 99 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.171/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 15298682 | 0 | 15298682 | 15298682 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 100 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Oktober 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.177/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 2876924 | 0 | 2876924 | 2876924 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 101 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode September 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.178/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1370062 | 0 | 1370062 | 1370062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 107 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.175/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 12237296 | 0 | 12237296 | 12237296 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 106 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.170/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5480248 | 0 | 5480248 | 5480248 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 98 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.172/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 9340430 | 3215 | 9343645 | 9343645 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 104 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juni 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.174/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 3287324 | 0 | 3287324 | 3287324 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 103 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Juli 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.173/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 2740124 | 0 | 2740124 | 2740124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 102 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Agustus 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.169/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 2968124 | 0 | 2968124 | 2968124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 108 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Januari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.181/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 5549444 | 3215 | 5552659 | 5552659 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 109 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Februari 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.180/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 2968124 | 0 | 2968124 | 2968124 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 110 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode Maret 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.182/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1826062 | 0 | 1826062 | 1826062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021412 | 1 | 111 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010965/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan PSB WIFI PT-1 102 LoP Januari - Oktober 2021 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode April 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-21 | 2022-01-01 | TEL.179/LG310/R7W-7A330000/2022 | 2022-01-14 | TEL.0002/LG.320/R7W-7A100000/2022 | 2022-01-14 | 1826062 | 0 | 1826062 | 1826062 | 4500447069 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 21 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.14/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 13930212 | 6430 | 13936642 | 13936642 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 24 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.10/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 9960950 | 6430 | 9967380 | 9967380 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 23 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.12/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 7306310 | 0 | 7306310 | 7306310 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 22 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.13/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 13385074 | 6430 | 13391504 | 13391504 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 20 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.9/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 12401816 | 3215 | 12405031 | 12405031 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 6 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.11/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 12330558 | 0 | 12330558 | 12330558 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 27 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.19/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 35455826 | 0 | 35455826 | 35455826 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 25 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.15/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 42471922 | 0 | 42471922 | 42471922 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 29 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.16/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 28176440 | 0 | 28176440 | 28176440 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 11 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-05 | 2022-01-01 | TEL.17/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 43841984 | 0 | 43841984 | 43841984 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 26 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.20/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 30575360 | 3215 | 30578575 | 30578575 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 28 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.18/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 38218750 | 0 | 38218750 | 38218750 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 19 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | BULUKUMBA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.21/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1370062 | 0 | 1370062 | 1370062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 32 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.25/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 2811382 | 3215 | 2814597 | 2814597 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 33 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.23/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 4708702 | 6430 | 4715132 | 4715132 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 17 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.24/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 2740124 | 0 | 2740124 | 2740124 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 31 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.26/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 2740124 | 0 | 2740124 | 2740124 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 30 | 01E07J04 | 007 | 72080064 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | KIMA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.22/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1370062 | 0 | 1370062 | 1370062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 38 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.28/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 8360826 | 6430 | 8367256 | 8367256 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 13 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.29/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 11044767 | 3215 | 11047982 | 11047982 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 35 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.32/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 11013404 | 12860 | 11026264 | 11026264 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 37 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.30/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 5549444 | 3215 | 5552659 | 5552659 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 34 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.27/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 6921568 | 3215 | 6924783 | 6924783 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 36 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MAROS |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.31/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 6392248 | 0 | 6392248 | 6392248 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 39 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.33/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 33237778 | 16075 | 33253853 | 33253853 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 40 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.38/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 31022850 | 19290 | 31042140 | 31042140 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 41 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.37/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 34313764 | 0 | 34313764 | 34313764 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 42 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.36/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 28046948 | 12860 | 28059808 | 28059808 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 43 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.34/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 26330436 | 3215 | 26333651 | 26333651 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 10 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.35/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 26199720 | 6430 | 26206150 | 26206150 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 9 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.41/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 38698820 | 12860 | 38711680 | 38711680 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 48 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.40/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 23889570 | 6430 | 23896000 | 23896000 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 47 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.42/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 41769572 | 9645 | 41779217 | 41779217 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 44 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.39/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 40159346 | 19290 | 40178636 | 40178636 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 45 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.44/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 42661160 | 19290 | 42680450 | 42680450 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 46 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.43/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 35517778 | 16075 | 35533853 | 35533853 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 53 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.46/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1370062 | 0 | 1370062 | 1370062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 52 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.48/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 5551506 | 3215 | 5554721 | 5554721 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 50 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.50/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1897320 | 3215 | 1900535 | 1900535 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 49 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.45/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 2811382 | 3215 | 2814597 | 2814597 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 51 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.49/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 11086724 | 16075 | 11102799 | 11102799 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 14 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.47/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 7018852 | 6430 | 7025282 | 7025282 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 54 | 01E07J04 | 007 | 72080112 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SELAYAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.51/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1826062 | 0 | 1826062 | 1826062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 18 | 01E07J04 | 007 | 72080115 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SINJAI |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.52/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 3039382 | 3215 | 3042597 | 3042597 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 55 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.53/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 20764704 | 9645 | 20774349 | 20774349 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 56 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.58/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 23254354 | 19290 | 23273644 | 23273644 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 57 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.57/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 17962692 | 19290 | 17981982 | 17981982 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 58 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.56/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 20235384 | 6430 | 20241814 | 20241814 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 59 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.54/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 23341900 | 12860 | 23354760 | 23354760 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 8 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.55/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 20972285 | 16075 | 20988360 | 20988360 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 62 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.63/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 25665176 | 28935 | 25694111 | 25694111 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 60 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.59/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 14056910 | 16075 | 14072985 | 14072985 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 64 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.60/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 31419024 | 28935 | 31447959 | 31447959 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 63 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-09 | 2022-01-01 | TEL.62/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 26998148 | 12860 | 27011008 | 27011008 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 61 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.64/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 30031344 | 16075 | 30047419 | 30047419 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 12 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.61/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 29445470 | 25720 | 29471190 | 29471190 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 16 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.67/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1454333 | 3215 | 1457548 | 1457548 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 67 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.66/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1441320 | 3215 | 1444535 | 1444535 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 66 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.68/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1370062 | 0 | 1370062 | 1370062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 65 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.65/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1370062 | 0 | 1370062 | 1370062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 69 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.74/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 15667136 | 6430 | 15673566 | 15673566 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 70 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.73/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 12262954 | 3215 | 12266169 | 12266169 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 71 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.72/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 5549444 | 3215 | 5552659 | 5552659 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 72 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.70/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 3404182 | 3215 | 3407397 | 3407397 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 7 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.71/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 5564519 | 3215 | 5567734 | 5567734 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 68 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.69/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1370062 | 0 | 1370062 | 1370062 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 73 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode AGUSTUS 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.75/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 8434146 | 9645 | 8443791 | 8443791 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 75 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode OKTOBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.79/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 12169692 | 3215 | 12172907 | 12172907 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 76 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode NOVEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.78/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 1897320 | 3215 | 1900535 | 1900535 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 77 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode DESEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.76/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 3652124 | 0 | 3652124 | 3652124 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 15 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode JULI 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.77/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 4278728 | 6430 | 4285158 | 4285158 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021413 | 1 | 74 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.010966/HK.810/R7W-7A100000/2021 | Surat Pesanan Pengadaan dan Pemasangan LME WIFI PT-1 72 LoP Periode Juli - Desember 2020 Area Witel Makassar - PT. TELKOM AKSES | 2021-12-28 | 2022-03-27 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | Pasang Sambungan Baru LME Wifi PT-1 Cons Periode SEPTEMBER 2020 |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-13 | 2022-01-01 | TEL.80/LG310/R7W-7A330000/2022 | 2022-01-19 | TEL.0003/LG.320/R7W-7A100000/2022 | 2022-01-19 | 27604704 | 9645 | 27614349 | 27614349 | 4500447068 |  |  |  |  | TELKOM AKSES | 2022-01-31
G2021414 | 1 | 6 | 01E07V06 | 007 | 73010161 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011000/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 3 LOP Area Witel Maluku | 2021-12-29 | 2022-02-11 | HEM | AMBON | PAO |  | R7 AMB PAO HEM KANTOR BLK AMBON |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-07 | 2022-01-01 | TEL.648/LG.310/DR7-12700000/2022 | 2022-02-09 | TEL.0027/LG.320/DR7-10400000/2022 | 2022-02-09 | 17988730 | 3671243 | 21659973 | 21659973 | 4500447302 |  |  |  |  | TELKOM AKSES | 2022-03-08
G2021414 | 1 | 8 | 01E07V06 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011000/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 3 LOP Area Witel Maluku | 2021-12-29 | 2022-02-11 | HEM | AMBON | TUAL |  | R7 AMB TUA HEM BANK ARTHA GRAHA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-07 | 2022-01-01 | TEL.649/LG.310/DR7-12700000/2022 | 2022-02-09 | TEL.0027/LG.320/DR7-10400000/2022 | 2022-02-09 | 46611494 | 8609012 | 55220506 | 55220506 | 4500447302 |  |  |  |  | TELKOM AKSES | 2022-03-08
G2021414 | 1 | 7 | 01E07V06 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011000/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 3 LOP Area Witel Maluku | 2021-12-29 | 2022-02-11 | HEM | AMBON | TUAL |  | R7 AMB TUA HEM POLRES TUAL |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-07 | 2022-01-01 | TEL.650/LG.310/DR7-12700000/2022 | 2022-02-09 | TEL.0027/LG.320/DR7-10400000/2022 | 2022-02-09 | 9779425 | 2606675 | 12386100 | 12386100 | 4500447302 |  |  |  |  | TELKOM AKSES | 2022-03-08
G2021415 | 1 | 10 | 01E07V06 | 007 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011053/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 1 LoP Area Witel Makassar | 2021-12-29 | 2022-01-27 | HEM | UJUNGPANDANG | JENEPONTO |  | Mandiri Jeneponto |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-24 | 2022-01-03 | TEL.418/LG.310/DR7-12700000/2022 | 2022-02-09 | TEL.0029/LG.320/DR7-10400000/2022 | 2022-02-09 | 9977268 | 2934567 | 12911835 | 12911835 | 4500447416 |  |  |  |  | RATI UTAMA KARYA | 2022-03-10
G2021416 | 1 | 24 | 01E07V06 | 007 | 72010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | BAHU |  | R7 MDO BAH HEM RSUP KANDOU MANADO |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.676/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 12831155 | 2277630 | 15108785 | 15108785 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 25 | 01E07V06 | 007 | 72010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | BAHU |  | R7 MDO BAH HEM KEPALA PTI UNSRAT |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.677/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 2130425 | 254518 | 2384943 | 2384943 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 10 | 01E07V06 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | BITUNG |  | R7 MDO BIT HEM KODAM MERDEKA MAKALISUNG |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.663/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 24137618 | 4978672 | 29116290 | 29116290 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 11 | 01E07V06 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | BITUNG |  | R7 MDO BIT HEM PELABUHAN BITUNG |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-05 | 2022-01-01 | TEL.665/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 12605492 | 2865007 | 15470499 | 15470499 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 12 | 01E07V06 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | BITUNG |  | R7 MDO BIT HEM BENDAHARA BAKTI KAU |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-24 | 2022-01-01 | TEL.664/LG.310/DR7-12700000/2021 | 2022-02-11 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 10921495 | 2090715 | 13012210 | 13012210 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 13 | 01E07V06 | 007 | 72010267 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | HULU SIAU |  | R7 MDO HLS HEM BPS Sitaro |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.666/LG.310/DR7-12700000/2021 | 2022-02-04 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 21059787 | 4091349 | 25151136 | 25151136 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 15 | 01E07V06 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | KOTAMOBAGU |  | R7 MDO KTG HEM SMK 1 MOOAT |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.667/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 70782508 | 15887011 | 86669519 | 86669519 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 14 | 01E07V06 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | KOTAMOBAGU |  | R7 MDO KTG HEM HOTEL SAPADIA KOTAMOBAGU |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.668/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 2718345 | 325629 | 3043974 | 3043974 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 17 | 01E07V06 | 007 | 72010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | LOLAK |  | R7 MDO LOL HEM KANTOR KPU BOLMONG |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.669/LG.310/DR7-12700000/2021 | 2022-02-04 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 14444035 | 2992503 | 17436538 | 17436538 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 16 | 01E07V06 | 007 | 72010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | LOLAK |  | R7 MDO LOL HEM PENGADILAN AGAMA LOLAK |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.670/LG.310/DR7-12700000/2021 | 2022-02-04 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 2718345 | 325629 | 3043974 | 3043974 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 19 | 01E07V06 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | MANADO |  | R7 MDO MDO HEM PT PEGADAIAN GALERI DUA EMPAT |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.674/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 3983832 | 919219 | 4903051 | 4903051 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 20 | 01E07V06 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | MANADO |  | R7 MDO MDO HEM PD PASAR MANADO |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.671/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 3046358 | 757481 | 3803839 | 3803839 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 21 | 01E07V06 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | MANADO |  | R7 MDO MDO HEM PT GEOPERSADA MULIA ABADI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.675/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 2776420 | 536346 | 3312766 | 3312766 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 18 | 01E07V06 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | MANADO |  | R7 MDO MDO HEM PANASONIC GOBEL GROUP |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.672/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 3066920 | 762812 | 3829732 | 3829732 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 22 | 01E07V06 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | MANADO |  | R7 MDO MDO HEM PT-INDOFARMA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.673/LG.310/DR7-12700000/2021 | 2022-02-14 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 28471289 | 5945447 | 34416736 | 34416736 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 27 | 01E07V06 | 007 | 72010077 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | MOLIBAGU |  | R7 MDO MOL HEM BKPSDM KAB BOLSEL |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.678/LG.310/DR7-12700000/2021 | 2022-02-15 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 8829650 | 1821649 | 10651299 | 10651299 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 29 | 01E07V06 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | PANIKI |  | R7 MDO PIK HEM BTKLPP PROVINSI SULUT |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-15 | 2022-01-01 | TEL.679/LG.310/DR7-12700000/2021 | 2022-02-15 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 12309580 | 2513865 | 14823445 | 14823445 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 31 | 01E07V06 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | TAHUNA |  | R7 MDO THN HEM HOTEL DIALOGH TAHUNA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.681/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 29380850 | 6061141 | 35441991 | 35441991 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 30 | 01E07V06 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | TAHUNA |  | R7 MDO THN HEM BAPELITBANG SANGIHE |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.680/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 2349003 | 366917 | 2715920 | 2715920 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 33 | 01E07V06 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | TOMOHON |  | R7 MDO TMH HEM RUMAH SAKIT ANUGRAH |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.682/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 115473808 | 20472461 | 135946269 | 135946269 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 32 | 01E07V06 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | TOMOHON |  | R7 MDO TMH HEM DISKOMINFO KOTA TOMOHON |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.683/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 6082427 | 1690859 | 7773286 | 7773286 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 34 | 01E07V06 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | TONDANO |  | R7 MDO TDN HEM PEMKAB MINAHASA (KANTOR KPU) |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.684/LG.310/DR7-12700000/2021 | 2022-02-04 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 17157978 | 3882199 | 21040177 | 21040177 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021416 | 1 | 35 | 01E07V06 | 007 | 72010283 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011065/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 23 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-02-26 | HEM | MANADO | TUTUYAN |  | R7 MDO TUT HEM RS RATATOTOK |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-26 | 2022-01-01 | TEL.685/LG.310/DR7-12700000/2021 | 2022-02-04 | TEL.0030/LG.320/DR7-10400000/2022 | 2022-02-15 | 11458980 | 2195149 | 13654129 | 13654129 | 4500447426 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021417 | 1 | 12 | 01E07V06 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011067/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE B 3 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-03-28 | FIMO NODE-B 2021 | MANADO | BEO |  | MGN044 - R7 MDO BEO MGN044 MELONGUANE TIMUR |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.686/LG.310/DR7-12700000/2021 | 2022-01-26 | TEL.0031/LG.320/DR7-10400000/2022 | 2022-02-03 | 49729354 | 10989743 | 60719097 | 60719097 | 4500447429 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021417 | 1 | 11 | 01E07V06 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011067/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE B 3 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-03-28 | FIMO NODE-B 2021 | MANADO | BITUNG |  | TDO292 - R7 MDO BIT TDO292 KAMP.RINONDORAN |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-14 | 2022-01-01 | TEL.687/LG.310/DR7-12700000/2021 | 2022-01-27 | TEL.0031/LG.320/DR7-10400000/2022 | 2022-02-03 | 24534424 | 5208616 | 29743040 | 29743040 | 4500447429 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021417 | 1 | 10 | 01E07V06 | 007 | 72010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011067/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan FIMO NODE B 3 LOP Area Witel Sulut Malut | 2021-12-29 | 2022-03-28 | FIMO NODE-B 2021 | MANADO | LOLAK |  | KTG272 - R7 MDO LOL KTG272 TADOY |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-14 | 2022-01-01 | TEL.688/LG.310/DR7-12700000/2021 | 2022-02-03 | TEL.0031/LG.320/DR7-10400000/2022 | 2022-02-03 | 331998121 | 86175884 | 418174005 | 418174005 | 4500447429 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-03-10
G2021418 | 2 | 10 | 01E07V06 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011072/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 1 LOP Area Witel Maluku | 2021-12-29 | 2022-03-28 | HEM | AMBON | DOBO |  | R7 AMB DOB HEM DURJELA DOBO |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-03-28 | 2022-01-01 | TEL.767/LG.310/DR7-12700000/2022 | 2022-03-25 | TEL.0042/LG.320/DR7-10400000/2022 | 2022-03-25 | 585243473 | 111214135 | 696457608 | 696457608 | 4500447431 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-04-09
G2021419 | 1 | 10 | 01E07V06 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011075/HK.810/DR7-10400000/2021 | Pengadaan Pekerjaan HEM EGBIS 1 LOP Area Witel Papua Barat | 2021-12-29 | 2022-02-11 | HEM | BIAK | BIAK |  | R7 SON BIA HEM Cogindo Nabire |  | 50 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.004/LG.310/DR7-12700000/2022 | 2022-01-12 | TEL.0005/LG.320/DR7-10400000/2022 | 2022-01-12 | 61755407 | 18668887 | 80424294 | 80424294 | 4500447434 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-01-27
G2021420 | 1 | 12 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011079/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 3 LoP Area Witel Makassar | 2021-12-29 | 2022-01-27 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM PEMKOT WALIKOTA |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-16 | 2022-01-03 | TEL.689/LG.310/DR7-12700000/2022 | 2022-02-02 | TEL.0032/LG.320/DR7-10400000/2022 | 2022-03-02 | 5067651 | 1161675 | 6229326 | 6229326 | 4500447440 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-03-10
G2021420 | 1 | 11 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011079/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 3 LoP Area Witel Makassar | 2021-12-29 | 2022-01-27 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM TVRI SULAWESI SELATAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-18 | 2022-01-03 | TEL.691/LG.310/DR7-12700000/2022 | 2022-03-02 | TEL.0032/LG.320/DR7-10400000/2022 | 2022-03-02 | 14266408 | 3360801 | 17627209 | 17627209 | 4500447440 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-03-10
G2021420 | 1 | 10 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011079/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 3 LoP Area Witel Makassar | 2021-12-29 | 2022-01-27 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM TVRI SULSEL |  | 100 | 100 | 100 | BAST-1 | 2022-01-03 | 2022-01-18 | 2022-01-03 | TEL.690/LG.310/DR7-12700000/2022 | 2022-02-02 | TEL.0032/LG.320/DR7-10400000/2022 | 2022-03-02 | 8341655 | 1851789 | 10193444 | 10193444 | 4500447440 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-03-10
G2021421 | 1 | 27 | 01E07V06 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | BAU-BAU |  | INSTALASI ACCES POINT NOVEMBER 2021 STO BAU-BAU |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.576/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 1692864 | 778266 | 2471130 | 2471130 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 32 | 01E07V06 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | BAU-BAU |  | INSTALASI ACCES POINT OKTOBER 2021 STO BAU-BAU |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.577/LG.310/DR7-12700000/2022BAU-BAU | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 33 | 01E07V06 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | KENDARI |  | INSTALASI ACCES POINT OKTOBER 2021 STO KENDARI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.579/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 28 | 01E07V06 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | KENDARI |  | INSTALASI ACCES POINT NOVEMBER 2021 STO KENDARI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.578/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 29 | 01E07V06 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | KOLAKA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO KOLAKA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.580/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 34 | 01E07V06 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | KOLAKA |  | INSTALASI ACCES POINT OKTOBER 2021 STO KOLAKA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.581/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 31 | 01E07V06 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | LASUSUA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO LASUSUA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.582/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 1128576 | 518844 | 1647420 | 1647420 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 35 | 01E07V06 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | MANDONGA |  | INSTALASI ACCES POINT OKTOBER 2021 STO MANDONGA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.584/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 30 | 01E07V06 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | KENDARI | MANDONGA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO MANDONGA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-13 | 2021-12-29 | TEL.583/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 10 | 01E07V06 | 007 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PALU | LUWUK |  | INSTALASI ACCES POINT OKTOBER 2021 STO LUWUK |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-05 | 2021-12-29 | TEL.572/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 1128576 | 518844 | 1647420 | 1647420 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 11 | 01E07V06 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PALU | PALU A |  | INSTALASI ACCES POINT OKTOBER 2021 STO PALU A |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-05 | 2021-12-29 | TEL.573/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 12 | 01E07V06 | 007 | 72030092 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PALU | PALU B |  | INSTALASI ACCES POINT OKTOBER 2021 STO PALU B |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-04 | 2021-12-29 | TEL.574/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 13 | 01E07V06 | 007 | 72030101 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PALU | POSO |  | INSTALASI ACCES POINT OKTOBER 2021 STO POSO |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-05 | 2021-12-29 | TEL.575/LG.310/DR7-12700000/2022 | 2022-01-22 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 22 | 01E07V06 | 007 | 72040193 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PARE-PARE | BARRU |  | INSTALASI ACCES POINT NOVEMBER 2021 STO BARRU |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-07 | 2021-12-29 | TEL.566/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 23 | 01E07V06 | 007 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PARE-PARE | MAJENE |  | INSTALASI ACCES POINT NOVEMBER 2021 STO MAJENE |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-07 | 2021-12-29 | TEL.567/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 1128576 | 518844 | 1647420 | 1647420 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 24 | 01E07V06 | 007 | 72040086 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PARE-PARE | MAMASA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO MAMASA |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-07 | 2021-12-29 | TEL.568/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 1128576 | 518844 | 1647420 | 1647420 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 25 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PARE-PARE | MAMUJU |  | INSTALASI ACCES POINT NOVEMBER 2021 STO MAMUJU |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-07 | 2021-12-29 | TEL.569/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 564288 | 259422 | 823710 | 823710 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 26 | 01E07V06 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | PARE-PARE | PINRANG |  | INSTALASI ACCES POINT NOVEMBER 2021 STO PINRANG |  | 100 | 100 | 100 | BAST-1 | 2022-01-01 | 2022-01-07 | 2021-12-29 | TEL.570/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 14 | 01E07V06 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | ANTANG |  | INSTALASI ACCES POINT NOVEMBER 2021 STO ANTANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.585/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2257152 | 1037688 | 3294840 | 3294840 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 19 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | BALAIKOTA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO BALAIKOTA |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.586/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 5642880 | 2594220 | 8237100 | 8237100 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 21 | 01E07V06 | 007 | 72080080 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | MAROS |  | INSTALASI ACCES POINT NOVEMBER 2021 STO MAROS |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.587/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 18 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | MATTOANGIN |  | INSTALASI ACCES POINT NOVEMBER 2021 STO MATTOANGIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.588/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 4514304 | 2075376 | 6589680 | 6589680 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 17 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | PANAKUKANG |  | INSTALASI ACCES POINT NOVEMBER 2021 STO PANAKUKANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.589/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 7335744 | 3372486 | 10708230 | 10708230 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 16 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | SUDIANG |  | INSTALASI ACCES POINT NOVEMBER 2021 STO SUDIANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.590/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 2821440 | 1297110 | 4118550 | 4118550 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 20 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | SUNGGUMINASA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO SUGGUMINASA |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.591/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 3950016 | 1815954 | 5765970 | 5765970 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021421 | 1 | 15 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011086/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan Access Point (AP) Wifi Consumer Area Witel Sulteng, Makassar, Sultra dan Sulselbar | 2021-12-29 | 2022-02-11 | AP WIFI | UJUNGPANDANG | TAMALANREA |  | INSTALASI ACCES POINT NOVEMBER 2021 STO TAMALANREA |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-01-10 | 2021-12-29 | TEL.592/LG.310/DR7-12700000/2022 | 2022-01-21 | TEL.0024/LG.320/DR7-10400000/2022 | 2022-01-22 | 3385728 | 1556532 | 4942260 | 4942260 | 4500447449 |  |  |  |  | TELKOM AKSES | 2022-03-04
G2021422 | 1 | 20 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM PT.CENTREPARK CITRA CORPORA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.626/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 7425984 | 2100480 | 9526464 | 9526464 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 10 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM POLRES MAKASSAR |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.622/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 7921502 | 1931622 | 9853124 | 9853124 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 7 | 01E07V06 | 007 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | BANTAENG |  | R7 MKS BTN HEM PT HUADI NICKEL ALLOY INDONESIA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.616/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 53739797 | 11957367 | 65697164 | 65697164 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 11 | 01E07V06 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK HEM POLRES BULUKUMBA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.623/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 45465408 | 12621653 | 58087061 | 58087061 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 8 | 01E07V06 | 007 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | KIMA |  | R7 MKS KIM HEM PT MASSINDO SOLARIS NUSANTARA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.617/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 18766343 | 5498820 | 24265163 | 24265163 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 22 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM BPSDM KAMPUS |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.629/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 19088082 | 4371808 | 23459890 | 23459890 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 13 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM MACCINI SOMBALA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.628/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 1715991 | 239588 | 1955579 | 1955579 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 6 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK HEM KODAM XIV HASANUDDIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.615/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 80494625 | 22211001 | 102705626 | 102705626 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 23 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK HEM RS PRIMAYA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.624/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 18313642 | 4556907 | 22870549 | 22870549 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 21 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK HEM BARANA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.627/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 1715991 | 239588 | 1955579 | 1955579 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 17 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM DINAS KESEHATAN GOWA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.620/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 2648074 | 294932 | 2943006 | 2943006 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 19 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM BBWS JENEBERANG |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.619/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 6655588 | 1894529 | 8550117 | 8550117 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 18 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM POLRES GOWA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.621/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 9934806 | 2598543 | 12533349 | 12533349 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 9 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM SUMBER ALFARIA TRIJAYA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.618/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 8838344 | 2731968 | 11570312 | 11570312 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021422 | 1 | 12 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011090/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 15 LoP Area Witel Makassar | 2021-12-29 | 2022-02-11 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM PESANTREN AL IKHLAS BONE |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-10 | 2022-01-01 | TEL.625/LG.310/DR7-12700000/2022 | 2022-02-04 | TEL.0025/LG.320/DR7-10400000/2022 | 2022-02-04 | 17316060 | 3425493 | 20741553 | 20741553 | 4500447455 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-03-04
G2021423 | 1 | 6 | 01E07V06 | 007 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011092/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 2 LoP Area Witel Makassar | 2021-12-29 | 2022-01-27 | HEM | UJUNGPANDANG | SINJAI |  | R7 MKS SIN HEM BNI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-06 | 2022-01-12 | TEL.019/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0008/LG.320/DR7-10400000/2022 | 2022-01-15 | 12375831 | 3677609 | 16053440 | 16053440 | 4500447457 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-28
G2021423 | 1 | 7 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011092/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM 2 LoP Area Witel Makassar | 2021-12-29 | 2022-01-27 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM SMP 9 |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-01-08 | 2022-01-12 | TEL.020/LG.310/DR7-12700000/2022 | 2022-01-15 | TEL.0008/LG.320/DR7-10400000/2022 | 2022-01-15 | 27836686 | 5726957 | 33563643 | 33563643 | 4500447457 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-01-28
G2021424 | 1 | 29 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | MESJID ULIL ALBAB UNM |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.41/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 830000 | 830000 | 830000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 28 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | FIP (F. ILMU PENDIDIKAN) |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.40/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 830000 | 830000 | 830000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 27 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | F.TEKNIK |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.39/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 51460000 | 51460000 | 51460000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 26 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | F.SENI dan DESAIN |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.38/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 14110000 | 14110000 | 14110000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 25 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | F.MIPA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.37/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 49800000 | 49800000 | 49800000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 24 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | MATTOANGIN |  | F.BAHASA dan SASTRA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.36/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 24070000 | 24070000 | 24070000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 15 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | GEDUNG AMANAGAPPA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.47/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 3320000 | 3320000 | 3320000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 14 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | FIP (F. ILMU PENDIDIKAN) |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.46/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 39010000 | 39010000 | 39010000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 13 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | F.PSIKOLOGI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.45/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 19920000 | 19920000 | 19920000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 12 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | F.ILMU SOSIAL |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.44/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 38180000 | 38180000 | 38180000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 11 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | F. OLAHRAGA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.43/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 29880000 | 29880000 | 29880000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 10 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | BAHASA ARAB |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.42/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 3320000 | 3320000 | 3320000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 20 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | F.EKONOMI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.52/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 38180000 | 38180000 | 38180000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 19 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | PINISI |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.51/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 47310000 | 47310000 | 47310000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 18 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | PERPUSTAKAAN |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.50/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 4980000 | 4980000 | 4980000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 17 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | PASCASARJANA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.49/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 24900000 | 24900000 | 24900000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 16 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | PANAKUKANG |  | GEDUNG PKM |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.48/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 2490000 | 2490000 | 2490000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 23 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | PGSD |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.55/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 11620000 | 11620000 | 11620000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 21 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | LAB |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.53/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 1660000 | 1660000 | 1660000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021424 | 1 | 22 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011094/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan PSB WIFI PT-I EGBIS UNM Area Witel Makassar | 2021-12-29 | 2022-02-11 | PSB WIFI 2021 | UJUNGPANDANG | WATAMPONE |  | PASCASARJANA |  | 100 | 100 | 100 | BAST-1 | 2021-12-29 | 2022-02-11 | 2022-01-01 | TEL.54/LG.310/DR7-12700000/2022 | 2022-02-05 | TEL.0019/LG.320/DR7-10400000/2022 | 2022-02-05 | 0 | 3320000 | 3320000 | 3320000 | 4500447460 |  |  |  |  | SIPAKALEBBI 2 | 2022-02-18
G2021425 | 3 | 11 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011140/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP-FO FTTH Batch-3 3 LoP Area Witel Makassar | 2021-12-30 | 2022-02-27 | FTTH BATCH-3 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT3 CENDRAWASIH (2) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-13 | 2021-12-30 | TEL.721/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0037/LG.320/DR7-10400000/2022 | 2022-03-04 | 26733446 | 7875754 | 34609200 | 34609200 | 4500447549 |  |  |  |  | TELKOM AKSES | 2022-03-18
G2021425 | 3 | 10 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011140/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP-FO FTTH Batch-3 3 LoP Area Witel Makassar | 2021-12-30 | 2022-02-27 | FTTH BATCH-3 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT3 CENDRAWASIH (1) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-13 | 2021-12-30 | TEL.720/LG.310/DR7-12700000/2022 | 2022-03-04 | TEL.0033/LG.320/DR7-10400000/2022 | 2022-03-04 | 127189922 | 29242646 | 156432568 | 156432568 | 4500447549 |  |  |  |  | TELKOM AKSES | 2022-03-11
G2021425 | 3 | 12 | 01E07V01 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011140/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan OSP-FO FTTH Batch-3 3 LoP Area Witel Makassar | 2021-12-30 | 2022-02-27 | FTTH BATCH-3 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT3 CENDRAWASIH (3) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-15 | 2021-12-30 | TEL.722/LG.310/DR7-12700000/2022 | 2022-02-17 | TEL.0033/LG.320/DR7-10400000/2022 | 2022-03-04 | 27548068 | 8281109 | 35829177 | 35829177 | 4500447549 |  |  |  |  | TELKOM AKSES | 2022-03-11
G2021426 | 1 | 10 | 01E07V06 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | ANTANG |  | R7 MKS ANT HEM KOLAM NIPA-NIPA (GOWA) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0593/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 18569981 | 5784973 | 24354954 | 24354954 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 30 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM POLDA SULSEL (MONUMEN MANDALA) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0613/LG.310/DR7-12700000/2022 | 2022-01-28 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 13089632 | 3434892 | 16524524 | 16524524 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 11 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM Kanwil DJBC Sulawesi Bagian Selatan |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0594/LG.310/DR7-12700000/2022 | 2022-01-28 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 4376641 | 1304835 | 5681476 | 5681476 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 15 | 01E07V06 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM HOTEL ALMADERA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0598/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 2611983 | 709153 | 3321136 | 3321136 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 13 | 01E07V06 | 007 | 72080009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | BANTAENG |  | R7 MKS BTN HEM KPPN BANTAENG |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0596/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 10964924 | 3370866 | 14335790 | 14335790 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 31 | 01E07V06 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK HEM SMAN 2 BULUKUMBA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0614/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 10725493 | 2262174 | 12987667 | 12987667 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 27 | 01E07V06 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK HEM BPR HASAMITRA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0610/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 10271433 | 3289664 | 13561097 | 13561097 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 18 | 01E07V06 | 007 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | KIMA |  | R7 MKS KIM HEM PT. BUNGASARI PARANGLOE |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0601/LG.310/DR7-12700000/2022 | 2022-01-28 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 13252534 | 11581931 | 24834465 | 24834465 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 22 | 01E07V06 | 007 | 72080064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | KIMA |  | R7 MKS KIM HEM JARUM (DSO MAKASSAR) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0605/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 13873226 | 4093504 | 17966730 | 17966730 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 26 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM KEMENKUMHAM |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0609/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 11928514 | 4105550 | 16034064 | 16034064 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 28 | 01E07V06 | 007 | 72080164 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM WIJAYA KARYA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0611/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 14995898 | 3050453 | 18046351 | 18046351 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 20 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK HEM PT. SOLID GOLD |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0603/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 20475730 | 6116773 | 26592503 | 26592503 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 29 | 01E07V06 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK HEM UNIVERSITAS PATRIA ARTHA |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0612/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 33837391 | 10261691 | 44099082 | 44099082 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 19 | 01E07V06 | 007 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | PANGKEP |  | R7 MKS PKN HEM BLK PANGKEP |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0602/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 7922174 | 2326113 | 10248287 | 10248287 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 24 | 01E07V06 | 007 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | PANGKEP |  | R7 MKS PKN HEM POLRES PANGKEP (PANJI PERKASA INDONESIA) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0607/LG.310/DR7-12700000/2022 | 2022-01-28 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 16126576 | 5011183 | 21137759 | 21137759 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 21 | 01E07V06 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD HEM DINAS PERHUBUNGAN |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0604/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 18254147 | 4793695 | 23047842 | 23047842 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 23 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM PEMKOT MAKASSAR (SATKER_BBWS_SA) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0606/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 19588008 | 6340768 | 25928776 | 25928776 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 12 | 01E07V06 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA HEM PPSDM |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0595/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 7757996 | 2474027 | 10232023 | 10232023 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 17 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM PESANTREN AL-IKHLAS BONE |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0600/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 15669828 | 4606580 | 20276408 | 20276408 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 16 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM YAKULT-2021242469 BONE |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0599/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 16688152 | 4926274 | 21614426 | 21614426 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 14 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM KPPN WATAMPONE |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0597/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 17197314 | 5086121 | 22283435 | 22283435 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
G2021426 | 1 | 25 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.011149/HK.810/DR7-10400000/2021 | Pengadaan dan Pemasangan Pekerjaan HEM Egbis Periode Agustus dan November Tahun 2021 Area Witel Makassar | 2021-12-30 | 2022-01-28 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM POLRES BONE (PANJI PERKASA INDONESIA) |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-01-28 | 2022-01-01 | TEL.0608/LG.310/DR7-12700000/2022 | 2022-01-27 | TEL.0020/LG.320/DR7-10400000/2022 | 2022-01-28 | 35411969 | 10369773 | 45781742 | 45781742 | 4500447563 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-02-18
12021479 | 1 | 19 | 01C11H01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011168/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan 2nd Platform ISP SKKL Repeaterless Sistem - Paket-1 | 2021-12-30 | 2022-11-23 | ISP SKKL | PALU | DONGGALA |  |  |  | 100 | 15 | 0 | Preparing | 2022-01-23 | 2022-06-28 | 2022-01-17 |  |  |  |  | 3123505400 | 312350500 | 3435855900 | 0 | 4500447522 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021479 | 1 | 20 | 01C11H01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011168/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan 2nd Platform ISP SKKL Repeaterless Sistem - Paket-1 | 2021-12-30 | 2022-11-23 | ISP SKKL | PALU | PALU |  |  |  | 100 | 15 | 0 | Preparing | 2022-01-23 | 2022-06-28 | 2022-01-17 |  |  |  |  | 919959500 | 91995900 | 1011955400 | 0 | 4500447522 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021479 | 1 | 28 | 01C11H01 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011168/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan 2nd Platform ISP SKKL Repeaterless Sistem - Paket-1 | 2021-12-30 | 2022-11-23 | ISP SKKL | UJUNGPANDANG | MAKASAR |  |  |  | 90 |  |  |  | 2022-01-23 | 2022-11-24 | [5 empty] | 842030000 | 84203000 | 926233000 | 0 | 4500447522 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA
12021481 | 4 | 99 | 01C11I01 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011189/HK.810/OPS-10050000/2021 | Pengadaan dan Pemasangan Perangkat GPON-XGPON-XGSPON Platform Nokia | 2021-12-30 | 2022-07-31 | GPON-XGPON-XGSPON | UJUNGPANDANG | ANTANG |  | STO ANTANG REKON 1 |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-06-11 | 2022-05-17 | TEL.0514/LG.310/DID-C0200000/2022 | 2022-05-28 23:27 | TEL.0656/LG.320/DID-A0000000/2022 | 2022-05-28 | 129414874 | 2244533 | 131659407 | 131659407 | 4500446470 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-05-30
12021481 | 4 | 100 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011189/HK.810/OPS-10050000/2021 | Pengadaan dan Pemasangan Perangkat GPON-XGPON-XGSPON Platform Nokia | 2021-12-30 | 2022-07-31 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | STO BULUKUMBA REKON 1 |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-06-11 | 2022-05-19 | TEL.0514/LG.310/DID-C0200000/2022 | 2022-05-28 23:27 | TEL.0656/LG.320/DID-A0000000/2022 | 2022-05-28 | 86547360 | 1869551 | 88416911 | 88416911 | 4500446470 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-05-30
12021481 | 4 | 101 | 01C11I01 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011189/HK.810/OPS-10050000/2021 | Pengadaan dan Pemasangan Perangkat GPON-XGPON-XGSPON Platform Nokia | 2021-12-30 | 2022-07-31 | GPON-XGPON-XGSPON | UJUNGPANDANG | PANGKEP |  | STO PANGKEP REKON 1 |  | 100 | 100 | 100 | BAST-1 | 2021-12-31 | 2022-06-11 | 2022-05-27 | TEL.0514/LG.310/DID-C0200000/2022 | 2022-05-28 23:27 | TEL.0656/LG.320/DID-A0000000/2022 | 2022-05-28 | 86547360 | 1869551 | 88416911 | 88416911 | 4500446470 |  |  |  |  | LINTAS TEKNOLOGI INDONESIA | 2022-05-30
12021483 | 5 | 20 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | AMBON | AMBON |  | ME2-D7-AMB |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-04-28 | 2022-03-01 | TEL.554/LG.310/DID-B0300000/2022 | 2022-04-28 | TEL.0663/LG.320/DID-A0000000/2022 | 2022-04-28 | 283885800 | 52705000 | 336590800 | 336590800 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-05-31
12021483 | 5 | 44 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | JAYAPURA | JAYAPURA |  | ME3-D7-JAP |  | 90 | 20 | 0 | Preparing | 2021-12-30 | 2022-08-20 | 2022-03-01 |  |  |  |  | 228475800 | 48274000 | 276749800 | 0 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT
12021483 | 5 | 45 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | JAYAPURA | JAYAPURA |  | ME-D7-JAP |  | 90 | 20 | 0 | Preparing | 2021-12-30 | 2022-08-20 | 2022-03-01 |  |  |  |  | 228475800 | 48274000 | 276749800 | 0 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT
12021483 | 5 | 28 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | JAYAPURA | TIMIKA |  | ME9-D7-TMK |  | 100 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-04-28 | 2022-03-01 | TEL.554/LG.310/DID-B0300000/2022 | 2022-04-28 | TEL.0663/LG.320/DID-A0000000/2022 | 2022-04-28 | 195229800 | 45615400 | 240845200 | 240845200 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-05-31
12021483 | 5 | 63 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | PALU | PALU |  | ME-D7-PAL |  | 90 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-08-20 | 2022-03-01 | TEL.1197/LG.310/DID-B0300000/2022 | 2022-07-28 | TEL.1153/LG.320/DID-A0000000/2022 | 2022-07-28 | 254333800 | 50341800 | 304675600 | 304675600 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021483 | 5 | 64 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | PALU | PALU |  | ME-D7-PAL2 |  | 90 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-08-20 | 2022-03-01 | TEL.1197/LG.310/DID-B0300000/2022 | 2022-07-28 | TEL.1153/LG.320/DID-A0000000/2022 | 2022-07-28 | 254333800 | 50341800 | 304675600 | 304675600 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12021483 | 5 | 42 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | SORONG | SORONG |  | ME2-D7-SRG |  | 90 | 20 | 0 | Preparing | 2021-12-30 | 2022-08-20 | 2022-03-01 |  |  |  |  | 228475800 | 48274000 | 276749800 | 0 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT
12021483 | 5 | 43 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | SORONG | SORONG |  | ME-D7-SRG |  | 90 | 20 | 0 | Preparing | 2021-12-30 | 2022-08-20 | 2022-03-01 |  |  |  |  | 228475800 | 48274000 | 276749800 | 0 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT
12021483 | 5 | 41 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.011199/HK.810/OPS-10050000/2021 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2021-12-30 | 2022-08-20 | PCEF | TERNATE | TERNATE |  | ME2-D7-TNT |  | 90 | 100 | 100 | BAST-1 | 2021-12-30 | 2022-08-20 | 2022-03-01 | TEL.973/LG.310/DID-B0300000/2022 | 2022-06-27 | TEL.0872/LG.320/DID-A0000000/2022 | 2022-06-27 | 420011600 | 63594000 | 483605600 | 483605600 | 4500447596 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-29
12022004 | 2 | 21 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000023/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan Perangkat Clocking Synchronization Support Layanan 5G Telkomsel | 2022-01-10 | 2022-08-14 | Clocking Synchronization | JAYAPURA | JAYAPURA |  |  |  | 90 | 80 | 0 | Instalasi | 2022-01-10 | 2022-08-14 | 2022-01-10 |  |  |  |  | 194199629 | 101886924 | 296086553 | 0 | 4500447783 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12022004 | 2 | 22 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000023/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan Perangkat Clocking Synchronization Support Layanan 5G Telkomsel | 2022-01-10 | 2022-08-14 | Clocking Synchronization | SORONG | SORONG |  |  |  | 90 | 80 | 0 | Instalasi | 2022-01-10 | 2022-08-14 | 2022-01-10 |  |  |  |  | 203385829 | 102685724 | 306071553 | 0 | 4500447783 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12022004 | 2 | 19 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000023/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan Perangkat Clocking Synchronization Support Layanan 5G Telkomsel | 2022-01-10 | 2022-08-14 | Clocking Synchronization | UJUNGPANDANG | BALAIKOTA |  |  |  | 90 | 80 | 0 | Instalasi | 2022-01-10 | 2022-08-14 | 2022-01-10 |  |  |  |  | 203385829 | 87185724 | 290571553 | 0 | 4500447783 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12022004 | 2 | 20 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000023/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan Perangkat Clocking Synchronization Support Layanan 5G Telkomsel | 2022-01-10 | 2022-08-14 | Clocking Synchronization | UJUNGPANDANG | PETTARANI |  |  |  | 90 | 80 | 0 | Instalasi | 2022-01-10 | 2022-08-14 | 2022-01-10 |  |  |  |  | 194199629 | 86386924 | 280586553 | 0 | 4500447783 |  |  |  |  | INFRASTRUKTUR TELEKOMUNIKASI INDONESIA
12022016 | 8 | 966 | 01C11I05 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | AMBON |  |  |  | 100 |  |  |  | 2022-01-20 | 2022-05-19 | [5 empty] | 0 | 323950000 | 323950000 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 684 | 01C11I05 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | MALUKU |  | 84-97601 Jln. Telaver Langgur Kec. Kei Kecil |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 666 | 01C11I05 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | MALUKU |  | 84-97601 Jln. Telaver Langgur Kec. Kei Kecil |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0486/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0716/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 18618000 | 18618000 | 18618000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 414 | 01C11I05 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | MALUKU |  | 84-97601 Jln. Telaver Langgur Kec. Kei Kecil |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 7986263 | 7986263 | 7986263 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 685 | 01C11I05 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | MALUKU |  | 84-97402 Jl.Bhineka No. 5 Saumlaki |  | 100 |  |  |  | 2022-01-20 | 2022-06-19 | [5 empty] | 0 | 1001882 | 1001882 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 962 | 01C11I05 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | MALUKU |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-23 | TEL.0571/LG.310/DID-C0200000/2022 | 2022-05-30 20:34 | TEL.0735/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 8260396 | 8260396 | 8260396 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1003 | 01C11I05 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | AMBON | MALUKU |  | 84-97601 Jln. Telaver Langgur Kec. Kei Kecil |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 899000 | 899000 | 899000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 952 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0571/LG.310/DID-C0200000/2022 | 2022-05-30 20:34 | TEL.0735/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 15811258 | 15811258 | 15811258 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 126 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  | 74-96210 Jalan Trans Sulawesi, Kelurahan Libuo, Kecamatan Paguat, Kabupaten Pohuwato, Provinsi Gorontalo |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 166 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  | 74-96210 Jalan Trans Sulawesi, Kelurahan Libuo, Kecamatan Paguat, Kabupaten Pohuwato, Provinsi Gorontalo |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 6167574 | 6963184 | 13130758 | 13130758 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 392 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  | 74-96210 Jalan Trans Sulawesi, Kelurahan Libuo, Kecamatan Paguat, Kabupaten Pohuwato, Provinsi Gorontalo |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8261647 | 8261647 | 8261647 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 997 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  | 74-96210 Jalan Trans Sulawesi, Kelurahan Libuo, Kecamatan Paguat, Kabupaten Pohuwato, Provinsi Goron |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 930000 | 930000 | 930000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 636 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  | 74-96210 Jalan Trans Sulawesi, Kelurahan Libuo, Kecamatan Paguat, Kabupaten Pohuwato, Provinsi Gorontalo |  | 100 |  |  |  | 2022-01-20 | 2022-05-19 | [5 empty] | 0 | 11556000 | 11556000 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 628 | 01C11I05 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | GORONTALO | GORONTALO |  | 74-96210 Jalan Trans Sulawesi, Kelurahan Libuo, Kecamatan Paguat, Kabupaten Pohuwato, Provinsi Gorontalo |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1012 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 83-99101 Jl. Raya Sentani Kecamatan Abepura |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 976500 | 976500 | 976500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 679 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99902 Jl. Cendrawasih SP 2 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 20223000 | 20223000 | 20223000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 632 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99902 Jl. Cendrawasih SP 2 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8674731 | 8674731 | 8674731 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 631 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99102 Jl. Dr. Sam Ratulangi Apo Jayapura Papua |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 10273844 | 10273844 | 10273844 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 449 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 83-99101 Jl. Raya Sentani Kecamatan Abepura |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 13472070 | 13472070 | 13472070 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 142 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99303 JL. RAYA DOYO BARU RT.004 RW.004 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 144 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99102 Jl. Dr. Sam Ratulangi Apo Jayapura Papua |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 143 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99902 Jl. Cendrawasih SP 2 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 200 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 83-99101 Jl. Raya Sentani Kecamatan Abepura |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 17451478 | 11459736 | 28911214 | 28911214 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 199 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99102 Jl. Dr. Sam Ratulangi Apo Jayapura Papua |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 12895598 | 10210954 | 23106552 | 23106552 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 796 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 83-99101 Jl. Raya Sentani Kecamatan Abepura |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0241/LG.320/DID-A0000000/2022 | 2022-02-28 | 4409910 | 23642874 | 28052784 | 28052784 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 730 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 83-99101 Jl. Raya Sentani Kecamatan Abepura |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 729 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99102 Jl. Dr. Sam Ratulangi Apo Jayapura Papua |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 728 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99902 Jl. Cendrawasih SP 2 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1013 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99904 Jl. Pendidikan Kel. Koperapoka |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 976500 | 976500 | 976500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1010 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99902 Jl. Cendrawasih SP 2 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 976500 | 976500 | 976500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 633 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99904 Wonosari Jaya, jl Poros makpur jaya, kilometer 8 |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 7075618 | 7075618 | 7075618 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 727 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99303 JL. RAYA DOYO BARU RT.004 RW.004 |  | 100 |  | 0 |  | 2022-01-20 | 2022-06-19 | [5 empty] | 0 | 1001882 | 1001882 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 967 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  |  |  | 100 |  | 0 |  | 2022-01-20 | 2022-05-19 | [5 empty] | 0 | 688656825 | 688656825 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 681 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 83-99101 Jl. Raya Sentani Kecamatan Abepura |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 20223000 | 20223000 | 20223000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 680 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99102 Jl. Dr. Sam Ratulangi Apo Jayapura Papua |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 20223000 | 20223000 | 20223000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 1011 | 01C11I05 | 019 | 74030164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | JAYAPURA | PAPUA |  | 84-99102 Jl. Dr. Sam Ratulangi Apo Jayapura Papua |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 976500 | 976500 | 976500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 1009 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95901 Jalan Raya Sonder Kab Minahasa |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 930000 | 930000 | 930000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 668 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95310 JL. RAYA TOMOHON, MATANI SATU |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 19260000 | 19260000 | 19260000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 1006 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 73-95107 JL. YOS SUDARSO NO.28, KAIRAGI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 930000 | 930000 | 930000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 1005 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 930000 | 930000 | 930000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 1004 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95310 JL. RAYA TOMOHON, MATANI SATU |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 930000 | 930000 | 930000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 433 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95901 Jl. Amurang Ratahan Tombatu Minahasa Tenggara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 5215719 | 5215719 | 5215719 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 432 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95110 Jl. Raya Manado- Tomohon Winangun atas |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 5215719 | 5215719 | 5215719 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 963 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-29 | TEL.0571/LG.310/DID-C0200000/2022 | 2022-05-30 20:34 | TEL.0735/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 40649455 | 40649455 | 40649455 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 120 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 119 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95310 JL. RAYA TOMOHON, MATANI SATU |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 118 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 73-95107 JL. YOS SUDARSO NO.28, KAIRAGI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 180 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 73-95107 JL. YOS SUDARSO NO.28, KAIRAGI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 11834950 | 10528751 | 22363701 | 22363701 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 179 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 10179833 | 9179670 | 19359503 | 19359503 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 177 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95310 JL. RAYA TOMOHON, MATANI SATU |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 12893695 | 9626683 | 22520378 | 22520378 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 794 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-15 | TEL.0266/LG.310/DID-C0200000/2022 | 2022-03-28 20:19 | TEL.0329/LG.320/DID-A0000000/2022 | 2022-03-28 | 4860904 | 20750722 | 25611626 | 25611626 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 705 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 84-97707 Jl.Pelabuhan Labuha Halsel |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 704 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95605 Borgo, Tombariri, Kabupaten Minahasa, Sulawesi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 703 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 73-95107 JL. YOS SUDARSO NO.28, KAIRAGI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 702 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 697 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95310 JL. RAYA TOMOHON, MATANI SATU |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1008 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 84-97707 Jl.Pelabuhan Labuha Halsel |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 899000 | 899000 | 899000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 431 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 84-97707 Jl.Pelabuhan Labuha Halsel |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 8261647 | 8261647 | 8261647 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 430 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95605 Borgo, Tombariri, Kabupaten Minahasa, Sulawesi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 5215719 | 5215719 | 5215719 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 429 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95310 JL. RAYA TOMOHON, MATANI SATU |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 12830539 | 12830539 | 12830539 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 428 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 5215719 | 5215719 | 5215719 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 421 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 73-95107 JL. YOS SUDARSO NO.28, KAIRAGI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 6738683 | 6738683 | 6738683 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 671 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 84-97707 Jl.Pelabuhan Labuha Halsel |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 11170800 | 11170800 | 11170800 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 670 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 73-95107 JL. YOS SUDARSO NO.28, KAIRAGI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 19260000 | 19260000 | 19260000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 669 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95307 JL. J.W LASUT, DESA SAWANGAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 19260000 | 19260000 | 19260000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 1007 | 01C11I05 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | MANADO | MANADO |  | 74-95605 Borgo, Tombariri, Kabupaten Minahasa, Sulawesi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 634 | 01C11I05 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | PALU |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 21186000 | 21186000 | 21186000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 630 | 01C11I05 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | PALU |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 17655000 | 17655000 | 17655000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 677 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 676 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 6177127 | 6177127 | 6177127 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 128 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 127 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 965 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-29 | TEL.0571/LG.310/DID-C0200000/2022 | 2022-05-30 20:34 | TEL.0735/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 32541589 | 32541589 | 32541589 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 253 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 14994922 | 10857845 | 25852767 | 25852767 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 1022 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 818 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0241/LG.320/DID-A0000000/2022 | 2022-02-28 | 9486565 | 21701193 | 31187758 | 31187758 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 816 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0241/LG.320/DID-A0000000/2022 | 2022-02-28 | 5773571 | 20070034 | 25843605 | 25843605 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 791 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 789 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1023 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 73-94702 Jl. Imam Bonjol Km.2 Desa Bungin Timur Kecamatan Luwuk |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 240 | 01C11I05 | 019 | 72030163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PALU | SULTENG |  | 74-94401 Jl. Parigi Palu Desa Toboli Barat Kecamatan Parigi Utara |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 11216930 | 8115789 | 19332719 | 19332719 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 1038 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1021 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-91907 JL. TRANS SULAWESI KEL. TABULUNG |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-03-25 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1020 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-91304 JL.POROS MAJENE-MAMUJU LINGK.KARANAMO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1019 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-11 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1017 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1016 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1015 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1014 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-92906 JL. POROS MASAMBA TOMONI,URASO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1018 | 01C11I05 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | PARE-PARE | PARE-PARE |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0449/LG.310/DID-C0200000/2022 | 2022-04-27 10:48 | TEL.0551/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 790 | 01C11I05 | 019 | 72080154 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0241/LG.320/DID-A0000000/2022 | 2022-02-28 | 10762299 | 22052717 | 32815016 | 32815016 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 642 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92104 Jl.Mustafa Daeng Bunga |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 24717000 | 24717000 | 24717000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 396 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92103 Jl. A. Mappatangka, Puncak Malino |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 6177127 | 6177127 | 6177127 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 954 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0571/LG.310/DID-C0200000/2022 | 2022-05-30 20:34 | TEL.0735/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 23678214 | 23678214 | 23678214 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 141 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 169 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 16887087 | 13615505 | 30502592 | 30502592 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 639 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 21186000 | 21186000 | 21186000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 665 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92734 Jl. Jend. Ahmad Yani |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-24 | TEL.0504/LG.310/DID-C0200000/2022 | 2022-05-27 15:38 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 664 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92103 Jl. A. Mappatangka, Puncak Malino |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 663 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92104 Jl.Mustafa Daeng Bunga |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0525/LG.310/DID-C0200000/2022 | 2022-05-30 08:56 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 662 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1002 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92734 Jl. Jend. Ahmad Yani |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1001 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92103 Jl. A. Mappatangka, Puncak Malino |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 1000 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-17 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 999 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92104 Jl.Mustafa Daeng Bunga |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0484/LG.310/DID-C0200000/2022 | 2022-05-24 08:53 | TEL.0722/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 852500 | 852500 | 852500 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 403 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92734 Jl. Jend. Ahmad Yani |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 644 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92734 Jl. Jend. Ahmad Yani |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 17655000 | 17655000 | 17655000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 643 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92103 Jl. A. Mappatangka, Puncak Malino |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 21186000 | 21186000 | 21186000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 402 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92117 Jl. Andi Mallombasang, Sungguminasa, Kec. Somba Opu, Kabupaten Gowa, Sulawesi Selatan |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 401 | 01C11I05 | 019 | 72081020 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | MAKASSAR |  | 74-92104 Jl.Mustafa Daeng Bunga |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 10365280 | 10365280 | 10365280 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 187 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 165 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92906 JL. POROS MASAMBA TOMONI,URASO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 215 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-24 | TEL.0258/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0326/LG.320/DID-A0000000/2022 | 2022-03-28 | 18135781 | 17862879 | 35998660 | 35998660 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 213 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0258/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0326/LG.320/DID-A0000000/2022 | 2022-03-28 | 17091451 | 12050969 | 29142420 | 29142420 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 964 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-29 | TEL.0571/LG.310/DID-C0200000/2022 | 2022-05-30 20:34 | TEL.0735/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 42044289 | 42044289 | 42044289 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 191 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 190 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 188 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0233/LG.320/DID-A0000000/2022 | 2022-02-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 214 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 19281655 | 13656095 | 32937750 | 32937750 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 212 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-27 | TEL.0195/LG.310/DID-C0200000/2022 | 2022-02-28 16:04 | TEL.0239/LG.320/DID-A0000000/2022 | 2022-02-28 | 11721381 | 10434245 | 22155626 | 22155626 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-04
12022016 | 8 | 211 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0258/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0326/LG.320/DID-A0000000/2022 | 2022-03-28 | 19766074 | 16008231 | 35774305 | 35774305 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 210 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-24 | TEL.0258/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0326/LG.320/DID-A0000000/2022 | 2022-03-28 | 10562093 | 9759181 | 20321274 | 20321274 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 208 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92906 JL. POROS MASAMBA TOMONI,URASO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-24 | TEL.0258/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0326/LG.320/DID-A0000000/2022 | 2022-03-28 | 15277025 | 11516147 | 26793172 | 26793172 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 802 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-26 | TEL.0266/LG.310/DID-C0200000/2022 | 2022-03-28 20:19 | TEL.0329/LG.320/DID-A0000000/2022 | 2022-03-28 | 10935342 | 21632858 | 32568200 | 32568200 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 800 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-26 | TEL.0266/LG.310/DID-C0200000/2022 | 2022-03-28 20:19 | TEL.0329/LG.320/DID-A0000000/2022 | 2022-03-28 | 3815388 | 18700084 | 22515472 | 22515472 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 799 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-26 | TEL.0266/LG.310/DID-C0200000/2022 | 2022-03-28 20:19 | TEL.0329/LG.320/DID-A0000000/2022 | 2022-03-28 | 9656653 | 21704955 | 31361608 | 31361608 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 661 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 24717000 | 24717000 | 24717000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 659 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0275/LG.310/DID-C0200000/2022 | 2022-03-28 22:19 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 21186000 | 21186000 | 21186000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 658 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 21186000 | 21186000 | 21186000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 656 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-02-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 14124000 | 14124000 | 14124000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 655 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 21186000 | 21186000 | 21186000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 654 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92906 JL. POROS MASAMBA TOMONI,URASO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-26 | TEL.0260/LG.310/DID-C0200000/2022 | 2022-03-28 20:18 | TEL.0333/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 17655000 | 17655000 | 17655000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 757 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91304 JL.POROS MAJENE-MAMUJU LINGK.KARANAMO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-24 | TEL.0504/LG.310/DID-C0200000/2022 | 2022-05-27 15:38 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 756 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 755 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 754 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0525/LG.310/DID-C0200000/2022 | 2022-05-30 08:56 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 753 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0525/LG.310/DID-C0200000/2022 | 2022-05-30 08:56 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 752 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 751 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0525/LG.310/DID-C0200000/2022 | 2022-05-30 08:56 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 749 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92906 JL. POROS MASAMBA TOMONI,URASO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-05-27 | TEL.0517/LG.310/DID-C0200000/2022 | 2022-05-29 11:25 | TEL.0741/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 1001882 | 1001882 | 1001882 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 651 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91304 JL.POROS MAJENE-MAMUJU LINGK.KARANAMO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-06-19 | 2022-04-26 | TEL.0485/LG.310/DID-C0200000/2022 | 2022-05-24 08:54 | TEL.0728/LG.320/DID-A0000000/2022 | 2022-05-24 | 0 | 6177127 | 6177127 | 6177127 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-05-31
12022016 | 8 | 660 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91304 JL.POROS MAJENE-MAMUJU LINGK.KARANAMO |  | 100 |  | 0 |  | 2022-01-20 | 2022-05-19 | [5 empty] | 0 | 14124000 | 14124000 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 798 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91304 JL.POROS MAJENE-MAMUJU LINGK.KARANAMO |  | 100 |  | 0 |  | 2022-01-20 | 2022-05-19 | [5 empty] | 8422067 | 18389247 | 26811314 | 0 | 4500447801 |  |  |  |  | TELKOM AKSES
12022016 | 8 | 348 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91304 JL.POROS MAJENE-MAMUJU LINGK.KARANAMO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-24 | TEL.0452/LG.310/DID-C0200000/2022 | 2022-04-27 10:49 | TEL.0534/LG.320/DID-A0000000/2022 | 2022-04-27 | 3556815 | 6633252 | 10190067 | 10190067 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 804 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-14 | TEL.0448/LG.310/DID-C0200000/2022 | 2022-04-27 10:47 | TEL.0539/LG.320/DID-A0000000/2022 | 2022-04-27 | 10416551 | 22047477 | 32464028 | 32464028 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 803 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-14 | TEL.0448/LG.310/DID-C0200000/2022 | 2022-04-27 10:47 | TEL.0539/LG.320/DID-A0000000/2022 | 2022-04-27 | 15436903 | 22850025 | 38286928 | 38286928 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 801 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-14 | TEL.0448/LG.310/DID-C0200000/2022 | 2022-04-27 10:47 | TEL.0539/LG.320/DID-A0000000/2022 | 2022-04-27 | 7679966 | 20501510 | 28181476 | 28181476 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 657 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-25 | TEL.0446/LG.310/DID-C0200000/2022 | 2022-04-27 10:44 | TEL.0545/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 17655000 | 17655000 | 17655000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 652 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91907 JL. TRANS SULAWESI KEL. TABULUNG |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 4781076 | 4781076 | 4781076 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 650 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92906 JL. POROS MASAMBA TOMONI,URASO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 7573178 | 7573178 | 7573178 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 649 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-92905 DS. BUNGADIDI KEC. TANALILI |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 7573178 | 7573178 | 7573178 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 648 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 647 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91602 JL. AP. PETARRANI, LALEBATA |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 646 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 645 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91214 JL. POROS PINRANG - POLMAN |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 8969229 | 8969229 | 8969229 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 638 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-90801 Cacaleppeng Kel. Jennae Kec. Liliriaja |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-04-26 | TEL.0447/LG.310/DID-C0200000/2022 | 2022-04-27 10:46 | TEL.0557/LG.320/DID-A0000000/2022 | 2022-04-27 | 0 | 10365280 | 10365280 | 10365280 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-04-27
12022016 | 8 | 192 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91219 Jl. Poros Pare-Pare Pinrang - Sawitto |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022016 | 8 | 189 | 01C11I05 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000050/HK.810/OPS-10050000/2022 | Pengadaan dan Pemasangan NTE Support Pelanggan Enterprise | 2022-01-19 | 2022-05-18 | NTE | UJUNGPANDANG | SULSELBAR |  | 74-91802 JL. POROS MAKALE RANTEPAO |  | 100 | 100 | 100 | BAST-1 | 2022-01-20 | 2022-05-19 | 2022-03-25 | TEL.0256/LG.310/DID-C0200000/2022 | 2022-03-28 16:29 | TEL.0324/LG.320/DID-A0000000/2022 | 2022-03-28 | 0 | 2560000 | 2560000 | 2560000 | 4500447801 |  |  |  |  | TELKOM AKSES | 2022-03-30
12022066 | 2 | 23 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.000545/HK.810/OPS-10060000/2022 | Surat Pesanan-4 (SP#4) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2022-03-14 | 2022-06-11 | Jasa Maintenance Support | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-18 | 2022-03-23 | C.TEL175/LG300/DR7-12800000/2022 | 2022-04-13 | TEL.0058/LG.320/COP-F3000000/2022 | 2022-04-13 | 0 | 577724500 | 577724500 | 577724500 | 4500451761 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-04-18
12022066 | 2 | 13 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.000545/HK.810/OPS-10060000/2022 | Surat Pesanan-4 (SP#4) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2022-03-14 | 2022-06-11 | Jasa Maintenance Support | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-03-14 | 2022-03-24 | 2022-03-14 | C.TEL84/LG300/DR7-12800000/2022 | 2022-03-22 | TEL.0041/LG.320/COP-F3000000/2022 | 2022-03-22 | 0 | 1305441000 | 1305441000 | 1305441000 | 4500451761 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-03-24
12022070 | 3 | 50 | 01C11I05 | 019 | 72030012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000580/HK.810/OPS-10050000/2022 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan OSP FO Bungku-Fatufia, RING STO Maba-Weda, Sirkuit Mandalika dan KITB | 2022-03-16 | 2022-08-12 | OSP-FO | PALU | BUNGKU | 2951703#2951708 | SS#1 BB Bungku - Bahodopi (MRW016) |  | 90 | 90 | 0 | Siap UT | 2022-04-16 | 2022-08-26 | 2022-08-01 |  |  |  |  | 4153594914 | 683018035 | 4836612949 | 0 | 4500451941 |  |  |  |  | TELKOM AKSES
12022070 | 3 | 15 | 01C11I05 | 019 | 72030012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000580/HK.810/OPS-10050000/2022 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan OSP FO Bungku-Fatufia, RING STO Maba-Weda, Sirkuit Mandalika dan KITB | 2022-03-16 | 2022-08-12 | OSP-FO | PALU | BUNGKU | 2951703#2951708 | SS#1 BB Bungku - Futufia (MRW046) |  | 86 | 90 | 0 | Siap UT | 2022-03-16 | 2022-08-26 | 2022-08-01 |  |  |  |  | 449067535 | 75517997 | 524585532 | 0 | 4500451941 |  |  |  |  | TELKOM AKSES
12022070 | 3 | 52 | 01C11I05 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000580/HK.810/OPS-10050000/2022 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan OSP FO Bungku-Fatufia, RING STO Maba-Weda, Sirkuit Mandalika dan KITB | 2022-03-16 | 2022-08-12 | OSP-FO | TERNATE | WEDA | 2945001#2945006 | SS-2 Ring Maba - Weda SSU007 menuju SSU005 Prioritas 2 |  | 90 | 50 | 0 | Mat. Delivery | 2022-04-16 | 2022-08-26 | 2022-07-11 |  |  |  |  | 4358274137 | 3729938279 | 8088212416 | 0 | 4500451941 |  |  |  |  | TELKOM AKSES
12022070 | 3 | 53 | 01C11I05 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000580/HK.810/OPS-10050000/2022 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan OSP FO Bungku-Fatufia, RING STO Maba-Weda, Sirkuit Mandalika dan KITB | 2022-03-16 | 2022-08-12 | OSP-FO | TERNATE | WEDA | 2952789#2952794 | SS-2 Ring Maba - Weda SSU005 Menuju HH-41 Prioritas 3 |  | 90 |  | 0 |  | 2022-04-16 | 2022-08-26 | [5 empty] | 1251638402 | 2279061916 | 3530700318 | 0 | 4500451941 |  |  |  |  | TELKOM AKSES
12022070 | 3 | 16 | 01C11I05 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS DATA INVENTORY | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.000580/HK.810/OPS-10050000/2022 | Surat Pesanan-7 (SP#7) Pengadaan dan Pemasangan OSP FO Bungku-Fatufia, RING STO Maba-Weda, Sirkuit Mandalika dan KITB | 2022-03-16 | 2022-08-12 | OSP-FO | TERNATE | WEDA | 2952390#2952395 | SS#2 Ring Maba - Weda ODC-SFI-FCC menuju SSU007 Prioritas 1 |  | 86 | 12 | 0 | Preparing | 2022-03-16 | 2022-08-26 | 2022-07-13 |  |  |  |  | 3618728038 | 4550072576 | 8168800614 | 0 | 4500451941 |  |  |  |  | TELKOM AKSES
G2022001 | 2 | 7 | 01E07V01 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000719/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 2 LoP Area Witel Sulteng | 2022-03-22 | 2022-05-11 | FEEDER BRANCHING 2022 | PALU | PARIGI |  | R7 PAL PGI FE BOYANTONGO |  | 100 | 100 | 100 | BAST-1 | 2022-03-22 | 2022-04-26 | 2022-03-22 | TEL.837/LG.310/DR7-12700000/2022 | 2022-05-10 | TEL.0059/LG.320/DR7-10400000/2022 | 2022-05-10 | 357428745 | 80434434 | 437863179 | 437863179 | 4500452766 |  |  |  |  | TELKOM AKSES | 2022-05-21
G2022001 | 2 | 6 | 01E07V01 | 007 | 72030088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000719/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 2 LoP Area Witel Sulteng | 2022-03-22 | 2022-05-11 | FEEDER BRANCHING 2022 | PALU | TAWAELI |  | R7 PAL TWL FE JL.TRANS SULAWESI |  | 100 | 100 | 100 | BAST-1 | 2022-03-22 | 2022-04-26 | 2022-03-22 | TEL.838/LG.310/DR7-12700000/2022 | 2022-05-10 | TEL.0059/LG.320/DR7-10400000/2022 | 2022-05-10 | 430408216 | 97732259 | 528140475 | 528140475 | 4500452766 |  |  |  |  | TELKOM AKSES | 2022-05-21
G2022002 | 1 | 6 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000778/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan PT2 Tahap 1B Tahun 2022 5 LOP Area Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-06 | 2022-04-01 | TEL.113/LG.320/R7W-7D1G0000/2020 | 2022-04-14 | TEL.0001/LG.320/R7W-7D1G0000/2022 | 2022-04-14 | 7274294 | 1056583 | 8330877 | 8330877 | 4500452950 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022002 | 1 | 7 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000778/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan PT2 Tahap 1B Tahun 2022 5 LOP Area Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT2 JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-06 | 2022-04-01 | TEL.114/LG.320/R7W-7D1G0000/2020 | 2022-04-14 | TEL.0001/LG.320/R7W-7D1G0000/2022 | 2022-04-14 | 20974652 | 3924969 | 24899621 | 24899621 | 4500452950 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022002 | 1 | 8 | 01E07P02 | 007 | 72040133 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000778/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan PT2 Tahap 1B Tahun 2022 5 LOP Area Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | RANTEPAO |  | R7 PRE RTP PT2 JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-03 | 2022-04-01 | TEL.115/LG.320/R7W-7D1G0000/2020 | 2022-04-14 | TEL.0001/LG.320/R7W-7D1G0000/2022 | 2022-04-14 | 2248486 | 353770 | 2602256 | 2602256 | 4500452950 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022002 | 1 | 9 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000778/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan PT2 Tahap 1B Tahun 2022 5 LOP Area Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-06 | 2022-04-01 | TEL.116/LG.320/R7W-7D1G0000/2020 | 2022-04-14 | TEL.0001/LG.320/R7W-7D1G0000/2022 | 2022-04-14 | 6863964 | 958352 | 7822316 | 7822316 | 4500452950 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022002 | 1 | 10 | 01E07P02 | 007 | 72040159 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000778/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan PT2 Tahap 1B Tahun 2022 5 LOP Area Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | SIDENRENG RAPPANG |  | R7 PRE SID PT2 JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-06 | 2022-04-01 | TEL.117/LG.320/R7W-7D1G0000/2020 | 2022-04-14 | TEL.0001/LG.320/R7W-7D1G0000/2022 | 2022-04-14 | 1715991 | 239588 | 1955579 | 1955579 | 4500452950 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022003 | 1 | 6 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | ENREKANG |  | R7 PRE ENR PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-03 | 2022-04-01 | TEL.118/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 1715991 | 301811 | 2017802 | 2017802 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 7 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-03 | 2022-04-01 | TEL.119/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 50591904 | 11628040 | 62219944 | 62219944 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 8 | 01E07P02 | 007 | 72040086 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | MAMASA |  | R7 PRE MMS PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.120/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 2248486 | 353770 | 2602256 | 2602256 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 9 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.121/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 6863964 | 1207244 | 8071208 | 8071208 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 20 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.122/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 22323093 | 4209506 | 26532599 | 26532599 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 11 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.123/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 13059080 | 1962927 | 15022007 | 15022007 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 12 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.124/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 11982666 | 1928400 | 13911066 | 13911066 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 13 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.125/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 8579955 | 1260163 | 9840118 | 9840118 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 14 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | POLEWALI |  | R7 PRE PLW PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.126/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 1715991 | 364034 | 2080025 | 2080025 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 15 | 01E07P02 | 007 | 72040133 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | RANTEPAO |  | R7 PRE RTP PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.127/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 1715991 | 239588 | 1955579 | 1955579 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 16 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.128/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 36599455 | 7254460 | 43853915 | 43853915 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 17 | 01E07P02 | 007 | 72040158 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | SIDRAP |  | R7 PRE SID PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.129/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 1715991 | 239588 | 1955579 | 1955579 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 18 | 01E07P02 | 007 | 72040186 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | WATANSOPPENG |  | R7 PRE WTG PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.130/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 16601857 | 2896344 | 19498201 | 19498201 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022003 | 1 | 19 | 01E07P02 | 007 | 72040187 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.000844/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap 1A Tahun 2022 14 LOP Area Witel Sulselbar | 2022-03-23 | 2022-05-06 | OSP FO FTTH PT2 2022 | PARE-PARE | WONOMULYO |  | R7 PRE WON PT2 DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-23 | 2022-04-04 | 2022-04-01 | TEL.131/LG.320/R7W-7D100000/2022 | 2022-04-14 | TEL.0004/LG.320/R7W-7D100000/2022 | 2022-04-14 | 1715991 | 239588 | 1955579 | 1955579 | 4500453057 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022004 | 2 | 8 | 01E07V01 | 007 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000930/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 4 LoP Area Witel Sulteng | 2022-03-25 | 2022-05-08 | OSP FO FTTH PT3 2022 | PALU | KOLONODALE |  | R7 PAL KOL PT3 TRANS SULAWESI (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-05-01 | 2022-03-25 | TEL.843/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0055/LG.320/DR7-10400000/2022 | 2022-05-11 | 216723491 | 51094174 | 267817665 | 267817665 | 4500453168 |  |  |  |  | WENANG PERKASA ABADI | 2022-05-13
G2022004 | 2 | 9 | 01E07V01 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000930/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 4 LoP Area Witel Sulteng | 2022-03-25 | 2022-05-08 | OSP FO FTTH PT3 2022 | PALU | PALU A |  | R7 PAL PLA PT3 JL.LAGARUTU (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-21 | 2022-03-25 | TEL.844/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0055/LG.320/DR7-10400000/2022 | 2022-05-11 | 67312694 | 14401337 | 81714031 | 81714031 | 4500453168 |  |  |  |  | WENANG PERKASA ABADI | 2022-05-13
G2022004 | 2 | 7 | 01E07V01 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000930/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 4 LoP Area Witel Sulteng | 2022-03-25 | 2022-05-08 | OSP FO FTTH PT3 2022 | PALU | PALU A |  | R7 PAL PLA PT3 JL.VETERAN (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-21 | 2022-03-25 | TEL.846/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0055/LG.320/DR7-10400000/2022 | 2022-05-11 | 153942381 | 31498248 | 185440629 | 185440629 | 4500453168 |  |  |  |  | WENANG PERKASA ABADI | 2022-05-13
G2022004 | 2 | 6 | 01E07V01 | 007 | 72030092 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000930/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 4 LoP Area Witel Sulteng | 2022-03-25 | 2022-05-08 | OSP FO FTTH PT3 2022 | PALU | PALU B |  | R7 PAL PLB JL.LAPATTA (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-22 | 2022-03-25 | TEL.845/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0055/LG.320/DR7-10400000/2022 | 2022-05-11 | 85719553 | 18442476 | 104162029 | 104162029 | 4500453168 |  |  |  |  | WENANG PERKASA ABADI | 2022-05-13
G2022005 | 2 | 19 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ARSO 4 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 1024924459 | 219926002 | 1244850461 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 8 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ARSO 7 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-04 |  |  |  |  | 483899225 | 127451047 | 611350272 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 12 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE FE ARSO 1 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 49364750 | 33368624 | 82733374 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 13 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ARSO 1 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 654780114 | 144085953 | 798866067 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 14 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE FE ARSO 6 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 314700778 | 91782067 | 406482845 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 15 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ARSO 6 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-04 |  |  |  |  | 707736998 | 156664004 | 864401002 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 16 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE FE ARSO 3 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 79263628 | 38386759 | 117650387 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 17 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ARSO 3 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 1027798558 | 226456526 | 1254255084 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 18 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE FE ARSO 4 |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 146238320 | 64629727 | 210868047 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 6 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 JALAN PASIR |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-06-22 | 2022-05-01 | TEL.1075/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0118/LG.320/DR7-10400000/2022 | 2022-07-08 | 205128350 | 50185911 | 255314261 | 255314261 | 4500453181 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022005 | 2 | 11 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | SENTANI |  | R7 JYP SNI FE PASAR BARU |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 66278407 | 35594704 | 101873111 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 10 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | SENTANI |  | R7 JYP SNI PT3 PASAR BARU |  | 100 | 0 | 0 | Preparing | 2022-03-25 | 2022-06-22 | 2022-05-01 |  |  |  |  | 663220082 | 156640442 | 819860524 | 0 | 4500453181 |  |  |  |  | TELKOM AKSES
G2022005 | 2 | 9 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM FE MAPURU |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-06-22 | 2022-05-01 | TEL.1077/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0118/LG.320/DR7-10400000/2022 | 2022-07-08 | 40233834 | 32788214 | 73022048 | 73022048 | 4500453181 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022005 | 2 | 20 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 MAPURU |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-06-22 | 2022-05-01 | TEL.1078/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0118/LG.320/DR7-10400000/2022 | 2022-07-08 | 249215855 | 62752090 | 311967945 | 311967945 | 4500453181 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022005 | 2 | 7 | 01E07V01 | 007 | 74030072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000931/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 15 LoP Area Witel Papua | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT3 2022 | JAYAPURA | WAENA |  | R7 JYP WAE PT3 YOKA |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-06-22 | 2022-05-01 | TEL.1076/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0118/LG.320/DR7-10400000/2022 | 2022-07-08 | 224038559 | 55848084 | 279886643 | 279886643 | 4500453181 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022006 | 2 | 6 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | LUWUK | LUWUK |  | R7 PAL LWU PT3 MONDONO, SOLOAN & KINTOM |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.1009/LG.310/DR7-12700000/2022 | 2022-06-23 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 702663482 | 141961810 | 844625292 | 844625292 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022006 | 2 | 12 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | LUWUK | LUWUK |  | R7 PAL LWU PT3 TOILI 1 (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.937/LG.310/DR7-12700000/2022. | 2022-06-19 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 45685385 | 7747920 | 53433305 | 53433305 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022006 | 2 | 7 | 01E07V01 | 007 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | PALU | BUNGKU |  | R7 PAL BKU PT3 TRANS SULAWESI BAHADOPI |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.972/LG.310/DR7-12700000/2022 | 2022-06-19 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 1103486836 | 250631428 | 1354118264 | 1354118264 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022006 | 2 | 10 | 01E07V01 | 007 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | PALU | KOLONODALE |  | R7 PAL KOL PT3 BOHUNSUAI |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.977/LG.310/DR7-12700000/2022 | 2022-06-18 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 471157630 | 78777679 | 549935309 | 549935309 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022006 | 2 | 11 | 01E07V01 | 007 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | PALU | KOLONODALE |  | R7 PAL KOL FE BOHUNSUAI |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.976/LG.310/DR7-12700000/2022 | 2022-06-18 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 58320171 | 30523261 | 88843432 | 88843432 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022006 | 2 | 8 | 01E07V01 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | PALU | PARIGI |  | R7 PAL PGI PT3 BOYANTONGO |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.974/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 820174994 | 146370807 | 966545801 | 966545801 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022006 | 2 | 9 | 01E07V01 | 007 | 72030088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000932/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 7 LoP Area Witel Sulteng | 2022-03-25 | 2022-06-22 | OSP FO FTTH PT2 2022 | PALU | TAWAELI |  | R7 PAL TWL PT3 JL.TRANS SULAWESI |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-04-10 | 2022-03-25 | TEL.975/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0104/LG.320/DR7-10400000/2022 | 2022-06-23 | 837609299 | 162043233 | 999652532 | 999652532 | 4500453275 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022007 | 2 | 7 | 01E07V01 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000933/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 Lokasi Grand Raya Marusu Area Witel Makassar | 2022-03-25 | 2022-05-13 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT3 GRAND RAYA, MARUSU dsk |  | 100 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-05-13 | 2022-03-25 | TEL.990/LG.310/DR7-12700000/2022 | 2022-06-22 | TEL.0105/LG.320/DR7-10400000/2022 | 2022-06-22 | 635411149 | 142376449 | 777787598 | 777787598 | 4500453276 |  |  |  |  | AKBAR BERSAUDARA GROUP | 2022-06-29
G2022008 | 2 | 7 | 01E07V01 | 007 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.000934/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 Lokasi Poros Sapanang Area Witel Makassar | 2022-03-25 | 2022-06-07 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | PANGKEP |  | R7 MKS PKN PT3 POROS SAPANANG DSK |  | 66 | 100 | 100 | BAST-1 | 2022-03-25 | 2022-06-07 | 2022-04-01 | TEL.816/LG.310/DR7-12700000/2022 | 2022-04-26 | TEL.0049/LG.320/DR7-10400000/2022 | 2022-04-26 | 320530183 | 65066813 | 385596996 | 385596996 | 4500453279 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-04-28
12022079 | 4 | 99 | 01C11G03 | 019 | 73010103 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | AMBON | SAUMLAKI | 2920997#2921002 | SML027 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 1196970757 | 220620306 | 1417591063 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 102 | 01C11G03 | 019 | 74030166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | JAYAPURA | ABEWAENA | 3118878#3118883 | WRS081 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-05-08 | TEL.2303/LG.310/DID-C0300000/2022 | 2022-06-25 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 20126352 | 8235345 | 28361697 | 28361697 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 100 | 01C11G03 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | JAYAPURA | SENTANI | 2437606#2437611 | JAP460 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 295661482 | 61595745 | 357257227 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 153 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547683#1547688 | TLI044 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2589/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 24464553 | 6034740 | 30499293 | 30499293 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 154 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547647#1547652 | TLI004 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2587/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 42643372 | 12151528 | 54794900 | 54794900 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 151 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547552#1547557 | TLI009 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2586/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 56499874 | 11475184 | 67975058 | 67975058 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 150 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547530#1547535 | DGL032 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2585/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 22399075 | 8646643 | 31045718 | 31045718 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 149 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547496#1547501 | TLI047 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2597/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 58010008 | 11295965 | 69305973 | 69305973 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 148 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547386#1547391 | TLI085 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2595/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 22959170 | 5852125 | 28811295 | 28811295 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 114 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547664#1547669 | TLI007 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2588/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 14082465 | 4856963 | 18939428 | 18939428 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 112 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547154#1547159 | TLI051 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2600/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 11359507 | 4484472 | 15843979 | 15843979 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 111 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547374#1547379 | TLI042 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2594/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 10443277 | 4350575 | 14793852 | 14793852 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 110 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547490#1547495 | TLI041 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2596/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 8104024 | 3909974 | 12013998 | 12013998 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 109 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547356#1547361 | TLI035 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2593/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 24503564 | 6864788 | 31368352 | 31368352 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 152 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547511#1547517 | TLI024 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2598/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 47340484 | 9636482 | 56976966 | 56976966 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 107 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547417#1547422 | TLI005 |  | 50 | 90 | 0 | Siap UT | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 7373570984 | 4964333836 | 12337904820 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 108 | 01C11G03 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PALU | KOTARAYA | 1547540#1547545 | TLI011 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2599/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1116/LG.320/DID-A0000000/2022 | 2022-07-24 | 42588582 | 9279092 | 51867674 | 51867674 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022079 | 4 | 156 | 01C11G03 | 019 | 72040193 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | BARRU | 2491474#2491479 | BAR076 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 662368837 | 110957266 | 773326103 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 116 | 01C11G03 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | MAMUJU | 1214604#1214609 | MAM008 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 2302800780 | 546426605 | 2849227385 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 121 | 01C11G03 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | PASANG KAYU | 1235055#1235060 | PSK027 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 179082964 | 192674536 | 371757500 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 120 | 01C11G03 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | PASANG KAYU | 1236156#1236161 | PSK021 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 650334687 | 526344195 | 1176678882 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 119 | 01C11G03 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | PASANG KAYU | 1233770#1233775 | PSK019 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 898181930 | 605400955 | 1503582885 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 117 | 01C11G03 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | PASANG KAYU | 1228305#1228310 | MAM030 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 2827892430 | 2059991796 | 4887884226 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 118 | 01C11G03 | 019 | 72040128 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | PARE-PARE | PINRANG | 2494457#2494462 | PIN156 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-06-01 | TEL.2236/LG.310/DID-C0300000/2022 | 2022-06-26 | TEL.0881/LG.320/DID-A0000000/2022 | 2022-06-26 | 1243660064 | 243171186 | 1486831250 | 1486831250 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-06-29
12022079 | 4 | 123 | 01C11G03 | 019 | 74060042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | SORONG | WARMARE / PRAFI | 2911967#2911972 | MWR309 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 530884168 | 132953006 | 663837174 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
12022079 | 4 | 122 | 01C11G03 | 019 | 74060042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | SORONG | WARMARE / PRAFI | 2916352#2916357 | MWR110 |  | 50 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-10-01 | 2022-07-01 | TEL.2703/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1190/LG.320/DID-A0000000/2022 | 2022-07-24 | 916072332 | 202012881 | 1118085213 | 1118085213 | 4500453118 |  |  |  |  | TELKOM AKSES | 2022-08-14
12022079 | 4 | 106 | 01C11G03 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.001035/HK.810/OPS-10000000/2022 | SP#8 OSP FO Node-B Telkomsel Tahap-1 | 2022-03-28 | 2022-09-29 | Node-B 2022 (DID) | UJUNGPANDANG | MAROS | 2435804#2435809 | WTP311 |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-02 | 2022-10-01 | 2022-07-01 |  |  |  |  | 877417142 | 1294140665 | 2171557807 | 0 | 4500453118 |  |  |  |  | TELKOM AKSES
G2022009 | 7 | 9 | 01E07V01 | 007 | 74010027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | BIAK | NABIRE |  | R7 SON NAB PT3 BATALYON NABIRE |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.904/LG.310/DR7-12700000/2022 | 2022-05-25 | TEL.0070/LG.320/DR7-10400000/2022 | 2022-05-25 | 295389802 | 62776612 | 358166414 | 358166414 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022009 | 7 | 6 | 01E07V01 | 007 | 74040005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR PT3 Marina Mart |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.8005/LG.310/DR7-12700000/2022 | 2022-06-29 | TEL.0123/LG.320/DR7-10400000/2022 | 2022-07-20 | 518705845 | 144790559 | 663496404 | 663496404 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022009 | 7 | 13 | 01E07V01 | 007 | 74040018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | MANOKWARI | WASIOR |  | R7 SON WSR FE PELABUHAN |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.1064/LG.310/DR7-12700000/2022 | 2022-07-20 | TEL.0123/LG.320/DR7-10400000/2022 | 2022-07-20 | 187285887 | 62432861 | 249718748 | 249718748 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022009 | 7 | 8 | 01E07V01 | 007 | 74040018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | MANOKWARI | WASIOR |  | R7 SON WSR PT3 PELABUHAN |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.1063/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0123/LG.320/DR7-10400000/2022 | 2022-07-20 | 312635035 | 75252627 | 387887662 | 387887662 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022009 | 7 | 15 | 01E07V01 | 007 | 74040018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | MANOKWARI | WASIOR |  | R7 SON WSR PT3 BANDARA |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.1089/LG.310/DR7-12700000/2022 | 2022-07-19 | TEL.0123/LG.320/DR7-10400000/2022 | 2022-07-20 | 388390965 | 91701338 | 480092303 | 480092303 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022009 | 7 | 14 | 01E07V01 | 007 | 74040018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | MANOKWARI | WASIOR |  | R7 SON WSR FE BANDARA |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.1065/LG.310/DR7-12700000/2022 | 2022-07-19 | TEL.0123/LG.320/DR7-10400000/2022 | 2022-07-20 | 55074104 | 36972810 | 92046914 | 92046914 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022009 | 7 | 11 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 JL KANAL VICTORY |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.903/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0070/LG.320/DR7-10400000/2022 | 2022-05-25 | 543672060 | 135042387 | 678714447 | 678714447 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022009 | 7 | 16 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON FE KATAPOP |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.905/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0070/LG.320/DR7-10400000/2022 | 2022-05-25 | 327311024 | 114941796 | 442252820 | 442252820 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022009 | 7 | 12 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 SP3 SORONG |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.1023/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0103/LG.320/DR7-10400000/2022 | 2022-06-26 | 1089453857 | 260412726 | 1349866583 | 1349866583 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022009 | 7 | 7 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001059/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-28 | 2022-07-07 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 KATAPOP |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-02 | 2022-03-28 | TEL.1024/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0103/LG.320/DR7-10400000/2022 | 2022-06-26 | 787330971 | 166103595 | 953434566 | 953434566 | 4500453821 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022010 | 4 | 6 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | ISIMU |  | R7 GTO ISM PT3 TOTOPO BILATO |  | 100 | 88 | 0 | Instalasi | 2022-03-28 | 2022-06-30 | 2022-04-01 |  |  |  |  | 341098150 | 63837163 | 404935313 | 0 | 4500453822 |  |  |  |  | TELKOM AKSES
G2022010 | 4 | 14 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | ISIMU |  | R7 GTO ISM PT3 PAGUYAMAN HELUMO |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-15 | 2022-04-01 | TEL.885/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0076/LG.320/DR7-10400000/2022 | 2022-05-21 | 448267063 | 84921757 | 533188820 | 533188820 | 4500453822 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022010 | 4 | 9 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | ISIMU |  | R7 GTO ISM PT3 BILATO BILUHU |  | 100 | 88 | 0 | Instalasi | 2022-03-28 | 2022-06-30 | 2022-04-01 |  |  |  |  | 377898647 | 71622204 | 449520851 | 0 | 4500453822 |  |  |  |  | TELKOM AKSES
G2022010 | 4 | 10 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | ISIMU |  | R7 GTO ISM FE BILATO BILUHU (FE) |  | 100 | 88 | 0 | Instalasi | 2022-03-28 | 2022-06-30 | 2022-04-01 |  |  |  |  | 477527510 | 103348016 | 580875526 | 0 | 4500453822 |  |  |  |  | TELKOM AKSES
G2022010 | 4 | 13 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | ISIMU |  | R7 GTO ISM FE TOTOPO BILATO (FE+UPLINK) |  | 100 | 88 | 0 | Instalasi | 2022-03-28 | 2022-06-30 | 2022-04-01 |  |  |  |  | 610769026 | 144364422 | 755133448 | 0 | 4500453822 |  |  |  |  | TELKOM AKSES
G2022010 | 4 | 7 | 01E07V01 | 007 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | LIMBOTO |  | R7 GTO LBT PT3 Jl. Runi S Kabli |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-15 | 2022-04-01 | TEL.884/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0076/LG.320/DR7-10400000/2022 | 2022-05-21 | 81680785 | 18234380 | 99915165 | 99915165 | 4500453822 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022010 | 4 | 11 | 01E07V01 | 007 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | LIMBOTO |  | R7 GTO LBT PT3 CITRA AGRINDO & PARINASA |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-15 | 2022-04-01 | TEL.883/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0076/LG.320/DR7-10400000/2022 | 2022-05-21 | 162522349 | 35502385 | 198024734 | 198024734 | 4500453822 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022010 | 4 | 8 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | TELAGA |  | R7 GTO TLG PT3 Galaxy Telaga Biru, dsk |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-15 | 2022-04-01 | TEL.881/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0076/LG.320/DR7-10400000/2022 | 2022-05-21 | 188022909 | 41088858 | 229111767 | 229111767 | 4500453822 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022010 | 4 | 12 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001062/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Gorontalo | 2022-03-28 | 2022-07-31 | OSP FO FTTH PT3 2022 | GORONTALO | TELAGA |  | R7 GTO TLG PT3 Griya Solaria Indah 4 |  | 100 | 100 | 100 | BAST-1 | 2022-03-28 | 2022-06-15 | 2022-04-01 | TEL.882/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0076/LG.320/DR7-10400000/2022 | 2022-05-21 | 143586503 | 34835575 | 178422078 | 178422078 | 4500453822 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022011 | 2 | 6 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001078/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 2 LOP Tahun 2022 Area Witel Gorontalo | 2022-03-29 | 2022-05-12 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 TALUDAA 2 |  | 100 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-05-12 | 2022-03-29 | TEL.848/LG.310/DR7-12700000/2022 | 2022-05-10 | TEL.0060/LG.320/DR7-10400000/2022 | 2022-05-10 | 808724692 | 142027258 | 950751950 | 950751950 | 4500453857 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-05-21
G2022011 | 2 | 7 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001078/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 2 LOP Tahun 2022 Area Witel Gorontalo | 2022-03-29 | 2022-05-12 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL FE TALUDAA 2 |  | 100 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-05-12 | 2022-03-29 | TEL.847/LG.310/DR7-12700000/2022 | 2022-05-10 | TEL.0060/LG.320/DR7-10400000/2022 | 2022-05-10 | 58704810 | 26390104 | 85094914 | 85094914 | 4500453857 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-05-21
G2022012 | 2 | 11 | 01E07V01 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | BIAK | BIAK |  | R7 SON BIA FE ASARYENDI |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.936/LG.310/DR7-12700000/2022 | 2022-06-01 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 207123189 | 79211917 | 286335106 | 286335106 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022012 | 2 | 10 | 01E07V01 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | BIAK | BIAK |  | R7 SON BIA PT3 ASARYENDI |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.935/LG.310/DR7-12700000/2022 | 2022-06-01 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 431723570 | 110566757 | 542290327 | 542290327 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022012 | 2 | 9 | 01E07V01 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | BIAK | BIAK |  | R7 SON BIA PT3 SORENDIWERI |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.934/LG.310/DR7-12700000/2022 | 2022-06-01 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 372012804 | 81230607 | 453243411 | 453243411 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022012 | 2 | 8 | 01E07V01 | 007 | 74010005 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | BIAK | BIAK |  | R7 SON BIA PT3 JL. WANDAMEN |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.933/LG.310/DR7-12700000/2022 | 2022-06-01 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 132516863 | 35590142 | 168107005 | 168107005 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022012 | 2 | 13 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN FE JL. UTARUM AIR MERAH |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.939/LG.310/DR7-12700000/2022 | 2022-06-02 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 125872492 | 63991487 | 189863979 | 189863979 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022012 | 2 | 12 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN PT3 JL. UTARUM AIR MERAH |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.938/LG.310/DR7-12700000/2022 | 2022-06-02 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 377797906 | 103337762 | 481135668 | 481135668 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022012 | 2 | 7 | 01E07V01 | 007 | 74060038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001080/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching dan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Papua Barat | 2022-03-29 | 2022-06-11 | OSP FO FTTH PT3 2022 | SORONG | FAKFAK |  | R7 SON FFA PT3 JL. YOS SUDARSO |  | 90 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-06-11 | 2022-04-01 | TEL.937/LG.310/DR7-12700000/2022 | 2022-06-02 | TEL.0080/LG.320/DR7-10400000/2022 | 2022-06-02 | 139237358 | 57777243 | 197014601 | 197014601 | 4500453870 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-10
G2022013 | 2 | 9 | 01E07V01 | 007 | 72030083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001117/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 2 LoP Area Witel Sulteng | 2022-03-29 | 2022-05-17 | OSP FO FTTH PT3 2022 | PALU | TOLAY |  | R7 PAL TLY PT3 ASTINA |  | 60 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-05-17 | 2022-04-01 | TEL.801/LG.310/DR7-12700000/2022 | 2022-04-26 | TEL.0050/LG.320/DR7-10400000/2022 | 2022-04-26 | 657763753 | 119358424 | 777122177 | 777122177 | 4500453854 |  |  |  |  | MITRATAMA ENERGI SELEBES | 2022-04-28
G2022013 | 2 | 8 | 01E07V01 | 007 | 72030083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001117/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 2 LoP Area Witel Sulteng | 2022-03-29 | 2022-05-17 | OSP FO FTTH PT3 2022 | PALU | TOLAY |  | R7 PAL TLY FE ASTINA |  | 82 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-05-17 | 2022-04-01 | TEL.802/LG.310/DR7-12700000/2022 | 2022-04-26 | TEL.0050/LG.320/DR7-10400000/2022 | 2022-04-26 | 142735534 | 45954605 | 188690139 | 188690139 | 4500453854 |  |  |  |  | MITRATAMA ENERGI SELEBES | 2022-04-28
G2022014 | 2 | 8 | 01E07V01 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001118/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 Lokasi Haji Banca Area Witel Makassar | 2022-03-29 | 2022-05-12 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT3 HAJI BANCA |  | 100 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-05-05 | 2022-04-01 | TEL.780/LG.310/DR7-12700000/2022 | 2022-04-29 | TEL.0053/LG.320/DR7-10400000/2022 | 2022-04-29 | 163723640 | 33057422 | 196781062 | 196781062 | 4500453855 |  |  |  |  | LAMUNA INDOTIMUR | 2022-05-11
G2022015 | 2 | 7 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001119/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 Lokasi Tanete Cluster 1 Area Witel Makassar | 2022-03-29 | 2022-05-12 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT3 TANETE CLUSTER 1 |  | 100 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-05-12 | 2022-03-29 | TEL.851/LG.310/DR7-12700000/2022 | 2022-05-12 | TEL.0057/LG.320/DR7-10400000/2022 | 2022-05-12 | 204790523 | 40496677 | 245287200 | 245287200 | 4500453856 |  |  |  |  | SANDHY PUTRAMAKMUR | 2022-05-17
G2022016 | 2 | 7 | 01E07V01 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001120/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 Lokasi Inner WTP 5 Area Witel Makassar | 2022-03-29 | 2022-05-12 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP PT3 INNER WTP 5 |  | 100 | 100 | 100 | BAST-1 | 2022-03-29 | 2022-05-07 | 2022-04-01 | TEL.836/LG.310/DR7-127000000/2022 | 2022-04-29 | TEL.0054/LG.320/DR7-10400000/2022 | 2022-04-29 | 427627140 | 93020496 | 520647636 | 520647636 | 4500453970 |  |  |  |  | MANDOR KAWAT | 2022-05-11
G2022017 | 1 | 6 | 01E07S02 | 007 | 72050093 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.001140/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS 1 LoP Periode Januari Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-05-28 | HEM | KENDARI | MANDONGA |  | ODC-MDG-FP POLDA SULTRA |  | 90 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-26 | 2022-04-01 | K.TEL.74/LG.310/R7W-7G100000/2022 | 2022-04-18 | TEL.0003/LG.320/R7W-7G100000/2022 | 2022-04-18 | 25934834 | 6190753 | 32125587 | 32125587 | 4500454192 |  |  |  |  | TELKOM AKSES | 2022-04-26
G2022018 | 4 | 12 | 01E07V01 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001161/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-17 | OSP FO FTTH PT3 2022 | AMBON | DOBO |  | R7 AMB DOB PT3 KANTOR PENGADILAN |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-04-01 | TEL.878/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0071/LG.320/DR7-10400000/2022 | 2022-05-25 | 356286466 | 90598780 | 446885246 | 446885246 | 4500454185 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-31
G2022018 | 4 | 10 | 01E07V01 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001161/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-17 | OSP FO FTTH PT3 2022 | AMBON | DOBO |  | R7 AMB DOB PT3 RUMAH SAKIT DOBO |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-04-01 | TEL.876/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0071/LG.320/DR7-10400000/2022 | 2022-05-25 | 98948434 | 26201011 | 125149445 | 125149445 | 4500454185 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-31
G2022018 | 4 | 13 | 01E07V01 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001161/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-17 | OSP FO FTTH PT3 2022 | AMBON | DOBO |  | R7 AMB DOB PT3 SMK NEGRI 1 |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-04-01 | TEL.877/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0071/LG.320/DR7-10400000/2022 | 2022-05-25 | 213550157 | 54833988 | 268384145 | 268384145 | 4500454185 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-31
G2022018 | 4 | 14 | 01E07V01 | 007 | 73010046 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001161/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-17 | OSP FO FTTH PT3 2022 | AMBON | NAMLEA |  | R7 AMB NML PT3 SAVANA JAYA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-04-01 | TEL.880/LG.310/DR7-12700000/2022 | 2022-05-25 | TEL.0071/LG.320/DR7-10400000/2022 | 2022-05-25 | 853774020 | 169166548 | 1022940568 | 1022940568 | 4500454185 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-31
G2022018 | 4 | 15 | 01E07V01 | 007 | 73010046 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001161/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-17 | OSP FO FTTH PT3 2022 | AMBON | NAMLEA |  | R7 AMB NML PT3 JIKUMARASA & UBUNG |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-04-01 | TEL.879/LG.310/DR7-12700000/2022 | 2022-05-25 | TEL.0071/LG.320/DR7-10400000/2022 | 2022-05-25 | 1069895200 | 223480548 | 1293375748 | 1293375748 | 4500454185 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-31
G2022018 | 4 | 11 | 01E07V01 | 007 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001161/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-17 | OSP FO FTTH PT3 2022 | AMBON | SAUMLAKI |  | R7 AMB SML PT3 SAUMLAKI |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-04-01 | TEL.989/LG.310/DR7-12700000/2022 | 2022-06-21 | TEL.0098/LG.320/DR7-10400000/2022 | 2022-06-21 | 681869978 | 162093789 | 843963767 | 843963767 | 4500454185 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-24
G2022019 | 4 | 27 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 BTN HALIM BAU BAU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.782/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 142886544 | 29188444 | 172074988 | 172074988 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 26 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU FE BTN HALIM BAU BAU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.781/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 64293931 | 35621764 | 99915695 | 99915695 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 8 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 MAWASANGKA INDUK |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.783/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 399668162 | 78334226 | 478002388 | 478002388 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 29 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 WAYONG |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.908/LG.310/DR7-12700000/2022 | 2022-05-25 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 237826328 | 48558122 | 286384450 | 286384450 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 35 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR FE WAYONG |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.907/LG.310/DR7-12700000/2022 | 2022-05-25 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 259453067 | 79629297 | 339082364 | 339082364 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 28 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 BPN PUUWATU & PASIR PUTIH |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.785/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 101490170 | 24348433 | 125838603 | 125838603 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 11 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 KENDARI MOROSI |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.784/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 103883907 | 21258129 | 125142036 | 125142036 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 30 | 01E07V01 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | LASUSUA |  | R7 KDI LSS PT3 BINTANG ELEGAN LASUSUA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.913/LG.310/DR7-12700000/2022 | 2022-05-27 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 78981762 | 14114518 | 93096280 | 93096280 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 16 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 POROS KONDA LORONG LAWAKO |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.793/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 216229554 | 39546471 | 255776025 | 255776025 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 15 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 JL. MERPATI 2 - LASITARDA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.792/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 64245366 | 16376071 | 80621437 | 80621437 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 10 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 LINGKAR TINANGGEA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.794/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 132936034 | 27722541 | 160658575 | 160658575 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 34 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 VILLA IBIS |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.906/LG.310/DR7-12700000/2022 | 2022-05-26 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 137846554 | 28436240 | 166282794 | 166282794 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 23 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 BUDI UTOMO |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.788/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 73610827 | 16088422 | 89699249 | 89699249 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 22 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 BARUGA NUSANTARA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.787/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 70258453 | 16273182 | 86531635 | 86531635 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 21 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 POROS JATIBALI |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.795/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 242781944 | 45324352 | 288106296 | 288106296 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 20 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 JL. AH NASUTION |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.791/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 94569358 | 20197182 | 114766540 | 114766540 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 19 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 GRIYA CENDANA ANDOUNOHU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.790/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 66371470 | 15152261 | 81523731 | 81523731 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 18 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 GRIYA 21 KAMBU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.789/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 114480776 | 21404266 | 135885042 | 135885042 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 17 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 BARUGA (CO FX) |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.786/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 54694962 | 11722137 | 66417099 | 66417099 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 36 | 01E07V01 | 007 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | POMALAA |  | R7 KDI PMA PT3 INNER POMALAA ODC-PMA-FC |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-25 | 2022-03-30 | TEL.911/LG.310/DR7-12700000/2022 | 2022-05-26 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 135970704 | 25686872 | 161657576 | 161657576 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 37 | 01E07V01 | 007 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | POMALAA |  | R7 KDI PMA PT3 INNER POMALAA ODC-PMA-FD |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.912/LG.310/DR7-12700000/2022 | 2022-05-26 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 90979103 | 19836910 | 110816013 | 110816013 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 24 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 LAMBANDIA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.796/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 282139118 | 57884373 | 340023491 | 340023491 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022019 | 4 | 32 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 ANGGOTOA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.909/LG.310/DR7-12700000/2022 | 2022-05-27 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 439640064 | 102262497 | 541902561 | 541902561 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 13 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 MOWEWE |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-03-30 | TEL.910/LG.310/DR7-12700000/2022 | 2022-05-27 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 385942279 | 73383518 | 459325797 | 459325797 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 9 | 01E07V01 | 007 | 72050074 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | WANCI |  | R7 KDI WNC FE WAHA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.797/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0072/LG.320/DR7-10400000/2022 | 2022-05-27 | 153932090 | 62828490 | 216760580 | 216760580 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022019 | 4 | 14 | 01E07V01 | 007 | 72050074 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001198/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Sultra | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | KENDARI | WANCI |  | R7 KDI WNC PT3 WAHA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-23 | 2022-04-01 | TEL.798/LG.310/DR7-12700000/2022 | 2022-04-24 | TEL.0046/LG.320/DR7-10400000/2022 | 2022-04-24 | 290594351 | 65234330 | 355828681 | 355828681 | 4500454236 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 8 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 GUNUNG NONA RCTI |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.774/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0047/LG.320/DR7-10400000/2022 | 2022-04-23 | 215459633 | 49886157 | 265345790 | 265345790 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 11 | 01E07V01 | 007 | 73010013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | BULA |  | R7 AMB BUL PT3 NEW ODC BULA |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.1006/LG.310/DR7-12700000/2022 | 2022-06-25 | TEL.0099/LG.320/DR7-10400000/2022 | 2022-06-27 | 374873513 | 97866058 | 472739571 | 472739571 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022020 | 4 | 9 | 01E07V01 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | MASOHI |  | R7 AMB MSH PT3 BTN HARURU |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.778/LG.310/DR7-12700000/2022 | 2022-04-23 | TEL.0047/LG.320/DR7-10400000/2022 | 2022-04-23 | 201717082 | 39371179 | 241088261 | 241088261 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 13 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 TOISAPU (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.776/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0047/LG.320/DR7-10400000/2022 | 2022-04-23 | 416539895 | 108165574 | 524705469 | 524705469 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 12 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 NEGRI LAMA |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.775/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0047/LG.320/DR7-10400000/2022 | 2022-04-23 | 100997975 | 25131768 | 126129743 | 126129743 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 7 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 HULUNG |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.773/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0047/LG.320/DR7-10400000/2022 | 2022-04-23 | 182548300 | 42525555 | 225073855 | 225073855 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 14 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 WAAI |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.777/LG.310/DR7-12700000/2022 | 2022-04-22 | TEL.0047/LG.320/DR7-10400000/2022 | 2022-04-23 | 321981133 | 69731114 | 391712247 | 391712247 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-04-27
G2022020 | 4 | 10 | 01E07V01 | 007 | 73010172 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | TIAKUR |  | R7 AMB TIA PT3 KAMPUNG BABAR |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.1005/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0099/LG.320/DR7-10400000/2022 | 2022-06-27 | 478878424 | 110586912 | 589465336 | 589465336 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022020 | 4 | 16 | 01E07V01 | 007 | 73010172 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | TIAKUR |  | R7 AMB TIA PT3 NEW ODC PATTI |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.1008/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0099/LG.320/DR7-10400000/2022 | 2022-06-27 | 115694500 | 41465597 | 157160097 | 157160097 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022020 | 4 | 6 | 01E07V01 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | TUAL |  | R7 AMB TUA PT3 OHOITEL & PERUMTEL TUAL |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-08 | 2022-04-01 | TEL.1004/LG.310/DR7-12700000/2022 | 2022-06-27 | TEL.0099/LG.320/DR7-10400000/2022 | 2022-06-27 | 694564365 | 145445944 | 840010309 | 840010309 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022020 | 4 | 15 | 01E07V01 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001199/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 Area Witel Maluku | 2022-03-30 | 2022-06-27 | OSP FO FTTH PT3 2022 | AMBON | TUAL |  | R7 AMB TUA PT3 OHOILUK & LANGGUR |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-09 | 2022-04-01 | TEL.1007/LG.310/DR7-12700000/2022 | 2022-06-27 | TEL.0099/LG.320/DR7-10400000/2022 | 2022-06-27 | 442476058 | 95180251 | 537656309 | 537656309 | 4500454249 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022021 | 2 | 9 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001200/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 Tahun 2022 Witel Sultra | 2022-03-30 | 2022-05-28 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 ANOA GREEN WISATA DSK |  | 95 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-28 | 2022-04-01 | TEL.873/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0064/LG.320/DR7-10400000/2022 | 2022-05-21 | 662834468 | 157766936 | 820601404 | 820601404 | 4500454241 |  |  |  |  | INNANDA INDAH | 2022-05-28
G2022021 | 2 | 10 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001200/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 Tahun 2022 Witel Sultra | 2022-03-30 | 2022-05-28 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 DEWI BUNGA LAND NANGA2 |  | 95 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-05-28 | 2022-04-01 | TEL.874/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0064/LG.320/DR7-10400000/2022 | 2022-05-21 | 118050526 | 21964641 | 140015167 | 140015167 | 4500454241 |  |  |  |  | INNANDA INDAH | 2022-05-28
G2022021 | 2 | 8 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001200/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 Tahun 2022 Witel Sultra | 2022-03-30 | 2022-05-28 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 ANDOUNOHU & GRIYA 21 |  | 95 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-05-28 | 2022-04-01 | TEL.872/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0064/LG.320/DR7-10400000/2022 | 2022-05-21 | 236994492 | 63649816 | 300644308 | 300644308 | 4500454241 |  |  |  |  | INNANDA INDAH | 2022-05-28
G2022021 | 2 | 7 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001200/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 Tahun 2022 Witel Sultra | 2022-03-30 | 2022-05-28 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 TIRAWUTA ONEMBUTE |  | 95 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-05-28 | 2022-04-01 | TEL.875/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0064/LG.320/DR7-10400000/2022 | 2022-05-21 | 229777659 | 44652042 | 274429701 | 274429701 | 4500454241 |  |  |  |  | INNANDA INDAH | 2022-05-28
G2022022 | 2 | 7 | 01E07V01 | 007 | 72080054 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001223/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 Lokasi Torawang Area Witel Makassar | 2022-03-30 | 2022-04-28 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | JENEPONTO |  | R7 MKS JNP PT3 TAROWANG |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-04-28 | 2022-04-01 | TEL.817/LG.310/DR7-12700000/2022 | 2022-04-27 | TEL.0051/LG.320/DR7-10400000/2022 | 2022-04-27 | 433633605 | 87177779 | 520811384 | 520811384 | 4500454326 |  |  |  |  | BAKTI SARANA PRATAMA | 2022-04-30
G2022023 | 8 | 9 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT3 SAPO LOHE / TANAH BERU |  | 100 | 95 | 0 | BAUT | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.979/LG.310/DR7-12700000/2022 | 2022-06-18 |  |  | 301958389 | 65931326 | 367889715 | 0 | 4500454328 |  |  |  |  | TELKOM AKSES
G2022023 | 8 | 12 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT3 CAILE 1 |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.980/LG.310/DR7-12700000/2022 | 2022-06-19 | TEL.0109/LG.320/DR7-10400000/2022 | 2022-06-19 | 132883473 | 28833563 | 161717036 | 161717036 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022023 | 8 | 14 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT3 HERLANG |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.1011/LG.310/DR7-12700000/2022 | 2022-06-24 | TEL.0124/LG.320/DR7-10400000/2022 | 2022-06-25 | 1019310047 | 184922357 | 1204232404 | 1204232404 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022023 | 8 | 13 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT3 BIKERU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.1010/LG.310/DR7-12700000/2022 | 2022-06-24 | TEL.0124/LG.320/DR7-10400000/2022 | 2022-06-25 | 361638497 | 68905073 | 430543570 | 430543570 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022023 | 8 | 15 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK PT3 BONTO TANGNGA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.982/LG.310/DR7-12700000/2022 | 2022-06-18 | TEL.0109/LG.320/DR7-10400000/2022 | 2022-06-19 | 345328249 | 76370165 | 421698414 | 421698414 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022023 | 8 | 10 | 01E07V01 | 007 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | PANGKEP |  | R7 MKS PKN PT3 Mattoangin Pangkep |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.981/LG.310/DR7-12700000/2022 | 2022-06-19 | TEL.0124/LG.320/DR7-10400000/2022 | 2022-06-25 | 219376375 | 40611115 | 259987490 | 259987490 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022023 | 8 | 7 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT3 BATARIA LAND |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.978/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0124/LG.320/DR7-10400000/2022 | 2022-06-25 | 217360573 | 42779225 | 260139798 | 260139798 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022023 | 8 | 8 | 01E07V01 | 007 | 72080120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | TAKALAR |  | R7 MKS TKA PT3 POROS TKA-SUG |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-04-01 | TEL.902/LG.310/DR7-12700000/2022 | 2022-05-24 | TEL.0073/LG.320/DR7-10400000/2022 | 2022-05-24 | 758105138 | 147612364 | 905717502 | 905717502 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022023 | 8 | 11 | 01E07V01 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA PT3 Sentraland BTP 2 |  | 100 | 0 | 0 | Preparing | 2022-03-30 | 2022-06-26 | [5 empty] | 842156581 | 207852491 | 1050009072 | 0 | 4500454328 |  |  |  |  | TELKOM AKSES
G2022023 | 8 | 16 | 01E07V01 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA PT3 MONCONGLOE 2 |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.983/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0124/LG.320/DR7-10400000/2022 | 2022-06-25 | 816061185 | 138974726 | 955035911 | 955035911 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022023 | 8 | 6 | 01E07V01 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001224/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 11 LoP Area Witel Makassar | 2022-03-30 | 2022-07-26 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP PT3 SAMBALOGE BARU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-26 | 2022-03-30 | TEL.1012/LG.310/DR7-12700000/2022 | 2022-06-25 | TEL.0124/LG.320/DR7-10400000/2022 | 2022-06-25 | 1375458621 | 281628462 | 1657087083 | 1657087083 | 4500454328 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022024 | 4 | 9 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001225/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 5 LoP Area Witel Makassar | 2022-03-30 | 2022-07-17 | FEEDER BRANCHING 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK FE BONTO TANGNGA |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-03-30 | TEL.984/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0110/LG.320/DR7-10400000/2022 | 2022-06-13 | 569462939 | 127746321 | 697209260 | 697209260 | 4500454329 |  |  |  |  | TELKOM AKSES | 2022-07-01
G2022024 | 4 | 6 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001225/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 5 LoP Area Witel Makassar | 2022-03-30 | 2022-07-17 | FEEDER BRANCHING 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK FE SAPO LOHE / TANAH BERU |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-06-15 | 2022-03-30 | TEL.986/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0116/LG.320/DR7-10400000/2022 | 2022-06-14 | 338302946 | 107346818 | 445649764 | 445649764 | 4500454329 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022024 | 4 | 10 | 01E07V01 | 007 | 72080036 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001225/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 5 LoP Area Witel Makassar | 2022-03-30 | 2022-07-17 | FEEDER BRANCHING 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK FE HERLANG (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-17 | 2022-03-30 | TEL.985/LG.310/DR7-12700000/2022 | 2022-06-14 | TEL.0116/LG.320/DR7-10400000/2022 | 2022-06-14 | 172431624 | 70518737 | 242950361 | 242950361 | 4500454329 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022024 | 4 | 7 | 01E07V01 | 007 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001225/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 5 LoP Area Witel Makassar | 2022-03-30 | 2022-07-17 | FEEDER BRANCHING 2022 | UJUNGPANDANG | SINJAI |  | R7 MKS SIN FE BIKERU |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-16 | 2022-03-30 | TEL.987/LG.310/DR7-12700000/2022 | 2022-06-14 | TEL.0116/LG.320/DR7-10400000/2022 | 2022-06-14 | 41582863 | 24151629 | 65734492 | 65734492 | 4500454329 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022024 | 4 | 8 | 01E07V01 | 007 | 72080166 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001225/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 5 LoP Area Witel Makassar | 2022-03-30 | 2022-07-17 | FEEDER BRANCHING 2022 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA FE MONCONGLOE 2 |  | 100 | 100 | 100 | BAST-1 | 2022-03-30 | 2022-06-14 | 2022-03-30 | TEL.988/LG.310/DR7-12700000/2022 | 2022-06-14 | TEL.0116/LG.320/DR7-10400000/2022 | 2022-06-14 | 101095421 | 36742832 | 137838253 | 137838253 | 4500454329 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022025 | 4 | 7 | 01E07V01 | 007 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001227/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 3 LoP Area Witel Sulselbar | 2022-03-30 | 2022-06-12 | FEEDER BRANCHING 2022 | PARE-PARE | MAJENE |  | R7 PRE MAJ FE ODC POLE MAJENE |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-05-18 | 2022-03-30 | TEL.770/LG.310/DR7-12700000/2022 | 2022-05-28 | TEL.0074/LG.320/DR7-10400000/2022 | 2022-05-28 | 182831927 | 49438518 | 232270445 | 232270445 | 4500454330 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022025 | 4 | 8 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001227/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 3 LoP Area Witel Sulselbar | 2022-03-30 | 2022-06-12 | FEEDER BRANCHING 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS FE TANALILI (FEEDER) |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-05-07 | 2022-03-30 | TEL.769/LG.310/DR7-12700000/2022 | 2022-05-28 | TEL.0074/LG.320/DR7-10400000/2022 | 2022-05-28 | 228183042 | 58437408 | 286620450 | 286620450 | 4500454330 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022025 | 4 | 6 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001227/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan Feeder Branching 3 LoP Area Witel Sulselbar | 2022-03-30 | 2022-06-12 | FEEDER BRANCHING 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS FE ODC POLE SABBANG (FEEDER) |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-05-06 | 2022-03-30 | TEL.768/LG.310/DR7-12700000/2022 | 2022-06-08 | TEL.0086/LG.320/DR7-10400000/2022 | 2022-06-08 | 184546378 | 69275558 | 253821936 | 253821936 | 4500454330 |  |  |  |  | TELKOM AKSES | 2022-06-14
12022089 | 1 | 15 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.001291/HK.810/OPS-10000000/2022 | SP#4 ONT Retail Dual Band Platform ZTE | 2022-03-31 | 2022-08-27 | ONT Retail | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 95 | 100 | 100 | BAST-1 | 2022-05-02 | 2022-05-19 | 2022-05-02 | C.TEL569/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0065/LG.320/COP-F3000000/2022 | 2022-05-13 | 22254750000 | 0 | 22254750000 | 22254750000 | 4500454478 |  |  |  |  | ZTE INDONESIA | 2022-05-19
G2022026 | 2 | 37 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | AMBON | AMBON |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-10 | 2022-04-01 | C.TEL.120/LG300/DR7-12800000/2022 | 2022-04-19 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 129881740 | 81815920 | 211697660 | 211697660 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 38 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | AMBON | MASOHI |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-11 | 2022-04-01 | C.TEL.121/LG300/DR7-12800000/2022 | 2022-04-19 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 26762600 | 19180410 | 45943010 | 45943010 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 39 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | AMBON | NAMLEA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-11 | 2022-04-01 | C.TEL.122/LG300/DR7-12800000/2022 | 2022-04-19 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 36603710 | 21318040 | 57921750 | 57921750 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 40 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | AMBON | PASSO |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-11 | 2022-04-01 | C.TEL.123/LG300/DR7-12800000/2022 | 2022-04-19 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 83441180 | 49107460 | 132548640 | 132548640 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 41 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | AMBON | SAUMLAKI |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-11 | 2022-04-01 | C.TEL.124/LG300/DR7-12800000/2022 | 2022-04-19 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 10101080 | 8394400 | 18495480 | 18495480 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 42 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | AMBON | TUAL |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-11 | 2022-04-01 | C.TEL.125/LG300/DR7-12800000/2022 | 2022-04-19 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 9965490 | 2442260 | 12407750 | 12407750 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 14 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | GORONTALO | GORONTALO |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-14 | 2022-03-31 | C.TEL.97/LG300/DR7-12800000/2022 | 2022-04-11 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 46725450 | 16847460 | 63572910 | 63572910 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 15 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | GORONTALO | ISIMU |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-14 | 2022-03-31 | C.TEL.98/LG300/DR7-12800000/2022 | 2022-04-11 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 6178700 | 3927560 | 10106260 | 10106260 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 16 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | GORONTALO | KWANDANG |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-14 | 2022-03-31 | C.TEL.99/LG300/DR7-12800000/2022 | 2022-04-11 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 16755000 | 6304110 | 23059110 | 23059110 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 17 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | GORONTALO | LIMBOTO |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-14 | 2022-03-31 | C.TEL.100/LG300/DR7-12800000/2022 | 2022-04-11 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 7273800 | 4048290 | 11322090 | 11322090 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 18 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | GORONTALO | MARISA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-14 | 2022-03-31 | C.TEL.101/LG300/DR7-12800000/2022 | 2022-04-11 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 27982990 | 13127160 | 41110150 | 41110150 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 19 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | GORONTALO | TELAGA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-14 | 2022-03-31 | C.TEL.102/LG300/DR7-12800000/2022 | 2022-04-11 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 21058650 | 9643720 | 30702370 | 30702370 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 43 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | ABEPURA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.126/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 64985760 | 43803770 | 108789530 | 108789530 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 46 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.127/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 74365150 | 32850990 | 107216140 | 107216140 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 47 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.128/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 16617490 | 12359450 | 28976940 | 28976940 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 49 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | SARMI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.130/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 92040 | 7280 | 99320 | 99320 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 50 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | SENTANI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.131/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 8145660 | 5961110 | 14106770 | 14106770 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 51 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | TIMIKA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.132/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 22476040 | 28177120 | 50653160 | 50653160 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 52 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | JAYAPURA | WAENA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.133/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 14508930 | 11865420 | 26374350 | 26374350 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 94 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | BAU-BAU |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.175/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 3029100 | 1848440 | 4877540 | 4877540 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 95 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | KENDARI |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.176/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 9384000 | 6356650 | 15740650 | 15740650 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 96 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | KOLAKA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.177/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 2472120 | 6269520 | 8741640 | 8741640 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 97 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | LASUSUA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.178/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 821540 | 1652810 | 2474350 | 2474350 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 98 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | MANDONGA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.179/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 54823320 | 43733180 | 98556500 | 98556500 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 99 | 01E07Y05 | 007 | 72050050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | POMALAA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.180/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 162100 | 213350 | 375450 | 375450 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 100 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | KENDARI | UNAAHA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-26 | 2022-04-01 | C.TEL.181/LG300/DR7-12800000/2022 | 2022-04-14 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 6129510 | 4395090 | 10524600 | 10524600 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 101 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | AIR MADIDI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.182/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 92457460 | 65100020 | 157557480 | 157557480 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 102 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | AMURANG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.183/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 17848980 | 14329870 | 32178850 | 32178850 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 103 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | BAHU |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.184/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 290618010 | 148011380 | 438629390 | 438629390 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 104 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | BITUNG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.185/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 138375310 | 36428890 | 174804200 | 174804200 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 105 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | BOROKO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.186/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 3780000 | 595980 | 4375980 | 4375980 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 106 | 01E07Y05 | 007 | 72010267 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | HULU SIAU |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.187/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 7639950 | 3511230 | 11151180 | 11151180 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 107 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | KAUDITAN |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.188/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 5525050 | 8778850 | 14303900 | 14303900 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 108 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | KOTAMOBAGU |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.189/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 110369550 | 39090030 | 149459580 | 149459580 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 109 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | LANGOWAN |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.190/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 9633900 | 5124450 | 14758350 | 14758350 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 110 | 01E07Y05 | 007 | 72010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | LOLAK |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.191/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 6158900 | 4274530 | 10433430 | 10433430 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 111 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | MANADO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.192/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 329142520 | 121809500 | 450952020 | 450952020 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 112 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | PANIKI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.193/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 192873200 | 107041060 | 299914260 | 299914260 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 113 | 01E07Y05 | 007 | 72010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | TAHUNA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.194/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 1042980 | 3277080 | 4320060 | 4320060 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 114 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | TOMOHON |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.195/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 261847480 | 113812860 | 375660340 | 375660340 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 115 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | TONDANO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.196/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 429226020 | 173660340 | 602886360 | 602886360 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 116 | 01E07Y05 | 007 | 72010283 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANADO | TUTUYAN |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.197/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 12839560 | 7522240 | 20361800 | 20361800 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 61 | 01E07Y05 | 007 | 74040018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MANOKWARI | WASIOR |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.142/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 7330450 | 5500050 | 12830500 | 12830500 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 48 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | MERAUKE | MERAUKE |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER -DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-03-31 | C.TEL.129/LG300/DR7-12800000/2022 | 2022-04-08 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 211260 | 211260 | 211260 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 85 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | BUNGKU |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.166/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 7041520 | 3680200 | 10721720 | 10721720 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 86 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | DONGGALA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.167/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 372180 | 372180 | 372180 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 87 | 01E07Y05 | 007 | 72030104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | KOLONODALE |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.168/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 62030 | 62030 | 62030 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 88 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | LUWUK |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.169/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 3821740 | 1536140 | 5357880 | 5357880 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 89 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | PALU A |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.170/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 18098730 | 44144220 | 62242950 | 62242950 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 90 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | PALU B |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.171/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 3204740 | 2988410 | 6193150 | 6193150 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 91 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | PARIGI |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.172/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 14732200 | 8227730 | 22959930 | 22959930 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 93 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PALU | TAWAELI |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.174/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 682330 | 682330 | 682330 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 62 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | BARRU |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-12 | 2022-04-01 | C.TEL.143/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 29153320 | 21350540 | 50503860 | 50503860 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 63 | 01E07Y05 | 007 | 72040044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | CANGADI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-12 | 2022-04-01 | C.TEL.144/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 742030 | 790460 | 1532490 | 1532490 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 64 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | ENREKANG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-12 | 2022-04-01 | C.TEL.145/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 9106080 | 9806540 | 18912620 | 18912620 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 65 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | MAJENE |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-12 | 2022-04-01 | C.TEL.146/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 28893680 | 26468350 | 55362030 | 55362030 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 66 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | MAKALE |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-12 | 2022-04-01 | C.TEL.147/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 10972600 | 6083560 | 17056160 | 17056160 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 67 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | MALILI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-12 | 2022-04-01 | C.TEL.148/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 10081400 | 5162940 | 15244340 | 15244340 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 68 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | MAMASA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.149/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 10760200 | 7404480 | 18164680 | 18164680 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 69 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | MAMUJU |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.150/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 39032970 | 19713040 | 58746010 | 58746010 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 70 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | MASAMBA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.151/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 26499720 | 18916500 | 45416220 | 45416220 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 71 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | PALOPO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-02 | C.TEL.152/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 79375650 | 65843860 | 145219510 | 145219510 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 72 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | PARE-PARE |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.153/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 27321460 | 32631410 | 59952870 | 59952870 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 73 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.154/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 13317160 | 10898320 | 24215480 | 24215480 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 74 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | PINRANG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.155/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 27042900 | 15934670 | 42977570 | 42977570 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 75 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | POLEWALI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.156/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 3089880 | 3691190 | 6781070 | 6781070 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 76 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | RANTEPAO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.157/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 31055720 | 19748250 | 50803970 | 50803970 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 77 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | RAPPANG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.158/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 62030 | 62030 | 62030 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 78 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | SENGKANG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.159/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 8559380 | 7743920 | 16303300 | 16303300 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 79 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | SIDRAP |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.160/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 14717300 | 8711620 | 23428920 | 23428920 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 80 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | SIWA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.161/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 248120 | 248120 | 248120 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 81 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | SOROWAKO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.162/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 16733850 | 8173370 | 24907220 | 24907220 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 82 | 01E07Y05 | 007 | 72040174 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | TANRUTEDONG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.163/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 0 | 62030 | 62030 | 62030 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 83 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.164/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 5193780 | 5639780 | 10833560 | 10833560 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 84 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | PARE-PARE | WONOMULYO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-12 | 2022-04-01 | C.TEL.165/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 7787420 | 10323020 | 18110440 | 18110440 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 92 | 01E07Y05 | 007 | 72070016 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | POSO | POSO |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-05-13 | 2022-03-31 | C.TEL.173/LG300/DR7-12800000/2022 | 2022-04-09 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 5439270 | 1082940 | 6522210 | 6522210 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 53 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | BIAK |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.134/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 16277760 | 7960560 | 24238320 | 24238320 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 54 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | FAKFAK |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.135/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 28760430 | 25132750 | 53893180 | 53893180 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 55 | 01E07Y05 | 007 | 74060078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | KAIMANA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.136/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 9150450 | 1361310 | 10511760 | 10511760 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 56 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | MANOKWARI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.137/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 4945350 | 4346310 | 9291660 | 9291660 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 57 | 01E07Y05 | 007 | 74060040 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | NABIRE |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.138/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 15639930 | 7745020 | 23384950 | 23384950 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 58 | 01E07Y05 | 007 | 74060049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | RAJA AMPAT |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.139/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 4691850 | 5357980 | 10049830 | 10049830 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 59 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | SORONG |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.140/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 216840120 | 119409760 | 336249880 | 336249880 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 60 | 01E07Y05 | 007 | 74060027 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | SORONG | TEMINABUAN |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-13 | 2022-03-31 | C.TEL.141/LG300/DR7-12800000/2022 | 2022-04-12 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 4076300 | 4350950 | 8427250 | 8427250 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 117 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | TERNATE | MOROTAI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.198/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 1775030 | 2025020 | 3800050 | 3800050 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 118 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | TERNATE | SANANA |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.199/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 862460 | 3176750 | 4039210 | 4039210 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 119 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | TERNATE | SOFIFI |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.200/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 100515600 | 51786150 | 152301750 | 152301750 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 120 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | TERNATE | TERNATE |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.201/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 97268400 | 81839630 | 179108030 | 179108030 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 121 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | TERNATE | TOBELO |  | PEKERJAAN QE RECOVERY PERIODE NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-12 | 2022-03-31 | C.TEL.202/LG300/DR7-12800000/2022 | 2022-04-23 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 42644050 | 38819440 | 81463490 | 81463490 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 20 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-02 | 2022-04-08 | 2022-04-04 | C.TEL.103/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 30273690 | 11820960 | 42094650 | 42094650 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 21 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-08 | 2022-04-04 | C.TEL.104/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 100487400 | 47432170 | 147919570 | 147919570 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 22 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.105/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 1385840 | 3129650 | 4515490 | 4515490 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 23 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-10 | 2022-04-04 | C.TEL.106/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 14562800 | 11997410 | 26560210 | 26560210 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 24 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.107/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 8699230 | 6019640 | 14718870 | 14718870 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 25 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | KIMA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.108/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 24963650 | 12480980 | 37444630 | 37444630 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 26 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | MALINO |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.109/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 5894660 | 4420950 | 10315610 | 10315610 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 27 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | MAROS |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-03-31 | 2022-04-08 | 2022-04-04 | C.TEL.110/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 34391490 | 30912220 | 65303710 | 65303710 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 28 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.111/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 84570580 | 39273750 | 123844330 | 123844330 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 29 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.112/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 110188100 | 51664670 | 161852770 | 161852770 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 30 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.113/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 136279410 | 81348870 | 217628280 | 217628280 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 31 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.114/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 8305540 | 6282120 | 14587660 | 14587660 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 32 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.115/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 156547810 | 98207110 | 254754920 | 254754920 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 33 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.116/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 92151750 | 49541530 | 141693280 | 141693280 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 34 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.117/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 47829770 | 36578270 | 84408040 | 84408040 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 35 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-04 | C.TEL.118/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 24372770 | 13111380 | 37484150 | 37484150 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022026 | 2 | 36 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001293/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 106 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulu | 2022-03-31 | 2022-05-14 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE RECOVERY PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-04 | 2022-04-09 | 2022-04-01 | C.TEL.119/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0048/LG.320/DR7-10400000/2022 | 2022-04-26 | 27105020 | 16576760 | 43681780 | 43681780 | 4500454485 |  |  |  |  | TELKOM AKSES | 2022-04-28
G2022027 | 2 | 8 | 01E07J04 | 007 | 72080075 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.001369/HK.810/R7W-7A1O0000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 3 LOP Periode Januari 2022 Area Witel Makassar - PT. MITRA CIPTA SARANA | 2022-04-01 | 2022-04-28 | HEM | UJUNGPANDANG | MALINO |  | R7 MKS MAL HEM TERAS BRI TOMBOLO |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-27 | 2022-04-01 | TEL.382/LG310/R7W-7A100000/2022 | 2022-04-25 | TEL.0001/LG.320/R7W-7A510000/2022 | 2022-04-25 | 27417961 | 4731334 | 32149295 | 32149295 | 4500454686 |  |  |  |  | MITRA CIPTASARANA | 2022-04-28
G2022027 | 2 | 6 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.001369/HK.810/R7W-7A1O0000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 3 LOP Periode Januari 2022 Area Witel Makassar - PT. MITRA CIPTA SARANA | 2022-04-01 | 2022-04-28 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM PT. AMS DAN NOVELL |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-27 | 2022-04-01 | TEL.383/LG310/R7W-7A100000/2022 | 2022-04-25 | TEL.0001/LG.320/R7W-7A510000/2022 | 2022-04-25 | 18173640 | 4861968 | 23035608 | 23035608 | 4500454686 |  |  |  |  | MITRA CIPTASARANA | 2022-04-28
G2022027 | 2 | 7 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.001369/HK.810/R7W-7A1O0000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 3 LOP Periode Januari 2022 Area Witel Makassar - PT. MITRA CIPTA SARANA | 2022-04-01 | 2022-04-28 | HEM | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP HEM PEGADAIAN SUKOWATI |  | 100 | 100 | 100 | BAST-1 | 2022-04-01 | 2022-04-27 | 2022-04-01 | TEL.384/LG310/R7W-7A100000/2022 | 2022-04-25 | TEL.0001/LG.320/R7W-7A510000/2022 | 2022-04-25 | 5610684 | 1469542 | 7080226 | 7080226 | 4500454686 |  |  |  |  | MITRA CIPTASARANA | 2022-04-28
G2022028 | 1 | 11 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAJENE |  | R7 PRE MAJ HEM UNSULBAR MAJENE |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.151/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 53726232 | 9352979 | 63079211 | 63079211 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 9 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM SMPN 2 MAKALE |  | 95 | 100 | 100 | BAST-1 | 2022-04-13 | 2022-05-24 | 2022-04-18 | TEL.152/LG.320/R7W-7D320000/2022 | 2022-05-12 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 13083516 | 2298004 | 15381520 | 15381520 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 16 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KANTOR BUPATI MAMTENG |  | 100 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-04-28 | 2022-04-18 | TEL.158/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 53254415 | 11993517 | 65247932 | 65247932 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 15 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM Lab PCR RS bhayangkara |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.157/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 11955142 | 2477838 | 14432980 | 14432980 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 14 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KANTOR BPOM |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.156/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 7144306 | 1291142 | 8435448 | 8435448 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 13 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM LANDASAN ANGKATAN LAUT |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.155/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 9707753 | 2180264 | 11888017 | 11888017 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 12 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM RSUD MAMUJU |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.154/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 12899497 | 3547291 | 16446788 | 16446788 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 6 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | MAMUJU |  | MAMUJU |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.153/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 46108437 | 12707622 | 58816059 | 58816059 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 7 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | PALOPO |  | R7 PRE PLP HEM BADAN PERTANAHAN NASIONAL |  | 100 | 100 | 100 | BAST-1 | 2022-04-13 | 2022-05-12 | 2022-04-18 | TEL.159/LG.320/R7W-7D320000/2022 | 2022-05-11 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 1715991 | 301811 | 2017802 | 2017802 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 10 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | POLEWALI |  | R7 PRE PLW HEM POLDA SULBAR (BRIMOB) |  | 95 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-05-24 | 2022-04-18 | TEL.160/LG.320/R7W-7D320000/2022 | 2022-05-10 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 25605963 | 4484433 | 30090396 | 30090396 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
G2022028 | 1 | 8 | 01E07P02 | 007 | 72040133 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.001768/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-13 | 2022-05-27 | HEM | PARE-PARE | RANTEPAO |  | R7 PRE RTP HEM SMKN 1 TORAJA UTARA |  | 95 | 100 | 100 | BAST-1 | 2022-04-13 | 2022-05-24 | 2022-04-18 | TEL.161/LG.320/R7W-7D320000/2022 | 2022-05-12 | TEL.0005/LG.320/R7W-7D100000/2022 | 2022-05-12 | 10248624 | 2427773 | 12676397 | 12676397 | 4500456968 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-25
12022096 | 0 | 15 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.001778/HK.810/OPS-10000000/2022 | SP#4 ONT Retail Dual Band Platform Fiberhome | 2022-04-13 | 2022-09-09 | ONT Retail | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 90 | 0 | Siap UT | 2022-06-01 | 2022-06-23 | 2022-06-01 |  |  |  |  | 13737500000 | 0 | 13737500000 | 0 | 4500455542 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022097 | 0 | 17 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.001779/HK.810/OPS-10000000/2022 | SP#3 NTE Platform Fiberhome | 2022-04-13 | 2022-09-09 | NTE | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-07-15 | 2022-07-01 |  |  |  |  | 900000000 | 0 | 900000000 | 0 | 4500455418 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022098 | 1 | 14 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.001780/HK.810/OPS-10000000/2022 | SP#11 Pengadaan ONT dan STB Platform ZTE - STB | 2022-04-13 | 2022-09-09 | ONT dan STB | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 95 | 100 | 100 | BAST-1 | 2022-05-18 | 2022-06-10 | 2022-06-01 | C.TEL856/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0073/LG.320/COP-F3000000/2022 | 2022-06-07 | 13715000000 | 0 | 13715000000 | 13715000000 | 4500455494 |  |  |  |  | ZTE INDONESIA | 2022-06-10
G2022029 | 4 | 10 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 JAYA ASRI |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.968/LG.310/DRT-12700000/2022 | 2022-06-18 | TEL.0097/LG.320/DR7-10400000/2022 | 2022-06-18 | 304969937 | 98465447 | 403435384 | 403435384 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-24
G2022029 | 4 | 7 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 PINTU ANGIN |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.969/LG.310/DRT-12700000/2022 | 2022-06-17 | TEL.0097/LG.320/DR7-10400000/2022 | 2022-06-18 | 201381576 | 52482348 | 253863924 | 253863924 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-24
G2022029 | 4 | 8 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 MUSI |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.970/LG.310/DRT-12700000/2022 | 2022-06-17 | TEL.0097/LG.320/DR7-10400000/2022 | 2022-06-18 | 149254710 | 35795279 | 185049989 | 185049989 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-24
G2022029 | 4 | 19 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 PASAR SENTRAL HASANUDIN |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.971/LG.310/DRT-12700000/2022 | 2022-06-18 | TEL.0097/LG.320/DR7-10400000/2022 | 2022-06-18 | 731036863 | 174981230 | 906018093 | 906018093 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-24
G2022029 | 4 | 13 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 JALAN RADIO |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.917/LG.310/DR7-12700000/2022 | 2022-05-29 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 169422758 | 44049451 | 213472209 | 213472209 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 12 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 GRAHA SIMPATI (DS 6) |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.916/LG.310/DR7-12700000/2022 | 2022-05-29 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 110683227 | 28744014 | 139427241 | 139427241 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 11 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 SP 4 (2022) |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.923/LG.310/DR7-12700000/2022 | 2022-05-31 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 782874181 | 197205579 | 980079760 | 980079760 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 15 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 KAMPUNG TIMUR GG MUMU |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.919/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 145549090 | 39509047 | 185058137 | 185058137 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 16 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 PERUM GURU JL. PENDIDIKAN |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.921/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 148172525 | 35818043 | 183990568 | 183990568 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 17 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 PERUM MARO JL. CEMARA |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.922/LG.310/DR7-12700000/2022 | 2022-05-31 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 166084659 | 42731038 | 208815697 | 208815697 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 18 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 KUPRIK (PT2) |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.920/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 29835531 | 8287989 | 38123520 | 38123520 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022029 | 4 | 14 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001820/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-1 12 LOP Area Witel Papua | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 JL. GAK OGGATMIT |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.918/LG.310/DR7-12700000/2022 | 2022-05-29 | TEL.0085/LG.320/DR7-10400000/2022 | 2022-05-31 | 175504396 | 45100136 | 220604532 | 220604532 | 4500457141 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-14
G2022030 | 2 | 6 | 01E07V01 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001821/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 2 LOP Area Witel Sulselbar | 2022-04-14 | 2022-06-12 | OSP FO FTTH PT2 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PT3 NEW DS 4ODC-PIN-FAN |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-11 | 2022-04-15 | TEL.949/LG.310/DR7-12700000/2022 | 2022-06-09 | TEL.0082/LG.320/DR7-10400000/2022 | 2022-06-09 | 443637774 | 99535841 | 543173615 | 543173615 | 4500457144 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-11
G2022030 | 2 | 7 | 01E07V01 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001821/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 2 LOP Area Witel Sulselbar | 2022-04-14 | 2022-06-12 | OSP FO FTTH PT2 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PT3 PADANG LAMPE |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-15 | TEL.950/LG.310/DR7-12700000/2022 | 2022-06-09 | TEL.0082/LG.320/DR7-10400000/2022 | 2022-06-09 | 682148489 | 153139808 | 835288297 | 835288297 | 4500457144 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-11
G2022031 | 2 | 9 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | JAILOLO |  | R7 MDO JLL PT3 CLUSTER BUKUMATITI |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.1000/LG.310/DR7-12700000/2022 | 2022-06-25 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 104755744 | 19115633 | 123871377 | 123871377 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 22 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | JAILOLO |  | R7 MDO JLL PT3 CLUSTER PRONITI |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.999/LG.310/DR7-12700000/2022 | 2022-06-25 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 146405667 | 30912322 | 177317989 | 177317989 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 29 | 01E07V01 | 007 | 73020032 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SANANA |  | R7 MDO SNN FE WAIHAMA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | 2022-04-14 |  |  |  |  | 425812083 | 98988965 | 524801048 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 10 | 01E07V01 | 007 | 73020032 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SANANA |  | R7 MDO SNN PT3 WAIHAMA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 476326346 | 90861147 | 567187493 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 8 | 01E07V01 | 007 | 73020034 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SOA SIU |  | R7 MDO SSI PT3 MOTI |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 321023290 | 74821598 | 395844888 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 25 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI PT3 CLUSTER GARAJOU |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 183431372 | 35583537 | 219014909 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 23 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI PT3 CLUSTER OBA PANTAI |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 390418921 | 69250953 | 459669874 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 28 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI FE KUSU |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 408030567 | 92604657 | 500635224 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 24 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI PT3 CLUSTER AMPERA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 191623332 | 39978173 | 231601505 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 11 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI PT3 CLUSTER KUSU |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 291191483 | 52532520 | 343724003 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 17 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 GIPSI PUNCAK |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.993/LG.310/DR7-12700000/2022 | 2022-06-23 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 99499395 | 22138733 | 121638128 | 121638128 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 14 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER SOA |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.994/LG.310/DR7-12700000/2022 | 2022-06-24 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 21436551 | 5744619 | 27181170 | 27181170 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 13 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER PERUM MALIARO |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.991/LG.310/DR7-12700000/2022 | 2022-06-23 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 64855741 | 15389063 | 80244804 | 80244804 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 12 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER PERUM JAMBULA |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.996/LG.310/DR7-12700000/2022 | 2022-06-24 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 195226656 | 42278959 | 237505615 | 237505615 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 27 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT FE FEEDER AKERICA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 321192297 | 65133164 | 386325461 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 18 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 AKEBOCA |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.992/LG.310/DR7-12700000/2022 | 2022-06-23 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 44656744 | 11862838 | 56519582 | 56519582 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 19 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER MALIARO |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.997/LG.310/DR7-12700000/2022 | 2022-06-23 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 88409286 | 23343372 | 111752658 | 111752658 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 21 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER PERUM FITU |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.995/LG.310/DR7-12700000/2022 | 2022-06-23 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 106049202 | 23043518 | 129092720 | 129092720 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022031 | 2 | 6 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER KASTELA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 314956458 | 98284603 | 413241061 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 20 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER AKERICA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 232675029 | 43057893 | 275732922 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 26 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT FE UPLINK KASTELA |  | 100 | 0 | 0 | Preparing | 2022-04-14 | 2022-06-11 | [5 empty] | 289188370 | 66135292 | 355323662 | 0 | 4500457161 |  |  |  |  | TELKOM AKSES
G2022031 | 2 | 7 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001822/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 22 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 CLUSTER PERUM NGADE |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.998/LG.310/DR7-12700000/2022 | 2022-06-24 | TEL.0102/LG.320/DR7-10400000/2022 | 2022-06-25 | 25694257 | 4838032 | 30532289 | 30532289 | 4500457161 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022032 | 2 | 41 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | AMBON | AMBON |  | PEKERJAAN QE RECOVERY PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.201/LG300/DR7-12800000/2022. | 2022-05-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 74009530 | 42445270 | 116454800 | 116454800 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 42 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | AMBON | MASOHI |  | PEKERJAAN QE RECOVERY PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.202/LG300/DR7-12800000/2022. | 2022-05-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 8780880 | 4997660 | 13778540 | 13778540 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 43 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | AMBON | NAMLEA |  | PEKERJAAN QE RECOVERY PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.203/LG300/DR7-12800000/2022. | 2022-05-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 10046560 | 5445080 | 15491640 | 15491640 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 44 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | AMBON | PASSO |  | PEKERJAAN QE RECOVERY PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.204/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 31302810 | 18879440 | 50182250 | 50182250 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 45 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | AMBON | SAUMLAKI |  | PEKERJAAN QE RECOVERY PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.205/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 3520110 | 825880 | 4345990 | 4345990 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 18 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | GORONTALO | GORONTALO |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-14 | C.TEL.178./LG300/DR7-12800000/2022 | 2022-04-25 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 59554170 | 28419180 | 87973350 | 87973350 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 19 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | GORONTALO | ISIMU |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-14 | C.TEL.179./LG300/DR7-12800000/2022 | 2022-04-25 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 32318770 | 11585470 | 43904240 | 43904240 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 20 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | GORONTALO | KWANDANG |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-14 | C.TEL.180/LG300/DR7-12800000/2022. | 2022-04-25 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 26802600 | 10915200 | 37717800 | 37717800 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 21 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | GORONTALO | LIMBOTO |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-14 | C.TEL.181/LG300/DR7-12800000/2022. | 2022-04-25 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 51972500 | 19747000 | 71719500 | 71719500 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 22 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | GORONTALO | MARISA |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-14 | C.TEL.182/LG300/DR7-12800000/2022. | 2022-04-25 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 56127170 | 41473990 | 97601160 | 97601160 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 23 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | GORONTALO | TELAGA |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-22 | 2022-04-14 | C.TEL.183/LG300/DR7-12800000/2022. | 2022-04-25 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 75105700 | 35534900 | 110640600 | 110640600 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 46 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | ABEPURA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.206/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 34174170 | 28480220 | 62654390 | 62654390 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 47 | 01E07Y05 | 007 | 74030025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | JAYAPURA A |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.207/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 21559810 | 11986960 | 33546770 | 33546770 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 48 | 01E07Y05 | 007 | 74030026 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | JAYAPURA B |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.208/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 8595580 | 4725020 | 13320600 | 13320600 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 50 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | SARMI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.210/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 39908540 | 54078420 | 93986960 | 93986960 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 51 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | SENTANI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.211/LG300/DR7-12800000/2022. | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 18082600 | 11388480 | 29471080 | 29471080 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 52 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | TIMIKA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.212/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 16934640 | 19670330 | 36604970 | 36604970 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 53 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | JAYAPURA | WAENA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.213/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 45160110 | 28473610 | 73633720 | 73633720 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 89 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | KENDARI | BAU-BAU |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-19 | 2022-04-14 | C.TEL.249/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 10858280 | 6426690 | 17284970 | 17284970 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 90 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | KENDARI | KENDARI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-19 | 2022-04-14 | C.TEL.250/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 7514330 | 2604140 | 10118470 | 10118470 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 91 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | KENDARI | KOLAKA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-19 | 2022-04-14 | C.TEL.251/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 5440440 | 5745540 | 11185980 | 11185980 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 92 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | KENDARI | MANDONGA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-19 | 2022-04-14 | C.TEL.252/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 10447860 | 6014260 | 16462120 | 16462120 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 93 | 01E07Y05 | 007 | 72050050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | KENDARI | POMALAA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-19 | 2022-04-14 | C.TEL.253/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 1513400 | 3134940 | 4648340 | 4648340 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 94 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | KENDARI | UNAAHA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-19 | 2022-04-14 | C.TEL.254/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 4195440 | 3690980 | 7886420 | 7886420 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 95 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | AIR MADIDI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.255/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 2853440 | 411470 | 3264910 | 3264910 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 96 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | BAHU |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.256/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 15922190 | 2742020 | 18664210 | 18664210 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 98 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | BITUNG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.257/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 21477720 | 3416610 | 24894330 | 24894330 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 99 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | KAUDITAN |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.258/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 4465750 | 4221350 | 8687100 | 8687100 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 100 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | KOTAMOBAGU |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.259/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 58673170 | 15751040 | 74424210 | 74424210 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 101 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | LANGOWAN |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.260/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 7595050 | 1238090 | 8833140 | 8833140 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 102 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | MANADO |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.261/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 27368650 | 25783050 | 53151700 | 53151700 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 103 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | PANIKI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.262/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 8074600 | 4452580 | 12527180 | 12527180 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 104 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANADO | TOMOHON |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.263/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 4106400 | 679140 | 4785540 | 4785540 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 56 | 01E07Y05 | 007 | 74040005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MANOKWARI | MANOKWARI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.216/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 2573510 | 1459810 | 4033320 | 4033320 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 49 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | MERAUKE | MERAUKE |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-24 | 2022-04-14 | C.TEL.209/LG300/DR7-12800000/2022 | 2022-04-22 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 11913780 | 2409320 | 14323100 | 14323100 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 78 | 01E07Y05 | 007 | 72030123 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | BANGGAI |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.238/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 0 | 124060 | 124060 | 124060 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 79 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | BUNGKU |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.239/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 14210020 | 10128630 | 24338650 | 24338650 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 80 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | DONGGALA |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.240/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 352980 | 470110 | 823090 | 823090 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 81 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | LUWUK |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.241/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 8933620 | 9795200 | 18728820 | 18728820 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 82 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | PALU A |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.242/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 16674470 | 10898160 | 27572630 | 27572630 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 83 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | PALU B |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.243/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 37189990 | 34671390 | 71861380 | 71861380 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 84 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | PARIGI |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.244/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 3055920 | 2319900 | 5375820 | 5375820 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 85 | 01E07Y05 | 007 | 72030101 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | POSO |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.245/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 3904470 | 847720 | 4752190 | 4752190 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 86 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | TAWAELI |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.246/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 352980 | 594170 | 947150 | 947150 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 88 | 01E07Y05 | 007 | 72030139 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | TENTENA |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.248/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 1889780 | 3740600 | 5630380 | 5630380 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 87 | 01E07Y05 | 007 | 72030084 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PALU | TOLI-TOLI |  | PEKERJAAN QE RECOVERY PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-01 | 2022-04-14 | C.TEL.247/LG300/DR7-12800000/2022 | 2022-04-28 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 0 | 744360 | 744360 | 744360 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 61 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | BARRU |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.221/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 5761350 | 5236930 | 10998280 | 10998280 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 62 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | ENREKANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.222/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 0 | 607280 | 607280 | 607280 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 63 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | MAJENE |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.223/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 7578070 | 5034950 | 12613020 | 12613020 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 64 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | MAKALE |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.224/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 60583220 | 42275520 | 102858740 | 102858740 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 65 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | MAMASA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.225/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 705960 | 71800 | 777760 | 777760 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 66 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | MAMUJU |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.226/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 24822000 | 29777770 | 54599770 | 54599770 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 67 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | PALOPO |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.227/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 17655730 | 18236660 | 35892390 | 35892390 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 68 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | PARE-PARE |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.228/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 17371090 | 17820650 | 35191740 | 35191740 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 69 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.229/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 0 | 1488720 | 1488720 | 1488720 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 70 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | PINRANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.230/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 4992940 | 5253540 | 10246480 | 10246480 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 71 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | POLEWALI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.231/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 1726050 | 733170 | 2459220 | 2459220 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 72 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | RANTEPAO |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.232/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 10047230 | 10158530 | 20205760 | 20205760 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 73 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | RAPPANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.233/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 0 | 124060 | 124060 | 124060 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 74 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | SENGKANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.234/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 17891670 | 12874790 | 30766460 | 30766460 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 75 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | SIDRAP |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.235/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 32420 | 1188680 | 1221100 | 1221100 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 76 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | SIWA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.236/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 352980 | 35900 | 388880 | 388880 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 77 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | PARE-PARE | WONOMULYO |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-14 | C.TEL.237/LG300/DR7-12800000/2022 | 2022-04-27 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 0 | 1073370 | 1073370 | 1073370 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 54 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | SORONG | BIAK |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.214/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 6359430 | 3342650 | 9702080 | 9702080 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 55 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | SORONG | FAKFAK |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.215/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 9569150 | 4696880 | 14266030 | 14266030 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 57 | 01E07Y05 | 007 | 74060040 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | SORONG | NABIRE |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.217/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 11861900 | 3978840 | 15840740 | 15840740 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 58 | 01E07Y05 | 007 | 74060049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | SORONG | RAJA AMPAT |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.218/LG300/DR7-12800000/2022. | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 42941440 | 24282780 | 67224220 | 67224220 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 59 | 01E07Y05 | 007 | 74060041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | SORONG | SERUI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.219/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 3288600 | 3543960 | 6832560 | 6832560 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 60 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | SORONG | SORONG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-30 | 2022-04-14 | C.TEL.220/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 66248620 | 85318230 | 151566850 | 151566850 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 106 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | TERNATE | SOFIFI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-28 | 2022-04-14 | C.TEL.264/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0065/LG.320/DR7-10400000/2022 | 2022-05-27 | 1842750 | 290540 | 2133290 | 2133290 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022032 | 2 | 24 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-15 | C.TEL.184/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 3166920 | 3072290 | 6239210 | 6239210 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 25 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.185/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 64882610 | 22948550 | 87831160 | 87831160 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 26 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.186/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 10454460 | 5453200 | 15907660 | 15907660 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 27 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.187/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 1478140 | 2414570 | 3892710 | 3892710 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 28 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.188/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 8548110 | 5111330 | 13659440 | 13659440 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 29 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | KIMA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.189/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 26386120 | 11806480 | 38192600 | 38192600 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 30 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | MALINO |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.190/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 0 | 744360 | 744360 | 744360 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 31 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | MAROS |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.191/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 24512910 | 13636180 | 38149090 | 38149090 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 32 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-15 | C.TEL.192/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 67846350 | 31906960 | 99753310 | 99753310 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 33 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-20 | 2022-04-15 | C.TEL.193/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 104893970 | 73827860 | 178721830 | 178721830 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 34 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-15 | C.TEL.194/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 22927210 | 18317480 | 41244690 | 41244690 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 35 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-15 | C.TEL.195/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 0 | 248120 | 248120 | 248120 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 36 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-15 | C.TEL.196/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 18065270 | 11374200 | 29439470 | 29439470 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 37 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-21 | 2022-04-15 | C.TEL.197/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 83919490 | 40503060 | 124422550 | 124422550 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 38 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-23 | 2022-04-15 | C.TEL.198/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 27072510 | 25065660 | 52138170 | 52138170 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 39 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-22 | 2022-04-15 | C.TEL.199/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 42412460 | 59772570 | 102185030 | 102185030 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022032 | 2 | 40 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001823/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 87 LOP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra Dan Sulut | 2022-04-14 | 2022-05-28 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE RECOVERY PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-04-22 | 2022-04-15 | C.TEL.200/LG300/DR7-12800000/2022. | 2022-05-28 | TEL.0088/LG.320/DR7-10400000/2022 | 2022-05-28 | 8104100 | 7633980 | 15738080 | 15738080 | 4500457148 |  |  |  |  | TELKOM AKSES | 2022-06-15
G2022033 | 8 | 35 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 PERUM PONDOK INDAH MAUMBI |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1022/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 91278715 | 19440052 | 110718767 | 110718767 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 34 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 CLUSTER PARK RESIDENCE |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1021/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 99260962 | 23105802 | 122366764 | 122366764 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 27 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 BELAKANG GMIM MORIA |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8014/LG.310/DR7-12700000/2022 | 2022-06-30 |  |  | 85966639 | 22284223 | 108250862 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 26 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 GMIM BETANIA KALAWAT |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8013/LG.310/DR7-12700000/2022 | 2022-06-30 |  |  | 22959713 | 4260772 | 27220485 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 10 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 LAIKIT DIMEMBE |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8012/LG.310/DR7-12700000/2022 | 2022-06-30 |  |  | 41158749 | 8324338 | 49483087 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 31 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 DE PREMIUM MATUNGKAS |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1061/LG.310/DR7-12700000/2022 | 2022-07-02 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 113094016 | 23629821 | 136723837 | 136723837 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 38 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 KOTA BEO |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8017/LG.310/DR7-12700000/2022 | 2022-06-30 |  |  | 53162375 | 11292976 | 64455351 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 15 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 TARUN |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8016/LG.310/DR7-12700000/2022 | 2022-06-30 |  |  | 524735229 | 122820674 | 647555903 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 11 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | BITUNG |  | R7 MDO BIT PT3 SAGERAT 1 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1060/LG.310/DR7-12700000/2022 | 2022-07-02 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 206793876 | 39946420 | 246740296 | 246740296 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 12 | 01E07V01 | 007 | 72010045 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | KAUDITAN |  | R7 MDO KAU PT3 SAGERAT 2 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1018/LG.310/DR7-12700000/2022 | 2022-06-27 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 111421357 | 25257845 | 136679202 | 136679202 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 6 | 01E07V01 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG PT3 FTTH PARSIAL |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8019/LG.310/DR7-12700000/2022 | 2022-07-28 |  | 2022-07-30 | 267527662 | 48329086 | 315856748 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 42 | 01E07V01 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG PT3 MOOAT PALELON |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8020/LG.310/DR7-12700000/2022 | 2022-07-28 |  | 2022-07-30 | 709400199 | 146288448 | 855688647 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 8 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN FE KAKAS KOTA DS KAWENG |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8021/LG.310/DR7-12700000/2022 | 2022-07-28 |  | 2022-07-30 | 210676014 | 69644256 | 280320270 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 40 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN PT3 TOMPASO 1 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1059/LG.310/DR7-12700000/2022 | 2022-07-04 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 564547713 | 126629316 | 691177029 | 691177029 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 39 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN FE TOMPASO 1 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1057/LG.310/DR7-12700000/2022 | 2022-07-04 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 68966048 | 31238182 | 100204230 | 100204230 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 21 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN PT3 KAKAS KOTA DS KAWENG |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8022/LG.310/DR7-12700000/2022 | 2022-07-28 |  | 2022-07-30 | 564049218 | 105017971 | 669067189 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 32 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 PAAL 4 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.869/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0075/LG.320/DR7-10400000/2022 | 2022-05-21 | 12310933 | 2281775 | 14592708 | 14592708 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022033 | 8 | 16 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 TINGKULU |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1020/LG.310/DR7-12700000/2022 | 2022-06-29 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 30707191 | 7333421 | 38040612 | 38040612 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 17 | 01E07V01 | 007 | 72010064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | MANADO BAHU |  | R7 MDO BAH PT3 GARDEN PALACE RESIDENCE |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1019/LG.310/DR7-12700000/2022 | 2022-06-29 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 126424531 | 24760097 | 151184628 | 151184628 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 33 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 PERUM CBA 2 |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8026/LG.310/DR7-12700000/2022 | 2022-07-30 |  | 2022-07-30 | 160809702 | 32190912 | 193000614 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 37 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 ODC-PIK-FAN |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.871/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0075/LG.320/DR7-10400000/2022 | 2022-05-21 | 44219478 | 12039863 | 56259341 | 56259341 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022033 | 8 | 36 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 ODC-PIK-FAM |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.870/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0075/LG.320/DR7-10400000/2022 | 2022-05-21 | 33432037 | 9396866 | 42828903 | 42828903 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-05-31
G2022033 | 8 | 18 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 TALAWAN-1 |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.8025/LG.310/DR7-12700000/2022 | 2022-07-30 |  | 2022-07-30 | 315704891 | 69337203 | 385042094 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 30 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TAHUNA |  | R7 MDO THN PT3 MALAHASA_1 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1054/LG.310/DR7-12700000/2022 | 2022-07-03 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 13139954 | 2605866 | 15745820 | 15745820 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 29 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TAHUNA |  | R7 MDO THN PT3 MALAHASA |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1056/LG.310/DR7-12700000/2022 | 2022-07-03 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 14936020 | 2954623 | 17890643 | 17890643 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 13 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TAHUNA |  | R7 MDO THN PT3 BATU LEWER |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1053/LG.310/DR7-12700000/2022 | 2022-07-02 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 184814100 | 43288597 | 228102697 | 228102697 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 28 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TAHUNA |  | R7 MDO THN PT3 PERUM PNS KOLONGAN |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1058/LG.310/DR7-12700000/2022 | 2022-07-03 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 66411330 | 12119163 | 78530493 | 78530493 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 14 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TAHUNA |  | R7 MDO THN PT3 KOMPLEX SPBU |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1055/LG.310/DR7-12700000/2022 | 2022-07-02 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 36252283 | 7260878 | 43513161 | 43513161 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 25 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TOMOHON |  | R7 MDO TMH PT3 KOLONGAN SATU |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1016/LG.310/DR7-12700000/2022 | 2022-06-27 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 68535006 | 17960380 | 86495386 | 86495386 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 24 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TOMOHON |  | R7 MDO TMH PT3 KINILOW |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1015/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 141286694 | 32887240 | 174173934 | 174173934 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 9 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TOMOHON |  | R7 MDO TMH PT3 PERUM BLESING |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1014/LG.310/DR7-12700000/2022 | 2022-06-26 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 192759420 | 37037783 | 229797203 | 229797203 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 41 | 01E07V01 | 007 | 72010110 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TOMOHON |  | R7 MDO TMH PT3 PERUM ATAS TOMOHON |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1017/LG.310/DR7-12700000/2022 | 2022-06-27 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 158778099 | 39424592 | 198202691 | 198202691 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 20 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 LININGAAN_1 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1013/LG.310/DR7-12700000/2022 | 2022-06-28 | TEL.0108/LG.320/DR7-10400000/2022 | 2022-06-29 | 283716716 | 60756805 | 344473521 | 344473521 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022033 | 8 | 19 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 SEPUTAR LAPANGAN TONDANO |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1062/LG.310/DR7-12700000/2022 | 2022-07-02 | TEL.0115/LG.320/DR7-10400000/2022 | 2022-07-04 | 127000753 | 27173597 | 154174350 | 154174350 | 4500457181 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022033 | 8 | 7 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 TANDENGAN |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1170/LG.310/DR7-12700000/2022 | 2022-07-29 |  | 2022-07-30 | 138096281 | 29214185 | 167310466 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 23 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 RANOMERUT |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1174/LG.310/DR7-12700000/2022 | 2022-07-29 |  | 2022-07-30 | 119724080 | 28998566 | 148722646 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022033 | 8 | 22 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001824/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 37 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN FE RANOMERUT |  | 100 | 95 | 0 | BAUT | 2022-04-14 | 2022-06-13 | 2022-04-14 | TEL.1175/LG.310/DR7-12700000/2022 | 2022-07-29 |  | 2022-07-30 | 42980232 | 21709036 | 64689268 | 0 | 4500457181 |  |  |  |  | TELKOM AKSES
G2022034 | 2 | 8 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001850/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 3 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-05-28 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN PT3 SIMBEL DIST 1 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-28 | 2022-04-14 | TEL.966/LG.310/DR7-12700000/2022 | 2022-06-16 | TEL.0096/LG.320/DR7-10400000/2022 | 2022-06-17 | 119241757 | 23560440 | 142802197 | 142802197 | 4500457191 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-06-24
G2022034 | 2 | 6 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001850/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 3 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-05-28 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN FE SIMBEL |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-28 | 2022-04-14 | TEL.965/LG.310/DR7-12700000/2022 | 2022-06-16 | TEL.0096/LG.320/DR7-10400000/2022 | 2022-06-17 | 100482692 | 38394515 | 138877207 | 138877207 | 4500457191 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-06-24
G2022034 | 2 | 7 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001850/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 3 LOP Tahun 2022 Area Witel Sulut Malut | 2022-04-14 | 2022-05-28 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN PT3 SIMBEL DIST 2 |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-28 | 2022-04-14 | TEL.967/LG.310/DR7-12700000/2022 | 2022-06-17 | TEL.0096/LG.320/DR7-10400000/2022 | 2022-06-17 | 271607644 | 48624443 | 320232087 | 320232087 | 4500457191 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-06-24
G2022035 | 2 | 17 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO FE LORENG_1 |  | 74 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.860/LG.310/DR7-12700000/2022 | 2022-05-19 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 130153080 | 48387820 | 178540900 | 178540900 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 16 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 TIKALA |  | 50 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.859/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 7426765 | 1827565 | 9254330 | 9254330 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 15 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 KARANGRIA |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.858/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 71538201 | 17342530 | 88880731 | 88880731 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 14 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 KAMPUNG ARAB |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.857/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 38282701 | 10885489 | 49168190 | 49168190 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 18 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 LORENG_1 |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.861/LG.310/DR7-12700000/2022 | 2022-05-19 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 142643931 | 33006927 | 175650858 | 175650858 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 19 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 BATU SAIKI |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.862/LG.310/DR7-12700000/2022 | 2022-05-19 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 142161333 | 26849088 | 169010421 | 169010421 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 20 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 SUMOMPO KAPLING |  | 50 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.863/LG.310/DR7-12700000/2022 | 2022-05-19 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 158003947 | 36149400 | 194153347 | 194153347 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 13 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 TELING BAWAH |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.856/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 58912145 | 14746656 | 73658801 | 73658801 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 12 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 KOMO LUAR |  | 50 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.855/LG.310/DR7-12700000/2022 | 2022-05-18 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 10340582 | 2838915 | 13179497 | 13179497 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 7 | 01E07V01 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH PT3 PURI WAREM |  | 95 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-23 | 2022-04-14 | TEL.852/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 252319102 | 62591509 | 314910611 | 314910611 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 8 | 01E07V01 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH PT3 PRM. GRIYA ASRI 3 |  | 70 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.853/LG.310/DR7-12700000/2022 | 2022-05-20 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 352971870 | 76471214 | 429443084 | 429443084 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 9 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 DELIMA |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.854/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 92735886 | 19159059 | 111894945 | 111894945 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 10 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 MAPANGET ANUGRAH |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.864/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 118226204 | 23973178 | 142199382 | 142199382 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022035 | 2 | 11 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001851/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 BATCH 1 14 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-27 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 RIZKY PANIKI RESIDEN |  | 60 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-27 | 2022-04-14 | TEL.865/LG.310/DR7-12700000/2022 | 2022-05-21 | TEL.0063/LG.320/DR7-10400000/2022 | 2022-05-21 | 125747647 | 23550297 | 149297944 | 149297944 | 4500457235 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-05-24
G2022036 | 2 | 8 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001852/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 4 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-12 | OSP FO FTTH PT3 2022 | TERNATE | JAILOLO |  | R7 MDO JLL PT3 CLUSTER HOKU-HOKU |  | 82 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-12 | 2022-04-14 | TEL.944/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0081/LG.320/DR7-10400000/2022 | 2022-05-30 | 152299016 | 35862493 | 188161509 | 188161509 | 4500457245 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-06-10
G2022036 | 2 | 7 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001852/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 4 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-12 | OSP FO FTTH PT3 2022 | TERNATE | JAILOLO |  | R7 MDO JLL FE ACANGO |  | 90 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-12 | 2022-04-14 | TEL.941/LG.310/DR7-12700000/2022 | 2022-05-29 | TEL.0081/LG.320/DR7-10400000/2022 | 2022-05-30 | 96638771 | 35710748 | 132349519 | 132349519 | 4500457245 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-06-10
G2022036 | 2 | 10 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001852/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 4 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-12 | OSP FO FTTH PT3 2022 | TERNATE | JAILOLO |  | R7 MDO JLL PT3 CLUSTER HATEBICARA |  | 90 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-12 | 2022-04-14 | TEL.943/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0081/LG.320/DR7-10400000/2022 | 2022-05-30 | 256320568 | 50443827 | 306764395 | 306764395 | 4500457245 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-06-10
G2022036 | 2 | 9 | 01E07V01 | 007 | 73020009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001852/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 Tahun 2022 4 LOP Area Witel Sulut Malut | 2022-04-14 | 2022-06-12 | OSP FO FTTH PT3 2022 | TERNATE | JAILOLO |  | R7 MDO JLL PT3 CLUSTER ACANGO |  | 90 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-12 | 2022-04-14 | TEL.942/LG.310/DR7-12700000/2022 | 2022-05-29 | TEL.0081/LG.320/DR7-10400000/2022 | 2022-05-30 | 71803707 | 16767820 | 88571527 | 88571527 | 4500457245 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-06-10
G2022037 | 2 | 12 | 01E07V01 | 007 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MAJENE |  | R7 PRE MAJ PT3 ODC POLE MAJENE |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-05-30 | 2022-04-14 | TEL.899/LG.310/DR7-12700000/2022 | 2022-06-12 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 545234197 | 89728206 | 634962403 | 634962403 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 8 | 01E07V01 | 007 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK PT3 POROS MAKALE-RTP |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-05 | 2022-04-14 | TEL.891/LG.310/DR7-12700000/2022 | 2022-06-12 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 1244759771 | 253754977 | 1498514748 | 1498514748 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 16 | 01E07V01 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT3 BTN MASEGENA |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-07 | 2022-04-14 | TEL.896/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 38628277 | 6954867 | 45583144 | 45583144 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 10 | 01E07V01 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT3 TOPOYO |  | 100 | 100 | 100 | BAST-1 | 2022-04-15 | 2022-06-08 | 2022-04-14 | TEL.894/LG.310/DR7-12700000/2022 | 2022-06-12 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 211617178 | 42991993 | 254609171 | 254609171 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 7 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS PT3 ODC-MAS-FAK (PERUM NANAK) |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-07 | 2022-04-14 | TEL.888/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 163245784 | 33238691 | 196484475 | 196484475 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 14 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS PT3 SABBANG (DISTRIBUSI) |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-09 | 2022-04-14 | TEL.890/LG.310/DR7-12700000/2022 | 2022-06-12 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 541928292 | 108233581 | 650161873 | 650161873 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 13 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS PT3 ODC-MAS-FAL |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.889/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 718417675 | 128216876 | 846634551 | 846634551 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 17 | 01E07V01 | 007 | 72040094 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS PT3 TANALILI (DISTRIBUSI) |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-08 | 2022-04-14 | TEL.897/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 778768925 | 137756086 | 916525011 | 916525011 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 15 | 01E07V01 | 007 | 72040119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | PASANG KAYU |  | R7 PRE PKA PT3 PERUM PT.LETAWA |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.892/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 123778945 | 29757751 | 153536696 | 153536696 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 6 | 01E07V01 | 007 | 72040119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | PASANG KAYU |  | R7 PRE PKA PT3 ODC-PKA-FC TSL |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-10 | 2022-04-14 | TEL.887/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 470564479 | 85178475 | 555742954 | 555742954 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 11 | 01E07V01 | 007 | 72040135 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | RAPPANG |  | R7 PRE RPN PT3 RAPPANG |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.895/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 164855291 | 40324489 | 205179780 | 205179780 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022037 | 2 | 9 | 01E07V01 | 007 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001870/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 12 LOP Area Witel Sulselbar | 2022-04-14 | 2022-07-12 | OSP FO FTTH PT3 2022 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT3 MAROANGIN |  | 100 | 100 | 100 | BAST-1 | 2022-04-14 | 2022-06-11 | 2022-04-14 | TEL.893/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0093/LG.320/DR7-10400000/2022 | 2022-06-13 | 509570074 | 104347285 | 613917359 | 613917359 | 4500457347 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022038 | 1 | 7 | 01E07P12 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.001900/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-18 | 2022-06-01 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM PKM RUJAB CAMAT BURAU |  | 100 | 100 | 100 | BAST-1 | 2022-04-18 | 2022-05-16 | 2022-05-22 | TEL.194/LG.320/R7W-7D100000/2022 | 2022-05-25 | TEL.0006/LG.320/R7W-7D100000/2022 | 2022-05-25 | 225260093 | 61764537 | 287024630 | 287024630 | 4500457448 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-02
G2022038 | 1 | 9 | 01E07P12 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.001900/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-18 | 2022-06-01 | HEM | PARE-PARE | MASAMBA |  | R7 PRE MAS HEM BPP MANGKUTANA |  | 100 | 100 | 100 | BAST-1 | 2022-04-18 | 2022-05-02 | 2022-05-22 | TEL.193/LG.320/R7W-7D100000/2022 | 2022-05-25 | TEL.0006/LG.320/R7W-7D100000/2022 | 2022-05-25 | 59282388 | 12072624 | 71355012 | 71355012 | 4500457448 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-02
G2022038 | 1 | 6 | 01E07P12 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.001900/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-18 | 2022-06-01 | HEM | PARE-PARE | SOROWAKO |  | R7 PRE SRK HEM BPP_ RUJAB CAMAT WASUPONDO |  | 100 | 100 | 100 | BAST-1 | 2022-04-18 | 2022-05-05 | 2022-05-22 | TEL.191/LG.320/R7W-7D100000/2022 | 2022-05-25 | TEL.0006/LG.320/R7W-7D100000/2022 | 2022-05-25 | 53007010 | 10000311 | 63007321 | 63007321 | 4500457448 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-02
G2022038 | 1 | 8 | 01E07P12 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.001900/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-18 | 2022-06-01 | HEM | PARE-PARE | SOROWAKO |  | R7 PRE SRK HEM TOWUTI |  | 100 | 100 | 100 | BAST-1 | 2022-04-18 | 2022-05-07 | 2022-05-22 | TEL.192/LG.320/R7W-7D100000/2022 | 2022-05-25 | TEL.0006/LG.320/R7W-7D100000/2022 | 2022-05-25 | 141886499 | 34885906 | 176772405 | 176772405 | 4500457448 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-02
G2022039 | 2 | 20 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | AMBON | AMBON |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-20 | C.TEL.274/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 15508840 | 6136170 | 21645010 | 21645010 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 21 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | AMBON | PASSO |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-20 | C.TEL.275/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 18178170 | 9173070 | 27351240 | 27351240 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 23 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | JAYAPURA | ABEPURA |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.276/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 66239850 | 36017480 | 102257330 | 102257330 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 22 | 01E07Y05 | 007 | 74030025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | JAYAPURA | JAYAPURA A |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.277/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 26767470 | 32426210 | 59193680 | 59193680 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 32 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | KENDARI | KENDARI |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.286/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 0 | 18389280 | 18389280 | 18389280 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 33 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MANADO | BAHU |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.287/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 61138130 | 45335620 | 106473750 | 106473750 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 34 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MANADO | BITUNG |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.288/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 216850480 | 107399770 | 324250250 | 324250250 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 35 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MANADO | KOTAMOBAGU |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.289/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 21672320 | 11315820 | 32988140 | 32988140 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 36 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MANADO | LANGOWAN |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.290/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 428550090 | 173367340 | 601917430 | 601917430 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 37 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MANADO | MANADO |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.291/LG300/DR7-12800000/2022. | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 41335550 | 27937580 | 69273130 | 69273130 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 39 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MANADO | TOMOHON |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.292/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 322764580 | 111415140 | 434179720 | 434179720 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 24 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | MERAUKE | MERAUKE |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.278/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 14465500 | 2954670 | 17420170 | 17420170 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 30 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | PARE-PARE | ENREKANG |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-19 | C.TEL.284/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 64650 | 10667260 | 10731910 | 10731910 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 31 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | PARE-PARE | MAMUJU |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-19 | C.TEL.285/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 7217550 | 15872030 | 23089580 | 23089580 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 28 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | PARE-PARE | PALOPO |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-19 | C.TEL.282/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 18440380 | 7427040 | 25867420 | 25867420 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 27 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | PARE-PARE | RANTEPAO |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-19 | C.TEL.281/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 38486670 | 28085060 | 66571730 | 66571730 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 29 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE RELOKASI PERIODE NOV-DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-19 | C.TEL.283/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 51720 | 10665610 | 10717330 | 10717330 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 26 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | SORONG | BIAK |  | PEKERJAAN QE RELOKASI PERIODE DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-19 | C.TEL.280/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 0 | 938670 | 938670 | 938670 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 25 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | SORONG | SORONG |  | PEKERJAAN QE RELOKASI PERIODE DES 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-19 | C.TEL.279/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 0 | 938670 | 938670 | 938670 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 40 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | TERNATE | TERNATE |  | PEKERJAAN QE RELOKASI PERIODE NOV 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.293/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0066/LG.320/DR7-10400000/2022 | 2022-05-18 | 52570310 | 13222930 | 65793240 | 65793240 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022039 | 2 | 12 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-21 | C.TEL.266/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 5633790 | 0 | 5633790 | 5633790 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 13 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | KIMA |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-21 | C.TEL.267/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 1877930 | 0 | 1877930 | 1877930 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 14 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | MAROS |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-26 | 2022-04-22 | C.TEL.268/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 7511720 | 0 | 7511720 | 7511720 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 15 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-21 | C.TEL.269/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 11267580 | 0 | 11267580 | 11267580 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 16 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-21 | C.TEL.270/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 9389650 | 0 | 9389650 | 9389650 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 17 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-21 | C.TEL.271/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 3755860 | 0 | 3755860 | 3755860 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 18 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-21 | C.TEL.272/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 15023440 | 0 | 15023440 | 15023440 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022039 | 2 | 19 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001955/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Relokasi Utilitas 28 LOP Witel Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE RELOKASI | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE RELOKASI PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-21 | C.TEL.273/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0078/LG.320/DR7-10400000/2022 | 2022-05-28 | 9259970 | 0 | 9259970 | 9259970 | 4500457628 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022040 | 2 | 6 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001956/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Januari 2022 Area Witel Gorontalo | 2022-04-19 | 2022-05-18 | HEM | GORONTALO | GORONTALO |  | R7 GTO GTL HEM POLTEKES KEMENKES |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | TEL.840/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0062/LG.320/DR7-10400000/2022 | 2022-05-11 | 44368987 | 11091022 | 55460009 | 55460009 | 4500457585 |  |  |  |  | TELKOM AKSES | 2022-05-21
G2022040 | 2 | 7 | 01E07V06 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001956/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Januari 2022 Area Witel Gorontalo | 2022-04-19 | 2022-05-18 | HEM | GORONTALO | KWANDANG |  | R7 GTO KWD HEM WILKER KKP KELAS 3 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | TEL.841/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0062/LG.320/DR7-10400000/2022 | 2022-05-11 | 44640043 | 12523159 | 57163202 | 57163202 | 4500457585 |  |  |  |  | TELKOM AKSES | 2022-05-21
G2022040 | 2 | 8 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001956/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Januari 2022 Area Witel Gorontalo | 2022-04-19 | 2022-05-18 | HEM | GORONTALO | MARISA |  | R7 GTO MRS HEM POHON CINTA |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | TEL.842/LG.310/DR7-12700000/2022 | 2022-05-11 | TEL.0062/LG.320/DR7-10400000/2022 | 2022-05-11 | 57991058 | 11126452 | 69117510 | 69117510 | 4500457585 |  |  |  |  | TELKOM AKSES | 2022-05-21
G2022041 | 1 | 38 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | AMBON |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.318/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 124335450 | 0 | 124335450 | 124335450 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 40 | 01E07Y05 | 007 | 73010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | BANDA NEIRA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.320/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 566800 | 0 | 566800 | 566800 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 39 | 01E07Y05 | 007 | 73010013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | BULA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.319/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 11049040 | 0 | 11049040 | 11049040 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 41 | 01E07Y05 | 007 | 73010120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | DOBO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.321/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 7430840 | 0 | 7430840 | 7430840 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 42 | 01E07Y05 | 007 | 73010125 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | LARAT |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.322/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1131160 | 0 | 1131160 | 1131160 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 43 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | MASOHI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.323/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 24121860 | 0 | 24121860 | 24121860 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 44 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | NAMLEA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.324/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 11652200 | 0 | 11652200 | 11652200 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 45 | 01E07Y05 | 007 | 73010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | NAMROLE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.325/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2665960 | 0 | 2665960 | 2665960 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 46 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | PASSO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.326/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 58672880 | 0 | 58672880 | 58672880 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 47 | 01E07Y05 | 007 | 73010059 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | PIRU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.327/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 5803240 | 0 | 5803240 | 5803240 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 48 | 01E07Y05 | 007 | 73010071 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | SAPARUA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.328/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 189840 | 0 | 189840 | 189840 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 49 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | SAUMLAKI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.329/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 6633840 | 0 | 6633840 | 6633840 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 50 | 01E07Y05 | 007 | 73010172 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | TIAKUR |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.330/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 4382920 | 0 | 4382920 | 4382920 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 51 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | TUAL |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.331/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 23293000 | 0 | 23293000 | 23293000 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 52 | 01E07Y05 | 007 | 73010089 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | WAHAI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.332/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1304320 | 0 | 1304320 | 1304320 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 14 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | GORONTALO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.294/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 71132250 | 0 | 71132250 | 71132250 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 15 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | ISIMU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.295/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 20534820 | 0 | 20534820 | 20534820 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 16 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | KWANDANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.296/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 4368720 | 0 | 4368720 | 4368720 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 17 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | LIMBOTO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.297/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 20449650 | 0 | 20449650 | 20449650 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 18 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | MARISA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.298/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 14374740 | 0 | 14374740 | 14374740 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 19 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | TELAGA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.299/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 17794200 | 0 | 17794200 | 17794200 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 53 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | ABEPURA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.333/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 36683130 | 0 | 36683130 | 36683130 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 54 | 01E07Y05 | 007 | 74030025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | JAYAPURA A |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.334/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 19623190 | 0 | 19623190 | 19623190 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 55 | 01E07Y05 | 007 | 74030026 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | JAYAPURA B |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.335/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 6434960 | 0 | 6434960 | 6434960 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 56 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.336/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 531760 | 0 | 531760 | 531760 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 58 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | SARMI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.338/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2331070 | 0 | 2331070 | 2331070 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 59 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | SENTANI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.339/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 20002690 | 0 | 20002690 | 20002690 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 62 | 01E07Y05 | 007 | 74030067 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | TEMBAGAPURA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.342/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 86630 | 0 | 86630 | 86630 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 60 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | TIMIKA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.340/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 13640060 | 0 | 13640060 | 13640060 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 61 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | WAENA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.341/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 10861160 | 0 | 10861160 | 10861160 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 104 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | BAU-BAU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.384/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 56148370 | 0 | 56148370 | 56148370 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 105 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | KENDARI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.385/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 102307870 | 0 | 102307870 | 102307870 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 106 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | KOLAKA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.386/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 13740810 | 0 | 13740810 | 13740810 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 107 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | LASUSUA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.387/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 8724380 | 0 | 8724380 | 8724380 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 108 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | MANDONGA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.388/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 147271290 | 0 | 147271290 | 147271290 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 109 | 01E07Y05 | 007 | 72050050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | POMALAA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.389/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 5411720 | 0 | 5411720 | 5411720 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 110 | 01E07Y05 | 007 | 72050057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | RAHA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.390/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 3711700 | 0 | 3711700 | 3711700 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 111 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | UNAAHA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.391/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 8316310 | 0 | 8316310 | 8316310 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 113 | 01E07Y05 | 007 | 72050074 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | WANCI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.392/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2947600 | 0 | 2947600 | 2947600 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 114 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | AIR MADIDI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.393/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 74159100 | 0 | 74159100 | 74159100 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 115 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | AMURANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.394/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 11526900 | 0 | 11526900 | 11526900 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 116 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BAHU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.395/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 80721180 | 0 | 80721180 | 80721180 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 117 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BITUNG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.396/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 80775900 | 0 | 80775900 | 80775900 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 118 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BOROKO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.397/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1940400 | 0 | 1940400 | 1940400 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 119 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | KAUDITAN |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.398/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 3596400 | 0 | 3596400 | 3596400 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 120 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | KOTAMOBAGU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.399/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 37179250 | 0 | 37179250 | 37179250 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 121 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | LANGOWAN |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.400/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 23293500 | 0 | 23293500 | 23293500 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 122 | 01E07Y05 | 007 | 72010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | LOLAK |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.401/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2827200 | 0 | 2827200 | 2827200 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 124 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | MANADO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.403/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 91421400 | 0 | 91421400 | 91421400 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 123 | 01E07Y05 | 007 | 72010077 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | MOLIBAGU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.402/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 320400 | 0 | 320400 | 320400 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 125 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | PANIKI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.404/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 21152700 | 0 | 21152700 | 21152700 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 126 | 01E07Y05 | 007 | 72010248 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TAGULANDANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.405/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 712800 | 0 | 712800 | 712800 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 127 | 01E07Y05 | 007 | 72010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TAHUNA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.406/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2954700 | 0 | 2954700 | 2954700 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 128 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TOMOHON |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.407/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 22845600 | 0 | 22845600 | 22845600 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 129 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TONDANO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.408/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 33360060 | 0 | 33360060 | 33360060 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 130 | 01E07Y05 | 007 | 72010283 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TUTUYAN |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.409/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 3106500 | 0 | 3106500 | 3106500 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 57 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MERAUKE | MERAUKE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.337/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 39443070 | 0 | 39443070 | 39443070 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 91 | 01E07Y05 | 007 | 72030159 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | AMPANA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.371/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 850760 | 0 | 850760 | 850760 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 92 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | BUNGKU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.372/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 6294630 | 0 | 6294630 | 6294630 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 93 | 01E07Y05 | 007 | 72030013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | BUOL |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.373/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 3149870 | 0 | 3149870 | 3149870 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 94 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | DONGGALA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.374/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2802840 | 0 | 2802840 | 2802840 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 95 | 01E07Y05 | 007 | 72030099 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | KOTARAYA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.375/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1994150 | 0 | 1994150 | 1994150 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 96 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | LUWUK |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | .C.TEL.376/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 28490590 | 0 | 28490590 | 28490590 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 97 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | PALU A |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.377/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 26681640 | 0 | 26681640 | 26681640 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 98 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | PALU B |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.378/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 45970760 | 0 | 45970760 | 45970760 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 99 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | PARIGI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.379/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 4805790 | 0 | 4805790 | 4805790 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 100 | 01E07Y05 | 007 | 72030101 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | POSO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.380/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 6062150 | 0 | 6062150 | 6062150 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 101 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | TAWAELI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.381/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 606840 | 0 | 606840 | 606840 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 102 | 01E07Y05 | 007 | 72030083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | TOLAY |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.382/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 850760 | 0 | 850760 | 850760 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 103 | 01E07Y05 | 007 | 72030084 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PALU | TOLI-TOLI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-03 | 2022-04-19 | C.TEL.383/LG300/DR7-12800000/2022 | 2022-04-29 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 610870 | 0 | 610870 | 610870 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 67 | 01E07Y05 | 007 | 72040275 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | AJANGALE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.347/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 541650 | 0 | 541650 | 541650 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 68 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | BARRU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.348/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 22309290 | 0 | 22309290 | 22309290 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 69 | 01E07Y05 | 007 | 72040044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | CANGADI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.349/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1392410 | 0 | 1392410 | 1392410 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 70 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | ENREKANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.350/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 14639500 | 0 | 14639500 | 14639500 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 71 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAJENE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.351/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 12835240 | 0 | 12835240 | 12835240 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 72 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAKALE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.352/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 32520220 | 0 | 32520220 | 32520220 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 73 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MALILI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.353/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1035010 | 0 | 1035010 | 1035010 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 74 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAMASA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.354/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 844000 | 0 | 844000 | 844000 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 75 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAMUJU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.355/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 121054000 | 0 | 121054000 | 121054000 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 76 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MASAMBA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.356/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 43650440 | 0 | 43650440 | 43650440 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 77 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PALOPO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.357/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 89079760 | 0 | 89079760 | 89079760 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 78 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PARE-PARE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.358/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 106633010 | 0 | 106633010 | 106633010 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 79 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.359/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 4915600 | 0 | 4915600 | 4915600 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 80 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PINRANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.360/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 49133310 | 0 | 49133310 | 49133310 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 81 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | POLEWALI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.361/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 8722740 | 0 | 8722740 | 8722740 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 82 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | RANTEPAO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.362/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 49564770 | 0 | 49564770 | 49564770 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 83 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | RAPPANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.363/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 10925830 | 0 | 10925830 | 10925830 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 84 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SENGKANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.364/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 44371860 | 0 | 44371860 | 44371860 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 85 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SIDRAP |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-28 | 2022-04-20 | C.TEL.365/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 14655900 | 0 | 14655900 | 14655900 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 86 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SIWA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.366/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 461760 | 0 | 461760 | 461760 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 87 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SOROWAKO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.367/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 6141180 | 0 | 6141180 | 6141180 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 88 | 01E07Y05 | 007 | 72040174 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | TANRUTEDONG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.368/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 7522070 | 0 | 7522070 | 7522070 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 89 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.369/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2437340 | 0 | 2437340 | 2437340 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 90 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | WONOMULYO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.370/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 27156180 | 0 | 27156180 | 27156180 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 63 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | BIAK |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.343/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 19194260 | 0 | 19194260 | 19194260 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 64 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | FAKFAK |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.344/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 79327860 | 0 | 79327860 | 79327860 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 65 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | MANOKWARI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.345/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 30615930 | 0 | 30615930 | 30615930 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 66 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | SORONG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.346/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 165395070 | 0 | 165395070 | 165395070 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 131 | 01E07Y05 | 007 | 73020005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | GALELA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.410/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 2419260 | 0 | 2419260 | 2419260 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 132 | 01E07Y05 | 007 | 73020009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | JAILOLO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.411/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 7237260 | 0 | 7237260 | 7237260 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 133 | 01E07Y05 | 007 | 73020013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | LABUHA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.412/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 27869040 | 0 | 27869040 | 27869040 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 134 | 01E07Y05 | 007 | 73020057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | MANGOLE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.413/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1983000 | 0 | 1983000 | 1983000 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 135 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | MOROTAI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.414/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 5289080 | 0 | 5289080 | 5289080 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 136 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | SANANA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.415/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 6306200 | 0 | 6306200 | 6306200 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 137 | 01E07Y05 | 007 | 73020034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | SOA SIU |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.416/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 605400 | 0 | 605400 | 605400 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 138 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | SOFIFI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.417/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 37256200 | 0 | 37256200 | 37256200 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 139 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | TERNATE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.418/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 181300070 | 0 | 181300070 | 181300070 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 140 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | TOBELO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.419/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 33270080 | 0 | 33270080 | 33270080 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 20 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.300/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 43535630 | 0 | 43535630 | 43535630 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 21 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.301/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 72039750 | 0 | 72039750 | 72039750 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 22 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.302/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 29391040 | 0 | 29391040 | 29391040 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 23 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.303/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 34261170 | 0 | 34261170 | 34261170 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 24 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.304/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 17532020 | 0 | 17532020 | 17532020 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 25 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | KIMA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.305/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 5950720 | 0 | 5950720 | 5950720 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 26 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | MALINO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.306/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 1805690 | 0 | 1805690 | 1805690 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 27 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | MAROS |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.307/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 16381860 | 0 | 16381860 | 16381860 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 28 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.308/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 77486010 | 0 | 77486010 | 77486010 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 29 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.309/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 132288000 | 0 | 132288000 | 132288000 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 30 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.310/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 17729890 | 0 | 17729890 | 17729890 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 31 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.311/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 28892960 | 0 | 28892960 | 28892960 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 32 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.312/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 21832590 | 0 | 21832590 | 21832590 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 33 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.313/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 35054090 | 0 | 35054090 | 35054090 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 34 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.314/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 123283520 | 0 | 123283520 | 123283520 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 35 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-27 | 2022-04-22 | C.TEL.315/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 50318890 | 0 | 50318890 | 50318890 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 36 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.316/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 30107090 | 0 | 30107090 | 30107090 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022041 | 1 | 37 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001957/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 126 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.317/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0067/LG.320/DR7-10400000/2022 | 2022-05-23 | 53127560 | 0 | 53127560 | 53127560 | 4500457583 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 41 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | AMBON |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.444/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 332523260 | 0 | 332523260 | 332523260 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 43 | 01E07Y05 | 007 | 73010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | BANDA NEIRA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.446/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1015360 | 0 | 1015360 | 1015360 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 42 | 01E07Y05 | 007 | 73010013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | BULA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.445/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 11433800 | 0 | 11433800 | 11433800 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 44 | 01E07Y05 | 007 | 73010120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | DOBO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.447/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 27042560 | 0 | 27042560 | 27042560 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 45 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | MASOHI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.448/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 78117400 | 0 | 78117400 | 78117400 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 46 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | NAMLEA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.449/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 31162000 | 0 | 31162000 | 31162000 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 47 | 01E07Y05 | 007 | 73010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | NAMROLE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.450/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2401640 | 0 | 2401640 | 2401640 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 48 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | PASSO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.451/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 154533110 | 0 | 154533110 | 154533110 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 49 | 01E07Y05 | 007 | 73010059 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | PIRU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.452/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 5560840 | 0 | 5560840 | 5560840 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 50 | 01E07Y05 | 007 | 73010071 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | SAPARUA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.453/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1140320 | 0 | 1140320 | 1140320 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 51 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | SAUMLAKI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.454/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 33842560 | 0 | 33842560 | 33842560 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 53 | 01E07Y05 | 007 | 73010172 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | TIAKUR |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.455/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 4425400 | 0 | 4425400 | 4425400 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 54 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | TUAL |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.456/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 81235720 | 0 | 81235720 | 81235720 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 55 | 01E07Y05 | 007 | 73010089 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | AMBON | WAHAI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-30 | 2022-04-20 | C.TEL.457/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1181520 | 0 | 1181520 | 1181520 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 13 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | GORONTALO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.420/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 110499840 | 0 | 110499840 | 110499840 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 14 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | ISIMU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.421/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 14901720 | 0 | 14901720 | 14901720 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 15 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | KWANDANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.422/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 3739320 | 0 | 3739320 | 3739320 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 16 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | LIMBOTO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.423/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 19525080 | 0 | 19525080 | 19525080 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 17 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | MARISA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.424/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 19303680 | 0 | 19303680 | 19303680 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 18 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | GORONTALO | TELAGA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-15 | 2022-04-19 | C.TEL.425/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 19775130 | 0 | 19775130 | 19775130 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 56 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | ABEPURA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.458/LG300/DR7-12800000/2022. | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 25760130 | 0 | 25760130 | 25760130 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 59 | 01E07Y05 | 007 | 74030025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | JAYAPURA A |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.459/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 12009600 | 0 | 12009600 | 12009600 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 58 | 01E07Y05 | 007 | 74030026 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | JAYAPURA B |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.460/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 5172170 | 0 | 5172170 | 5172170 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 60 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.461/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 24700 | 0 | 24700 | 24700 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 62 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | SARMI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.463/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2086570 | 0 | 2086570 | 2086570 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 63 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | SENTANI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.464/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 16461080 | 0 | 16461080 | 16461080 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 65 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | TIMIKA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.465/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 17568350 | 0 | 17568350 | 17568350 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 66 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | JAYAPURA | WAENA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.466/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 13710060 | 0 | 13710060 | 13710060 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 95 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | BAU-BAU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.495/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 49459180 | 0 | 49459180 | 49459180 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 96 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | KENDARI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.496/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 82500610 | 0 | 82500610 | 82500610 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 97 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | KOLAKA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.497/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 14194690 | 0 | 14194690 | 14194690 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 98 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | LASUSUA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.498/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 7221910 | 0 | 7221910 | 7221910 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 99 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | MANDONGA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.499/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 128423200 | 0 | 128423200 | 128423200 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 100 | 01E07Y05 | 007 | 72050050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | POMALAA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.500/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 7737090 | 0 | 7737090 | 7737090 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 101 | 01E07Y05 | 007 | 72050057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | RAHA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.501/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1477760 | 0 | 1477760 | 1477760 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 102 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | UNAAHA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.502/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 11609080 | 0 | 11609080 | 11609080 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 103 | 01E07Y05 | 007 | 72050074 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | KENDARI | WANCI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.503/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2065000 | 0 | 2065000 | 2065000 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 104 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | AIR MADIDI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.504/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 77005200 | 0 | 77005200 | 77005200 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 105 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | AMURANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.505/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 7067100 | 0 | 7067100 | 7067100 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 106 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BAHU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.506/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 64201200 | 0 | 64201200 | 64201200 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 107 | 01E07Y05 | 007 | 72010258 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BEO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.507/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1730700 | 0 | 1730700 | 1730700 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 108 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BITUNG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.508/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 74191500 | 0 | 74191500 | 74191500 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 109 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | BOROKO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.509/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 5127600 | 0 | 5127600 | 5127600 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 110 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | KAUDITAN |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.510/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 7981500 | 0 | 7981500 | 7981500 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 111 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | KOTAMOBAGU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.511/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 40064100 | 0 | 40064100 | 40064100 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 112 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | LANGOWAN |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.512/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 17792700 | 0 | 17792700 | 17792700 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 113 | 01E07Y05 | 007 | 72010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | LOLAK |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.513/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 950400 | 0 | 950400 | 950400 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 114 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | MANADO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.514/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 114753100 | 0 | 114753100 | 114753100 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 115 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | PANIKI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.515/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 25604700 | 0 | 25604700 | 25604700 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 116 | 01E07Y05 | 007 | 72010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TAHUNA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.516/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 3387600 | 0 | 3387600 | 3387600 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 117 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TOMOHON |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.517/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 28243500 | 0 | 28243500 | 28243500 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 118 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TONDANO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.518/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 23020200 | 0 | 23020200 | 23020200 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 119 | 01E07Y05 | 007 | 72010283 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MANADO | TUTUYAN |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.519/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 7266600 | 0 | 7266600 | 7266600 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 61 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | MERAUKE | MERAUKE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.462/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 60550610 | 0 | 60550610 | 60550610 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 71 | 01E07Y05 | 007 | 72040275 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | AJANGALE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.471/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1671390 | 0 | 1671390 | 1671390 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 72 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | BARRU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.472/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 18061290 | 0 | 18061290 | 18061290 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 73 | 01E07Y05 | 007 | 72040044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | CANGADI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.473/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1273240 | 0 | 1273240 | 1273240 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 74 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | ENREKANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.474/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 12256760 | 0 | 12256760 | 12256760 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 75 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAJENE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.475/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 19289560 | 0 | 19289560 | 19289560 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 76 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAKALE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.476/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 19435430 | 0 | 19435430 | 19435430 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 77 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MALILI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.477/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2027100 | 0 | 2027100 | 2027100 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 78 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAMASA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.478/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2717240 | 0 | 2717240 | 2717240 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 79 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MAMUJU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.479/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 147299790 | 0 | 147299790 | 147299790 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 80 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | MASAMBA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.480/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 45266690 | 0 | 45266690 | 45266690 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 81 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PALOPO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.481/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 77994020 | 0 | 77994020 | 77994020 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 82 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PARE-PARE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.482/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 78036700 | 0 | 78036700 | 78036700 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 83 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.483/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2650020 | 0 | 2650020 | 2650020 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 84 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | PINRANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.484/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 47675740 | 0 | 47675740 | 47675740 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 85 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | POLEWALI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.485/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 8140160 | 0 | 8140160 | 8140160 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 86 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | RANTEPAO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.486/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 24355730 | 0 | 24355730 | 24355730 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 87 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | RAPPANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.487/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 12613120 | 0 | 12613120 | 12613120 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 88 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SENGKANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.488/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 31277010 | 0 | 31277010 | 31277010 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 89 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SIDRAP |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.489/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 13055520 | 0 | 13055520 | 13055520 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 90 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SIWA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.490/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 5489090 | 0 | 5489090 | 5489090 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 91 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | SOROWAKO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.491/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 20312810 | 0 | 20312810 | 20312810 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 92 | 01E07Y05 | 007 | 72040174 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | TANRUTEDONG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.492/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 8553430 | 0 | 8553430 | 8553430 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 93 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.493/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1420000 | 0 | 1420000 | 1420000 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 94 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | PARE-PARE | WONOMULYO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-29 | 2022-04-20 | C.TEL.494/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 17192400 | 0 | 17192400 | 17192400 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 67 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | BIAK |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.467/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 26187910 | 0 | 26187910 | 26187910 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 68 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | FAKFAK |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.468/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 31686760 | 0 | 31686760 | 31686760 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 69 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | MANOKWARI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.469/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 69219350 | 0 | 69219350 | 69219350 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 70 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | SORONG | SORONG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.470/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 85897890 | 0 | 85897890 | 85897890 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 120 | 01E07Y05 | 007 | 73020005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | GALELA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.520/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2565240 | 0 | 2565240 | 2565240 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 121 | 01E07Y05 | 007 | 73020009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | JAILOLO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.521/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 2493320 | 0 | 2493320 | 2493320 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 122 | 01E07Y05 | 007 | 73020013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | LABUHA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.522/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 24868380 | 0 | 24868380 | 24868380 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 123 | 01E07Y05 | 007 | 73020057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | MANGOLE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.523/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1426540 | 0 | 1426540 | 1426540 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 124 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | MOROTAI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.524/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 5716240 | 0 | 5716240 | 5716240 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 125 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | SANANA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.525/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 4792780 | 0 | 4792780 | 4792780 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 126 | 01E07Y05 | 007 | 73020034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | SOA SIU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.526/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 1790380 | 0 | 1790380 | 1790380 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 127 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | SOFIFI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.527/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 30927160 | 0 | 30927160 | 30927160 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 128 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | TERNATE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.528/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 121756700 | 0 | 121756700 | 121756700 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 129 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | TERNATE | TOBELO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.529/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0068/LG.320/DR7-10400000/2022 | 2022-05-18 | 28262460 | 0 | 28262460 | 28262460 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022042 | 2 | 19 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.426/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 31095280 | 0 | 31095280 | 31095280 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 20 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.427/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 50098820 | 0 | 50098820 | 50098820 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 23 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.428/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 119388320 | 0 | 119388320 | 119388320 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 24 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.429/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 4665730 | 0 | 4665730 | 4665730 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 25 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.430/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 7280510 | 0 | 7280510 | 7280510 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 26 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | KIMA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.431/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 4436350 | 0 | 4436350 | 4436350 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 28 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | MALINO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.432/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 2252040 | 0 | 2252040 | 2252040 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 29 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | MAROS |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-26 | 2022-04-22 | C.TEL.433/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 9025650 | 0 | 9025650 | 9025650 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 30 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-27 | 2022-04-22 | C.TEL.434/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 79134440 | 0 | 79134440 | 79134440 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 32 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-26 | 2022-04-22 | C.TEL.435/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 91628810 | 0 | 91628810 | 91628810 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 33 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-04-27 | 2022-04-22 | C.TEL.436/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 9288650 | 0 | 9288650 | 9288650 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 34 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-22 | C.TEL.437/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 4035630 | 0 | 4035630 | 4035630 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 35 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.438/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 17211250 | 0 | 17211250 | 17211250 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 36 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.439/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 25568140 | 0 | 25568140 | 25568140 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 37 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.440/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 124364500 | 0 | 124364500 | 124364500 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 38 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-25 | 2022-04-22 | C.TEL.441/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 53121810 | 0 | 53121810 | 53121810 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 39 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.442/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 25897510 | 0 | 25897510 | 25897510 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022042 | 2 | 40 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001958/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 110 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra dan Sulut Malut | 2022-04-19 | 2022-06-02 | QE AKSES | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-22 | C.TEL.443/LG300/DR7-12800000/2022 | 2022-05-28 | TEL.0079/LG.320/DR7-10400000/2022 | 2022-05-28 | 59594140 | 0 | 59594140 | 59594140 | 4500457577 |  |  |  |  | TELKOM AKSES | 2022-06-10
G2022043 | 4 | 24 | 01E07V06 | 007 | 72040049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | ENREKANG |  | ENR051 Buntu Batuan-R7 PRE ENR ENR051 Buntu Batuan |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1052/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 496773731 | 85619724 | 582393455 | 582393455 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 23 | 01E07V06 | 007 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | MAJENE |  | PLW125 Napo Limboro-R7 PRE MAJ PLW125 Napo Limboro |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1029/LG.310/DR7-12700000/2022 | 2022-06-15 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 224732766 | 40434732 | 265167498 | 265167498 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 22 | 01E07V06 | 007 | 72040078 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | MAJENE |  | PLW123 Galung Lombok-R7 PRE MAJ PLW123 Galung Lombok |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1030/LG.310/DR7-12700000/2022 | 2022-06-15 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 174093412 | 45807872 | 219901284 | 219901284 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 25 | 01E07V06 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | MALILI |  | MLI114 Cendana Burau-R7 PRE MLL MLI114 Cendana Burau |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1034/LG.310/DR7-12700000/2022 | 2022-06-17 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 414105967 | 71170408 | 485276375 | 485276375 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 15 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | MAMUJU |  | MAM100 Pokkang-R7 PRE MAM MAM100 Pokkang |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1066/LG.310/DR7-12700000/2022 | 2022-06-16 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 185196951 | 42754871 | 227951822 | 227951822 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 16 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | MAMUJU |  | MAM109 Parili Topoyo-R7 PRE MAM MAM109 Parili Topoyo |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1067/LG.310/DR7-12700000/2022 | 2022-06-16 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 245354442 | 51015093 | 296369535 | 296369535 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 17 | 01E07V06 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | MAMUJU |  | MAM150 StikesAndini-R7 PRE MAM MAM150 StikesAndini |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1068/LG.310/DR7-12700000/2022 | 2022-06-16 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 147269482 | 43862888 | 191132370 | 191132370 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 8 | 01E07V06 | 007 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | PLP070 Protelindo Jendral Sudirman-R7 PRE PLP PLP070 Protelindo Jendral Sudirman |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1033/LG.310/DR7-12700000/2022 | 2022-06-17 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 17702752 | 3606524 | 21309276 | 21309276 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 14 | 01E07V06 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | PIN161 Sabbang Paru-R7 PRE PIN PIN161 Sabbang Paru |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1070/LG.310/DR7-12700000/2022 | 2022-06-22 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 30166917 | 8019414 | 38186331 | 38186331 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 13 | 01E07V06 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | PIN174 Patobong-R7 PRE PIN PIN174 Patobong |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1071/LG.310/DR7-12700000/2022 | 2022-06-22 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 16585655 | 4871693 | 21457348 | 21457348 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 37 | 01E07V06 | 007 | 72040128 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | PIN144 TBG TONYAMANG-R7 PRE PIN PIN144 TBG TONYAMANG |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1069/LG.310/DR7-12700000/2022 | 2022-06-22 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 29914965 | 7079462 | 36994427 | 36994427 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 26 | 01E07V06 | 007 | 72040195 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | POLEWALI |  | PLW127 Rea Binuang-R7 PRE PLW PLW127 Rea Binuang |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1051/LG.310/DR7-12700000/2022 | 2022-06-15 | TEL.0113/LG.320/DR7-10400000/2022 | 2022-06-22 | 30259254 | 8835897 | 39095151 | 39095151 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-17
G2022043 | 4 | 34 | 01E07V06 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | RANTEPAO |  | MLE050 TBG Tagari-R7 PRE RTP MLE050 TBG Tagari |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1035/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 4264037 | 1804266 | 6068303 | 6068303 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 10 | 01E07V06 | 007 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | SENGKANG |  | SKG200 DMT Wage-R7 PRE SKG SKG200 DMT Wage |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1037/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 92743248 | 16705841 | 109449089 | 109449089 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 20 | 01E07V06 | 007 | 72040160 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | SIWA |  | SDR141 Dengeng-Dengeng-R7 PRE SIW SDR141 Dengeng-Dengeng |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1031/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 379168817 | 67093887 | 446262704 | 446262704 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 19 | 01E07V06 | 007 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | TANRUTEDONG |  | SDR140 TBG Salo Mallori-R7 PRE TTE SDR140 TBG Salo Mallori |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1032/LG.310/DR7-12700000/202 | 2022-06-20 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 32689793 | 8191262 | 40881055 | 40881055 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 21 | 01E07V06 | 007 | 72040186 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | WATANSOPPENG |  | WTG063 Tottong Donri Donri-R7 PRE WTG WTG063 Tottong Donri Donri |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1036/LG.310/DR7-12700000/2022 | 2022-06-20 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 14435765 | 3354968 | 17790733 | 17790733 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 27 | 01E07V06 | 007 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | WONOMULYO |  | PLW141 Tenggelan Luyo-R7 PRE WON PLW141 Tenggelan Luyo |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1027/LG.310/DR7-12700000/2022 | 2022-06-15 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 330232274 | 63847825 | 394080099 | 394080099 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 33 | 01E07V06 | 007 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | WONOMULYO |  | PLW136 Kurma Mapilli-R7 PRE WON PLW136 Kurma Mapilli |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1026/LG.310/DR7-12700000/2022 | 2022-06-15 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 477933695 | 94396142 | 572329837 | 572329837 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 32 | 01E07V06 | 007 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | PARE-PARE | WONOMULYO |  | PLW121 Batu Tapango-R7 PRE WON PLW121 Batu Tapango |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1028/LG.310/DR7-12700000/2022 | 2022-06-15 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 374425680 | 67984452 | 442410132 | 442410132 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 36 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | UJUNGPANDANG | SUNGGUMINASA |  | SNS355 Maminasata-R7 MKS SUG SNS355 Maminasata |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1003/LG.310/DR7-12700000/2022 | 2022-06-14 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 159606760 | 28244852 | 187851612 | 187851612 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 35 | 01E07V06 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | UJUNGPANDANG | SUNGGUMINASA |  | SNS380 Borong Palala-R7 MKS SUG SNS380 Borong Palala |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1002/LG.310/DR7-12700000/2022 | 2022-06-14 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 117980145 | 21541885 | 139522030 | 139522030 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022043 | 4 | 18 | 01E07V06 | 007 | 72080199 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001959/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 26 LoP Area Witel Sulselbar dan Makassar | 2022-04-19 | 2022-07-17 | FIMO NODE-B 2022 | UJUNGPANDANG | WATAMPONE |  | MRS151 Batalion Bance'e-R7 PRE WTP MRS151 Batalion Bance |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-07-13 | 2022-04-19 | TEL.1001/LG.310/DR7-12700000/2022 | 2022-06-14 | TEL.0111/LG.320/DR7-10400000/2022 | 2022-06-20 | 34397881 | 8460018 | 42857899 | 42857899 | 4500457576 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA | 2022-07-01
G2022044 | 2 | 8 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001960/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 4 LoP Area Witel Papua | 2022-04-19 | 2022-07-07 | FTTH BATCH-3 | JAYAPURA | JAYAPURA A |  | R7 JAP PT3 NEW ODC ANGKASA |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-06-01 | 2022-04-19 | TEL.1074/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0114/LG.320/DR7-10400000/2022 | 2022-07-07 | 529089152 | 176744513 | 705833665 | 705833665 | 4500457575 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022044 | 2 | 9 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001960/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 4 LoP Area Witel Papua | 2022-04-19 | 2022-07-07 | FTTH BATCH-3 | JAYAPURA | SENTANI |  | R7 SNI PT3 BTN KOLAM DOYO BARU |  | 100 | 80 | 0 | Instalasi | 2022-04-19 | 2022-05-08 | 2022-04-19 |  |  |  |  | 347088742 | 93580099 | 440668841 | 0 | 4500457575 |  |  |  |  | TELKOM AKSES
G2022044 | 2 | 6 | 01E07V01 | 007 | 74030063 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001960/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 4 LoP Area Witel Papua | 2022-04-19 | 2022-07-07 | FTTH BATCH-3 | JAYAPURA | SENTANI |  | R7 SNI PT3 JL.KEMIRI BTN KASIH |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-12 | 2022-04-19 | TEL.1072/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0114/LG.320/DR7-10400000/2022 | 2022-07-07 | 249831693 | 56463581 | 306295274 | 306295274 | 4500457575 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022044 | 2 | 7 | 01E07V01 | 007 | 74030067 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001960/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 4 LoP Area Witel Papua | 2022-04-19 | 2022-07-07 | FTTH BATCH-3 | JAYAPURA | TEMBAGAPURA |  | R7 TBG PT3 BARAK T RIDGECAMP |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-12 | 2022-04-19 | TEL.1073/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0114/LG.320/DR7-10400000/2022 | 2022-07-07 | 55963832 | 14152499 | 70116331 | 70116331 | 4500457575 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022045 | 2 | 8 | 01E07V01 | 007 | 72040117 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001961/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 2 LoP Area Witel Sulselbar | 2022-04-19 | 2022-05-18 | OSP FO FTTH PT3 2022 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT3 ODC-PRE-FM |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-17 | 2022-04-19 | TEL.849/LG.310/DR7-12700000/2022 | 2022-05-12 | TEL.0058/LG.320/DR7-10400000/2022 | 2022-05-12 | 146924874 | 27997496 | 174922370 | 174922370 | 4500457574 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-17
G2022045 | 2 | 7 | 01E07V01 | 007 | 72040174 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001961/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 2 LoP Area Witel Sulselbar | 2022-04-19 | 2022-05-18 | OSP FO FTTH PT3 2022 | PARE-PARE | TANRUTEDONG |  | R7 PRE TTE PT3 ODC-TTE-FAD |  | 95 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-17 | 2022-04-19 | TEL.850/LG.310/DR7-12700000/2022 | 2022-05-12 | TEL.0058/LG.320/DR7-10400000/2022 | 2022-05-12 | 651358120 | 109478501 | 760836621 | 760836621 | 4500457574 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-05-17
G2022046 | 2 | 7 | 01E07V01 | 007 | 72040194 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001962/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 2 LoP Area Witel Sulselbar | 2022-04-19 | 2022-06-02 | OSP FO FTTH PT3 2022 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT3 ODC-SKG-FRB (2022) |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-28 | 2022-04-19 | TEL.914/LG.310/DR7-12700000/2022 | 2022-05-28 | TEL.0077/LG.320/DR7-10400000/2022 | 2022-05-29 | 260847684 | 50804377 | 311652061 | 311652061 | 4500457573 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-05-31
G2022046 | 2 | 8 | 01E07V01 | 007 | 72040186 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.001962/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-1 2 LoP Area Witel Sulselbar | 2022-04-19 | 2022-06-02 | OSP FO FTTH PT3 2022 | PARE-PARE | WATANSOPPENG |  | R7 PRE WTG PT3 ODC-WTG-FRK (ENREKENG) |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-05-28 | 2022-04-19 | TEL.915/LG.310/DR7-12700000/2022 | 2022-05-29 | TEL.0077/LG.320/DR7-10400000/2022 | 2022-05-29 | 570756924 | 100658628 | 671415552 | 671415552 | 4500457573 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-05-31
G2022047 | 1 | 15 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001996/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 6 LoP Area Witel Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-04-19 | 2022-06-02 | QE RELOKASI | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE RELOKASI PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-27 | 2022-04-19 | C.TEL.530/LG300/DR7-12800000/2022 | 2022-04-26 | TEL.0069/LG.320/DR7-10400000/2022 | 2022-05-18 | 96156890 | 52442270 | 148599160 | 148599160 | 4500457736 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022047 | 1 | 20 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001996/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 6 LoP Area Witel Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-04-19 | 2022-06-02 | QE RELOKASI | KENDARI | KENDARI |  | PEKERJAAN QE RELOKASI PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.535/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0069/LG.320/DR7-10400000/2022 | 2022-05-18 | 113972960 | 68523480 | 182496440 | 182496440 | 4500457736 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022047 | 1 | 19 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001996/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 6 LoP Area Witel Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-04-19 | 2022-06-02 | QE RELOKASI | PALU | PALU B |  | PEKERJAAN QE RELOKASI PERIODE FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-30 | 2022-04-19 | C.TEL.534/LG300/DR7-12800000/2022 | 2022-05-18 | TEL.0069/LG.320/DR7-10400000/2022 | 2022-05-18 | 17678500 | 14704280 | 32382780 | 32382780 | 4500457736 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022047 | 1 | 18 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001996/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 6 LoP Area Witel Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-04-19 | 2022-06-02 | QE RELOKASI | PARE-PARE | SENGKANG |  | PEKERJAAN QE RELOKASI PERIODE JAN 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-26 | 2022-04-19 | C.TEL.533/LG300/DR7-12800000/2022 | 2022-05-13 | TEL.0069/LG.320/DR7-10400000/2022 | 2022-05-18 | 11683020 | 3902780 | 15585800 | 15585800 | 4500457736 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022047 | 1 | 16 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001996/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 6 LoP Area Witel Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-04-19 | 2022-06-02 | QE RELOKASI | SORONG | BIAK |  | PEKERJAAN QE RELOKASI PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.531/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0069/LG.320/DR7-10400000/2022 | 2022-05-18 | 0 | 312890 | 312890 | 312890 | 4500457736 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022047 | 1 | 17 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.001996/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Relokasi Utilitas 6 LoP Area Witel Papua, Papua Barat, Sulselbar, Sulteng dan Sultra | 2022-04-19 | 2022-06-02 | QE RELOKASI | SORONG | SORONG |  | PEKERJAAN QE RELOKASI PERIODE JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-04-19 | 2022-04-28 | 2022-04-19 | C.TEL.532/LG300/DR7-12800000/2022 | 2022-05-09 | TEL.0069/LG.320/DR7-10400000/2022 | 2022-05-18 | 0 | 9876010 | 9876010 | 9876010 | 4500457736 |  |  |  |  | TELKOM AKSES | 2022-05-30
G2022048 | 1 | 27 | 01E07T02 | 007 | 74040016 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | MANOKWARI | WARMARE |  | MWR112-MWR112 |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL252/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 92185414 | 19736878 | 111922292 | 111922292 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 8 | 01E07T02 | 007 | 74060035 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | BIAK |  | BIA212-STP BMJ Babrinbo |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL231/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 97058645 | 30108373 | 127167018 | 127167018 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 9 | 01E07T02 | 007 | 74060035 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | BIAK |  | BIA277-STP Bosnik Raya Paray |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.232/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 12674963 | 4048569 | 16723532 | 16723532 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 17 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR218-TBG Reremi Permai |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.265/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 4427091 | 2192819 | 6619910 | 6619910 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 10 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR303-DMT Inamberi Ayambori |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL259/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 40237958 | 9953597 | 50191555 | 50191555 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 11 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR119-TBG ANDAY |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL260/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 5367597 | 2479007 | 7846604 | 7846604 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 12 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | COK353-Combat Naru Bumi Marina |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.261/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 6503382 | 2913865 | 9417247 | 9417247 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 13 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR313-DMT Trikora Maruni |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.268/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 22942062 | 8192661 | 31134723 | 31134723 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 14 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR217-TBG Trikora Arfai |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL262/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 7687082 | 3318679 | 11005761 | 11005761 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 15 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR200-DMT Manunggal Amban |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.263/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 8739553 | 3638937 | 12378490 | 12378490 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 19 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR311-TRIKORA ARFAI2 |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL267/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 13280062 | 5200295 | 18480357 | 18480357 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 18 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR116-TBG Amban |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.266/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 63392899 | 15878831 | 79271730 | 79271730 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 16 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR183-MWR183 |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL264/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 6794491 | 3002447 | 9796938 | 9796938 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 24 | 01E07T02 | 007 | 74060049 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | RAJA AMPAT |  | WSI100-DMT Setapak Waisai |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-02 | TEL251/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 63635355 | 15468197 | 79103552 | 79103552 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 20 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON285-SON285 |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-02 | TEL.248/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 6637740 | 2954749 | 9592489 | 9592489 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 21 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON300-DMT Ani Weho |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL249/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 19045192 | 6039277 | 25084469 | 25084469 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 22 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON252-TBG Putra Residence |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL250/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 3067376 | 1689821 | 4757197 | 4757197 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 23 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON005-SON005 |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL253/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 37876623 | 9081320 | 46957943 | 46957943 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 25 | 01E07T02 | 007 | 74060027 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | TEMINABUAN |  | TMB200-TBG Srer |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-02 | TEL.233/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 7549387 | 2514220 | 10063607 | 10063607 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022048 | 1 | 26 | 01E07T02 | 007 | 74060027 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002010/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 20 LOP AREA WITEL PAPUA BARAT | 2022-04-20 | 2022-06-18 | FIMO NODE-B 2022 | SORONG | TEMINABUAN |  | TMB080-DMT Wersar Teminabuan |  | 74 | 100 | 100 | BAST-1 | 2022-04-20 | 2022-06-18 | 2022-05-01 | TEL.234/LG000/R7W-7H100000/2022 | 2022-06-02 | TEL.0003/LG.320/R7W-7H100000/2022 | 2022-06-02 | 255214336 | 54803448 | 310017784 | 310017784 | 4500457516 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-03
G2022049 | 2 | 6 | 01E07V01 | 007 | 74010053 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002056/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 2 LOP Tahun 2022 Area Witel Papua Barat | 2022-04-21 | 2022-06-19 | OSP FO FTTH PT3 2022 | BIAK | WAROPEN |  | R7 SON WPN PT3 WAREN 1 |  | 100 | 50 | 0 | Mat. Delivery | 2022-04-21 | 2022-06-10 | 2022-05-01 |  |  |  |  | 759927802 | 179179870 | 939107672 | 0 | 4500458059 |  |  |  |  | TELKOM AKSES
G2022049 | 2 | 7 | 01E07V01 | 007 | 74040018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002056/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH/PT3 Batch 1 2 LOP Tahun 2022 Area Witel Papua Barat | 2022-04-21 | 2022-06-19 | OSP FO FTTH PT3 2022 | MANOKWARI | WASIOR |  | R7 SON WSR PT3 PERUM PEMDA |  | 100 | 100 | 100 | BAST-1 | 2022-04-21 | 2022-06-10 | 2022-05-01 | TEL.940/LG.310/DR7-12700000/2022 | 2022-06-09 | TEL.0084/LG.320/DR7-10400000/2022 | 2022-06-09 | 136857639 | 30211163 | 167068802 | 167068802 | 4500458059 |  |  |  |  | TELKOM AKSES | 2022-06-14
G2022050 | 2 | 10 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002089/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 5 LoP April 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-04-22 | 2022-06-20 | FIMO NODE-B 2022 | UJUNGPANDANG | BULUKUMBA |  | BLK160 BONTOJAMMU BULUKUMBA-R7 MKS BLK BLK160 BONTOJAMMU BULUKUMBA |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-03 | 2022-04-22 | TEL.387/LG310/R7W-7A1C0000/2022 | 2022-06-11 | TEL.0005/LG.320/R7W-7A100000/2022 | 2022-06-11 | 3038040 | 1466304 | 4504344 | 4504344 | 4500457829 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-06-20
G2022050 | 2 | 11 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002089/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 5 LoP April 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-04-22 | 2022-06-20 | FIMO NODE-B 2022 | UJUNGPANDANG | BULUKUMBA |  | BLK179 PEMANDIAN BENDUNGAN BETTU-R7 MKS BLK BLK179 PEMANDIAN BENDUNGAN BETTU |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-03 | 2022-04-22 | TEL.388/LG310/R7W-7A1C0000/2022 | 2022-06-11 | TEL.0005/LG.320/R7W-7A100000/2022 | 2022-06-11 | 353925019 | 64277175 | 418202194 | 418202194 | 4500457829 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-06-20
G2022050 | 2 | 8 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002089/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 5 LoP April 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-04-22 | 2022-06-20 | FIMO NODE-B 2022 | UJUNGPANDANG | MAROS |  | MRS173 DMT Pajukukang-R7 MKS MAR MRS173 DMT Pajukukang |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-03 | 2022-04-22 | TEL.386/LG310/R7W-7A1C0000/2022 | 2022-06-11 | TEL.0005/LG.320/R7W-7A100000/2022 | 2022-06-11 | 327188050 | 56939550 | 384127600 | 384127600 | 4500457829 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-06-20
G2022050 | 2 | 9 | 01E07J04 | 007 | 72080112 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002089/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 5 LoP April 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-04-22 | 2022-06-20 | FIMO NODE-B 2022 | UJUNGPANDANG | SELAYAR |  | SLY085 Bandara Aroepala Sly-R7 MKS SLY SLY085 Bandara Aroepala Sly |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-03 | 2022-04-22 | TEL.389/LG310/R7W-7A1C0000/2022 | 2022-06-11 | TEL.0005/LG.320/R7W-7A100000/2022 | 2022-06-11 | 9981744 | 3097458 | 13079202 | 13079202 | 4500457829 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-06-20
G2022050 | 2 | 7 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002089/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 5 LoP April 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-04-22 | 2022-06-20 | FIMO NODE-B 2022 | UJUNGPANDANG | SUNGGUMINASA |  | SNS273 Combat Pattallassang Gowa-R7 MKS SUG SNS273 Combat Pattallassang Gowa |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-03 | 2022-04-22 | TEL.385/LG310/R7W-7A1C0000/2022 | 2022-06-11 | TEL.0005/LG.320/R7W-7A100000/2022 | 2022-06-11 | 13961019 | 4580383 | 18541402 | 18541402 | 4500457829 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-06-20
12022107 | 0 | 18 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002113/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2022-04-22 | 2022-09-18 | BNG dan PCEF | AMBON | AMBON |  | ME2-D7-AMB |  | 50 | 0 | 0 | Preparing | 2022-04-22 | 2022-09-18 | [5 empty] | 73880000 | 5908000 | 79788000 | 0 | 4500457473 |  |  |  |  | HUAWEI TECH INVESTMENT
12022107 | 0 | 20 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002113/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2022-04-22 | 2022-09-18 | BNG dan PCEF | JAYAPURA | JAYAPURA |  | ME2-D7-JAP |  | 50 | 0 | 0 | Preparing | 2022-04-22 | 2022-09-18 | [5 empty] | 73880000 | 5908000 | 79788000 | 0 | 4500457473 |  |  |  |  | HUAWEI TECH INVESTMENT
12022107 | 0 | 16 | 01C11B01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002113/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2022-04-22 | 2022-09-18 | BNG dan PCEF | PARE-PARE | PALOPO |  | ME-D7-PLP |  | 50 | 0 | 0 | Preparing | 2022-04-22 | 2022-09-18 | [5 empty] | 131377500 | 40507400 | 171884900 | 0 | 4500457473 |  |  |  |  | HUAWEI TECH INVESTMENT
12022107 | 0 | 17 | 01C11B01 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002113/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2022-04-22 | 2022-09-18 | BNG dan PCEF | POSO | POSO |  | ME-D7-PSO |  | 50 | 0 | 0 | Preparing | 2022-04-22 | 2022-09-18 | [5 empty] | 131377500 | 40507400 | 171884900 | 0 | 4500457473 |  |  |  |  | HUAWEI TECH INVESTMENT
12022107 | 0 | 22 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002113/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2022-04-22 | 2022-09-18 | BNG dan PCEF | SORONG | SORONG |  | ME2-D7-SRG |  | 50 | 0 | 0 | Preparing | 2022-04-22 | 2022-09-18 | [5 empty] | 73880000 | 5908000 | 79788000 | 0 | 4500457473 |  |  |  |  | HUAWEI TECH INVESTMENT
12022107 | 0 | 19 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002113/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Implementasi BNG dan PCEF Congestion Management Platform Huawei | 2022-04-22 | 2022-09-18 | BNG dan PCEF | TERNATE | TERNATE |  | ME2-D7-TNT |  | 50 | 0 | 0 | Preparing | 2022-04-22 | 2022-09-18 | [5 empty] | 73880000 | 5908000 | 79788000 | 0 | 4500457473 |  |  |  |  | HUAWEI TECH INVESTMENT
G2022052 | 2 | 13 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002125/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 3 LOP Area Witel Gorontalo | 2022-04-22 | 2022-06-16 | FIMO NODE-B 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL ISM TBG KARYA INDAH |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-05 | 2022-04-22 | TEL.946/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0090/LG.320/DR7-10400000/2022 | 2022-05-30 | 23949812 | 7733670 | 31683482 | 31683482 | 4500458468 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-06-17
G2022052 | 2 | 12 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002125/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 3 LOP Area Witel Gorontalo | 2022-04-22 | 2022-06-16 | FIMO NODE-B 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL ISM 124 TBG BUATA |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-05 | 2022-04-22 | TEL.947/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0090/LG.320/DR7-10400000/2022 | 2022-05-30 | 458432270 | 83157664 | 541589934 | 541589934 | 4500458468 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-06-17
G2022052 | 2 | 11 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002125/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 3 LOP Area Witel Gorontalo | 2022-04-22 | 2022-06-16 | FIMO NODE-B 2022 | GORONTALO | MARISA |  | R7 GTO MRS COI938 COMBAT BALAYO |  | 100 | 100 | 100 | BAST-1 | 2022-04-22 | 2022-06-05 | 2022-04-22 | TEL.945/LG.310/DR7-12700000/2022 | 2022-05-30 | TEL.0090/LG.320/DR7-10400000/2022 | 2022-05-30 | 15956145 | 3806066 | 19762211 | 19762211 | 4500458468 |  |  |  |  | TECHNOLOGY KARYA MANDIRI | 2022-06-17
12022108 | 3 | 30 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002175/HK.810/OPS-10000000/2022 | SP#4 Ekspan IP Backbone Platform Cisco | 2022-04-25 | 2022-08-22 | Ekspan IP Backbone Platform Cisco | AMBON | AMBON |  | P-D7-AB1 |  | 80 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-08-22 | 2022-05-09 | K.TEL.768/LG.310/DID-B0300000/2022 | 2022-05-28 | TEL.0857/LG.320/DID-A0000000/2022 | 2022-05-28 | 59962500 | 23800400 | 83762900 | 83762900 | 4500458194 |  |  |  |  | MASTERSYSTEM INFOTAMA | 2022-06-29
G2022053 | 1 | 12 | 01E07R03 | 007 | 72010004 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002180/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO FIMO Node B 6 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-04-25 | 2022-06-23 | FIMO NODE-B 2022 | MANADO | AMURANG |  | AMR103-R7 MDO AMR AMR103 DESA MAESAAN |  | 95 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-06-23 | 2022-04-25 | TEL.558/LG.310/R7W-7F100000/2022 | 2022-06-15 | TEL.0003/LG.320/R7W-7F100000/2022 | 2022-06-15 | 338029231 | 80192430 | 418221661 | 418221661 | 4500458813 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022053 | 1 | 11 | 01E07R03 | 007 | 72010267 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002180/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO FIMO Node B 6 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-04-25 | 2022-06-23 | FIMO NODE-B 2022 | MANADO | HULU SIAU |  | THN068-R7 MDO HLS THN068 BEBALI SIAU TIMUR |  | 95 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-06-23 | 2022-04-25 | TEL.662/LG.310/R7W-7F100000/2022 | 2022-06-15 | TEL.0003/LG.320/R7W-7F100000/2022 | 2022-06-15 | 71219589 | 19697359 | 90916948 | 90916948 | 4500458813 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022053 | 1 | 9 | 01E07R03 | 007 | 72010267 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002180/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO FIMO Node B 6 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-04-25 | 2022-06-23 | FIMO NODE-B 2022 | MANADO | HULU SIAU |  | THN062-R7 MDO HLS THN062 DAME SIAU TIMUR |  | 95 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-06-23 | 2022-04-25 | TEL.661/LG.310/R7W-7F100000/2022 | 2022-06-15 | TEL.0003/LG.320/R7W-7F100000/2022 | 2022-06-15 | 145725376 | 32824397 | 178549773 | 178549773 | 4500458813 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022053 | 1 | 10 | 01E07R03 | 007 | 72010267 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002180/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO FIMO Node B 6 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-04-25 | 2022-06-23 | FIMO NODE-B 2022 | MANADO | HULU SIAU |  | THN115-R7 MDO HLS THN115 BEONG |  | 95 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-06-23 | 2022-04-25 | TEL.663/LG.310/R7W-7F100000/2022 | 2022-06-15 | TEL.0003/LG.320/R7W-7F100000/2022 | 2022-06-15 | 98961203 | 21657398 | 120618601 | 120618601 | 4500458813 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022053 | 1 | 13 | 01E07R03 | 007 | 72010248 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002180/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO FIMO Node B 6 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-04-25 | 2022-06-23 | FIMO NODE-B 2022 | MANADO | TAGULANDANG |  | THN101-R7 MDO TAG THN101 LESAH TAGULANDANG |  | 95 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-06-23 | 2022-04-25 | TEL.660/LG.310/R7W-7F100000/2022 | 2022-06-15 | TEL.0003/LG.320/R7W-7F100000/2022 | 2022-06-15 | 198938136 | 37950605 | 236888741 | 236888741 | 4500458813 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022053 | 1 | 8 | 01E07R03 | 007 | 72010104 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002180/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO FIMO Node B 6 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-04-25 | 2022-06-23 | FIMO NODE-B 2022 | MANADO | TAHUNA |  | THN072-R7 MDO THN THN072 TOLA MARANGE |  | 95 | 100 | 100 | BAST-1 | 2022-04-25 | 2022-06-23 | 2022-04-25 | TEL.559/LG.310/R7W-7F100000/2022 | 2022-06-15 | TEL.0003/LG.320/R7W-7F100000/2022 | 2022-06-15 | 271354546 | 48942023 | 320296569 | 320296569 | 4500458813 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022054 | 1 | 22 | 01E07Q02 | 007 | 73010120 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | DOBO |  | TUL307-R7 AMB DOB TUL307 Dobo |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.192/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 9471073 | 2737079 | 12208152 | 12208152 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 21 | 01E07Q02 | 007 | 73010028 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | KAIRATU |  | MSH393-R7 AMB MSH MSH393 TBG Waimital 2 |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.186/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 10083737 | 2973033 | 13056770 | 13056770 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 13 | 01E07Q02 | 007 | 73010042 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | MASOHI |  | MSH063-R7 AMB MSH MSH063 Tbg Waisamu |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.181/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 17212692 | 3990979 | 21203671 | 21203671 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 12 | 01E07Q02 | 007 | 73010042 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | MASOHI |  | MSH396-R7 AMB MSH MSH396 TBG Ampera |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.189/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 12466539 | 4403361 | 16869900 | 16869900 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 19 | 01E07Q02 | 007 | 73010046 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | NAMLEA |  | NLA154-R7 AMB NML NLA154 DMT Waekerta Waepo |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.185/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 8574711 | 3226203 | 11800914 | 11800914 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 18 | 01E07Q02 | 007 | 73010046 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | NAMLEA |  | NLA151-R7 AMB NML NLA151 TBG Waetele Waepo |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.184/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 3850489 | 1523657 | 5374146 | 5374146 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 20 | 01E07Q02 | 007 | 73010046 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | NAMLEA |  | NLA230-R7 AMB NML NLA230 DMT Batu Boi |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.190/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 379644845 | 70487946 | 450132791 | 450132791 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 9 | 01E07Q02 | 007 | 73010057 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | PASSO |  | MSH366-R7 AMB MSH MSH366 STP Lai Lingkungan 3 |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.191/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 352056192 | 66123989 | 418180181 | 418180181 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 10 | 01E07Q02 | 007 | 73010057 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | PASSO |  | AMB400-R7 AMB PAO AMB400 DMT Lateri Baguala |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.193/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 16072544 | 3662467 | 19735011 | 19735011 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 8 | 01E07Q02 | 007 | 73010057 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | PASSO |  | AMB405- R7 AMB PAO AMB405 Protelindo Mendes Laha |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.180/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 7492743 | 2866125 | 10358868 | 10358868 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 7 | 01E07Q02 | 007 | 73010057 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | PASSO |  | MSH468-R7 AMB PAO MSH468 DMT LARIKE ATAS |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.179/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 14463428 | 3953081 | 18416509 | 18416509 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 17 | 01E07Q02 | 007 | 73010119 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | TUAL |  | TUL311-R7 AMB TUL TUL311 TBG Dulah Utara Tual |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.188/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 15575465 | 4573341 | 20148806 | 20148806 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 16 | 01E07Q02 | 007 | 73010119 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | TUAL |  | TUL165-R7 AMB TUL TUL165 TBG Taar Lodar |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.183/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 33783235 | 7875653 | 41658888 | 41658888 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 15 | 01E07Q02 | 007 | 73010089 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | WAHAI |  | MSH433-R7 AMB MSH MSH433 TBG Seti Seram Utara |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.187/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 139235504 | 25980687 | 165216191 | 165216191 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
G2022054 | 1 | 14 | 01E07Q02 | 007 | 73010089 | TELKOM REGIONAL VII | WITEL MALUKU (AMBON) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002202/HK.810/R7W-7E100000/2022 | Pengadaan Pekerjaan FIMO NODE-B 16 LOP Periode April 2022 Area Witel Maluku_TDS | 2022-04-26 | 2022-06-24 | FIMO NODE-B 2022 | AMBON | WAHAI |  | MSH151-R7 AMB MSH MSH151 TBG Samai |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-24 | 2022-06-01 | TEL.182/LG.310/R7W-7E1H0000/2022 | 2022-06-22 | TEL.0001/LG.320/R7W-7E100000/2022 | 2022-06-22 | 272605567 | 47189925 | 319795492 | 319795492 | 4500458951 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-30
12022111 | 3 | 17 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002220/HK.810/OPS-10000000/2022 | SP#5 Ekspan IP Backbone Platform Cisco | 2022-04-26 | 2022-08-23 | Ekspan IP Backbone Platform Cisco | JAYAPURA | TIMIKA |  | P-D7-TIM |  | 80 | 20 | 0 | Preparing | 2022-04-26 | 2022-08-23 | 2022-05-09 |  |  |  |  | 3000000 | 24240000 | 27240000 | 0 | 4500458424 |  |  |  |  | MASTERSYSTEM INFOTAMA
12022111 | 3 | 15 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002220/HK.810/OPS-10000000/2022 | SP#5 Ekspan IP Backbone Platform Cisco | 2022-04-26 | 2022-08-23 | Ekspan IP Backbone Platform Cisco | PALU | PALU-1 |  | P-D7-PL1 |  | 80 | 20 | 0 | Preparing | 2022-04-26 | 2022-08-23 | 2022-05-09 |  |  |  |  | 15000000 | 121200000 | 136200000 | 0 | 4500458424 |  |  |  |  | MASTERSYSTEM INFOTAMA
G2022055 | 4 | 7 | 01E07V06 | 007 | 73010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002237/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP area Witel Maluku | 2022-04-26 | 2022-07-24 | FIMO NODE-B 2022 | AMBON | BANDA NEIRA |  | MSH301 TANAH RATA-R7 AMB NIR MSH301 TANAH RATA |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-07-24 | 2022-06-01 | TEL.1096/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0117/LG.320/DR7-10400000/2022 | 2022-07-09 | 186605933 | 37255921 | 223861854 | 223861854 | 4500459146 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-23
G2022055 | 4 | 11 | 01E07V06 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002237/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP area Witel Maluku | 2022-04-26 | 2022-07-24 | FIMO NODE-B 2022 | AMBON | DOBO |  | TUL159 DMT Wangel Aru-R7 AMB DOB TUL159 DMT Wangel Aru |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-07-24 | 2022-06-01 | TEL.1097/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0117/LG.320/DR7-10400000/2022 | 2022-07-09 | 129017874 | 24682853 | 153700727 | 153700727 | 4500459146 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-23
G2022055 | 4 | 12 | 01E07V06 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002237/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP area Witel Maluku | 2022-04-26 | 2022-07-24 | FIMO NODE-B 2022 | AMBON | MASOHI |  | MSH440 KOKROMAN-R7 AMB MSH MSH440 KOKROMAN |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-07-24 | 2022-06-01 | TEL.1098/LG.310/DR7-12700000/2022 | 2022-07-07 | TEL.0117/LG.320/DR7-10400000/2022 | 2022-07-09 | 327143718 | 61019687 | 388163405 | 388163405 | 4500459146 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-23
G2022055 | 4 | 10 | 01E07V06 | 007 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002237/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP area Witel Maluku | 2022-04-26 | 2022-07-24 | FIMO NODE-B 2022 | AMBON | PIRU |  | MSH427 KULUR-R7 AMB PIR MSH427 KULUR |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-07-24 | 2022-06-01 | TEL.1110/LG.310/DR7-12700000/2022 | 2022-07-26 | TEL.0127/LG.320/DR7-10400000/2022 | 2022-07-26 | 434014115 | 123113351 | 557127466 | 557127466 | 4500459146 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-08-09
G2022055 | 4 | 9 | 01E07V06 | 007 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002237/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP area Witel Maluku | 2022-04-26 | 2022-07-24 | FIMO NODE-B 2022 | AMBON | PIRU |  | MSH411 CMI Masika Jaya Waesala-R7 AMB PIR MSH411 CMI Masika Jaya Waesala |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-07-24 | 2022-06-01 | TEL.1099/LG.310/DR7-12700000/2022 | 2022-07-09 | TEL.0117/LG.320/DR7-10400000/2022 | 2022-07-09 | 542357530 | 99107835 | 641465365 | 641465365 | 4500459146 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-23
G2022055 | 4 | 8 | 01E07V06 | 007 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002237/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 6 LoP area Witel Maluku | 2022-04-26 | 2022-07-24 | FIMO NODE-B 2022 | AMBON | PIRU |  | MSH426 IHA-R7 AMB PIR MSH426 IHA |  | 100 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-07-24 | 2022-06-01 | TEL.1100/LG.310/DR7-12700000/2022 | 2022-07-09 | TEL.0117/LG.320/DR7-10400000/2022 | 2022-07-09 | 9961130 | 2292807 | 12253937 | 12253937 | 4500459146 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-23
12022112 | 7 | 8 | 01C11G03 | 019 | 70000231 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | KANTOR DIVRE VII | SULAWESI AREA |  | SS#1.1 : Redeploy |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-06-01 | TEL.1791/LG.310/DID-C0300000/2022 | 2022-06-07 | TEL.0806/LG.320/DID-A0000000/2022 | 2022-06-07 | 208469246 | 129184291 | 337653537 | 337653537 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-06-13
12022112 | 7 | 9 | 01C11G03 | 019 | 70000231 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | KANTOR DIVRE VII | SULAWESI AREA |  | SS#2.1 : Upgrade Hardware Radio IP |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-06-01 | TEL.1794/LG.310/DID-C0300000/2022 | 2022-06-07 | TEL.0806/LG.320/DID-A0000000/2022 | 2022-06-07 | 212794399 | 23689314 | 236483713 | 236483713 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-06-13
12022112 | 7 | 10 | 01C11G03 | 019 | 70000231 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | KANTOR DIVRE VII | SULAWESI AREA |  | SS#3.1 : Upgrade License Radio IP |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-06-06 | TEL.2188/LG.310/DID-C0300000/2022 | 2022-06-29 | TEL.0877/LG.320/DID-A0000000/2022 | 2022-06-29 | 2002088 | 2688274 | 4690362 | 4690362 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-06-29
12022112 | 7 | 19 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#4.1 BHP-ISR |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-06-01 | TEL.1884/LG.310/DID-C0300000/2022 | 2022-06-07 | TEL.0806/LG.320/DID-A0000000/2022 | 2022-06-07 | 0 | 95768240 | 95768240 | 95768240 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-06-13
12022112 | 7 | 28 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#4.2 : BHP-ISR |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-06-06 | TEL.2261/LG.310/DID-C0300000/2022 | 2022-06-29 | TEL.0877/LG.320/DID-A0000000/2022 | 2022-06-29 | 0 | 35557794 | 35557794 | 35557794 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-06-29
12022112 | 7 | 26 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#1.2 : Redeploy |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-06-06 | TEL.2183/LG.310/DID-C0300000/2022 | 2022-06-29 | TEL.0877/LG.320/DID-A0000000/2022 | 2022-06-29 | 241804313 | 192123816 | 433928129 | 433928129 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-06-29
12022112 | 7 | 27 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#2.2 : Upgrade Hardware Radio IP |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-07-06 | TEL.2770/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1135/LG.320/DID-A0000000/2022 | 2022-07-29 | 122013361 | 22031062 | 144044423 | 144044423 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-07-29
12022112 | 7 | 50 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#2.3 : Upgrade Hardware Radio IP |  | 50 |  |  |  | 2022-04-26 | 2022-10-06 | [5 empty] | 1845226274 | 440368872 | 2285595146 | 0 | 4500458981 |  |  |  |  | ERICSSON INDONESIA
12022112 | 7 | 49 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#1.4 : Redeploy |  | 50 |  |  |  | 2022-04-26 | 2022-10-06 | [5 empty] | 1299664495 | 938471769 | 2238136264 | 0 | 4500458981 |  |  |  |  | ERICSSON INDONESIA
12022112 | 7 | 51 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#4.4 : BHP-ISR |  | 50 |  | 0 |  | 2022-04-26 | 2022-10-06 | [5 empty] | 0 | 655200000 | 655200000 | 0 | 4500458981 |  |  |  |  | ERICSSON INDONESIA
12022112 | 7 | 38 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#1.3 : Redeploy |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-07-06 | TEL.2767/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1135/LG.320/DID-A0000000/2022 | 2022-07-29 | 35997341 | 32020636 | 68017977 | 68017977 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-07-29
12022112 | 7 | 40 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#4.3 : BHP-ISR |  | 50 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-10-06 | 2022-07-06 | TEL.2774/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1135/LG.320/DID-A0000000/2022 | 2022-07-29 | 0 | 3932006 | 3932006 | 3932006 | 4500458981 |  |  |  |  | ERICSSON INDONESIA | 2022-07-29
12022112 | 7 | 39 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002256/HK.810/OPS-10050000/2022 | Surat Pesanan-2 (SP#2) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-04-26 | 2022-09-22 | RADIO IP | UJUNGPANDANG | SULSELBAR |  | SS#3.2 : Upgrade License Radio IP |  | 50 |  |  |  | 2022-04-26 | 2022-10-06 | [5 empty] | 1001044 | 3890873 | 4891917 | 0 | 4500458981 |  |  |  |  | ERICSSON INDONESIA
12022113 | 2 | 199 | 01C11I01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | GORONTALO |  | TALUDAA 2 SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-04 |  |  |  |  | 130612206 | 26366564 | 156978770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 200 | 01C11I01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | ISIMU |  | TOTOPO BILATO SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-08 |  |  |  |  | 217159566 | 27902262 | 245061828 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 598 | 01C11I01 | 019 | 72020018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | ISIMU |  | SS#3 GPON CARD |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-10-28 | 2022-08-04 |  |  |  |  | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 599 | 01C11I01 | 019 | 72020019 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | KWANDANG |  | SS#3 GPON CARD |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-10-28 | 2022-08-11 |  |  |  |  | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 600 | 01C11I01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | MARISA |  | SS#3 GPON CARD |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-10-28 | 2022-08-11 |  |  |  |  | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 213 | 01C11I01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | BAU-BAU |  | BTN HALIM SS#2 MINI OLT |  | 20 | 70 | 0 | Instalasi | 2022-04-26 | 2022-11-05 | 2022-08-03 |  |  |  |  | 139412206 | 27064729 | 166476935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 586 | 01C11I01 | 019 | 72050030 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | KOLAKA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 215 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | MANDONGA |  | BUNGKUTOKO SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 214 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | MANDONGA |  | MOROSI SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 139412206 | 27064729 | 166476935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 587 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | MANDONGA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 20620000 | 985000 | 21605000 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 588 | 01C11I01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | UNAAHA |  | SS#3 GPON CARD |  | 20 |  | 0 |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 216 | 01C11I01 | 019 | 72050074 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | WANCI |  | WAHA SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-03 |  |  |  |  | 139412206 | 27064729 | 166476935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 210 | 01C11I01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | LUWUK | LUWUK |  | MONDONO, SOLOAN, & KINTOM SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 589 | 01C11I01 | 019 | 72060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | LUWUK | LUWUK |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 545 | 01C11I01 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | AIR MADIDI |  | SS#3 GPON CARD |  | 20 |  | 0 |  | 2022-04-26 | 2022-10-28 | [5 empty] | 86547360 | 1535698 | 88083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 546 | 01C11I01 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | AMURANG |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 173094720 | 3071396 | 176166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 218 | 01C11I01 | 019 | 72010258 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | BEO |  | TARUN SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-15 |  |  |  |  | 139412206 | 26366564 | 165778770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 220 | 01C11I01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | KOTAMOBAGU |  | LABUANUKI SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 139412206 | 26366564 | 165778770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 548 | 01C11I01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | KOTAMOBAGU |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 269952080 | 5099594 | 275051674 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 550 | 01C11I01 | 019 | 72010127 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | LANGOWAN |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 86547360 | 1535698 | 88083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 552 | 01C11I01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | MANADO |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 96857360 | 2028198 | 98885558 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 221 | 01C11I01 | 019 | 72010132 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | MANADO - BAHU |  | PURI WAREM-GRIYA ASRI SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 139412206 | 26366564 | 165778770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 553 | 01C11I01 | 019 | 72010132 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | MANADO - BAHU |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 269952080 | 5099594 | 275051674 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 554 | 01C11I01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | PANIKI |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 259642080 | 4607094 | 264249174 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 557 | 01C11I01 | 019 | 72010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | TAHUNA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 173094720 | 3071396 | 176166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 560 | 01C11I01 | 019 | 72010110 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | TOMOHON |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 259642080 | 4607094 | 264249174 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 561 | 01C11I01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | TONDANO |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 346189440 | 6142792 | 352332232 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 90 | 01C11I01 | 019 | 72030013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | BUOL |  | SS#1 BIG OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-08 |  |  |  |  | 167542990 | 19513963 | 187056953 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 209 | 01C11I01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | KOLONODALE |  | BOHUNSUAI SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 139412206 | 27064729 | 166476935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 543 | 01C11I01 | 019 | 72030103 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | PALU A |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 259642080 | 4607094 | 264249174 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 590 | 01C11I01 | 019 | 72030092 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | PALU B |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 91 | 01C11I01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | PARIGI |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-09 |  |  |  |  | 255346905 | 21210606 | 276557511 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 211 | 01C11I01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | TAWAELI |  | TOAYA SS#2 MINI OLT |  | 20 |  | 0 |  | 2022-04-26 | 2022-11-05 | [5 empty] | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 591 | 01C11I01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | TAWAELI |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 592 | 01C11I01 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | TOLI-TOLI |  | SS#3 GPON CARD |  | 20 |  | 0 |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 529 | 01C11I01 | 019 | 72040275 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | AJANGALE |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 86547360 | 1535698 | 88083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 98 | 01C11I01 | 019 | 72040014 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | BELOPA |  | SS#1 BIG OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 175705119 | 19856570 | 195561689 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 87 | 01C11I01 | 019 | 72040044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | CANGADI |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-03 |  |  |  |  | 179299319 | 20243714 | 199543033 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 530 | 01C11I01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | ENREKANG |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 73547360 | 1535698 | 75083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 99 | 01C11I01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | ENREKANG |  | SS#1 BIG OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 172182990 | 19953963 | 192136953 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 531 | 01C11I01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MAJENE |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-04 |  |  |  |  | 160094720 | 3071396 | 163166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 532 | 01C11I01 | 019 | 72040197 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MAKALE |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 83857360 | 2028198 | 85885558 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 225 | 01C11I01 | 019 | 72040086 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MAMASA |  | TANDUKALUA SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 533 | 01C11I01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MAMUJU |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-04 |  |  |  |  | 330499440 | 6635292 | 337134732 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 227 | 01C11I01 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MASAMBA |  | SABBANG SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 226 | 01C11I01 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MASAMBA |  | BURAU SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 593 | 01C11I01 | 019 | 72040094 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | MASAMBA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 534 | 01C11I01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | PALOPO |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 330499440 | 6635292 | 337134732 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 535 | 01C11I01 | 019 | 72040117 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | PARE-PARE |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 269952080 | 5099594 | 275051674 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 228 | 01C11I01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | PASANG KAYU |  | LETAWA SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 566 | 01C11I01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | PASANG KAYU |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-04 |  |  |  |  | 173094720 | 3071396 | 176166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 229 | 01C11I01 | 019 | 72040128 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | PINRANG |  | MALONGILONGI SS#2 MINI OLT |  | 20 |  | 0 |  | 2022-04-26 | 2022-11-05 | [5 empty] | 225959566 | 28600427 | 254559993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 594 | 01C11I01 | 019 | 72040128 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | PINRANG |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 100 | 01C11I01 | 019 | 72040195 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | POLEWALI |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-04 |  |  |  |  | 170481301 | 19976652 | 190457953 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 88 | 01C11I01 | 019 | 72040135 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | RAPPANG |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-03 |  |  |  |  | 263276679 | 21499412 | 284776091 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 595 | 01C11I01 | 019 | 72040194 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | SENGKANG |  | SS#3 GPON CARD |  | 20 |  | 0 |  | 2022-04-26 | 2022-10-28 | [5 empty] | 10310000 | 492500 | 10802500 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 538 | 01C11I01 | 019 | 72040158 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | SIDRAP |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 173094720 | 3071396 | 176166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 539 | 01C11I01 | 019 | 72040160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | SIWA |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 147094720 | 3071396 | 150166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 101 | 01C11I01 | 019 | 72040161 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | SOROWAKO |  | SS#1 BIG OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 173580119 | 19997970 | 193578089 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 102 | 01C11I01 | 019 | 72040174 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | TANRUTEDONG |  | SS#1 BIG OLT |  | 20 |  | 0 |  | 2022-04-26 | 2022-11-05 | [5 empty] | 174495119 | 19835470 | 194330589 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 540 | 01C11I01 | 019 | 72040280 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | TOPOYO |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-04 |  |  |  |  | 173094720 | 3071396 | 176166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 541 | 01C11I01 | 019 | 72040187 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | WONOMULYO |  | SS#3 GPON CARD |  | 20 | 10 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-04 |  |  |  |  | 83857360 | 2028198 | 85885558 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 94 | 01C11I01 | 019 | 73020005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | GALELA |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-09 |  |  |  |  | 233115261 | 3989294 | 237104555 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 95 | 01C11I01 | 019 | 73020009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | JAILOLO |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-09 |  |  |  |  | 257028661 | 21512350 | 278541011 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 219 | 01C11I01 | 019 | 73020009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | JAILOLO |  | SIDONGOLI SS#2 MINI OLT |  | 20 |  |  |  | 2022-04-26 | 2022-11-05 | [5 empty] | 139412206 | 26366564 | 165778770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 549 | 01C11I01 | 019 | 73020013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | LABUHA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 86547360 | 1535698 | 88083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 551 | 01C11I01 | 019 | 73020081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | MABA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 173094720 | 3071396 | 176166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 96 | 01C11I01 | 019 | 73020019 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | MOROTAI |  | SS#1 BIG OLT |  | 20 |  | 0 |  | 2022-04-26 | 2022-11-05 | [5 empty] | 343691517 | 23048552 | 366740069 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 555 | 01C11I01 | 019 | 73020032 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | SANANA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 86547360 | 1535698 | 88083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 222 | 01C11I01 | 019 | 73020034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | SOA SIU |  | MOTI SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-07 |  |  |  |  | 139412206 | 26366564 | 165778770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 556 | 01C11I01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | SOFIFI |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 220642080 | 4607094 | 225249174 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 223 | 01C11I01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | TERNATE |  | KASTELA SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-07 |  |  |  |  | 139412206 | 26366564 | 165778770 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 558 | 01C11I01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | TERNATE |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 343499440 | 6635292 | 350134732 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 559 | 01C11I01 | 019 | 73020044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | TOBELO |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 183404720 | 3563896 | 186968616 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 93 | 01C11I01 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | WEDA |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-09 |  |  |  |  | 257028661 | 21512350 | 278541011 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 562 | 01C11I01 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | WEDA |  | SS#3 GPON CARD |  | 20 |  | 0 |  | 2022-04-26 | 2022-10-28 | [5 empty] | 259642080 | 4607094 | 264249174 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 512 | 01C11I01 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | ANTANG |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-06 |  |  |  |  | 346189440 | 6142792 | 352332232 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 513 | 01C11I01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BALAIKOTA |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-05 |  |  |  |  | 147094720 | 3071396 | 150166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 514 | 01C11I01 | 019 | 72080009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BANTAENG |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 73547360 | 1535698 | 75083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 202 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | BIKERU SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 130612206 | 27064729 | 157676935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 203 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | BONTOTANGNGA SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 130612206 | 27064729 | 157676935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 205 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | SAPOLOHE SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 217159566 | 28600427 | 245759993 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 204 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | HERLANG SS#2 MINI OLT |  | 20 | 45 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 130612206 | 27064729 | 157676935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 515 | 01C11I01 | 019 | 72080036 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BULUKUMBA |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 320189440 | 6142792 | 326332232 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 516 | 01C11I01 | 019 | 72080054 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | JENEPONTO |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 233642080 | 4607094 | 238249174 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 517 | 01C11I01 | 019 | 72080064 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | KIMA |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-08 |  |  |  |  | 73547360 | 1535698 | 75083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 518 | 01C11I01 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | MAROS |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 86547360 | 1535698 | 88083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 519 | 01C11I01 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | MATTOANGIN |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-05 |  |  |  |  | 256952080 | 5099594 | 262051674 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 520 | 01C11I01 | 019 | 72080091 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | PANAKUKANG |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 800473600 | 15356980 | 815830580 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 521 | 01C11I01 | 019 | 72080093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | PANGKEP |  | SS#3 GPON CARD |  | 20 |  |  |  | 2022-04-26 | 2022-10-28 | [5 empty] | 147094720 | 3071396 | 150166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 207 | 01C11I01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | SELAYAR |  | TILE TILE SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 130612206 | 27064729 | 157676935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 206 | 01C11I01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | SELAYAR |  | BONTOSIKUYU SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 130612206 | 27064729 | 157676935 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 84 | 01C11I01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | SELAYAR |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-05 | 2022-08-02 |  |  |  |  | 260272479 | 21487168 | 281759647 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 522 | 01C11I01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | SINJAI |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-05 |  |  |  |  | 73547360 | 1535698 | 75083058 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 523 | 01C11I01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUDIANG |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-08 |  |  |  |  | 307189440 | 6142792 | 313332232 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 524 | 01C11I01 | 019 | 72080165 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | SUNGGUMINASA |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 700926240 | 13821282 | 714747522 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 525 | 01C11I01 | 019 | 72080120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | TAKALAR |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-03 |  |  |  |  | 147094720 | 3071396 | 150166116 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 85 | 01C11I01 | 019 | 72080120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | TAKALAR |  | SS#1 BIG OLT |  | 20 |  | 0 |  | 2022-04-26 | 2022-11-05 | [5 empty] | 259395350 | 21382161 | 280777511 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 526 | 01C11I01 | 019 | 72080166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | TAMALANREA |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-06 |  |  |  |  | 256952080 | 5099594 | 262051674 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022113 | 2 | 527 | 01C11I01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002258/HK.810/OPS-10000000/2022 | SP#4 Perangkat GPON-XGPON-XGSPON Platform Fiberhome | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | WATAMPONE |  | SS#3 GPON CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-10-28 | 2022-08-05 |  |  |  |  | 443046800 | 8170990 | 451217790 | 0 | 4500458466 |  |  |  |  | KONSORSIUM PT FIBERHOME TECHNOLOGIES INDONESIA - PT ABHIMATA CITRA ABADI
12022114 | 4 | 911 | 01C11I01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | AMBON |  | AMAHUSU SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 125929116 | 25763883 | 151692999 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 720 | 01C11I01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | AMBON |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 432736800 | 9349035 | 442085835 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 725 | 01C11I01 | 019 | 73010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | BANDA NEIRA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 912 | 01C11I01 | 019 | 73010013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | BULA |  | SERI SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 125929116 | 25763883 | 151692999 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 721 | 01C11I01 | 019 | 73010013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | BULA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1085 | 01C11I01 | 019 | 73010120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | DOBO |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 722 | 01C11I01 | 019 | 73010120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | DOBO |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 913 | 01C11I01 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | MASOHI |  | KAIRATU SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 125929116 | 25763883 | 151692999 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 723 | 01C11I01 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | MASOHI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 943 | 01C11I01 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | NAMLEA |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 915 | 01C11I01 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | NAMLEA |  | SAVANA JAYA SS#2 MINI OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-18 | TEL.0761/LG.310/DID-C0200000/2022 | 2022-07-22 05:20 | TEL.1036/LG.320/DID-A0000000/2022 | 2022-07-22 | 213685836 | 27694215 | 241380051 | 241380051 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 914 | 01C11I01 | 019 | 73010046 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | NAMLEA |  | JIKUMARASA & UBUNG SS#2 MINI OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-18 | TEL.0761/LG.310/DID-C0200000/2022 | 2022-07-22 05:20 | TEL.1036/LG.320/DID-A0000000/2022 | 2022-07-22 | 213685836 | 27694215 | 241380051 | 241380051 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 724 | 01C11I01 | 019 | 73010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | NAMROLE |  | Namlea SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 727 | 01C11I01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | PASSO |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 480284160 | 11218977 | 491503137 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1086 | 01C11I01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | PASSO |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 916 | 01C11I01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | PASSO |  | WAYAME SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 125929116 | 25763883 | 151692999 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 917 | 01C11I01 | 019 | 73010059 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | PIRU |  | WAISALA SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 125929116 | 25763883 | 151692999 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 728 | 01C11I01 | 019 | 73010059 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | PIRU |  | Passo SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 730 | 01C11I01 | 019 | 73010071 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | SAPARUA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 731 | 01C11I01 | 019 | 73010103 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | SAUMLAKI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1087 | 01C11I01 | 019 | 73010103 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | SAUMLAKI |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 726 | 01C11I01 | 019 | 73010172 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | TIAKUR |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 918 | 01C11I01 | 019 | 73010172 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | TIAKUR |  | PATTI SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 213685836 | 27694215 | 241380051 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 732 | 01C11I01 | 019 | 73010119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | TUAL |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1088 | 01C11I01 | 019 | 73010119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | AMBON | TUAL |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 909 | 01C11I01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | GORONTALO |  | BILUNGALA SS#2 MINI OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-18 | TEL.0761/LG.310/DID-C0200000/2022 | 2022-07-22 05:20 | TEL.1036/LG.320/DID-A0000000/2022 | 2022-07-22 | 130129116 | 25768477 | 155897593 | 155897593 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 718 | 01C11I01 | 019 | 72020025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | GORONTALO | MARISA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 944 | 01C11I01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | ABEPURA |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 897 | 01C11I01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | ABEPURA |  | ARSO 3 SS#2 MINI OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-18 | TEL.0761/LG.310/DID-C0200000/2022 | 2022-07-22 05:20 | TEL.1036/LG.320/DID-A0000000/2022 | 2022-07-22 | 138929116 | 26141914 | 165071030 | 165071030 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 898 | 01C11I01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | ABEPURA |  | KOYA BARAT SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 217885836 | 28072246 | 245958082 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 896 | 01C11I01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | ABEPURA |  | ARSO 10 SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 226685836 | 28072246 | 254758082 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 738 | 01C11I01 | 019 | 74030114 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | AGATS |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1216 | 01C11I01 | 019 | 74030025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | JAYAPURA A |  | SS#1 BIG OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-20 | TEL.0764/LG.310/DID-C0200000/2022 | 2022-07-22 05:21 | TEL.1033/LG.320/DID-A0000000/2022 | 2022-07-22 | 339806905 | 15107001 | 354913906 | 354913906 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 734 | 01C11I01 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | KUALA KENCANA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1217 | 01C11I01 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | SARMI |  | SS#1 BIG OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-20 | TEL.0764/LG.310/DID-C0200000/2022 | 2022-07-22 05:21 | TEL.1033/LG.320/DID-A0000000/2022 | 2022-07-22 | 257958495 | 13561444 | 271519939 | 271519939 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 741 | 01C11I01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | SENTANI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 246642080 | 5609466 | 252251546 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1089 | 01C11I01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | SENTANI |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 742 | 01C11I01 | 019 | 74030067 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | TEMBAGAPURA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1090 | 01C11I01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | TIMIKA |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 900 | 01C11I01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | TIMIKA |  | POMAPO SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 217885836 | 28072246 | 245958082 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 743 | 01C11I01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | TIMIKA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 246642080 | 5609466 | 252251546 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 735 | 01C11I01 | 019 | 74030072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | WAENA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 736 | 01C11I01 | 019 | 74030073 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | JAYAPURA | WAMENA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 765 | 01C11I01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | BAU-BAU |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 763 | 01C11I01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | KENDARI |  | Morosi SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 907 | 01C11I01 | 019 | 72050031 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | KOLONEDALE |  | BETELEME SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-13 |  |  |  |  | 419242274 | 33761711 | 453003985 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 762 | 01C11I01 | 019 | 72050041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | LASUSUA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 764 | 01C11I01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | MANDONGA |  | Boro Boro SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 766 | 01C11I01 | 019 | 72050050 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | KENDARI | POMALAA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 770 | 01C11I01 | 019 | 72010012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | BOROKO |  | Bintauna SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 772 | 01C11I01 | 019 | 72010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | LOLAK |  | Inobonto SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 769 | 01C11I01 | 019 | 72010124 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | MANADO CENTRUM |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 220642080 | 5609556 | 226251636 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 773 | 01C11I01 | 019 | 72010276 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | SANANA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 768 | 01C11I01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANADO | TONDANO |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 904 | 01C11I01 | 019 | 74040005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANOKWARI | MANOKWARI |  | WARMARE SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 226685836 | 28072246 | 254758082 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 753 | 01C11I01 | 019 | 74040010 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANOKWARI | RANSIKI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 757 | 01C11I01 | 019 | 74040018 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MANOKWARI | WASIOR |  | Manokwari SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 740 | 01C11I01 | 019 | 74050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MERAUKE | KEPI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1116 | 01C11I01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MERAUKE | MERAUKE |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 739 | 01C11I01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MERAUKE | MERAUKE |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 899 | 01C11I01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MERAUKE | MERAUKE |  | AGATS SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 213685836 | 28067652 | 241753488 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1218 | 01C11I01 | 019 | 74050022 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | MERAUKE | TANAH MERAH |  | SS#1 BIG OLT |  | 20 | 50 | 0 | Mat. Delivery | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 347962605 | 15717001 | 363679606 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 759 | 01C11I01 | 019 | 72030120 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PALU | PASANGKAYU |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 147094720 | 3739704 | 150834424 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 760 | 01C11I01 | 019 | 72040133 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | PARE-PARE | RANTEPAO |  | SS#3 INSERTCARD REKON 2 |  | 10 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-20 | TEL.0772/LG.310/DID-C0200000/2022 | 2022-07-25 14:10 | TEL.1043/LG.320/DID-A0000000/2022 | 2022-07-25 | 432736800 | 9349035 | 442085835 | 442085835 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 906 | 01C11I01 | 019 | 72070003 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | POSO | BUNGKU TENGAH |  | JL. TRANS SULAWESI BAHADOPI SS#2 MINI OLT REKON 2 |  | 20 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-11-06 | 2022-07-18 | TEL.0761/LG.310/DID-C0200000/2022 | 2022-07-22 05:20 | TEL.1036/LG.320/DID-A0000000/2022 | 2022-07-22 | 432242274 | 33766305 | 466008579 | 466008579 | 4500458461 |  |  |  |  | ZTE INDONESIA | 2022-07-28
12022114 | 4 | 746 | 01C11I01 | 019 | 74060001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | AIMAS |  | Sorong SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 747 | 01C11I01 | 019 | 74060035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | BIAK |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 259642080 | 5609421 | 265251501 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 902 | 01C11I01 | 019 | 74060035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | BIAK |  | BOSNIK SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 130129116 | 26141914 | 156271030 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 903 | 01C11I01 | 019 | 74060037 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | BINTUINI |  | SP 4 SS#2 MINI OLT |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 130129116 | 26141914 | 156271030 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 748 | 01C11I01 | 019 | 74060038 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | FAKFAK |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 393736800 | 9349170 | 403085970 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 749 | 01C11I01 | 019 | 74060078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | KAIMANA |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 346189440 | 7479228 | 353668668 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 750 | 01C11I01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | MANOKWARI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 700926240 | 16828533 | 717754773 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1091 | 01C11I01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | MANOKWARI |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 751 | 01C11I01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | NABIRE |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 320189440 | 7479318 | 327668758 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 752 | 01C11I01 | 019 | 74060049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | RAJA AMPAT |  | Sorong SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 86547360 | 1869807 | 88417167 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 754 | 01C11I01 | 019 | 74060041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | SERUI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 945 | 01C11I01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | SORONG |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1220 | 01C11I01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | SORONG |  | SS#1 BIG OLT |  | 20 | 90 | 0 | Siap UT | 2022-04-26 | 2022-11-06 | 2022-08-03 |  |  |  |  | 1208391030 | 34030171 | 1242421201 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 755 | 01C11I01 | 019 | 74060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | TEMINABUAN |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 160094720 | 3739659 | 163834379 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 1092 | 01C11I01 | 019 | 74060027 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | TEMINABUAN |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 11246970 | 494797 | 11741767 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 756 | 01C11I01 | 019 | 74060042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | SORONG | WARMARE / PRAFI |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 173094720 | 3739614 | 176834334 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 774 | 01C11I01 | 019 | 73020034 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | SOA SIU |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 775 | 01C11I01 | 019 | 73020044 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | TOBELO |  | SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 771 | 01C11I01 | 019 | 73020047 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | TERNATE | WEDA |  | Lelilef SS#3 INSERTCARD |  | 10 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-08 |  |  |  |  | 73547360 | 1869852 | 75417212 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
12022114 | 4 | 946 | 01C11I01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002259/HK.810/OPS-10000000/2022 | SP#5 Perangkat GPON-XGPON-XGSPON Platform ZTE | 2022-04-26 | 2022-10-22 | GPON-XGPON-XGSPON | UJUNGPANDANG | BALAIKOTA |  | SS#4 P2P CARD |  | 20 | 20 | 0 | Preparing | 2022-04-26 | 2022-11-06 | 2022-08-11 |  |  |  |  | 22493940 | 989594 | 23483534 | 0 | 4500458461 |  |  |  |  | ZTE INDONESIA
G2022056 | 1 | 11 | 01E07P12 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | ENREKANG |  | R7 PRE ENR ENR085 Desa Tuncung |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-13 | K.TEL.207/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 638871002 | 120069094 | 758940096 | 758940096 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 12 | 01E07P12 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MAS085 Tamboke Sukamaju |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-17 | K.TEL.205/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 12715361 | 2927492 | 15642853 | 15642853 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 9 | 01E07P12 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MAS084 Beringin Jaya |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-17 | K.TEL.204/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 228673079 | 39383343 | 268056422 | 268056422 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 15 | 01E07P12 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP012 |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-17 | K.TEL.210/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 162160552 | 46896003 | 209056555 | 209056555 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 16 | 01E07P12 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP065 |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-17 | K.TEL.211/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 10446436 | 3373766 | 13820202 | 13820202 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 8 | 01E07P12 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP211 |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-17 | K.TEL.203/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 5264948 | 1758789 | 7023737 | 7023737 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 14 | 01E07P12 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PIN003 |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-13 | K.TEL.209/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 26487638 | 7859779 | 34347417 | 34347417 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 10 | 01E07P12 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PIN160 Desa Benteng Paremba |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-17 | K.TEL.206/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 172295552 | 29071533 | 201367085 | 201367085 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
G2022056 | 1 | 13 | 01E07P12 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.002263/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node B 9 LOP Tahun 2022 Area Witel Sulselbar | 2022-04-26 | 2022-06-09 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PIN001 |  | 95 | 100 | 100 | BAST-1 | 2022-04-26 | 2022-06-09 | 2022-05-13 | K.TEL.208/LG/320/R7W-7D100000/2022 | 2022-06-06 | TEL.0007/LG.320/R7W-7D100000/2022 | 2022-06-06 | 41317149 | 10700463 | 52017612 | 52017612 | 4500459173 |  |  |  |  | BAGAMAS PRIMA TEKNIK | 2022-06-08
12022116 | 4 | 8 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002265/HK.810/OPS-10000000/2022 | SP#6 Ekspan IP Backbone Platform Cisco | 2022-04-27 | 2022-08-24 | Ekspan IP Backbone Platform Cisco | JAYAPURA | JAYAPURA |  | T-D7-JAP |  | 80 | 20 | 0 | Preparing | 2022-04-27 | 2022-08-24 | 2022-05-09 |  |  |  |  | 11939746700 | 1187818000 | 13127564700 | 0 | 4500458465 |  |  |  |  | MASTERSYSTEM INFOTAMA
12022116 | 4 | 11 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002265/HK.810/OPS-10000000/2022 | SP#6 Ekspan IP Backbone Platform Cisco | 2022-04-27 | 2022-08-24 | Ekspan IP Backbone Platform Cisco | JAYAPURA | TIMIKA |  | T-D7-TIM |  | 80 | 20 | 0 | Preparing | 2022-04-27 | 2022-08-24 | 2022-05-09 |  |  |  |  | 11939746700 | 1187818000 | 13127564700 | 0 | 4500458465 |  |  |  |  | MASTERSYSTEM INFOTAMA
12022116 | 4 | 21 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002265/HK.810/OPS-10000000/2022 | SP#6 Ekspan IP Backbone Platform Cisco | 2022-04-27 | 2022-08-24 | Ekspan IP Backbone Platform Cisco | SORONG | SORONG |  | T-D7-SON |  | 80 | 20 | 0 | Preparing | 2022-04-27 | 2022-08-24 | 2022-05-09 |  |  |  |  | 12622627100 | 1240005000 | 13862632100 | 0 | 4500458465 |  |  |  |  | MASTERSYSTEM INFOTAMA
12022116 | 4 | 19 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002265/HK.810/OPS-10000000/2022 | SP#6 Ekspan IP Backbone Platform Cisco | 2022-04-27 | 2022-08-24 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | BALAIKOTA |  | P-D7-BAL |  | 80 | 20 | 0 | Preparing | 2022-04-27 | 2022-08-24 | 2022-05-09 |  |  |  |  | 5821032000 | 436592000 | 6257624000 | 0 | 4500458465 |  |  |  |  | MASTERSYSTEM INFOTAMA
12022116 | 4 | 18 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002265/HK.810/OPS-10000000/2022 | SP#6 Ekspan IP Backbone Platform Cisco | 2022-04-27 | 2022-08-24 | Ekspan IP Backbone Platform Cisco | UJUNGPANDANG | PETTARANI |  | P-D7-PTR |  | 80 | 20 | 0 | Preparing | 2022-04-27 | 2022-08-24 | 2022-05-09 |  |  |  |  | 6558888000 | 490352000 | 7049240000 | 0 | 4500458465 |  |  |  |  | MASTERSYSTEM INFOTAMA
G2022057 | 1 | 8 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | ABEPURA |  | WRS025-R7 JYP ABE WRS025 TBG Koya Timir |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.457/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 8624709 | 3210051 | 11834760 | 11834760 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 7 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | ABEPURA |  | WRS035-R7 JYP ABE WRS035 KOYASWKRSA |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.456/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 15123048 | 4139493 | 19262541 | 19262541 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 11 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | ABEPURA |  | JAP632-R7 JYP ABE JAP632 DMT Holtekamp Muara |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.467/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 142276584 | 38319590 | 180596174 | 180596174 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 9 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | ABEPURA |  | WRS033-R7 JYP ABE WRS033 KOYA BARAT_2 |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.464/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 44009099 | 13784809 | 57793908 | 57793908 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 10 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | ABEPURA |  | WRS082-R7 JYP ABE WRS082 DMT Koya Tengah |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.465/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 11363195 | 3459286 | 14822481 | 14822481 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 18 | 01E07L12 | 007 | 74030162 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | JAYAPURA |  | JAP501-R7 JYP JAP JAP501 TBG Polimak IV Adipura |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.458/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 22107525 | 5744675 | 27852200 | 27852200 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 19 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | SENTANI |  | JAP633-R7 JYP SNI JAP633 TBG Ifar Gunung Sentani |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.466/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 78561143 | 17246265 | 95807408 | 95807408 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 17 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | TIM096-R7 JYP TIM TIM096 TBG BAYANGKARA |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.468/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 33219980 | 10364513 | 43584493 | 43584493 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 22 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | TIM097-R7 JYP TIM TIM097 TBG DEWANTARA |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.469/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 30378938 | 11083445 | 41462383 | 41462383 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 23 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | TIM286-R7 JYP TIM TIM286 TBG BATALYON754 |  | 95 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.470/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 6817664 | 2292786 | 9110450 | 9110450 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 24 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | TIM062-R7 JYP TIM TIM062 TBG SP7 |  | 95 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.471/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 366181536 | 78423949 | 444605485 | 444605485 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 26 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | TIM365-R7 JYP TIM TIM365 TBG Pasar Sentral |  | 95 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.473/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 103654875 | 26714421 | 130369296 | 130369296 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 25 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | TIM235-R7 JYP TIM TIM235 TBG Mandiri Jaya |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.472/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 164969903 | 35460735 | 200430638 | 200430638 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 13 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK265-R7 JYP MRK MRK265 DMT Semangga Jaya 2 |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.460/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 69640491 | 15750553 | 85391044 | 85391044 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 14 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK211-R7 JYP MRK MRK211 Wasur |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.462/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 2552337 | 1533099 | 4085436 | 4085436 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 15 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK166-R7 JYP MRK MRK166 TBG Buti |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.474/LG.000/R7W-7C100000/2021 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 13120682 | 4319293 | 17439975 | 17439975 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 16 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK144-R7 JYP TIM MRK144 TBG MERAUKE |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.475/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 15950839 | 5707075 | 21657914 | 21657914 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 20 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK186-R7 JYP MRK MRK186 TBG Samkai |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.461/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 9072319 | 3784819 | 12857138 | 12857138 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 21 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK263-R7 JYP MRK263 HIDUP BARU |  | 95 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.463/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 92675266 | 26611119 | 119286385 | 119286385 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
G2022057 | 1 | 12 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002287/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 20 LOP Periode April 2022 Area Witel Papua | 2022-04-27 | 2022-06-25 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | MRK208- R7 JYP MRK MRK208 TBG Dermaga Macan Tutul |  | 50 | 100 | 100 | BAST-1 | 2022-04-27 | 2022-06-25 | 2022-05-01 | TEL.459/LG.270/R7W-7B100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7B100000/2022 | 2022-06-14 | 123811412 | 27968269 | 151779681 | 151779681 | 4500459245 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-23
12022125 | 4 | 93 | 01C11H01 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | FAK-FAK | FAK-FAK |  |  |  | 20 | 90 | 0 | Siap UT | 2022-04-28 | 2022-10-29 | 2022-07-28 |  |  |  |  | 234531768 | 118240328 | 352772096 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 29 | 01C11H01 | 019 | 74020026 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | FAK-FAK | FAK-FAK |  |  |  | 50 | 90 | 0 | Siap UT | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 237194226 | 638070994 | 875265220 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 94 | 01C11H01 | 019 | 74020007 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | FAK-FAK | KAIMANA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-04-28 | 2022-10-29 | 2022-07-28 |  |  |  |  | 184544274 | 111492016 | 296036290 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 30 | 01C11H01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | JAYAPURA | JAYAPURA |  |  |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 228419234 | 550307831 | 778727065 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 72 | 01C11H01 | 019 | 74030060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | JAYAPURA | SARMI |  |  |  | 50 | 100 | 100 | BAST-1 | 2022-04-28 | 2022-09-25 | 2022-06-28 | TEL.1847/LG.310/DID-B0400000/2022 | 2022-06-29 | TEL.0954/LG.320/DID-A0000000/2022 | 2022-06-29 | 17549984 | 175526326 | 193076310 | 193076310 | 4500459283 |  |  |  |  | NEC INDONESIA | 2022-06-30
12022125 | 4 | 13 | 01C11H01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | JAYAPURA | SENTANI |  | CLS |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-06-29 |  |  |  |  | 1772182995 | 238360932 | 2010543927 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 12 | 01C11H01 | 019 | 74030063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | JAYAPURA | SENTANI |  | TLS |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-06-29 |  |  |  |  | 272076070 | 36730269 | 308806339 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 92 | 01C11H01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | JAYAPURA | TIMIKA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-04-28 | 2022-10-29 | 2022-07-28 |  |  |  |  | 184544274 | 111492016 | 296036290 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 36 | 01C11H01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | JAYAPURA | TIMIKA |  |  |  | 50 | 90 | 0 | Siap UT | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 60039846 | 267840996 | 327880842 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 87 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | MANADO | PANIKI |  |  |  | 50 | 100 | 100 | BAST-1 | 2022-04-28 | 2022-09-25 | 2022-07-07 | TEL.2143/LG.310/DID-B0400000/2022 | 2022-07-28 | TEL.1056/LG.320/DID-A0000000/2022 | 2022-07-28 | 8774992 | 87763163 | 96538155 | 96538155 | 4500459283 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022125 | 4 | 33 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | MANADO | PANIKI |  |  |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 1915514604 | 535718703 | 2451233307 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 18 | 01C11H01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | MANADO | PANIKI |  |  |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-06-29 |  |  |  |  | 1265559272 | 311839103 | 1577398375 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 91 | 01C11H01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | MERAUKE | MERAUKE |  |  |  | 20 | 90 | 0 | Siap UT | 2022-04-28 | 2022-10-29 | 2022-07-28 |  |  |  |  | 184544274 | 111492016 | 296036290 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 47 | 01C11H01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | MERAUKE | MERAUKE |  |  |  | 50 | 90 | 0 | Siap UT | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 184544274 | 111492016 | 296036290 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 35 | 01C11H01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | SORONG | SORONG |  |  |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 245969218 | 725834157 | 971803375 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 56 | 01C11H01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | SORONG | SORONG |  |  |  | 50 | 70 | 0 | Instalasi | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 200816898 | 113688821 | 314505719 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 84 | 01C11H01 | 019 | 74060052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | SORONG | WAISAI |  |  |  | 50 | 100 | 100 | BAST-1 | 2022-04-28 | 2022-09-25 | 2022-07-18 | TEL.2142/LG.310/DID-B0400000/2022 | 2022-07-28 | TEL.1055/LG.320/DID-A0000000/2022 | 2022-07-28 | 16026120 | 2163526 | 18189646 | 18189646 | 4500459283 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022125 | 4 | 15 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 50 | 20 | 0 | Preparing | 2022-04-28 | 2022-09-25 | 2022-06-29 |  |  |  |  | 1294433611 | 315737138 | 1610170749 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 26 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 2013150674 | 551714323 | 2564864997 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 82 | 01C11H01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | UJUNGPANDANG | BALAIKOTA |  |  |  | 50 | 100 | 100 | BAST-1 | 2022-04-28 | 2022-09-25 | 2022-07-18 | TEL.2142/LG.310/DID-B0400000/2022 | 2022-07-28 | TEL.1055/LG.320/DID-A0000000/2022 | 2022-07-28 | 1934338854 | 540783553 | 2475122407 | 2475122407 | 4500459283 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022125 | 4 | 51 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | UJUNGPANDANG | PETTARANI |  |  |  | 50 | 90 | 0 | Siap UT | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 2098235194 | 561259506 | 2659494700 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022125 | 4 | 32 | 01C11H01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002357/HK.810/OPS-10000000/2022 | SP#1 ISP SKKL Repeatered System Platform NEC | 2022-04-28 | 2022-10-28 | ISP SKKL | UJUNGPANDANG | PETTARANI |  |  |  | 50 | 50 | 0 | Mat. Delivery | 2022-04-28 | 2022-09-25 | 2022-07-19 |  |  |  |  | 2197975396 | 586468792 | 2784444188 | 0 | 4500459283 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 24 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#1.1 High Cap Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1788/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 1925563444 | 406577956 | 2332141400 | 2332141400 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 25 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#2.1 Redeploy Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1789/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 1984643882 | 856377856 | 2841021738 | 2841021738 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 26 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#3.1 Upgrade Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1790/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 5958102368 | 1160774709 | 7118877077 | 7118877077 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 47 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#5.1 BHP ISR Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1876/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 476794092 | 476794092 | 476794092 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 45 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#1.2 High Cap Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-30 | TEL.2193/LG.310/DID-C0300000/2022 | 2022-06-30 | TEL.0932/LG.320/DID-A0000000/2022 | 2022-06-30 | 3310186180 | 587065762 | 3897251942 | 3897251942 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-06-30
12022126 | 6 | 71 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#1.4 High Cap Sumalpua |  | 50 | 20 | 0 | Preparing | 2022-07-28 | 2022-10-01 | 2022-07-29 |  |  |  |  | 21417052230 | 3495527620 | 24912579850 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 72 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#3.4 Upgrade Sumalpua |  | 50 | 20 | 0 | Preparing | 2022-07-28 | 2022-10-01 | 2022-07-29 |  |  |  |  | 14219746659 | 4676999298 | 18896745957 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 48 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#5.2 BHP ISR Sumalpua |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-10-01 | 2022-06-29 |  |  |  |  | 0 | 3904656236 | 3904656236 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 46 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#3.2 Upgrade Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-30 | TEL.2271/LG.310/DID-C0300000/2022 | 2022-06-30 | TEL.0932/LG.320/DID-A0000000/2022 | 2022-06-30 | 747082661 | 150744483 | 897827144 | 897827144 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-06-30
12022126 | 6 | 60 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#2.2 Redeploy Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-30 | TEL.2197/LG.310/DID-C0300000/2022 | 2022-06-30 | TEL.0932/LG.320/DID-A0000000/2022 | 2022-06-30 | 1136139558 | 670992158 | 1807131716 | 1807131716 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-06-30
12022126 | 6 | 58 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#1.3 High Cap Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-29 | TEL.2650/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1122/LG.320/DID-A0000000/2022 | 2022-07-29 | 486160762 | 117315612 | 603476374 | 603476374 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022126 | 6 | 59 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#3.3 Upgrade Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-29 | TEL.2757/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1122/LG.320/DID-A0000000/2022 | 2022-07-29 | 338089740 | 156561706 | 494651446 | 494651446 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022126 | 6 | 70 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#2.3 Redeploy Sumalpua |  | 50 | 100 | 100 | BAST-1 | 2022-07-28 | 2022-10-01 | 2022-07-29 | TEL.2754/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1122/LG.320/DID-A0000000/2022 | 2022-07-29 | 181253686 | 172808654 | 354062340 | 354062340 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022126 | 6 | 66 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#3.4 Upgrade Bali Nusra |  | 50 | 20 | 0 | Preparing | 2022-07-28 | 2022-10-01 | 2022-07-29 |  |  |  |  | 12153937638 | 2056203122 | 14210140760 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 22 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#2.1 Redeploy Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1783/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 281360234 | 207741982 | 489102216 | 489102216 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 21 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#1.1 High Cap Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1782/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 345989533 | 69728732 | 415718265 | 415718265 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 54 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#3.3 Upgrade Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-29 | TEL.2755/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1122/LG.320/DID-A0000000/2022 | 2022-07-29 | 882735970 | 164945028 | 1047680998 | 1047680998 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022126 | 6 | 53 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#2.3 Redeploy Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-29 | TEL.2752/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1122/LG.320/DID-A0000000/2022 | 2022-07-29 | 202881520 | 89829286 | 292710806 | 292710806 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022126 | 6 | 52 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#1.3 High Cap Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-29 | TEL.2648/LG.310/DID-C0300000/2022 | 2022-07-29 | TEL.1122/LG.320/DID-A0000000/2022 | 2022-07-29 | 129257468 | 25820412 | 155077880 | 155077880 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-07-29
12022126 | 6 | 34 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#5.2 BHP ISR Bali Nusra |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-10-01 | 2022-06-29 |  |  |  |  | 0 | 2608271760 | 2608271760 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 64 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#2.4 Redeploy Bali Nusra |  | 50 | 20 | 0 | Preparing | 2022-07-28 | 2022-10-01 | 2022-07-29 |  |  |  |  | 29949432 | 29677426 | 59626858 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 65 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#1.4 High Cap Bali Nusra |  | 50 | 20 | 0 | Preparing | 2022-07-28 | 2022-10-01 | 2022-07-29 |  |  |  |  | 8104642208 | 713426336 | 8818068544 | 0 | 4500459291 |  |  |  |  | NEC INDONESIA
12022126 | 6 | 23 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#3.1 Upgrade Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1784/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 826952742 | 119079504 | 946032246 | 946032246 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 35 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#5.1 BHP ISR Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-10-01 | 2022-05-30 | TEL.1874/LG.310/DID-C0300000/2022 | 2022-05-30 | TEL.0661/LG.320/DID-A0000000/2022 | 2022-05-30 | 0 | 294378784 | 294378784 | 294378784 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-05-31
12022126 | 6 | 31 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#1.2 High Cap Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-30 | TEL.2191/LG.310/DID-C0300000/2022 | 2022-06-30 | TEL.0932/LG.320/DID-A0000000/2022 | 2022-06-30 | 343876135 | 69728732 | 413604867 | 413604867 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-06-30
12022126 | 6 | 32 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#2.2 Redeploy Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-30 | TEL.2195/LG.310/DID-C0300000/2022 | 2022-06-30 | TEL.0932/LG.320/DID-A0000000/2022 | 2022-06-30 | 98991685 | 89032278 | 188023963 | 188023963 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-06-30
12022126 | 6 | 33 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002358/HK.810/OPS-10000000/2022 | SP#2 Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-04-28 | 2022-09-24 | IP RADIO | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#3.2 Upgrade Bali Nusra |  | 50 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-10-01 | 2022-06-30 | TEL.2199/LG.310/DID-C0300000/2022 | 2022-06-30 | TEL.0932/LG.320/DID-A0000000/2022 | 2022-06-30 | 1930045208 | 350699190 | 2280744398 | 2280744398 | 4500459291 |  |  |  |  | NEC INDONESIA | 2022-06-30
G2022058 | 1 | 10 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI043-DMT Manokwari Bintuni |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.336/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 130715959 | 28720394 | 159436353 | 159436353 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 8 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI005-Combat LNG Steenkul |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.332/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 284362355 | 81527370 | 365889725 | 365889725 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 7 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI107-TBG Kampung Bina |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.331/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 63377546 | 14412968 | 77790514 | 77790514 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 13 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI103-DMT Raya Bintuni |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.340/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 40025393 | 9280755 | 49306148 | 49306148 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 12 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI029-Tbg Teenkol |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.338/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 7697457 | 3278435 | 10975892 | 10975892 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 11 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI044-DMT Bintuni Timur 2 |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.337/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 60710162 | 20647922 | 81358084 | 81358084 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 9 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI102-TBG Manokwari Bintuni |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.335/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 16042899 | 4157101 | 20200000 | 20200000 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 20 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | MANOKWARI | BINTUNI |  | BTI101-DMT Bina Desa |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.334/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 22788675 | 5042914 | 27831589 | 27831589 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 14 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR111-PADARNI |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.333/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 9831052 | 3183191 | 13014243 | 13014243 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 15 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR366-MWR366 |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.339/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 302265927 | 129008776 | 431274703 | 431274703 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 19 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | SORONG | SERUI |  | SRU128-SRU128 |  | 100 | 90 | 0 | Siap UT | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.548/LG.000/R7W-7H100000/2022 | 2022-08-13 |  |  | 33859570 | 8935683 | 42795253 | 0 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO
G2022058 | 1 | 18 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | SORONG | SERUI |  | SRU108-DMT Warari Yapen |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.343/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 6577807 | 2937735 | 9515542 | 9515542 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 17 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | SORONG | SERUI |  | SRU109-DMT BAWAI |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.342/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 50387626 | 11589764 | 61977390 | 61977390 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022058 | 1 | 16 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002385/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 14 LOP AREA WITEL PAPUA BARAT | 2022-04-29 | 2022-06-27 | FIMO NODE-B 2022 | SORONG | SERUI |  | SRU031-CMI Iriwi Mariadei |  | 100 | 100 | 100 | BAST-1 | 2022-04-29 | 2022-06-27 | 2022-05-01 | TEL.341/LG000/R7W-7H100000/2022 | 2022-06-06 | TEL.0004/LG.320/R7W-7H100000/2022 | 2022-06-06 | 5327178 | 2073991 | 7401169 | 7401169 | 4500459671 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-08
G2022059 | 2 | 6 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002395/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 3 LoP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-05-09 | 2022-08-05 | FIMO NODE-B 2022 | UJUNGPANDANG | TAKALAR |  | R7 MKS TKA TKA104 TBG Pelabuhan Galesong |  | 100 | 0 | 0 | Preparing | 2022-06-01 | 2022-07-22 | [5 empty] | 105471207 | 30338016 | 135809223 | 0 | 4500459752 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022059 | 2 | 8 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002395/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 3 LoP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-05-09 | 2022-08-05 | FIMO NODE-B 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP WTP037 ULAWENG |  | 100 | 0 | 0 | Preparing | 2022-06-01 | 2022-07-22 | [5 empty] | 8414251 | 2758936 | 11173187 | 0 | 4500459752 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022059 | 2 | 7 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.002395/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 3 LoP Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-05-09 | 2022-08-05 | FIMO NODE-B 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP WTP089 Protelindo Saungeng |  | 100 | 0 | 0 | Preparing | 2022-06-01 | 2022-07-22 | [5 empty] | 324601853 | 59183207 | 383785060 | 0 | 4500459752 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022060 | 1 | 7 | 01E07O02 | 007 | 72030099 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.002425/HK.810/R7W-7C100000/2022 | FIMO NODE B 1 LOP WITEL SULTENG | 2022-05-11 | 2022-06-24 | FIMO NODE-B 2022 | PALU | KOTARAYA |  | R7 PLA KOR PGI118 TBG Wanamukti Utara |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-24 | 2022-05-11 | TEL.43/LG000/R7W-7C100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7C100000/2022 | 2022-06-14 | 463136967 | 78101077 | 541238044 | 541238044 | 4500460132 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-06-22
G2022061 | 1 | 38 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | AMBON |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.594/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 613703430 | 0 | 613703430 | 613703430 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 40 | 01E07Y05 | 007 | 73010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | BANDA NEIRA |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.596/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 1519560 | 0 | 1519560 | 1519560 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 39 | 01E07Y05 | 007 | 73010013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | BULA |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.595/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 26644480 | 0 | 26644480 | 26644480 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 41 | 01E07Y05 | 007 | 73010120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | DOBO |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.597/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 26273680 | 0 | 26273680 | 26273680 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 42 | 01E07Y05 | 007 | 73010125 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | LARAT |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.598/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 443360 | 0 | 443360 | 443360 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 43 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | MASOHI |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.599/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 110801520 | 0 | 110801520 | 110801520 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 44 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | NAMLEA |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.600/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 42651920 | 0 | 42651920 | 42651920 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 45 | 01E07Y05 | 007 | 73010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | NAMROLE |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-20 | 2022-05-11 | C.TEL.601/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 7301080 | 0 | 7301080 | 7301080 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 46 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | PASSO |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.602/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 292179120 | 0 | 292179120 | 292179120 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 47 | 01E07Y05 | 007 | 73010059 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | PIRU |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.603/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 11150800 | 0 | 11150800 | 11150800 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 48 | 01E07Y05 | 007 | 73010071 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | SAPARUA |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.604/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 5360440 | 0 | 5360440 | 5360440 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 49 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | SAUMLAKI |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.605/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 22066920 | 0 | 22066920 | 22066920 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 50 | 01E07Y05 | 007 | 73010172 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | TIAKUR |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.606/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 3673080 | 0 | 3673080 | 3673080 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 51 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | TUAL |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.607/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 150737740 | 0 | 150737740 | 150737740 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 52 | 01E07Y05 | 007 | 73010089 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | AMBON | WAHAI |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-20 | 2022-05-11 | C.TEL.608/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 5230800 | 0 | 5230800 | 5230800 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 14 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | GORONTALO | GORONTALO |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-19 | 2022-05-11 | C.TEL.570/LG300/DR7-12800000/2022 | 2022-05-20 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 218210300 | 0 | 218210300 | 218210300 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 15 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | GORONTALO | ISIMU |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-19 | 2022-05-11 | C.TEL.571/LG300/DR7-12800000/2022 | 2022-05-20 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 39582450 | 0 | 39582450 | 39582450 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 16 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | GORONTALO | KWANDANG |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-19 | 2022-05-11 | C.TEL.572/LG300/DR7-12800000/2022 | 2022-05-20 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 12299100 | 0 | 12299100 | 12299100 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 17 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | GORONTALO | LIMBOTO |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-19 | 2022-05-11 | C.TEL.573/LG300/DR7-12800000/2022 | 2022-05-20 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 39107370 | 0 | 39107370 | 39107370 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 18 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | GORONTALO | MARISA |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-19 | 2022-05-11 | C.TEL.574/LG300/DR7-12800000/2022 | 2022-05-20 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 49856570 | 0 | 49856570 | 49856570 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 19 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | GORONTALO | TELAGA |  | PEKERJAAN QE ACCESS PERIODE FEB-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-19 | 2022-05-11 | C.TEL.575/LG300/DR7-12800000/2022 | 2022-05-20 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 36323070 | 0 | 36323070 | 36323070 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 53 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | ABEPURA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.609/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 22421880 | 0 | 22421880 | 22421880 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 54 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.610/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 15529320 | 0 | 15529320 | 15529320 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 55 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.611/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 7145200 | 0 | 7145200 | 7145200 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 56 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.612/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2992140 | 0 | 2992140 | 2992140 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 58 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | SARMI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.614/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 4081920 | 0 | 4081920 | 4081920 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 59 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | SENTANI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.615/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 20888680 | 0 | 20888680 | 20888680 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 61 | 01E07Y05 | 007 | 74030067 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | TEMBAGAPURA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.617/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 417900 | 0 | 417900 | 417900 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 62 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | TIMIKA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.618/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 9821860 | 0 | 9821860 | 9821860 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 63 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | WAENA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.619/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 11830820 | 0 | 11830820 | 11830820 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 64 | 01E07Y05 | 007 | 74030073 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | JAYAPURA | WAMENA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.620/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 417900 | 0 | 417900 | 417900 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 108 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | BAU-BAU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.664/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 70019430 | 0 | 70019430 | 70019430 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 109 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | KENDARI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.665/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 118138130 | 0 | 118138130 | 118138130 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 110 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | KOLAKA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.666/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 23024520 | 0 | 23024520 | 23024520 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 111 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | LASUSUA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.667/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 10607330 | 0 | 10607330 | 10607330 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 112 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | MANDONGA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.668/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 146091910 | 0 | 146091910 | 146091910 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 113 | 01E07Y05 | 007 | 72050082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | POMAALA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.669/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 9629150 | 0 | 9629150 | 9629150 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 114 | 01E07Y05 | 007 | 72050057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | RAHA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.670/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 3609150 | 0 | 3609150 | 3609150 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 115 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | UNAAHA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.671/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 16004660 | 0 | 16004660 | 16004660 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 116 | 01E07Y05 | 007 | 72050074 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | KENDARI | WANCI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-16 | 2022-05-11 | C.TEL.672/LG300/DR7-12800000/2022 | 2022-05-27 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 3913230 | 0 | 3913230 | 3913230 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 117 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | AIR MADIDI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 50 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-22 | 2022-05-11 | C.TEL.673/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 159911000 | 0 | 159911000 | 159911000 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 118 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | AMURANG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.674/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 15118500 | 0 | 15118500 | 15118500 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 119 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | BAHU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.675/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 141138480 | 0 | 141138480 | 141138480 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 120 | 01E07Y05 | 007 | 72010258 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | BEO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.676/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 5640000 | 0 | 5640000 | 5640000 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 121 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | BITUNG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.677/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 145722360 | 0 | 145722360 | 145722360 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 122 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | BOROKO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.678/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 7129800 | 0 | 7129800 | 7129800 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 123 | 01E07Y05 | 007 | 72010267 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | HULU SIAU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.679/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2263200 | 0 | 2263200 | 2263200 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 124 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | KAUDITAN |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.680/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 20765700 | 0 | 20765700 | 20765700 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 125 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | KOTAMOBAGU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.681/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 76346700 | 0 | 76346700 | 76346700 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 126 | 01E07Y05 | 007 | 72010055 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | LANGOAN |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.682/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 59208900 | 0 | 59208900 | 59208900 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 127 | 01E07Y05 | 007 | 72010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | LOLAK |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.683/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2033400 | 0 | 2033400 | 2033400 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 129 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | MANADO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.685/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 216064190 | 0 | 216064190 | 216064190 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 128 | 01E07Y05 | 007 | 72010077 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | MOLIBAGU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.684/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 319500 | 0 | 319500 | 319500 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 130 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | PANIKI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.686/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 50145900 | 0 | 50145900 | 50145900 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 131 | 01E07Y05 | 007 | 72010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | TAHUNA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.687/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 9264000 | 0 | 9264000 | 9264000 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 132 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | TOMOHON |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.688/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 37342200 | 0 | 37342200 | 37342200 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 133 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | TONDANO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.689/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 71839800 | 0 | 71839800 | 71839800 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 134 | 01E07Y05 | 007 | 72010283 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MANADO | TUTUYAN |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.690/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 6959400 | 0 | 6959400 | 6959400 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 57 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MERAUKE | MERAUKE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.613/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 20573470 | 0 | 20573470 | 20573470 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 60 | 01E07Y05 | 007 | 74050022 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | MERAUKE | TANAH MERAH |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-23 | 2022-05-11 | C.TEL.616/LG300/DR7-12800000/2022 | 2022-05-19 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 1253700 | 0 | 1253700 | 1253700 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 93 | 01E07Y05 | 007 | 72030159 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | AMPANA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.649/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 736980 | 0 | 736980 | 736980 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 95 | 01E07Y05 | 007 | 72030123 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | BANGGAI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.651/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2836500 | 0 | 2836500 | 2836500 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 94 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | BUNGKU |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.650/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 11300340 | 0 | 11300340 | 11300340 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 96 | 01E07Y05 | 007 | 72030013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | BUOL |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.652/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 4237200 | 0 | 4237200 | 4237200 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 97 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | DONGGALA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.653/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 5301340 | 0 | 5301340 | 5301340 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 98 | 01E07Y05 | 007 | 72030104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | KOLONODALE |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.654/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 3026250 | 0 | 3026250 | 3026250 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 99 | 01E07Y05 | 007 | 72030099 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | KOTARAYA |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.655/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 5084640 | 0 | 5084640 | 5084640 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 107 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | LUWUK |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.656/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 18971210 | 0 | 18971210 | 18971210 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 100 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | PALU A |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.657/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 35127400 | 0 | 35127400 | 35127400 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 101 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | PALU B |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.658/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 49101820 | 0 | 49101820 | 49101820 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 102 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | PARIGI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.659/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 8866230 | 0 | 8866230 | 8866230 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 103 | 01E07Y05 | 007 | 72030101 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | POSO |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.660/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 8820600 | 0 | 8820600 | 8820600 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 104 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | TAWAELI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.661/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 246530 | 0 | 246530 | 246530 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 105 | 01E07Y05 | 007 | 72030083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | TOLAY |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.662/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 426210 | 0 | 426210 | 426210 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 106 | 01E07Y05 | 007 | 72030084 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PALU | TOLI-TOLI |  | PEKERJAAN QE ACCESS PERIODE JANUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-31 | 2022-05-11 | C.TEL.663/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 1529190 | 0 | 1529190 | 1529190 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 69 | 01E07Y05 | 007 | 72040275 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | AJANGALE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.625/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 116270 | 0 | 116270 | 116270 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 70 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | BARRU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.626/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 19264280 | 0 | 19264280 | 19264280 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 71 | 01E07Y05 | 007 | 72040044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | CANGADI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.627/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 1109450 | 0 | 1109450 | 1109450 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 72 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | ENREKANG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.628/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 5667500 | 0 | 5667500 | 5667500 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 73 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | MAJENE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.629/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 22731350 | 0 | 22731350 | 22731350 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 74 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | MAKALE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.630/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 27027360 | 0 | 27027360 | 27027360 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 75 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | MALILI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.631/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2274160 | 0 | 2274160 | 2274160 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 76 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | MAMASA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.632/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 708300 | 0 | 708300 | 708300 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 77 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | MAMUJU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.633/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 113323020 | 0 | 113323020 | 113323020 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 78 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | MASAMBA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.634/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 23170700 | 0 | 23170700 | 23170700 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 79 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | PALOPO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.635/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 56238030 | 0 | 56238030 | 56238030 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 80 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | PARE-PARE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.636/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 65174890 | 0 | 65174890 | 65174890 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 81 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.637/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 1458960 | 0 | 1458960 | 1458960 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 82 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | PINRANG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.638/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 48017040 | 0 | 48017040 | 48017040 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 83 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | POLEWALI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.639/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2088110 | 0 | 2088110 | 2088110 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 84 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | RANTEPAO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.640/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 25875200 | 0 | 25875200 | 25875200 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 85 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | RAPPANG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.641/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 15061880 | 0 | 15061880 | 15061880 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 86 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | SENGKANG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.642/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 19518130 | 0 | 19518130 | 19518130 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 87 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | SIDRAP |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.643/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 22571360 | 0 | 22571360 | 22571360 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 88 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | SIWA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.644/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 3973680 | 0 | 3973680 | 3973680 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 89 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | SOROWAKO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.645/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 8484360 | 0 | 8484360 | 8484360 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 90 | 01E07Y05 | 007 | 72040174 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | TANRUTEDONG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.646/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 4190440 | 0 | 4190440 | 4190440 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 91 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.647/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 659580 | 0 | 659580 | 659580 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 92 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | PARE-PARE | WONOMULYO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-06-02 | 2022-05-11 | C.TEL.648/LG300/DR7-12800000/2022 | 2022-05-23 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 16808800 | 0 | 16808800 | 16808800 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 65 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | SORONG | BIAK |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-24 | 2022-05-11 | C.TEL.621/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 60463060 | 0 | 60463060 | 60463060 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 66 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | SORONG | FAKFAK |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-24 | 2022-05-11 | C.TEL.622/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 162813080 | 0 | 162813080 | 162813080 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 67 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | SORONG | MANOKWARI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-24 | 2022-05-11 | C.TEL.623/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 67042050 | 0 | 67042050 | 67042050 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 68 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | SORONG | SORONG |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-24 | 2022-05-11 | C.TEL.624/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 215077410 | 0 | 215077410 | 215077410 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 135 | 01E07Y05 | 007 | 73020005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | GALELA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.691/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 18453960 | 0 | 18453960 | 18453960 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 136 | 01E07Y05 | 007 | 73020009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | JAILOLO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.692/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 14475360 | 0 | 14475360 | 14475360 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 137 | 01E07Y05 | 007 | 73020013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | LABUHA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.693/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 53618840 | 0 | 53618840 | 53618840 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 138 | 01E07Y05 | 007 | 73020057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | MANGOLE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.694/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 8383620 | 0 | 8383620 | 8383620 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 139 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | MOROTAI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.695/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 10913920 | 0 | 10913920 | 10913920 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 140 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | SANANA |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.696/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 4016240 | 0 | 4016240 | 4016240 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 141 | 01E07Y05 | 007 | 73020034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | SOA SIU |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.697/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 1674720 | 0 | 1674720 | 1674720 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 143 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | SOFIFI |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.698/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 56424120 | 0 | 56424120 | 56424120 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 144 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | TERNATE |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.699/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 240524620 | 0 | 240524620 | 240524620 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 145 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | TERNATE | TOBELO |  | PEKERJAAN QE ACCESS PERIODE FEBRUARI-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-22 | 2022-05-11 | C.TEL.700/LG300/DR7-12800000/2022 | 2022-06-07 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 94528760 | 0 | 94528760 | 94528760 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 20 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.576/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 83045830 | 37017260 | 120063090 | 120063090 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 21 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.577/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 48080520 | 1144570 | 49225090 | 49225090 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 22 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.578/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 23756730 | 0 | 23756730 | 23756730 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 23 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-17 | 2022-05-11 | C.TEL.579/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 25250440 | 0 | 25250440 | 25250440 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 24 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.580/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 28140430 | 11734480 | 39874910 | 39874910 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 25 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | KIMA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-17 | 2022-05-11 | C.TEL.581/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 7565080 | 1276100 | 8841180 | 8841180 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 26 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | MALINO |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-17 | 2022-05-11 | C.TEL.582/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 2304470 | 0 | 2304470 | 2304470 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 27 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | MAROS |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.583/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 7088530 | 0 | 7088530 | 7088530 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 28 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.584/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 109769360 | 27961900 | 137731260 | 137731260 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 29 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.585/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 302607600 | 169447770 | 472055370 | 472055370 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 30 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.586/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 8555670 | 0 | 8555670 | 8555670 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 31 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.587/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 19750930 | 0 | 19750930 | 19750930 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 32 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.588/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 21665080 | 5576800 | 27241880 | 27241880 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 33 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.589/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 39126900 | 6088700 | 45215600 | 45215600 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 34 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.590/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 123076760 | 27456980 | 150533740 | 150533740 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 35 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.591/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 53091510 | 10941500 | 64033010 | 64033010 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 36 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.592/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 33537680 | 6034200 | 39571880 | 39571880 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
G2022061 | 1 | 37 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002426/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE Access 131 LOP Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sultra, Sulteng dan Sulut Malut | 2022-05-11 | 2022-06-24 | QE AKSES | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE ACCESS PERIODE DESEMBER 2021, FEB-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-11 | 2022-05-18 | 2022-05-11 | C.TEL.593/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0094/LG.320/DR7-10400000/2022 | 2022-06-13 | 98704030 | 44069750 | 142773780 | 142773780 | 4500460133 |  |  |  |  | TELKOM AKSES | 2022-06-18
12022128 | 3 | 15 | 01C11B01 | 019 | 74060063 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002559/HK.810/OPS-10000000/2022 | SP#9 Ekspan PE VPN Cisco | 2022-05-18 | 2022-11-13 | Ekspan PE-VPN Cisco | SORONG | SORONG-1 |  | sr-sorong.1-new |  | 50 | 100 | 100 | BAST-1 | 2022-05-18 | 2022-11-13 | 2022-05-18 | TEL.1173/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1096/LG.320/DID-A0000000/2022 | 2022-07-27 | 431450100 | 32257800 | 463707900 | 463707900 | 4500460070 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-07-29
12022128 | 3 | 16 | 01C11B01 | 019 | 74060060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002559/HK.810/OPS-10000000/2022 | SP#9 Ekspan PE VPN Cisco | 2022-05-18 | 2022-11-13 | Ekspan PE-VPN Cisco | SORONG | SORONG-2 |  | sr-sorong.2-new |  | 50 | 100 | 100 | BAST-1 | 2022-05-18 | 2022-11-13 | 2022-05-18 | TEL.1173/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1096/LG.320/DID-A0000000/2022 | 2022-07-27 | 431450100 | 32257800 | 463707900 | 463707900 | 4500460070 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-07-29
12022128 | 3 | 14 | 01C11B01 | 019 | 72080167 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002559/HK.810/OPS-10000000/2022 | SP#9 Ekspan PE VPN Cisco | 2022-05-18 | 2022-11-13 | Ekspan PE-VPN Cisco | UJUNGPANDANG | SUDIANG |  | core-sudiang.1-new |  | 50 | 100 | 100 | BAST-1 | 2022-05-18 | 2022-11-13 | 2022-05-18 | TEL.1173/LG.310/DID-B0300000/2022 | 2022-07-27 | TEL.1096/LG.320/DID-A0000000/2022 | 2022-07-27 | 3880318400 | 291043100 | 4171361500 | 4171361500 | 4500460070 |  |  |  |  | SISINDOKOM LINTASBUANA | 2022-07-29
G2022062 | 1 | 6 | 01E07R03 | 007 | 73020034 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002682/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 2 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-05-20 | 2022-06-18 | OSP-FO | TERNATE | SOA SIU |  | R7 MDO SSI TDE052 MAHTUTU |  | 95 | 100 | 100 | BAST-1 | 2022-05-20 | 2022-06-18 | 2022-05-20 | TEL.580/LG.300/R7W-7F100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7F100000/2022 | 2022-06-14 | 737553848 | 169050207 | 906604055 | 906604055 | 4500461402 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-06-20
G2022062 | 1 | 7 | 01E07R03 | 007 | 73020041 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.002682/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 2 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-05-20 | 2022-06-18 | OSP-FO | TERNATE | TERNATE |  | R7 MDO TNT TER199 GIPSI PUNCAK |  | 95 | 100 | 100 | BAST-1 | 2022-05-20 | 2022-06-18 | 2022-05-20 | TEL.581/LG.300/R7W-7F100000/2022 | 2022-06-14 | TEL.0002/LG.320/R7W-7F100000/2022 | 2022-06-14 | 12953925 | 4130669 | 17084594 | 17084594 | 4500461402 |  |  |  |  | SOLUSI AKSES MANDIRI | 2022-06-20
G2022063 | 2 | 8 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002684/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Februari 2022 Area Witel Gorontalo | 2022-05-20 | 2022-06-18 | HEM | GORONTALO | GORONTALO |  | R7 GTO GTL HEM KKP PRATAMA GORONTALO |  | 100 | 100 | 100 | BAST-1 | 2022-05-20 | 2022-06-09 | 2022-05-20 | TEL.962/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0091/LG.320/DR7-10400000/2022 | 2022-06-11 | 7249351 | 1968301 | 9217652 | 9217652 | 4500461281 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022063 | 2 | 6 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002684/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Februari 2022 Area Witel Gorontalo | 2022-05-20 | 2022-06-18 | HEM | GORONTALO | GORONTALO |  | R7 GTO GTL HEM ULANTA GTL-FCB |  | 100 | 100 | 100 | BAST-1 | 2022-05-20 | 2022-06-09 | 2022-05-20 | TEL.960/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0091/LG.320/DR7-10400000/2022 | 2022-06-11 | 38655043 | 10762036 | 49417079 | 49417079 | 4500461281 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022063 | 2 | 7 | 01E07V06 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002684/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Februari 2022 Area Witel Gorontalo | 2022-05-20 | 2022-06-18 | HEM | GORONTALO | KWANDANG |  | R7 GTO KWD HEM HEM PTLU TANJUNG KARANG |  | 100 | 100 | 100 | BAST-1 | 2022-05-20 | 2022-06-09 | 2022-05-20 | TEL.961/LG.310/DR7-12700000/2022 | 2022-06-11 | TEL.0091/LG.320/DR7-10400000/2022 | 2022-06-11 | 50395191 | 14725085 | 65120276 | 65120276 | 4500461281 |  |  |  |  | TELKOM AKSES | 2022-06-17
12022132 | 1 | 115 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | AMBON | AMBON |  | PE-D7-AB1-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 1512594000 | 134599000 | 1647193000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 82 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | JAYAPURA | JAYAPURA |  | PE-D7-JAP-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 0 | 80000000 | 80000000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 118 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | JAYAPURA | JAYAPURA |  | PE-D7-JAP-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 237000000 | 22130000 | 259130000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 86 | 01C11B01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | JAYAPURA | TIMIKA |  | PE-D7-TIM-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 0 | 80000000 | 80000000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 95 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | MANADO | MANADO |  | R7.MDO.PE-SN.1 |  | 50 | 20 | 0 | Preparing | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 398326000 | 31550000 | 429876000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 81 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | MANADO | MANADO |  | PE-D7-MDO-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 0 | 80000000 | 80000000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 64 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | MANADO | MANADO |  | PE-D7-MDO-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 948000000 | 88520000 | 1036520000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 143 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | MANADO | PANIKI |  | PE-D7-PNK-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 0 | 80000000 | 80000000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 68 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | PALU | PALU-1 |  | PE-D7-PL1-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 3562474000 | 327812000 | 3890286000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 79 | 01C11B01 | 019 | 72030155 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | PALU | PALU-1 |  | PE-D7-PAL.1-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 0 | 80000000 | 80000000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 69 | 01C11B01 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | PALU | PALU-2 |  | PE-D7-PL2-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 3562474000 | 327812000 | 3890286000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 80 | 01C11B01 | 019 | 72030156 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | PALU | PALU-2 |  | PE-D7-PAL.2-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 0 | 80000000 | 80000000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 117 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | SORONG | SORONG |  | PE-D7-SON-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 1474757000 | 128244000 | 1603001000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 33 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | SORONG | SORONG |  | PE-D7-SON-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 118500000 | 11065000 | 129565000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 116 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | TERNATE | TERNATE |  | PE-D7-TNT-HSI |  | 50 | 50 | 0 | Mat. Delivery | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 199163000 | 15775000 | 214938000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 141 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | UJUNGPANDANG | BALAIKOTA |  | R7.BAL.DCN-SN.1 |  | 50 | 20 | 0 | Preparing | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 685344000 | 59176000 | 744520000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 102 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | UJUNGPANDANG | BALAIKOTA |  | R7.BAL.PE-SN.2 |  | 50 | 20 | 0 | Preparing | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 398326000 | 31550000 | 429876000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 63 | 01C11B01 | 019 | 72080163 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | UJUNGPANDANG | BALAIKOTA |  | PE-D7-BAL-HSI |  | 50 | 90 | 0 | Siap UT | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 474000000 | 44260000 | 518260000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 101 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | UJUNGPANDANG | PETTARANI |  | R7.PTR.PE-SN.1 |  | 50 | 20 | 0 | Preparing | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 534731000 | 268128000 | 802859000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
12022132 | 1 | 142 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002692/HK.810/OPS-10000000/2022 | SP#4 Ekspan PE Platform Juniper | 2022-05-23 | 2022-11-18 | Ekspan PE Platform Juniper | UJUNGPANDANG | PETTARANI |  | R7.PTR.DCN-SN.1 |  | 50 | 20 | 0 | Preparing | 2022-05-23 | 2022-11-18 | 2022-06-08 |  |  |  |  | 685344000 | 59176000 | 744520000 | 0 | 4500460413 |  |  |  |  | NEC INDONESIA
G2022064 | 1 | 6 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002705/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile Lastmile HEM Untuk Pelanggan EGBIS 1 LOP Area Witel Gorontalo | 2022-05-23 | 2022-07-06 | HEM | GORONTALO | MARISA |  | R7 GTO MRS HEM PLTG MALEO PAGUAT |  | 20 | 100 | 100 | BAST-1 | 2022-05-24 | 2022-07-05 | 2022-06-03 | TEL.951/LG.310/DR7-12700000/2022 | 2022-06-03 | TEL.0083/LG.320/DR7-10400000/2022 | 2022-06-03 | 321690671 | 80286131 | 401976802 | 401976802 | 4500461521 |  |  |  |  | MITRATAMA ENERGI SELEBES | 2022-06-14
12022135 | 3 | 23 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.002708/HK.810/OPS-10000000/2022 | Surat Pesanan-5 (SP#5) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2022-05-23 | 2022-08-20 | Refurbished NTE | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-23 | 2022-06-01 | C.TEL1053/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0076/LG.320/COP-F3000000/2022 | 2022-06-21 | 0 | 787700000 | 787700000 | 787700000 | 4500461507 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-06-23
12022135 | 3 | 13 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.002708/HK.810/OPS-10000000/2022 | Surat Pesanan-5 (SP#5) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2022-05-23 | 2022-08-20 | Refurbished NTE | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 100 | 100 | 100 | BAST-1 | 2022-05-23 | 2022-05-27 | 2022-05-23 | C.TEL706/LG300/DR7-12800000/2022 | 2022-05-25 | TEL.0072/LG.320/COP-F3000000/2022 | 2022-05-25 | 0 | 512060000 | 512060000 | 512060000 | 4500461507 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-05-27
12022135 | 3 | 31 | 01E-7C01 | 000 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SSO PROCUREMENT & SOURCING | K.TEL.002708/HK.810/OPS-10000000/2022 | Surat Pesanan-5 (SP#5) Pengadaan Pekerjaan Refurbished NTE Indihome Segmen Consumer | 2022-05-23 | 2022-08-20 | Refurbished NTE | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 95 | 100 | 100 | BAST-1 | 2022-06-16 | 2022-07-15 | 2022-06-16 | C.TEL1083/LG300/DR7-12800000/2022 | 2022-07-12 | TEL.0084/LG.320/COP-F3000000/2022 | 2022-07-12 | 0 | 827787000 | 827787000 | 827787000 | 4500461507 |  |  |  |  | PERUSAHAAN PERSEROAN (PERSERO) PT. INDUSTRI TELEKOMUNIKASI INDONESIA | 2022-07-15
G2022065 | 1 | 7 | 01E07T02 | 007 | 74010005 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002820/HK.810/R7W-7H100000/2022 | PENGADAAN PELAKSANAAN PEKERJAAN LASTMILE HEM EGBIS 3 LOP AREA WITEL PAPUA BARAT | 2022-05-25 | 2022-07-23 | HEM | BIAK | BIAK |  | R7 SON BIA HEM KANTOR BUPATI |  | 100 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-06-07 | 2022-05-25 | TEL.387/LG.000/R7W-7H100000/2022 | 2022-06-13 | TEL.0005/LG.320/R7W-7H100000/2022 | 2022-06-14 | 3763514 | 832852 | 4596366 | 4596366 | 4500461974 |  |  |  |  | TELKOM AKSES | 2022-06-16
G2022065 | 1 | 6 | 01E07T02 | 007 | 74060027 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002820/HK.810/R7W-7H100000/2022 | PENGADAAN PELAKSANAAN PEKERJAAN LASTMILE HEM EGBIS 3 LOP AREA WITEL PAPUA BARAT | 2022-05-25 | 2022-07-23 | HEM | SORONG | TEMINABUAN |  | R7 SON TMB HEM PERKANTORAN BUPATI |  | 100 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-06-07 | 2022-05-25 | TEL.382/LG.000/R7W-7H100000/2022 | 2022-06-14 | TEL.0005/LG.320/R7W-7H100000/2022 | 2022-06-14 | 177959471 | 36053410 | 214012881 | 214012881 | 4500461974 |  |  |  |  | TELKOM AKSES | 2022-06-16
G2022065 | 1 | 8 | 01E07T02 | 007 | 74060027 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002820/HK.810/R7W-7H100000/2022 | PENGADAAN PELAKSANAAN PEKERJAAN LASTMILE HEM EGBIS 3 LOP AREA WITEL PAPUA BARAT | 2022-05-25 | 2022-07-23 | HEM | SORONG | TEMINABUAN |  | R7 SON TMB HEM KODIM TEMINABUAN |  | 100 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-06-04 | 2022-05-25 | TEL.381/LG.000/R7W-7H100000/2022 | 2022-06-14 | TEL.0005/LG.320/R7W-7H100000/2022 | 2022-06-14 | 16286011 | 2734378 | 19020389 | 19020389 | 4500461974 |  |  |  |  | TELKOM AKSES | 2022-06-16
12022138 | 4 | 290 | 01C11G01 | 019 | 73010013 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | BULA | 2894950#2894955 | MSH094 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 823395763 | 169408899 | 992804662 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 267 | 01C11G01 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | MASOHI | 2893871#2893876 | MSH039 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1762028 | 2018744 | 3780772 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 268 | 01C11G01 | 019 | 73010042 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | MASOHI | 2893503#2893508 | MSH043 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 7972529053 | 1358388481 | 9330917534 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 272 | 01C11G01 | 019 | 73010059 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | PIRU | 2893503#2893508 | MSH024 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1762028 | 2018744 | 3780772 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 273 | 01C11G01 | 019 | 73010059 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | PIRU | 2894218#2894223 | MSH074 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 3938966830 | 689840053 | 4628806883 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 277 | 01C11G01 | 019 | 73010089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | WAHAI | 2893871#2893876 | MSH078 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1762028 | 2018744 | 3780772 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 276 | 01C11G01 | 019 | 73010089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | WAHAI | 2893871#2893876 | MSH038 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 10773049012 | 2037634754 | 12810683766 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 275 | 01C11G01 | 019 | 73010089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | AMBON | WAHAI | 2893871#2893876 | MSH029 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1762028 | 2018744 | 3780772 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 230 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | KENDARI | BAU-BAU | 2878404#2878409 | BAU006 |  | 20 | 90 | 0 | Siap UT | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 378638910 | 73879306 | 452518216 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 237 | 01C11G01 | 019 | 72050084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | KENDARI | BULUKUMBA | 2887030#2887035 | BLK007 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2583/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 245208041 | 60216477 | 305424518 | 305424518 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 234 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | KENDARI | RAHA | 2876301#2876306 | RHA021 |  | 20 | 90 | 0 | Siap UT | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1058060421 | 194838708 | 1252899129 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 235 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | KENDARI | RAHA | 2875790#2875795 | RHA057 |  | 20 | 60 | 0 | Instalasi | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 8615727 | 3575765 | 12191492 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 233 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | KENDARI | RAHA | 2880058#2880063 | RHA015 |  | 20 | 60 | 0 | Instalasi | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 651293736 | 113479146 | 764772882 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 236 | 01C11G01 | 019 | 72050072 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | KENDARI | UNAAHA | 2878846#2878851 | ADL045 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-30 | TEL.2225/LG.310/DID-C0300000/2022 | 2022-06-25 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 394689526 | 70583686 | 465273212 | 465273212 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 223 | 01C11G01 | 019 | 72010077 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | MANADO | MOLIBAGU | 2893183#2893188 | KTG113 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 23014833 | 5892822 | 28907655 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 286 | 01C11G01 | 019 | 74040016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | MANOKWARI | WARMARE | 2916352#2916357 | MWR013 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 11799468 | 3587908 | 15387376 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 285 | 01C11G01 | 019 | 74040016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | MANOKWARI | WARMARE | 2911967#2911972 | MWR021 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 3867812 | 2362732 | 6230544 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 350 | 01C11G01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | MERAUKE | MERAUKE | 2903496#2903503 | MRK139 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 40108089 | 11705562 | 51813651 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 348 | 01C11G01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | MERAUKE | MERAUKE | 2903496#2903503 | MRK704 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 258580684 | 60064650 | 318645334 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 279 | 01C11G01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | MERAUKE | MERAUKE | 2903496#2903503 | MRK021 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 2754593424 | 601156959 | 3355750383 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 243 | 01C11G01 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | BANGGAI | 2902141#2902146 | SAK022 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1659112193 | 321333546 | 1980445739 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 242 | 01C11G01 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | BANGGAI | 2902141#2902146 | SAK002 |  | 20 | 85 | 0 | Instalasi | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 60414200 | 10773670 | 71187870 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 244 | 01C11G01 | 019 | 72030123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | BANGGAI | 2902141#2902146 | SAK075 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 19683225 | 5540488 | 25223713 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 344 | 01C11G01 | 019 | 72030012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | BUNGKU | 2901840#2901845 | MRW920 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 12884410 | 4540011 | 17424421 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 246 | 01C11G01 | 019 | 72030012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | BUNGKU | 2901840#2901845 | MRW094 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1377749524 | 238652996 | 1616402520 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 247 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | DONGGALA | 2903892#2903897 | DGL034 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1235996928 | 219135561 | 1455132489 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 248 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | DONGGALA | 2897368#2897373 | DGL051 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-26 | TEL.2301/LG.310/DID-C0300000/2022 | 2022-06-25 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 1214681909 | 249160877 | 1463842786 | 1463842786 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 249 | 01C11G01 | 019 | 72030017 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | DONGGALA | 2903892#2903897 | DGL087 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-26 | TEL.2230/LG.310/DID-C0300000/2022 | 2022-06-25 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 111762952 | 22198160 | 133961112 | 133961112 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 250 | 01C11G01 | 019 | 72030104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | KOLONODALE | 2901920#2901925 | MRW114 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2731/LG.310/DID-C0300000/2022 | 2022-07-27 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 193867956 | 34624643 | 228492599 | 228492599 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 252 | 01C11G01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | LUWUK | 2896852#2896857 | LWK017 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2701/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 1647768226 | 306674092 | 1954442318 | 1954442318 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 253 | 01C11G01 | 019 | 72030125 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | PAGIMANA | 2902155#2902160 | LWK016 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1735334828 | 320955932 | 2056290760 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 254 | 01C11G01 | 019 | 72030092 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | PALU B | 2899544#2899549 | DGL016 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 2597378636 | 462821534 | 3060200170 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 255 | 01C11G01 | 019 | 72030061 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | PARIGI | 2906807#2906814 | PGI007 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1786579529 | 1675173524 | 3461753053 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 257 | 01C11G01 | 019 | 72030088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | TAWAELI | 2903892#2903897 | DGL117 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-27 | 2229/LG.310/DID-C0300000/2022 | 2022-06-25 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 33664880 | 11484625 | 45149505 | 45149505 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 259 | 01C11G01 | 019 | 72030081 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | TINOMBO | 2906807#2906814 | PGI063 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 16078216 | 10932759 | 27010975 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 260 | 01C11G01 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PALU | TOLI-TOLI | 2906828#2906833 | TLI036 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 3350500344 | 593157821 | 3943658165 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 261 | 01C11G01 | 019 | 72040193 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PARE-PARE | BARRU | 2918642#2918647 | BAR008 |  | 20 | 55 | 0 | Instalasi | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 361384412 | 99671590 | 461056002 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 262 | 01C11G01 | 019 | 72040086 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PARE-PARE | MAMASA | 2910452#2910457 | MMS007 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2582/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 797957667 | 167458243 | 965415910 | 965415910 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 263 | 01C11G01 | 019 | 72040088 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PARE-PARE | MAMUJU | 2916645#2916650 | MAM077 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2702/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 20245388 | 4669592 | 24914980 | 24914980 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 264 | 01C11G01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PARE-PARE | PASANG KAYU | 2921352#2921358 | COI021 |  | 20 | 55 | 0 | Instalasi | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 451457727 | 82071040 | 533528767 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 265 | 01C11G01 | 019 | 72040161 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | PARE-PARE | SOROWAKO | 2911082#2911087 | MLI073 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1740878002 | 306721284 | 2047599286 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 281 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | SORONG | NABIRE | 2907101#2907106 | NAB004 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 3158062 | 1834420 | 4992482 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 282 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | SORONG | NABIRE | 2907101#2907106 | NAB202 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1022611682 | 243063369 | 1265675051 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 283 | 01C11G01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | SORONG | SORONG | 2906053#2906058 | SON002 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 2493704910 | 584168905 | 3077873815 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 345 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2893965#2893970 | MBA021 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-26 | TEL.2238/LG.310/DID-C0300000/2022 | 2022-06-26 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 23195897 | 7576001 | 30771898 | 30771898 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 225 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2893965#2893970 | MBA009 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-26 | TEL.2237/LG.310/DID-C0300000/2022 | 2022-06-26 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 454521572 | 107105464 | 561627036 | 561627036 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 226 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2895112#2895117 | TDE009 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1098484531 | 1544932233 | 2643416764 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 227 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2893857#2893862 | TOB012 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 3092373176 | 3874750522 | 6967123698 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 346 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2893965#2893970 | TER037 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 15829295 | 3574670 | 19403965 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 224 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2896101#2896106 | SSU001 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2581/LG.310/DID-C0300000/2022 | 2022-07-23 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 5693337 | 2281611 | 7974948 | 7974948 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 347 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | TERNATE | SOFIFI | 2893857#2893862 | TER010 |  | 20 | 50 | 0 | Mat. Delivery | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 180631601 | 251246107 | 431877708 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
12022138 | 4 | 238 | 01C11G01 | 019 | 72080054 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | UJUNGPANDANG | JENEPONTO | 2892506#2892512 | SNS111 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-07-01 | TEL.2592/LG.310/DID-C0300000/2022 | 2022-07-24 | TEL.1121/LG.320/DID-A0000000/2022 | 2022-07-27 | 830567419 | 146849317 | 977416736 | 977416736 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-07-29
12022138 | 4 | 239 | 01C11G01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | UJUNGPANDANG | SELAYAR | 2892560#2892565 | SLY002 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-26 | TEL.2161/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 14334468 | 3466074 | 17800542 | 17800542 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 240 | 01C11G01 | 019 | 72080112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | UJUNGPANDANG | SELAYAR | 2888494#2888499 | SLY021 |  | 20 | 100 | 100 | BAST-1 | 2022-05-25 | 2022-12-04 | 2022-05-26 | TEL.2162/LG.310/DID-C0300000/2022 | 2022-06-27 | TEL.0898/LG.320/DID-A0000000/2022 | 2022-06-27 | 569354394 | 100257704 | 669612098 | 669612098 | 4500460169 |  |  |  |  | TELKOM AKSES | 2022-06-30
12022138 | 4 | 241 | 01C11G01 | 019 | 72080199 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002856/HK.810/OPS-10000000/2022 | SP#13 OSP FO Node-B Telkomsel Tahap-2 | 2022-05-25 | 2022-11-20 | Node-B 2022 (DID) | UJUNGPANDANG | WATAMPONE | 2888833#2888838 | WTP015 |  | 20 | 85 | 0 | Instalasi | 2022-05-25 | 2022-12-04 | 2022-07-01 |  |  |  |  | 1510679134 | 340108789 | 1850787923 | 0 | 4500460169 |  |  |  |  | TELKOM AKSES
G2022066 | 2 | 7 | 01E07V06 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002879/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Maret Tahun 2022 Area Witel Gorontalo | 2022-05-27 | 2022-06-25 | HEM | GORONTALO | KWANDANG |  | R7 GTO KWD HEM POI Kwandang |  | 80 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-23 | 2022-05-30 | TEL.964/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0092/LG.320/DR7-10400000/2022 | 2022-06-13 | 2205067 | 2102940 | 4308007 | 4308007 | 4500462018 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022066 | 2 | 6 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.002879/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Periode Maret Tahun 2022 Area Witel Gorontalo | 2022-05-27 | 2022-06-25 | HEM | GORONTALO | MARISA |  | R7 GTO MRS HEM POI Marisa |  | 80 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-23 | 2022-05-30 | TEL.963/LG.310/DR7-12700000/2022 | 2022-06-13 | TEL.0092/LG.320/DR7-10400000/2022 | 2022-06-13 | 2211362 | 2137032 | 4348394 | 4348394 | 4500462018 |  |  |  |  | TELKOM AKSES | 2022-06-17
G2022067 | 1 | 33 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | ABEPURA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.731/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 33811270 | 23839970 | 57651240 | 57651240 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 34 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-08 | 2022-05-27 | C.TEL.732/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 30245670 | 18516980 | 48762650 | 48762650 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 35 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.733/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 16813740 | 3071550 | 19885290 | 19885290 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 36 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.734/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 14966680 | 5242200 | 20208880 | 20208880 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 38 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | SENTANI |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.736/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 23547410 | 11229970 | 34777380 | 34777380 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 39 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | TIMIKA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.737/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 12606300 | 3309910 | 15916210 | 15916210 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 40 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | JAYAPURA | WAENA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.738/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 3884250 | 4651950 | 8536200 | 8536200 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 37 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | MERAUKE | MERAUKE |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-06-09 | 2022-05-27 | C.TEL.735/LG300/DR7-12800000/2022 | 2022-06-06 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 2021300 | 361330 | 2382630 | 2382630 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 41 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | BARRU |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.739/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 5161620 | 5263630 | 10425250 | 10425250 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 42 | 01E07Y05 | 007 | 72040044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | CANGADI |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.740/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 6528000 | 4295270 | 10823270 | 10823270 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 43 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | MAJENE |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.741/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 4127900 | 2837840 | 6965740 | 6965740 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 44 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | MAKALE |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.742/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 12779290 | 10261310 | 23040600 | 23040600 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 45 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | MALILI |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.743/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 0 | 124060 | 124060 | 124060 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 46 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | MAMUJU |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.744/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 9879560 | 7807340 | 17686900 | 17686900 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 47 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | MASAMBA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.745/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 5937420 | 7338350 | 13275770 | 13275770 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 48 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | PALOPO |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.746/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 12733740 | 11027850 | 23761590 | 23761590 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 49 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | PARE-PARE |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.747/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 7511980 | 21256210 | 28768190 | 28768190 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 50 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.748/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 1332000 | 352590 | 1684590 | 1684590 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 51 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | PINRANG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.749/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 7175620 | 6822270 | 13997890 | 13997890 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 52 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | POLEWALI |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.750/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 1813090 | 360980 | 2174070 | 2174070 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 53 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | RANTEPAO |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.751/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 6577250 | 4446560 | 11023810 | 11023810 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 54 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | RAPPANG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.752/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 774450 | 1638490 | 2412940 | 2412940 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 55 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | SENGKANG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.753/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 7139010 | 8033770 | 15172780 | 15172780 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 56 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | SIDRAP |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.754/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 3324260 | 5173210 | 8497470 | 8497470 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 57 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | SOROWAKO |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.755/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 226940 | 2779890 | 3006830 | 3006830 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 59 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.756/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 0 | 124060 | 124060 | 124060 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 60 | 01E07Y05 | 007 | 72040187 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | PARE-PARE | WONOMULYO |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.757/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 1813090 | 421980 | 2235070 | 2235070 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 12 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.713/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 32196200 | 17286310 | 49482510 | 49482510 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 14 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-05-30 | C.TEL.714/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 23093270 | 15059950 | 38153220 | 38153220 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 15 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.715/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 9730600 | 4113010 | 13843610 | 13843610 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 16 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.716/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 4148640 | 4014770 | 8163410 | 8163410 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 18 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.717/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 3074700 | 1329070 | 4403770 | 4403770 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 19 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | KIMA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.718/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 5903320 | 4568140 | 10471460 | 10471460 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 20 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | MALINO |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.719/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 0 | 1302630 | 1302630 | 1302630 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 22 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | MAROS |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.720/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 8142820 | 6207700 | 14350520 | 14350520 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 23 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.721/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 51391030 | 40126700 | 91517730 | 91517730 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 24 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.722/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 47745740 | 64720910 | 112466650 | 112466650 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 25 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-05-30 | C.TEL.723/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 35678050 | 24624450 | 60302500 | 60302500 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 26 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.724/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 40800360 | 9917640 | 50718000 | 50718000 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 27 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.725/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 15031670 | 9935660 | 24967330 | 24967330 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 28 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-06-08 | 2022-05-30 | C.TEL.726/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 34338970 | 28620810 | 62959780 | 62959780 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 29 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-05-30 | C.TEL.727/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 48667970 | 21457940 | 70125910 | 70125910 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 30 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.728/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 43345270 | 33009240 | 76354510 | 76354510 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 31 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.729/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 16919710 | 8950280 | 25869990 | 25869990 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022067 | 1 | 32 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002909/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE Recovery 45 Lop Area Witel Makassar, Papua dan Sulselbar | 2022-05-27 | 2022-07-10 | QE RECOVERY | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE RECOVERY PERIODE FEBRUARI 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-05-30 | C.TEL.730/LG300/DR7-12800000/2022 | 2022-06-16 | TEL.0100/LG.320/DR7-10400000/2022 | 2022-06-16 | 10768720 | 6918710 | 17687430 | 17687430 | 4500462226 |  |  |  |  | TELKOM AKSES | 2022-06-29
12022141 | 3 | 23 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | AMBON | AMBON |  | PE-D7-AB1-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.984/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0863/LG.320/DID-A0000000/2022 | 2022-06-28 | 1599503000 | 159950300 | 1759453300 | 1759453300 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-29
12022141 | 3 | 21 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | AMBON | AMBON |  | PE-D7-AB1-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.983/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0864/LG.320/DID-A0000000/2022 | 2022-06-28 | 0 | 22500000 | 22500000 | 22500000 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-29
12022141 | 3 | 22 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | MANADO | PANIKI |  | PE-D7-PNK-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.984/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0863/LG.320/DID-A0000000/2022 | 2022-06-28 | 1599503000 | 159950300 | 1759453300 | 1759453300 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-29
12022141 | 3 | 19 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | MANADO | PANIKI |  | PE-D7-PNK-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.983/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0864/LG.320/DID-A0000000/2022 | 2022-06-28 | 0 | 22500000 | 22500000 | 22500000 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-29
12022141 | 3 | 26 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | PALU | PALU |  | PE-D7-PL1-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.1176/LG.310/DID-B0300000/2022 | 2022-07-26 | TEL.1049/LG.320/DID-A0000000/2022 | 2022-07-26 | 9121221000 | 752122100 | 9873343100 | 9873343100 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12022141 | 3 | 28 | 01C11B01 | 019 | 72030058 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | PALU | PALU |  | PE-D7-PL2-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.1176/LG.310/DID-B0300000/2022 | 2022-07-26 | TEL.1049/LG.320/DID-A0000000/2022 | 2022-07-26 | 9121221000 | 752122100 | 9873343100 | 9873343100 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-07-29
12022141 | 3 | 33 | 01C11B01 | 019 | 72080175 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.002920/HK.810/OPS-10000000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PE Transit Platform Huawei | 2022-05-27 | 2022-10-23 | Ekspan PE Transit | UJUNGPANDANG | PETTARANI |  | PE4-D7-PTR-TRANSIT |  | 50 | 100 | 100 | BAST-1 | 2022-05-27 | 2022-10-23 | 2022-06-10 | TEL.985/LG.310/DID-B0300000/2022 | 2022-06-28 | TEL.0865/LG.320/DID-A0000000/2022 | 2022-06-28 | 882740000 | 88274000 | 971014000 | 971014000 | 4500462010 |  |  |  |  | HUAWEI TECH INVESTMENT | 2022-06-29
G2022068 | 1 | 6 | 01E07T02 | 007 | 74040005 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002949/HK.810/R7W-7H100000/2022 | PENGADAAN PELAKSANAAN PEKERJAAN LASTMILE HEM EGBIS 2 LOP AREA WITEL PAPUA BARAT | 2022-05-30 | 2022-07-28 | HEM | MANOKWARI | MANOKWARI |  | R7 SON MWR HEM COGINDO MANSEL |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-07-28 | 2022-06-01 | TEL.416/LG000/R7W-7H100000/2022 | 2022-07-04 | TEL.0006/LG.320/R7W-7H100000/2022 | 2022-07-04 | 54476752 | 11854167 | 66330919 | 66330919 | 4500462458 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-12
G2022068 | 1 | 7 | 01E07T02 | 007 | 74040005 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.002949/HK.810/R7W-7H100000/2022 | PENGADAAN PELAKSANAAN PEKERJAAN LASTMILE HEM EGBIS 2 LOP AREA WITEL PAPUA BARAT | 2022-05-30 | 2022-07-28 | HEM | MANOKWARI | MANOKWARI |  | R7 SON MWR HEM SORIBO MANOKWARI |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-07-28 | 2022-06-01 | TEL.417/LG000/R7W-7H100000/2022 | 2022-07-04 | TEL.0006/LG.320/R7W-7H100000/2022 | 2022-07-04 | 413414439 | 90568639 | 503983078 | 503983078 | 4500462458 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-12
G2022069 | 1 | 42 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | AMBON |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.781/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 19611040 | 0 | 19611040 | 19611040 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 46 | 01E07Y05 | 007 | 73010013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | BULA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.785/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 507680 | 0 | 507680 | 507680 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 47 | 01E07Y05 | 007 | 73010120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | DOBO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.786/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 121680 | 0 | 121680 | 121680 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 44 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | MASOHI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.783/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 507680 | 0 | 507680 | 507680 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 43 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | PASSO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.782/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 7590760 | 0 | 7590760 | 7590760 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 45 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | SAUMLAKI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.784/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 497760 | 0 | 497760 | 497760 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 48 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | AMBON | TUAL |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.787/LG300/DR7-12800000/2022 | 2022-06-21 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 121680 | 0 | 121680 | 121680 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 19 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | GORONTALO | GORONTALO |  | PEKERJAAN QE HEM PERIODE DESEMBER 2021 |  | 95 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-30 | 2022-05-30 | C.TEL.758/LG300/DR7-12800000/2022 | 2022-06-08 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 10505160 | 0 | 10505160 | 10505160 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 22 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | GORONTALO | ISIMU |  | PEKERJAAN QE HEM PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-30 | 2022-05-30 | C.TEL.761/LG300/DR7-12800000/2022 | 2022-06-08 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2243640 | 0 | 2243640 | 2243640 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 23 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | GORONTALO | KWANDANG |  | PEKERJAAN QE HEM PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-30 | 2022-05-30 | C.TEL.762/LG300/DR7-12800000/2022 | 2022-06-08 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 662400 | 0 | 662400 | 662400 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 21 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | GORONTALO | LIMBOTO |  | PEKERJAAN QE HEM PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-30 | 2022-05-30 | C.TEL.760/LG300/DR7-12800000/2022 | 2022-06-08 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1139220 | 0 | 1139220 | 1139220 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 24 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | GORONTALO | MARISA |  | PEKERJAAN QE HEM PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-30 | 2022-05-30 | C.TEL.763/LG300/DR7-12800000/2022 | 2022-06-08 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2193060 | 0 | 2193060 | 2193060 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 20 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | GORONTALO | TELAGA |  | PEKERJAAN QE HEM PERIODE DESEMBER 2021 |  | 90 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-30 | 2022-05-30 | C.TEL.759/LG300/DR7-12800000/2022 | 2022-06-08 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 949560 | 0 | 949560 | 949560 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 50 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | ABEPURA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.788/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2209550 | 0 | 2209550 | 2209550 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 51 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.789/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6778390 | 0 | 6778390 | 6778390 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 52 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.790/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1040000 | 0 | 1040000 | 1040000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 53 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.791/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 93940 | 0 | 93940 | 93940 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 55 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | SARMI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.793/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 624000 | 0 | 624000 | 624000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 56 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | SENTANI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.794/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2839250 | 0 | 2839250 | 2839250 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 57 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | TIMIKA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.795/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1664000 | 0 | 1664000 | 1664000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 58 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | WAENA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.796/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1040000 | 0 | 1040000 | 1040000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 59 | 01E07Y05 | 007 | 74030073 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | JAYAPURA | WAMENA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.797/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 750700 | 0 | 750700 | 750700 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 93 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | BAU-BAU |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.829/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 3037820 | 0 | 3037820 | 3037820 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 94 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | KENDARI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.830/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6018000 | 0 | 6018000 | 6018000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 95 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | KOLAKA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.831/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1026780 | 0 | 1026780 | 1026780 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 96 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | LASUSUA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.832/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 5063420 | 2297290 | 7360710 | 7360710 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 97 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | MANDONGA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.833/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 9464320 | 0 | 9464320 | 9464320 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 98 | 01E07Y05 | 007 | 72050050 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | POMALAA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.834/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 441180 | 0 | 441180 | 441180 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 99 | 01E07Y05 | 007 | 72050057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | RAHA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.835/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 292800 | 0 | 292800 | 292800 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 100 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | UNAAHA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.836/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 173160 | 0 | 173160 | 173160 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 101 | 01E07Y05 | 007 | 72050074 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | KENDARI | WANCI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-04 | 2022-06-01 | C.TEL.837/LG300/DR7-12800000/2022 | 2022-06-13 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 350520 | 0 | 350520 | 350520 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 102 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | AIR MADIDI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.838/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 8829000 | 0 | 8829000 | 8829000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 103 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | AMURANG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.839/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1422600 | 0 | 1422600 | 1422600 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 104 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | BAHU |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.840/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 12489600 | 0 | 12489600 | 12489600 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 105 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | BITUNG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.841/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 10161000 | 0 | 10161000 | 10161000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 106 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | BOROKO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.842/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 594000 | 0 | 594000 | 594000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 107 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | KAUDITAN |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.843/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1544400 | 0 | 1544400 | 1544400 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 108 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | KOTAMOBAGU |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.844/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 957000 | 0 | 957000 | 957000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 109 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | LANGOWAN |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.845/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 522600 | 0 | 522600 | 522600 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 110 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | MANADO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.846/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 15716700 | 0 | 15716700 | 15716700 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 111 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | PANIKI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.847/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1675500 | 0 | 1675500 | 1675500 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 113 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | TOMOHON |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.849/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2425800 | 0 | 2425800 | 2425800 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 112 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MANADO | TONDANO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.848/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1034400 | 0 | 1034400 | 1034400 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 54 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | MERAUKE | MERAUKE |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-13 | 2022-05-30 | C.TEL.792/LG300/DR7-12800000/2022 | 2022-06-10 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2600000 | 0 | 2600000 | 2600000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 87 | 01E07Y05 | 007 | 72030123 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | BANGGAI |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.823/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 367660 | 0 | 367660 | 367660 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 89 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | BUNGKU |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.825/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 370980 | 0 | 370980 | 370980 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 84 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | DONGGALA |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.821/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 924960 | 0 | 924960 | 924960 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 92 | 01E07Y05 | 007 | 72030099 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | KOTARAYA |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.828/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 184660 | 0 | 184660 | 184660 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 90 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | LUWUK |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.826/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 13022100 | 8228600 | 21250700 | 21250700 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 81 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | PALU A |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.818/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 24491810 | 7297340 | 31789150 | 31789150 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 82 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | PALU B |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.819/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 9048830 | 3630480 | 12679310 | 12679310 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 85 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | PARIGI |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.822/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 919980 | 0 | 919980 | 919980 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 88 | 01E07Y05 | 007 | 72030101 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | POSO |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.824/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 3844640 | 2255220 | 6099860 | 6099860 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 83 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | TAWAELI |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.820/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 7041230 | 3277220 | 10318450 | 10318450 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 91 | 01E07Y05 | 007 | 72030084 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PALU | TOLI-TOLI |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 50 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-28 | 2022-05-31 | C.TEL.827/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1769080 | 0 | 1769080 | 1769080 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 64 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | BARRU |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-11 | 2022-06-01 | C.TEL.802/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 3659780 | 0 | 3659780 | 3659780 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 65 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | ENREKANG |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.803/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2222640 | 0 | 2222640 | 2222640 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 66 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | MALILI |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.804/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 191800 | 0 | 191800 | 191800 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 67 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | MAMASA |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.805/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 461900 | 0 | 461900 | 461900 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 68 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | MAMUJU |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.806/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6177300 | 0 | 6177300 | 6177300 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 69 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | MASAMBA |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.807/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1751700 | 0 | 1751700 | 1751700 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 70 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | PALOPO |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.808/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6203020 | 0 | 6203020 | 6203020 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 72 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | PARE-PARE |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.809/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 7446260 | 0 | 7446260 | 7446260 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 73 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.810/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1471880 | 0 | 1471880 | 1471880 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 74 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | PINRANG |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.811/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1156140 | 0 | 1156140 | 1156140 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 75 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | POLEWALI |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.812/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1504540 | 0 | 1504540 | 1504540 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 76 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | RANTEPAO |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.813/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2562000 | 0 | 2562000 | 2562000 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 77 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | RAPPANG |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.814/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 95900 | 0 | 95900 | 95900 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 78 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | SENGKANG |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.815/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 772540 | 0 | 772540 | 772540 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 79 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | SIDRAP |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.816/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1649780 | 0 | 1649780 | 1649780 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 80 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | PARE-PARE | SIWA |  | PEKERJAAN QE HEM NOVEMBER-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-10 | 2022-06-01 | C.TEL.817/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 415340 | 0 | 415340 | 415340 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 63 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | SORONG | BIAK |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-10 | 2022-05-30 | C.TEL.801/LG300/DR7-12800000/2022 | 2022-06-04 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6949280 | 0 | 6949280 | 6949280 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 61 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | SORONG | FAKFAK |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-10 | 2022-05-30 | C.TEL.799/LG300/DR7-12800000/2022 | 2022-06-04 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 4291040 | 0 | 4291040 | 4291040 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 62 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | SORONG | MANOKWARI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-10 | 2022-05-30 | C.TEL.800/LG300/DR7-12800000/2022 | 2022-06-04 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6617170 | 0 | 6617170 | 6617170 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 60 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | SORONG | SORONG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-10 | 2022-05-30 | C.TEL.798/LG300/DR7-12800000/2022 | 2022-06-04 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 29195890 | 0 | 29195890 | 29195890 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 114 | 01E07Y05 | 007 | 73020013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | TERNATE | LABUHA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.850/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1447500 | 0 | 1447500 | 1447500 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 117 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | TERNATE | MOROTAI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.854/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 309680 | 0 | 309680 | 309680 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 119 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | TERNATE | SANANA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.853/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 501800 | 0 | 501800 | 501800 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 115 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | TERNATE | SOFIFI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.851/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2874040 | 0 | 2874040 | 2874040 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 116 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | TERNATE | TERNATE |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.852/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 29607380 | 0 | 29607380 | 29607380 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 118 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | TERNATE | TOBELO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-05-30 | 2022-06-12 | 2022-05-30 | C.TEL.855/LG300/DR7-12800000/2022 | 2022-06-15 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2997160 | 0 | 2997160 | 2997160 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 25 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.764/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2990390 | 0 | 2990390 | 2990390 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 26 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.765/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 6722620 | 0 | 6722620 | 6722620 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 27 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.766/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 427870 | 0 | 427870 | 427870 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 28 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.767/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1038160 | 0 | 1038160 | 1038160 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 29 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.768/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 836200 | 0 | 836200 | 836200 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 30 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | KIMA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.769/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 19470270 | 0 | 19470270 | 19470270 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 31 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | MAROS |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.770/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 1711250 | 0 | 1711250 | 1711250 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 32 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.771/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 2890100 | 0 | 2890100 | 2890100 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 33 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.772/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 12401910 | 0 | 12401910 | 12401910 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 34 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.773/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 3913390 | 0 | 3913390 | 3913390 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 35 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.774/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 575430 | 0 | 575430 | 575430 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 36 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.775/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 557960 | 0 | 557960 | 557960 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 37 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-07 | 2022-06-02 | C.TEL.776/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 13126730 | 0 | 13126730 | 13126730 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 38 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.777/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 7193020 | 0 | 7193020 | 7193020 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 39 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-09 | 2022-06-02 | C.TEL.778/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 994970 | 0 | 994970 | 994970 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 40 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.779/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 4761480 | 0 | 4761480 | 4761480 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022069 | 1 | 41 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.002965/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 98 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng Sultra dan Sulut Malut | 2022-05-30 | 2022-07-13 | QE HEM | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE HEM DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-01 | 2022-06-08 | 2022-06-02 | C.TEL.780/LG300/DR7-12800000/2022 | 2022-06-14 | TEL.0101/LG.320/DR7-10400000/2022 | 2022-06-21 | 5079150 | 0 | 5079150 | 5079150 | 4500462224 |  |  |  |  | TELKOM AKSES | 2022-06-29
G2022070 | 2 | 7 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003066/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 2 LOP Maret 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-06-02 | 2022-07-01 | HEM | UJUNGPANDANG | MATTOANGIN |  | SD KATOLIK SANTO YACOBUS |  | 100 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-06-26 | 2022-06-02 | TEL.396/LG310/R7W-7A1C0000/2022 | 2022-07-11 | TEL.0002/LG.320/R7W-7A510000/2022 | 2022-07-11 | 3161553 | 760996 | 3922549 | 3922549 | 4500462715 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-07-26
G2022070 | 2 | 8 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003066/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 2 LOP Maret 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-06-02 | 2022-07-01 | HEM | UJUNGPANDANG | PANAKUKANG |  | GRAHA PENA |  | 100 | 100 | 100 | BAST-1 | 2022-06-02 | 2022-06-26 | 2022-06-02 | TEL.390/LG310/R7W-7A1C0000/2022 | 2022-07-11 | TEL.0002/LG.320/R7W-7A510000/2022 | 2022-07-11 | 10886169 | 3420319 | 14306488 | 14306488 | 4500462715 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-07-26
G2022071 | 0 | 9 | 01E07V06 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD MDO466 TBG Jalan Maumbi |  | 70 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 29396138 | 8994414 | 38390552 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 15 | 01E07V06 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | AMURANG |  | R7 MDO AMR AMR043 |  | 70 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 667425738 | 119314279 | 786740017 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 16 | 01E07V06 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | AMURANG |  | R7 MDO AMR AMR111 |  | 74 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 428770808 | 115149861 | 543920669 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 14 | 01E07V06 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | AMURANG |  | R7 MDO AMR AMR113 |  | 74 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 618450931 | 140090159 | 758541090 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 20 | 01E07V06 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | BITUNG |  | R7 MDO BIT BIT802 |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1190/LG.310/DR7-12700000/2022 | 2022-07-15 |  |  | 9594771 | 2425233 | 12020004 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 21 | 01E07V06 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | BITUNG |  | R7 MDO BIT BIT066 DMT Lingk 3 Pateten 2 |  | 60 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 26311304 | 8880844 | 35192148 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 13 | 01E07V06 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG KTG164 |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1189/LG.310/DR7-12700000/2022 | 2022-07-14 |  |  | 42022108 | 12756718 | 54778826 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 12 | 01E07V06 | 007 | 72010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG KTG908 |  | 74 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 232227004 | 61402042 | 293629046 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 10 | 01E07V06 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | LANGOWAN |  | R7 MDO LAN TDO805 |  | 74 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 64750585 | 20487884 | 85238469 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 19 | 01E07V06 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | LANGOWAN |  | R7 MDO LAN RTN005 DMT COMBAT RASI |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1119/LG.310/DR7-12700000/2022 | 2022-07-23 |  |  | 14272624 | 4064781 | 18337405 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 11 | 01E07V06 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | LANGOWAN |  | R7 MDO LAN COI033 Combat Desa Pangu |  | 74 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 16731383 | 5873356 | 22604739 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 24 | 01E07V06 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH MDO569 DMT MCP Kalasey Mandolang |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1193/LG.310/DR7-12700000/2022 | 2022-07-22 |  |  | 9289214 | 2311096 | 11600310 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 25 | 01E07V06 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH MDO452 MC Santo Yosef Sario |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1195/LG.310/DR7-12700000/2022 | 2022-07-22 |  |  | 12500210 | 3353095 | 15853305 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 17 | 01E07V06 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | PANIKI |  | R7 MDO PIK MDO306 MC Kayuwatu |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1194/LG.310/DR7-12700000/2022 | 2022-07-24 |  |  | 6283349 | 1964509 | 8247858 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 18 | 01E07V06 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | PANIKI |  | R7 MDO PIK TDO158 Kantor Camat Talawaan |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1192/LG.310/DR7-12700000/2022 | 2022-07-24 |  |  | 159434843 | 34146123 | 193580966 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 22 | 01E07V06 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | TAHUNA |  | R7 MDO THN THN111 |  | 74 |  | 0 |  | 2022-06-03 | 2022-08-31 | [5 empty] | 15173804 | 3360045 | 18533849 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 23 | 01E07V06 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | TAHUNA |  | R7 MDO THN THN017 Bebu |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1191LG.310/DR7-12700000/2022 | 2022-07-15 |  |  | 686556277 | 120277483 | 806833760 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 7 | 01E07V06 | 007 | 72010283 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | TUTUYAN |  | R7 MDO TUT KTG131 TBG TUTUYAN |  | 74 | 90 | 0 | Siap UT | 2022-06-03 | 2022-08-31 | 2022-06-03 | TEL.1188/LG.310/DR7-12700000/2022 | 2022-07-14 |  |  | 60159134 | 15413216 | 75572350 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022071 | 0 | 8 | 01E07V06 | 007 | 72010283 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003087/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 19 LoP Witel Sulut Malut | 2022-06-03 | 2022-08-31 | FIMO NODE-B 2022 | MANADO | TUTUYAN |  | R7 MDO TUT KTG133 TBG Tombolikat Selatan |  | 74 | 0 | 0 | Preparing | 2022-06-03 | 2022-08-31 | [5 empty] | 511058502 | 119365129 | 630423631 | 0 | 4500462858 |  |  |  |  | TRANSDATA SATKOMINDO
G2022072 | 0 | 6 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003090/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LoP Periode Februari 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM KASMAWATI & EDWARD |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-13 | [5 empty] | 7481507 | 1634513 | 9116020 | 0 | 4500463069 |  |  |  |  | RATI UTAMA KARYA
G2022072 | 0 | 8 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003090/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LoP Periode Februari 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK HEM NIMROD |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-13 | [5 empty] | 3916487 | 981911 | 4898398 | 0 | 4500463069 |  |  |  |  | RATI UTAMA KARYA
G2022072 | 0 | 9 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003090/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LoP Periode Februari 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD HEM RSPR BIRINGKANAYA |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-13 | [5 empty] | 30371298 | 7330739 | 37702037 | 0 | 4500463069 |  |  |  |  | RATI UTAMA KARYA
G2022072 | 0 | 7 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003090/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LoP Periode Februari 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA HEM IBRAHIM SE |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 9452304 | 1876400 | 11328704 | 0 | 4500463069 |  |  |  |  | RATI UTAMA KARYA
G2022072 | 0 | 10 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003090/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LoP Periode Februari 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA HEM ANDI MANSYUR |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 3123030 | 397916 | 3520946 | 0 | 4500463069 |  |  |  |  | RATI UTAMA KARYA
G2022073 | 0 | 9 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003091/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 6 LoP Periode Maret 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | ANTANG |  | R7 MKS ANT HEM BALAI KB MANGGALA |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 10491943 | 1866543 | 12358486 | 0 | 4500463070 |  |  |  |  | RATI UTAMA KARYA
G2022073 | 0 | 11 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003091/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 6 LoP Periode Maret 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM LANTAMAL IV |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 13870739 | 2998222 | 16868961 | 0 | 4500463070 |  |  |  |  | RATI UTAMA KARYA
G2022073 | 0 | 7 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003091/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 6 LoP Periode Maret 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL HEM BALAI KB UJUNG TANAH |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 3263958 | 786441 | 4050399 | 0 | 4500463070 |  |  |  |  | RATI UTAMA KARYA
G2022073 | 0 | 6 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003091/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 6 LoP Periode Maret 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM BALAI KB TAMALATE |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 2611429 | 590971 | 3202400 | 0 | 4500463070 |  |  |  |  | RATI UTAMA KARYA
G2022073 | 0 | 10 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003091/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 6 LoP Periode Maret 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM BALAI KB TJ MERDEKA |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 28710691 | 5090590 | 33801281 | 0 | 4500463070 |  |  |  |  | RATI UTAMA KARYA
G2022073 | 0 | 8 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003091/HK.810/R7W-7A510000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 6 LoP Periode Maret 2022 Area Witel Makassar - PT. RATI UTAMA KARYA | 2022-06-03 | 2022-07-17 | HEM | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD HEM BALAI KB BIRINGKANAYA |  | 100 | 0 | 0 | Preparing | 2022-06-03 | 2022-07-14 | [5 empty] | 17859800 | 3066932 | 20926732 | 0 | 4500463070 |  |  |  |  | RATI UTAMA KARYA
G2022074 | 1 | 43 | 01E07Y05 | 007 | 73010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | AMBON |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.887/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 60049040 | 0 | 60049040 | 60049040 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 47 | 01E07Y05 | 007 | 73010013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | BULA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.891/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 8580200 | 0 | 8580200 | 8580200 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 48 | 01E07Y05 | 007 | 73010120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | DOBO |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.892/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 398880 | 0 | 398880 | 398880 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 45 | 01E07Y05 | 007 | 73010042 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | MASOHI |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.889/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3503400 | 0 | 3503400 | 3503400 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 50 | 01E07Y05 | 007 | 73010046 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | NAMLEA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.894/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1291440 | 0 | 1291440 | 1291440 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 44 | 01E07Y05 | 007 | 73010057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | PASSO |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.888/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 33142960 | 0 | 33142960 | 33142960 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 51 | 01E07Y05 | 007 | 73010059 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | PIRU |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.895/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 308800 | 0 | 308800 | 308800 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 46 | 01E07Y05 | 007 | 73010103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | SAUMLAKI |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.890/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 6468240 | 0 | 6468240 | 6468240 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 49 | 01E07Y05 | 007 | 73010119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | AMBON | TUAL |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.893/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 8933120 | 0 | 8933120 | 8933120 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 18 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | GORONTALO | GORONTALO |  | PEKERJAAN QE HEM PERIODE JAN-MAR 2022 |  | 95 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-30 | 2022-06-06 | C.TEL.864/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 40173770 | 0 | 40173770 | 40173770 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 21 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | GORONTALO | ISIMU |  | PEKERJAAN QE HEM PERIODE JAN-MAR 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-30 | 2022-06-06 | C.TEL.867/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 5058180 | 0 | 5058180 | 5058180 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 22 | 01E07Y05 | 007 | 72020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | GORONTALO | KWANDANG |  | PEKERJAAN QE HEM PERIODE JAN-MAR 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-30 | 2022-06-06 | C.TEL.868/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2555100 | 0 | 2555100 | 2555100 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 20 | 01E07Y05 | 007 | 72020023 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | GORONTALO | LIMBOTO |  | PEKERJAAN QE HEM PERIODE JAN-MAR 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-30 | 2022-06-06 | C.TEL.866/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 5530710 | 0 | 5530710 | 5530710 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 23 | 01E07Y05 | 007 | 72020025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | GORONTALO | MARISA |  | PEKERJAAN QE HEM PERIODE JAN-MAR 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-30 | 2022-06-06 | C.TEL.869/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 7170630 | 0 | 7170630 | 7170630 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 19 | 01E07Y05 | 007 | 72020038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | GORONTALO | TELAGA |  | PEKERJAAN QE HEM PERIODE JAN-MAR 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-30 | 2022-06-06 | C.TEL.865/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 4499540 | 0 | 4499540 | 4499540 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 52 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | ABEPURA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.896/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 26492480 | 0 | 26492480 | 26492480 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 53 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.897/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 44365000 | 0 | 44365000 | 44365000 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 54 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.898/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 15267200 | 0 | 15267200 | 15267200 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 55 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.899/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 7746360 | 0 | 7746360 | 7746360 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 57 | 01E07Y05 | 007 | 74030060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | SARMI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.901/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 416000 | 0 | 416000 | 416000 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 58 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | SENTANI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.902/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 15921820 | 0 | 15921820 | 15921820 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 59 | 01E07Y05 | 007 | 74030067 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | TEMBAGAPURA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.903/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1456000 | 0 | 1456000 | 1456000 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 60 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | TIMIKA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.904/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 17272840 | 0 | 17272840 | 17272840 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 61 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | JAYAPURA | WAENA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.905/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 6452340 | 0 | 6452340 | 6452340 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 100 | 01E07Y05 | 007 | 72050009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | KENDARI | BAU-BAU |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.944/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 8363190 | 0 | 8363190 | 8363190 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 101 | 01E07Y05 | 007 | 72050025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | KENDARI | KENDARI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.945/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 16867850 | 0 | 16867850 | 16867850 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 102 | 01E07Y05 | 007 | 72050030 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | KENDARI | KOLAKA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.946/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2086400 | 0 | 2086400 | 2086400 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 103 | 01E07Y05 | 007 | 72050041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | KENDARI | LASUSUA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.947/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3140350 | 0 | 3140350 | 3140350 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 104 | 01E07Y05 | 007 | 72050093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | KENDARI | MANDONGA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.948/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 24203330 | 0 | 24203330 | 24203330 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 105 | 01E07Y05 | 007 | 72050072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | KENDARI | UNAAHA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.949/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 12726510 | 10997730 | 23724240 | 23724240 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 106 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | AIR MADIDI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.950/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 71067300 | 0 | 71067300 | 71067300 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 107 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | AMURANG |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.951/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2807700 | 0 | 2807700 | 2807700 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 108 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | BAHU |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.952/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 49758600 | 0 | 49758600 | 49758600 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 109 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | BITUNG |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.953/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 41152010 | 0 | 41152010 | 41152010 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 110 | 01E07Y05 | 007 | 72010012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | BOROKO |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.955/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1874100 | 0 | 1874100 | 1874100 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 111 | 01E07Y05 | 007 | 72010045 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | KAUDITAN |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.956/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2139300 | 0 | 2139300 | 2139300 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 113 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | KOTAMOBAGU |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.957/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 5312510 | 0 | 5312510 | 5312510 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 114 | 01E07Y05 | 007 | 72010127 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | LANGOWAN |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.958/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 4114800 | 0 | 4114800 | 4114800 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 115 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | MANADO |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.959/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 65705700 | 0 | 65705700 | 65705700 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 116 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | PANIKI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.960/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 45921000 | 0 | 45921000 | 45921000 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 117 | 01E07Y05 | 007 | 72010104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | TAHUNA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.961/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3698400 | 0 | 3698400 | 3698400 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 119 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | TOMOHON |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.963/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 12251100 | 0 | 12251100 | 12251100 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 118 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | TONDANO |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.962/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 5235300 | 0 | 5235300 | 5235300 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 120 | 01E07Y05 | 007 | 72010283 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANADO | TUTUYAN |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.964/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 900900 | 0 | 900900 | 900900 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 64 | 01E07Y05 | 007 | 74040005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MANOKWARI | MANOKWARI |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.908/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 9949830 | 0 | 9949830 | 9949830 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 56 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | MERAUKE | MERAUKE |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-17 | 2022-06-06 | C.TEL.900/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 4700800 | 0 | 4700800 | 4700800 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 96 | 01E07Y05 | 007 | 72030159 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | AMPANA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.940/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2239360 | 0 | 2239360 | 2239360 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 90 | 01E07Y05 | 007 | 72030123 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | BANGGAI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.934/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 30220 | 0 | 30220 | 30220 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 92 | 01E07Y05 | 007 | 72030012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | BUNGKU |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.936/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 26032100 | 8458820 | 34490920 | 34490920 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 99 | 01E07Y05 | 007 | 72030013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | BUOL |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.943/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 664440 | 0 | 664440 | 664440 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 88 | 01E07Y05 | 007 | 72030017 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | DONGGALA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.932/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 19865720 | 6516680 | 26382400 | 26382400 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 98 | 01E07Y05 | 007 | 72030104 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | KOLONODALE |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.942/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 460820 | 0 | 460820 | 460820 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 93 | 01E07Y05 | 007 | 72030102 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | LUWUK |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.937/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 33103260 | 9788260 | 42891520 | 42891520 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 85 | 01E07Y05 | 007 | 72030103 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | PALU A |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.929/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 66283410 | 1804960 | 68088370 | 68088370 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 86 | 01E07Y05 | 007 | 72030092 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | PALU B |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.930/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 24534650 | 13241640 | 37776290 | 37776290 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 89 | 01E07Y05 | 007 | 72030061 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | PARIGI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.933/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 4579220 | 3556600 | 8135820 | 8135820 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 87 | 01E07Y05 | 007 | 72030088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | TAWAELI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.931/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 10734620 | 3532720 | 14267340 | 14267340 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 97 | 01E07Y05 | 007 | 72030139 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | TENTENA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.941/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 298440 | 0 | 298440 | 298440 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 95 | 01E07Y05 | 007 | 72030083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | TOLAY |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.939/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 367660 | 0 | 367660 | 367660 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 94 | 01E07Y05 | 007 | 72030084 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PALU | TOLI-TOLI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.938/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 8894600 | 1743440 | 10638040 | 10638040 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 66 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | BARRU |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.910/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3095020 | 0 | 3095020 | 3095020 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 67 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | ENREKANG |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.911/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2694500 | 0 | 2694500 | 2694500 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 68 | 01E07Y05 | 007 | 72040078 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | MAJENE |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.912/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1234440 | 0 | 1234440 | 1234440 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 69 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | MAKALE |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.913/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1823980 | 0 | 1823980 | 1823980 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 70 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | MALILI |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.914/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 278900 | 0 | 278900 | 278900 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 71 | 01E07Y05 | 007 | 72040086 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | MAMASA |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.915/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 644900 | 0 | 644900 | 644900 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 72 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | MAMUJU |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.916/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 10373100 | 0 | 10373100 | 10373100 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 73 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | MASAMBA |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.917/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3017880 | 0 | 3017880 | 3017880 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 74 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | PALOPO |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.918/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 7588720 | 0 | 7588720 | 7588720 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 76 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | PARE-PARE |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.919/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 10853080 | 0 | 10853080 | 10853080 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 75 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-10 | 2022-06-06 | C.TEL.920/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2020880 | 0 | 2020880 | 2020880 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 77 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | PINRANG |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.921/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 7472200 | 0 | 7472200 | 7472200 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 78 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | POLEWALI |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.922/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1559900 | 0 | 1559900 | 1559900 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 79 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | RANTEPAO |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.923/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3284040 | 0 | 3284040 | 3284040 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 80 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | RAPPANG |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.924/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2143420 | 0 | 2143420 | 2143420 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 81 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | SENGKANG |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.925/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2869400 | 0 | 2869400 | 2869400 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 82 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | SIDRAP |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.926/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2918980 | 0 | 2918980 | 2918980 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 83 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | SIWA |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.927/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 366000 | 0 | 366000 | 366000 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 84 | 01E07Y05 | 007 | 72040161 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | PARE-PARE | SOROWAKO |  | PEKERJAAN QE HEM JAN-FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-11 | 2022-06-06 | C.TEL.928/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1134600 | 0 | 1134600 | 1134600 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 91 | 01E07Y05 | 007 | 72070016 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | POSO | POSO |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-27 | 2022-06-06 | C.TEL.935/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 6399660 | 3305620 | 9705280 | 9705280 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 65 | 01E07Y05 | 007 | 74060035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | SORONG | BIAK |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-15 | 2022-06-06 | C.TEL.909/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 16936320 | 0 | 16936320 | 16936320 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 63 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | SORONG | FAKFAK |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.907/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 4454310 | 0 | 4454310 | 4454310 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 62 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | SORONG | SORONG |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.906/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 48553190 | 0 | 48553190 | 48553190 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 121 | 01E07Y05 | 007 | 73020009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | JAILOLO |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.965/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 121680 | 0 | 121680 | 121680 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 122 | 01E07Y05 | 007 | 73020013 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | LABUHA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.966/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 3194200 | 0 | 3194200 | 3194200 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 123 | 01E07Y05 | 007 | 73020057 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | MANGOLE |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.967/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 772880 | 0 | 772880 | 772880 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 128 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | MOROTAI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.972/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1858680 | 0 | 1858680 | 1858680 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 127 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | SANANA |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.971/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 386880 | 0 | 386880 | 386880 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 124 | 01E07Y05 | 007 | 73020034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | SOA SIU |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.968/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2490680 | 0 | 2490680 | 2490680 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 125 | 01E07Y05 | 007 | 73020035 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | SOFIFI |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.969/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 9151520 | 0 | 9151520 | 9151520 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 126 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | TERNATE |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.970/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 75006520 | 0 | 75006520 | 75006520 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 129 | 01E07Y05 | 007 | 73020044 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | TERNATE | TOBELO |  | PEKERJAAN QE HEM JAN-MARET 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-18 | 2022-06-06 | C.TEL.973/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 6366920 | 0 | 6366920 | 6366920 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 24 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-13 | 2022-06-06 | C.TEL.870/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 8646030 | 0 | 8646030 | 8646030 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 25 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.871/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 13762760 | 2238560 | 16001320 | 16001320 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 27 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.872/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2302670 | 0 | 2302670 | 2302670 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 28 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.873/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2295370 | 0 | 2295370 | 2295370 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 29 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.874/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1400550 | 0 | 1400550 | 1400550 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 31 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | KIMA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.875/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 53592390 | 0 | 53592390 | 53592390 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 32 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | MAROS |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.876/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2982260 | 0 | 2982260 | 2982260 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 33 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.877/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 15950820 | 0 | 15950820 | 15950820 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 34 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.878/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 36074660 | 0 | 36074660 | 36074660 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 35 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-13 | 2022-06-06 | C.TEL.879/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1662270 | 0 | 1662270 | 1662270 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 36 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-13 | 2022-06-06 | C.TEL.880/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 1352190 | 0 | 1352190 | 1352190 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 37 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.881/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2743110 | 0 | 2743110 | 2743110 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 38 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.882/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 28552280 | 0 | 28552280 | 28552280 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 39 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-13 | 2022-06-06 | C.TEL.883/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 23118680 | 0 | 23118680 | 23118680 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 40 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.884/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 2015940 | 0 | 2015940 | 2015940 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 41 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.885/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 26691050 | 4793360 | 31484410 | 31484410 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022074 | 1 | 42 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003155/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan QE HEM 109 LoP Area Witel Gorontalo, Makassar, Maluku, Papua, Papua Barat, Sulselbar, Sulteng, Sultra dan Sulut Mal | 2022-06-06 | 2022-07-20 | QE HEM | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE HEM JAN-MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-06 | 2022-06-14 | 2022-06-06 | C.TEL.886/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0106/LG.320/DR7-10400000/2022 | 2022-06-20 | 7636840 | 0 | 7636840 | 7636840 | 4500463390 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022075 | 0 | 6 | 01E07J04 | 007 | 72080054 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003156/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LOP Maret 2022 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-06-07 | 2022-08-05 | HEM | UJUNGPANDANG | JENEPONTO |  | R7 MKS JNP HEM GARDU INDUK PLTB TOLO |  | 85 |  | 0 |  | 2022-06-07 | 2022-08-05 | [5 empty] | 23275735 | 11363052 | 34638787 | 0 | 4500463423 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022075 | 0 | 10 | 01E07J04 | 007 | 72080080 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003156/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LOP Maret 2022 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-06-07 | 2022-08-05 | HEM | UJUNGPANDANG | MAROS |  | R7 MKS MAR HEM BOSOWA |  | 85 |  | 0 |  | 2022-06-07 | 2022-08-05 | [5 empty] | 12949087 | 3011492 | 15960579 | 0 | 4500463423 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022075 | 0 | 8 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003156/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LOP Maret 2022 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-06-07 | 2022-08-05 | HEM | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT HEM BANK SULSELBAR |  | 85 |  | 0 |  | 2022-06-07 | 2022-08-05 | [5 empty] | 2734942 | 237284 | 2972226 | 0 | 4500463423 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022075 | 0 | 7 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003156/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LOP Maret 2022 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-06-07 | 2022-08-05 | HEM | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD HEM JAPFA COMFEED |  | 85 |  | 0 |  | 2022-06-07 | 2022-08-05 | [5 empty] | 156201978 | 37680500 | 193882478 | 0 | 4500463423 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022075 | 0 | 9 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003156/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan HEM 5 LOP Maret 2022 Area Witel Makassar - PT. AKBAR BERSAUDARA GROUP | 2022-06-07 | 2022-08-05 | HEM | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG HEM SMK NEGERI 3 GOWA |  | 85 |  | 0 |  | 2022-06-07 | 2022-08-05 | [5 empty] | 13147255 | 3063989 | 16211244 | 0 | 4500463423 |  |  |  |  | AKBAR BERSAUDARA GROUP
G2022076 | 2 | 7 | 01E07J04 | 007 | 72080091 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003157/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 3 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-06-07 | 2022-08-05 | FIMO NODE-B 2022 | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK COI531 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-07-01 | 2022-06-29 | TEL.0394/LG.310/R7W-7A330000/2022 | 2022-07-12 | TEL.0006/LG.320/R7W-7A100000/2022 | 2022-07-12 | 4454996 | 1735156 | 6190152 | 6190152 | 4500463400 |  |  |  |  | SIPAKALEBBI 2 | 2022-07-29
G2022076 | 2 | 8 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003157/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 3 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-06-07 | 2022-08-05 | FIMO NODE-B 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG SIN052 Protelindo Simaturue |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-07-09 | 2022-06-17 | TEL.0393/LG.310/R7W-7A330000/2022 | 2022-07-12 | TEL.0006/LG.320/R7W-7A100000/2022 | 2022-07-12 | 313432314 | 55900737 | 369333051 | 369333051 | 4500463400 |  |  |  |  | SIPAKALEBBI 2 | 2022-07-29
G2022076 | 2 | 6 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003157/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 3 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-06-07 | 2022-08-05 | FIMO NODE-B 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG TKA080 Isoka |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-07-08 | 2022-06-20 | TEL.0392/LG.310/R7W-7A330000/2022 | 2022-07-12 | TEL.0006/LG.320/R7W-7A100000/2022 | 2022-07-12 | 159442598 | 28388364 | 187830962 | 187830962 | 4500463400 |  |  |  |  | SIPAKALEBBI 2 | 2022-07-29
G2022077 | 1 | 6 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003158/HK.810/R7W-7C1H0000/2022 | LASTMILE HEM EGBIS 1 LOP (HOTEL TIARA) WITEL SULTENG | 2022-06-07 | 2022-07-06 | LME HEM | PALU | PALU A |  | R7 PAL PLA HEM HOTEL TIARA |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-19 | 2022-06-07 | C.TEL.55/LG.000/R7W-7C100000/2022 | 2022-06-23 | TEL.0002/LG.320/R7W-7C1H0000/2022 | 2022-06-23 | 37492812 | 11565665 | 49058477 | 49058477 | 4500462852 |  |  |  |  | TELKOM AKSES | 2022-07-05
G2022078 | 2 | 14 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | GORONTALO |  | R7 GTO GTL PT2 Jl. Imam Samadi-Tapa |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-06-30 | 2022-06-08 | TEL.1088/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 1722832 | 250972 | 1973804 | 1973804 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 12 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | GORONTALO |  | R7 GTO GTL PT2 Talulobutu, Tapa |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-01 | 2022-06-08 | TEL.1085/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 21836802 | 5677479 | 27514281 | 27514281 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 6 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | GORONTALO |  | R7 GTO GTL PT2 WONGGADITI BARAT |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-05 | 2022-06-08 | TEL.1084/LG.310/DR7-12700000/2022 | 2022-07-08 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 14367025 | 3431879 | 17798904 | 17798904 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 11 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | ISIMU |  | R7 GTO ISM PT2 BATU DOA MOLAWAHU TIBAWA |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-06 | 2022-06-08 | TEL.1082/LG.310/DR7-12700000/2022 | 2022-07-09 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 1722832 | 250972 | 1973804 | 1973804 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 7 | 01E07V01 | 007 | 72020023 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | LIMBOTO |  | R7 GTO LBT PT2 TUNGGULO LIMBOTO |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-09 | 2022-06-08 | TEL.1083/LG.310/DR7-12700000/2022 | 2022-07-09 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 1722832 | 250972 | 1973804 | 1973804 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 16 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | MARISA |  | R7 GTO MRS PT2 DS-MRA-FE-01-02/04.01 |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-04 | 2022-06-08 | TEL.1086/LG.310/DR7-12700000/2022 | 2022-07-10 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 1722832 | 250972 | 1973804 | 1973804 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 17 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | MARISA |  | R7 GTO MRS PT2 Trans Sulawesi SPBU maleo |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-02 | 2022-06-08 | TEL.1087/LG.310/DR7-12700000/2022 | 2022-07-10 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 4033584 | 573055 | 4606639 | 4606639 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 10 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | MARISA |  | R7 GTO MRS PT2 TELAGA BIRU POPAYATO |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-05 | 2022-06-08 | TEL.1081/LG.310/DR7-12700000/2022 | 2022-07-10 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 1722832 | 250972 | 1973804 | 1973804 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 8 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | MARISA |  | R7 GTO MRS PT2 TRANS SULAWESI PALOPO |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-07 | 2022-06-08 | TEL.1080/LG.310/DR7-12700000/2022 | 2022-07-10 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 1722832 | 250972 | 1973804 | 1973804 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022078 | 2 | 9 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003159/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan PT2 Periode Januari-Maret Tahun 2022 Area Witel Gorontalo | 2022-06-07 | 2022-07-21 | PT2 | GORONTALO | TELAGA |  | R7 GTO TLG PT2 PERUM SAFA MARWAH |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-06-30 | 2022-06-08 | TEL.1079/LG.310/DR7-12700000/2022 | 2022-07-09 | TEL.0120/LG.320/DR7-10400000/2022 | 2022-07-10 | 26622285 | 5351457 | 31973742 | 31973742 | 4500463579 |  |  |  |  | TELKOM AKSES | 2022-07-26
G2022079 | 1 | 6 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003170/HK.810/R7W-7C1H0000/2022 | LASTMILE HEM EGBIS UNTAD 1 BUMI ROVIEGA 1 LOP WITEL SULTENG | 2022-06-07 | 2022-07-06 | HEM | PALU | PALU A |  | R7 PAL PLA HEM Untad I Bumi Roviega |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-19 | 2022-06-07 | C.TEL.54/LG000/R7W-7C100000/2022 | 2022-06-23 | TEL.0001/LG.320/R7W-7C1H0000/2022 | 2022-06-23 | 20742367 | 2879336 | 23621703 | 23621703 | 4500463672 |  |  |  |  | TELKOM AKSES | 2022-07-04
G2022080 | 1 | 46 | 01E07Y05 | 007 | 74010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | BIAK | BIAK |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.1005/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 124800 | 0 | 124800 | 124800 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 15 | 01E07Y05 | 007 | 72020004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | GORONTALO | GORONTALO |  | PEKERJAAN QE WIBS PERIODE NOVEMBER 2021 |  | 95 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-30 | 2022-06-07 | C.TEL.974/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 835230 | 0 | 835230 | 835230 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 16 | 01E07Y05 | 007 | 72020018 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | GORONTALO | ISIMU |  | PEKERJAAN QE WIBS PERIODE NOVEMBER 2021 |  | 70 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-30 | 2022-06-07 | C.TEL.975/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 437430 | 0 | 437430 | 437430 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 35 | 01E07Y05 | 007 | 74030001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | ABEPURA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.994/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 459900 | 0 | 459900 | 459900 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 36 | 01E07Y05 | 007 | 74030163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | JAYAPURA-1 |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.995/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3163120 | 0 | 3163120 | 3163120 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 37 | 01E07Y05 | 007 | 74030034 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | JAYAPURA-2 |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.996/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 332800 | 0 | 332800 | 332800 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 38 | 01E07Y05 | 007 | 74030043 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | KUALA KENCANA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.997/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3800 | 0 | 3800 | 3800 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 40 | 01E07Y05 | 007 | 74030063 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | SENTANI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.999/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 489060 | 0 | 489060 | 489060 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 41 | 01E07Y05 | 007 | 74030068 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | TIMIKA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.1000/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 2191850 | 0 | 2191850 | 2191850 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 42 | 01E07Y05 | 007 | 74030072 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | JAYAPURA | WAENA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.1001/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3121900 | 0 | 3121900 | 3121900 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 67 | 01E07Y05 | 007 | 72010002 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | AIR MADIDI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1025/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 7698140 | 4674440 | 12372580 | 12372580 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 68 | 01E07Y05 | 007 | 72010004 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | AMURANG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1026/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 25613150 | 11617240 | 37230390 | 37230390 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 69 | 01E07Y05 | 007 | 72010005 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | BAHU |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1027/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 31340860 | 23512700 | 54853560 | 54853560 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 70 | 01E07Y05 | 007 | 72010008 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | BITUNG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1028/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 32643270 | 16036180 | 48679450 | 48679450 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 71 | 01E07Y05 | 007 | 72010052 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | KOTAMOBAGU |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1029/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 65227660 | 25145320 | 90372980 | 90372980 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 72 | 01E07Y05 | 007 | 72010060 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | MANADO |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1030/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 132520670 | 94337960 | 226858630 | 226858630 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 73 | 01E07Y05 | 007 | 72010083 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | PANIKI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1031/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 2105400 | 2032740 | 4138140 | 4138140 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 75 | 01E07Y05 | 007 | 72010110 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | TOMOHON |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1033/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 14630540 | 8399710 | 23030250 | 23030250 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 74 | 01E07Y05 | 007 | 72010112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MANADO | TONDANO |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1032/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 148091580 | 74680970 | 222772550 | 222772550 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 39 | 01E07Y05 | 007 | 74050012 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | MERAUKE | MERAUKE |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-17 | 2022-06-07 | C.TEL.998/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3064100 | 0 | 3064100 | 3064100 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 49 | 01E07Y05 | 007 | 72040193 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | BARRU |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1008/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 42993660 | 13364950 | 56358610 | 56358610 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 50 | 01E07Y05 | 007 | 72040049 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | ENREKANG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1009/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 21012670 | 17574250 | 38586920 | 38586920 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 51 | 01E07Y05 | 007 | 72040197 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | MAKALE |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1010/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 2823730 | 2003840 | 4827570 | 4827570 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 52 | 01E07Y05 | 007 | 72040082 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | MALILI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1011/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 1332000 | 166500 | 1498500 | 1498500 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 53 | 01E07Y05 | 007 | 72040088 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | MAMUJU |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1012/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 11527240 | 6977320 | 18504560 | 18504560 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 54 | 01E07Y05 | 007 | 72040094 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | MASAMBA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1013/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 5663330 | 2788230 | 8451560 | 8451560 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 55 | 01E07Y05 | 007 | 72040109 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | PALOPO |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1014/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 15838210 | 11297660 | 27135870 | 27135870 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 56 | 01E07Y05 | 007 | 72040117 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | PARE-PARE |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1015/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3579690 | 1560980 | 5140670 | 5140670 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 58 | 01E07Y05 | 007 | 72040119 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | PASANG KAYU |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1016/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 7946560 | 4467250 | 12413810 | 12413810 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 59 | 01E07Y05 | 007 | 72040128 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | PINRANG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1017/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 5776270 | 1551060 | 7327330 | 7327330 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 60 | 01E07Y05 | 007 | 72040195 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | POLEWALI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1018/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 6011120 | 2427190 | 8438310 | 8438310 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 61 | 01E07Y05 | 007 | 72040133 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | RANTEPAO |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1019/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 4352370 | 2510110 | 6862480 | 6862480 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 62 | 01E07Y05 | 007 | 72040135 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | RAPPANG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1020/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 1332830 | 166500 | 1499330 | 1499330 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 63 | 01E07Y05 | 007 | 72040194 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | SENGKANG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1021/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 5086290 | 2660220 | 7746510 | 7746510 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 64 | 01E07Y05 | 007 | 72040158 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | SIDRAP |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1022/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 4264200 | 2374070 | 6638270 | 6638270 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 65 | 01E07Y05 | 007 | 72040160 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | SIWA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1023/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 5810 | 0 | 5810 | 5810 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 66 | 01E07Y05 | 007 | 72040186 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | PARE-PARE | WATANSOPPENG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-06-21 | 2022-06-08 | C.TEL.1024/LG300/DR7-12800000/2022 | 2022-06-20 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3320 | 0 | 3320 | 3320 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 47 | 01E07Y05 | 007 | 74060037 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | SORONG | BINTUINI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.1006/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 371100 | 0 | 371100 | 371100 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 44 | 01E07Y05 | 007 | 74060038 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | SORONG | FAKFAK |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.1003/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 2506990 | 0 | 2506990 | 2506990 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 45 | 01E07Y05 | 007 | 74060039 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | SORONG | MANOKWARI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-15 | 2022-06-07 | C.TEL.1004/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3534610 | 0 | 3534610 | 3534610 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 48 | 01E07Y05 | 007 | 74060040 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | SORONG | NABIRE |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-15 | 2022-06-07 | C.TEL.1007/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 2650450 | 3745210 | 6395660 | 6395660 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 43 | 01E07Y05 | 007 | 74060025 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | SORONG | SORONG |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-15 | 2022-06-07 | C.TEL.1002/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 30524020 | 0 | 30524020 | 30524020 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 78 | 01E07Y05 | 007 | 73020019 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | TERNATE | MOROTAI |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1036/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 6437690 | 19847920 | 26285610 | 26285610 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 77 | 01E07Y05 | 007 | 73020032 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | TERNATE | SANANA |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1035/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 372060 | 0 | 372060 | 372060 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 76 | 01E07Y05 | 007 | 73020041 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | TERNATE | TERNATE |  | PEKERJAAN QE WIBS JULI-DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-18 | 2022-06-07 | C.TEL.1034/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 2858630 | 1148230 | 4006860 | 4006860 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 17 | 01E07Y05 | 007 | 72080001 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | ANTANG |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.976/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 40607070 | 17929800 | 58536870 | 58536870 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 18 | 01E07Y05 | 007 | 72080163 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | BALAIKOTA |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.977/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3616840 | 1841470 | 5458310 | 5458310 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 19 | 01E07Y05 | 007 | 72080009 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | BANTAENG |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.978/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 3924320 | 2425300 | 6349620 | 6349620 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 20 | 01E07Y05 | 007 | 72080036 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | BULUKUMBA |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.979/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 5165020 | 2254620 | 7419640 | 7419640 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 21 | 01E07Y05 | 007 | 72080054 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | JENEPONTO |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-13 | 2022-06-07 | C.TEL.980/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 30611860 | 22484180 | 53096040 | 53096040 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 22 | 01E07Y05 | 007 | 72080064 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | KIMA |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-13 | 2022-06-07 | C.TEL.981/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 19184370 | 14641160 | 33825530 | 33825530 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 23 | 01E07Y05 | 007 | 72080075 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | MALINO |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.982/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 28490240 | 12577160 | 41067400 | 41067400 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 24 | 01E07Y05 | 007 | 72080080 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | MAROS |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-13 | 2022-06-07 | C.TEL.983/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 20380980 | 7991890 | 28372870 | 28372870 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 25 | 01E07Y05 | 007 | 72080164 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | MATTOANGIN |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.984/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 10509690 | 6388840 | 16898530 | 16898530 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 26 | 01E07Y05 | 007 | 72080091 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | PANAKUKANG |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.985/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 113694540 | 56694790 | 170389330 | 170389330 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 27 | 01E07Y05 | 007 | 72080093 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | PANGKEP |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-15 | 2022-06-07 | C.TEL.986/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 59463060 | 34895550 | 94358610 | 94358610 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 28 | 01E07Y05 | 007 | 72080112 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | SELAYAR |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-15 | 2022-06-07 | C.TEL.987/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 90510 | 0 | 90510 | 90510 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 29 | 01E07Y05 | 007 | 72080115 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | SINJAI |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.988/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 20390220 | 9141250 | 29531470 | 29531470 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 30 | 01E07Y05 | 007 | 72080167 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | SUDIANG |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-15 | 2022-06-07 | C.TEL.989/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 13027260 | 8737190 | 21764450 | 21764450 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 31 | 01E07Y05 | 007 | 72080165 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | SUNGGUMINASA |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-13 | 2022-06-07 | C.TEL.990/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 136981050 | 70596240 | 207577290 | 207577290 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 32 | 01E07Y05 | 007 | 72080120 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | TAKALAR |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.991/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 41628320 | 26159200 | 67787520 | 67787520 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 33 | 01E07Y05 | 007 | 72080166 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | TAMALANREA |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.992/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 50621270 | 16529460 | 67150730 | 67150730 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022080 | 1 | 34 | 01E07Y05 | 007 | 72080199 | TELKOM REGIONAL VII | ACCESS MANAGEMENT | CAPEX QE & PERFORMANCE | TELKOM REGIONAL VII | K.TEL.003171/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Capex QE WIBS 63 LOP Area Witel Gto, Mks, Papua, Pabar, Sulselbar & SuMa | 2022-06-07 | 2022-07-21 | QE WIBS | UJUNGPANDANG | WATAMPONE |  | PEKERJAAN QE WIBS MEI - DESEMBER 2021 |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-14 | 2022-06-07 | C.TEL.993/LG300/DR7-12800000/2022 | 2022-06-17 | TEL.0107/LG.320/DR7-10400000/2022 | 2022-06-20 | 57236830 | 34516110 | 91752940 | 91752940 | 4500463619 |  |  |  |  | TELKOM AKSES | 2022-06-30
G2022081 | 1 | 6 | 01E07O02 | 007 | 72030088 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003178/HK.810/R7W-7C1H0000/2022 | LASTMILE HEM EGBIS DISKOMINFO 1 LOP WITEL SULTENG | 2022-06-07 | 2022-07-06 | HEM | PALU | TAWAELI |  | R7 PAL TWL HEM DISKOMINFO PALU |  | 100 | 100 | 100 | BAST-1 | 2022-06-07 | 2022-06-19 | 2022-06-07 | C.TEL.54/LG.000/R7W-7C100000/2022 | 2022-06-23 | TEL.0003/LG.320/R7W-7C1H0000/2022 | 2022-06-23 | 88208280 | 19761334 | 107969614 | 107969614 | 4500463706 |  |  |  |  | TELKOM AKSES | 2022-07-06
G2022082 | 1 | 14 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM TAMAN TERBUKA HIJAU |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.270/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 13 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM TAMAN BACA |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.268/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 8 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM PASAR SENTRAL |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.266/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 15 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM PENGADILAN AGAMA MAKALE |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.267/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 11211026 | 2994416 | 14205442 | 14205442 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 16 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK HEM TAMAN PKK MKALE |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.269/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 2248486 | 353770 | 2602256 | 2602256 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 7 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM DPRD MAMUJU |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.271/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 8525581 | 1819858 | 10345439 | 10345439 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 17 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM POLDA SULBAR (FH) |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.272/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 26568480 | 6897351 | 33465831 | 33465831 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 10 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | PARE-PARE |  | R7 PRE PRE HEM SMPN 1 PAREPARE |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.273/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 7334393 | 1281900 | 8616293 | 8616293 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 12 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKA HEM DINAS KOMINFO PASANGKAYU |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.274/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 6 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKA HEM DISBUDPAR KAB PASANGKAYU |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.275/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 11 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKA HEM KANTOR BUPATI PASANGKAYU |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.276/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022082 | 1 | 9 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003202/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 12 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | POLEWALI |  | R7 PRE PLW HEM KOMINFO POLEWALI |  | 100 | 100 | 100 | BAST-1 | 2022-07-04 | 2022-07-16 | 2022-07-04 | TEL.277/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0009/LG.320/R7W-7D100000/2022 | 2022-07-13 | 21317723 | 4518591 | 25836314 | 25836314 | 4500463687 |  |  |  |  | TELKOM AKSES | 2022-07-20
G2022083 | 1 | 22 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAKALE |  | R7 PRE MAK PT2 PLUS HEM PLASA KOLAM MAKALE |  | 85 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-14 | 2022-06-09 | TEL.227/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 4533780 | 1101959 | 5635739 | 5635739 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 9 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM KANTOR PERTANAHAN |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.228/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 2278231 | 361730 | 2639961 | 2639961 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 10 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 HEM BPBJ Prov sulbar |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.230/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 1715991 | 301811 | 2017802 | 2017802 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 11 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MAMUJU |  | R7 PRE MAM HEM POLRES MAMTENG |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.229/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 53847346 | 9288803 | 63136149 | 63136149 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 20 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKA HEM KOMINFO PASANGKAYU (1) |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.231/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 1715991 | 364034 | 2080025 | 2080025 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 21 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | PASANG KAYU |  | R7 PRE PKA HEM KOMINFO PASANGKAYU (2) |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.232/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 5500119 | 1063665 | 6563784 | 6563784 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 14 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | POLEWALI |  | R7 PRE PLW HEM KANTOR DINAS PUPR |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.236/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 14752021 | 3813418 | 18565439 | 18565439 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 15 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | POLEWALI |  | HEM KTR. LITBANG - ODP-PLW-FAE-149 |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.235/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 13002090 | 2314938 | 15317028 | 15317028 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 16 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | POLEWALI |  | HEM KANTOR KELAUTAN - ODP-PLW-FB-087 |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.234/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 19592113 | 4527701 | 24119814 | 24119814 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 17 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | POLEWALI |  | HEM DP2KBP3A - ODP-PLW-FC-089 |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.233/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 1715991 | 301811 | 2017802 | 2017802 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 19 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | POLEWALI |  | R7 PRE PLW HEM KANTOR PERTANAHAN |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | TEL.237/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 23907289 | 6892857 | 30800146 | 30800146 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022083 | 1 | 7 | 01E07P02 | 007 | 72040133 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003203/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 16 LOP Tahun 2022 Area Witel Sulselbar. | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | RANTEPAO |  | R7 PRE RTP HEM LPSE TORAJA UTARA |  | 80 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-09 | TEL.238/LG.320/R7W-7D320000/2022 | 2022-06-24 | TEL.0008/LG.320/R7W-7D100000/2022 | 2022-06-24 | 35369826 | 10507577 | 45877403 | 45877403 | 4500463727 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-01
G2022084 | 1 | 8 | 01E07P02 | 007 | 72040082 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003204/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MALILI |  | R7 PRE MLL HEM PA dan PN Malili |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | 281/LG.320/R7W-7D320000/2022 | 2022-07-18 | TEL.0011/LG.320/R7W-7D100000/2022 | 2022-07-18 | 1449952 | 206965 | 1656917 | 1656917 | 4500463746 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-07-22
G2022084 | 1 | 9 | 01E07P02 | 007 | 72040082 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003204/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MALILI |  | R7 PRE MLL HEM SMA 1 MALILI |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | 282/LG.320/R7W-7D320000/2022 | 2022-07-18 | TEL.0011/LG.320/R7W-7D100000/2022 | 2022-07-18 | 1449952 | 206965 | 1656917 | 1656917 | 4500463746 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-07-22
G2022084 | 1 | 7 | 01E07P02 | 007 | 72040082 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003204/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | MALILI |  | R7 PRE MLL HEM BPN MALILI & KPU MALILI |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | 280/LG.320/R7W-7D320000/2022 | 2022-07-18 | TEL.0011/LG.320/R7W-7D100000/2022 | 2022-07-18 | 6040785 | 1576411 | 7617196 | 7617196 | 4500463746 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-07-22
G2022084 | 1 | 10 | 01E07P02 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003204/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan Lastmile HEM untuk Pelanggan EGBIS 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | HEM | PARE-PARE | SOROWAKO |  | R7 PRE SRK HEM SMAN 5 LUWU TIMUR |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-19 | 2022-06-08 | 283/LG.320/R7W-7D320000/2022 | 2022-07-18 | TEL.0011/LG.320/R7W-7D100000/2022 | 2022-07-18 | 65404871 | 12201783 | 77606654 | 77606654 | 4500463746 |  |  |  |  | CELEBES ANDHIKA PRATAMA | 2022-07-22
G2022085 | 1 | 9 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003205/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | FIMO NODE-B 2022 | PARE-PARE | MAJENE |  | MAJ021 DMT ISAT Malundak-MAJENE |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-18 | 2022-06-08 | TEL.256/LG.320/R7W-7D320000/2022 | 2022-07-01 | TEL.0010/LG.320/R7W-7D100000/2022 | 2022-07-01 | 32598277 | 9150537 | 41748814 | 41748814 | 4500463752 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-21
G2022085 | 1 | 10 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003205/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | FIMO NODE-B 2022 | PARE-PARE | MAJENE |  | PLW081 DMT Balanipa-MAJENE |  | 100 | 100 | 100 | BAST-1 | 2022-06-09 | 2022-07-19 | 2022-06-08 | TEL.257/LG.320/R7W-7D320000/2022 | 2022-07-01 | TEL.0010/LG.320/R7W-7D100000/2022 | 2022-07-01 | 14944927 | 3514815 | 18459742 | 18459742 | 4500463752 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-21
G2022085 | 1 | 11 | 01E07P02 | 007 | 72040086 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003205/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | FIMO NODE-B 2022 | PARE-PARE | MAMASA |  | MMS003 Sumarorong-MAMASA |  | 100 | 100 | 100 | BAST-1 | 2022-06-10 | 2022-07-18 | 2022-06-08 | TEL.258/LG.320/R7W-7D320000/2022 | 2022-07-01 | TEL.0010/LG.320/R7W-7D100000/2022 | 2022-07-01 | 21662887 | 7224734 | 28887621 | 28887621 | 4500463752 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-21
G2022085 | 1 | 8 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003205/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | FIMO NODE-B 2022 | PARE-PARE | MAMUJU |  | MAM056 - Protelindo Tangkau-MAMUJU |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-18 | 2022-06-08 | TEL.255/LG.320/R7W-7D320000/2022 | 2022-07-01 | TEL.0010/LG.320/R7W-7D100000/2022 | 2022-07-01 | 12674631 | 4016124 | 16690755 | 16690755 | 4500463752 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-21
G2022085 | 1 | 7 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003205/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan FIMO Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-08 | 2022-07-22 | FIMO NODE-B 2022 | PARE-PARE | MAMUJU |  | MAM022 Bambu-MAMUJU |  | 100 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-18 | 2022-06-08 | TEL.254/LG.320/R7W-7D320000/2022 | 2022-07-01 | TEL.0010/LG.320/R7W-7D100000/2022 | 2022-07-01 | 4613266 | 1617526 | 6230792 | 6230792 | 4500463752 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-07-21
G2022086 | 1 | 6 | 01E07O02 | 007 | 72030092 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003227/HK.810/R7W-7C100000/2022 | LASTMILE HEM EGBIS UIN DATOKARAMA 1 LOP WITEL SULTENG | 2022-06-08 | 2022-07-22 | HEM | PALU | PALU B |  | R7 PAL PLB HEM UIN DATOKARAMA |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-07-22 | 2022-06-08 | TEL.66/LG.310/R7W-7C100000/2022 | 2022-07-05 | TEL.0003/LG.320/R7W-7C100000/2022 | 2022-07-05 | 569531462 | 97014154 | 666545616 | 666545616 | 4500463911 |  |  |  |  | PERKONSUMA | 2022-07-21
G2022087 | 1 | 12 | 01E07T02 | 007 | 74060038 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | FAKFAK |  | FFK077 TBG TPA Fakfak Utara 2-R7 SON FFA FFK077 TBG TPA Fakfak Utara 2 |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.452/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 65065670 | 23987590 | 89053260 | 89053260 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 18 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | RAS006 DMT Maniwak Wasior-R7 SON MWR RAS006 DMT Maniwak Wasior |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.457/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 14054722 | 3885578 | 17940300 | 17940300 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 17 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR304 WOSI-R7 SON MWR MWR304 WOSI |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.456/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 3052229 | 1686435 | 4738664 | 4738664 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 19 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | RAS027 DMT Bandara Wondama-R7 SON MWR RAS027 DMT Bandara Wondama |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.458/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 23629779 | 7683992 | 31313771 | 31313771 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 20 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR224 TBG Sowi-R7 SON MWR MWR224 TBG Sowi |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.454/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 42682077 | 14663586 | 57345663 | 57345663 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 21 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR290 SWAPEN PERMAI-R7 SON MWR MWR290 SWAPEN PERMAI |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.455/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 7585742 | 2805877 | 10391619 | 10391619 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 16 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | MWR106 UDOPI INGGRAMUI-R7 SON MWR MWR106 UDOPI INGGRAMUI |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.453/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 15772933 | 5304847 | 21077780 | 21077780 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 7 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | NABIRE |  | NAB111 DMT Poros Wadio-R7 SON NAB NAB111 DMT Poros Wadio |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.459/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 18348128 | 6088457 | 24436585 | 24436585 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 8 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | NABIRE |  | NAB119 DMT Wonorejo Nabire-R7 SON NAB NAB119 DMT Wonorejo Nabire |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.461/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 12165499 | 3599984 | 15765483 | 15765483 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 10 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | NABIRE |  | NAB113 BUMI MULIA-R7 SON NAB NAB113 BUMI MULIA |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.460/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 5102540 | 2075580 | 7178120 | 7178120 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 9 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | NABIRE |  | NAB128 DMT Sanoba Nabire-R7 SON NAB NAB128 DMT Sanoba Nabire |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.462/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 22680854 | 5831109 | 28511963 | 28511963 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 11 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | NABIRE |  | NAB110 NABARUA-R7 SON NAB NAB110 NABARUA |  | 90 | 0 | 0 | Preparing | 2022-06-08 | 2022-08-06 | 2022-06-08 |  |  |  |  | 79716237 | 20950487 | 100666724 | 0 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO
G2022087 | 1 | 15 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON250 TBG Klaligi Manoi-R7 SON SON SON250 TBG Klaligi Manoi |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.464/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 22743579 | 9502868 | 32246447 | 32246447 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 14 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON327 TBG Teminabuan Giwu-R7 SON SON SON327 TBG Teminabuan Giwu |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.465/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 29609093 | 11287294 | 40896387 | 40896387 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022087 | 1 | 13 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003239/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAN PEKERJAAN FIMO NODE B 15 LOP AREA WITEL PAPUA BARAT | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | SORONG | SORONG |  | SON237 TBG KM 10 Malasemen-R7 SON SON SON237 TBG KM 10 Malasemen |  | 90 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.463/LG000/R7W-7H100000/2022 | 2022-07-13 | TEL.0007/LG.320/R7W-7H100000/2022 | 2022-07-13 | 9370924 | 3438341 | 12809265 | 12809265 | 4500463949 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022088 | 1 | 10 | 01E07R03 | 007 | 72010008 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003242/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO FIMO Node B 4 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | MANADO | BITUNG |  | R7 MDO BIT TDO028 KANUNANG |  | 95 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.767/LG.310/R7W-7F100000/2022 | 2022-07-18 | TEL.0004/LG.320/R7W-7F100000/2022 | 2022-07-18 | 431213921 | 75509723 | 506723644 | 506723644 | 4500463900 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022088 | 1 | 8 | 01E07R03 | 007 | 72010052 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003242/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO FIMO Node B 4 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | MANADO | KOTAMOBAGU |  | R7 MDO KTG KTG296 PINOBATUAN |  | 95 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.766/LG.310/R7W-7F100000/2022 | 2022-07-18 | TEL.0004/LG.320/R7W-7F100000/2022 | 2022-07-18 | 367891088 | 74657031 | 442548119 | 442548119 | 4500463900 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022088 | 1 | 9 | 01E07R03 | 007 | 72010104 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003242/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO FIMO Node B 4 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | MANADO | TAHUNA |  | R7 MDO THN THN097 SASIWUNG |  | 95 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.768/LG.310/R7W-7F100000/2022 | 2022-07-18 | TEL.0004/LG.320/R7W-7F100000/2022 | 2022-07-18 | 161409455 | 47976328 | 209385783 | 209385783 | 4500463900 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
G2022088 | 1 | 7 | 01E07R03 | 007 | 72010283 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003242/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO FIMO Node B 4 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-08 | 2022-08-06 | FIMO NODE-B 2022 | MANADO | TUTUYAN |  | R7 MDO TUT TDO375 SAYOWAN |  | 95 | 100 | 100 | BAST-1 | 2022-06-08 | 2022-08-06 | 2022-06-08 | TEL.769/LG.310/R7W-7F100000/2022 | 2022-07-18 | TEL.0004/LG.320/R7W-7F100000/2022 | 2022-07-18 | 476400615 | 89504322 | 565904937 | 565904937 | 4500463900 |  |  |  |  | TRANSDATA SATKOMINDO | 2022-07-28
12022147 | 0 | 47 | 01C11B03 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | AMBON | AMBON |  | (HTTP) |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 21000000 | 45000000 | 66000000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 23 | 01C11B03 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | JAYAPURA | JAYAPURA |  |  |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 555202000 | 124218000 | 679420000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 24 | 01C11B03 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | JAYAPURA | TIMIKA |  |  |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 556752000 | 124342000 | 681094000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 46 | 01C11B03 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | JAYAPURA | TIMIKA |  | (HTTP) |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 21000000 | 45000000 | 66000000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 31 | 01C11B03 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | KENDARI | KENDARI |  |  |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 1255920000 | 145128000 | 1401048000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 30 | 01C11B03 | 019 | 72050098 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | KENDARI | KENDARI-2 |  |  |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 1477020000 | 166518000 | 1643538000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 48 | 01C11B03 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | TERNATE | TERNATE |  | (HTTP) |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 7000000 | 15000000 | 22000000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022147 | 0 | 36 | 01C11B03 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CLOUD & DEFA DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003302/HK.810/SSP-10400000/2022 | Surat Pesanan-4 (SP#4) Pengadaan dan Pemasangan Ekspan PCEF Sandvine dan Load Balancer Cache DNS | 2022-06-10 | 2022-10-07 | Ekspan PCEF | TERNATE | TERNATE |  |  |  | 50 | 20 | 0 | Preparing | 2022-06-10 | 2022-10-07 | 2022-06-12 |  |  |  |  | 555202000 | 124218000 | 679420000 | 0 | 4500463548 |  |  |  |  | MULTIPOLAR TECHNOLOGY TBK
12022150 | 0 | 90 | 01C11I01 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003316/HK.810/SSP-10000000/2022 | Pengadaan dan Pemasangan OSP FO & Migrasi T-Cloud TREG-4 Phase-2, Revitalisasi FTM dan Node-B Telkomsel TREG-6 Phase-2 | 2022-06-10 | 2022-11-06 | OSP FO & Migrasi T-Cloud | AMBON | MALUKU |  | 2.1 EXPAND FTM PAKET-11 |  | 40 | 0 | 0 | Preparing | 2022-06-10 | 2022-11-20 | [5 empty] | 94011208 | 39490426 | 133501634 | 0 | 4500463950 |  |  |  |  | BANGTELINDO
12022150 | 0 | 104 | 01C11I01 | 019 | 73010160 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003316/HK.810/SSP-10000000/2022 | Pengadaan dan Pemasangan OSP FO & Migrasi T-Cloud TREG-4 Phase-2, Revitalisasi FTM dan Node-B Telkomsel TREG-6 Phase-2 | 2022-06-10 | 2022-11-06 | OSP FO & Migrasi T-Cloud | AMBON | MALUKU |  | 2.2 MIGRASI FTM FTM PAKET-11 |  | 35 | 0 | 0 | Preparing | 2022-06-10 | 2022-11-20 | [5 empty] | 337345720 | 263553338 | 600899058 | 0 | 4500463950 |  |  |  |  | BANGTELINDO
12022150 | 0 | 75 | 01C11I01 | 019 | 72010123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003316/HK.810/SSP-10000000/2022 | Pengadaan dan Pemasangan OSP FO & Migrasi T-Cloud TREG-4 Phase-2, Revitalisasi FTM dan Node-B Telkomsel TREG-6 Phase-2 | 2022-06-10 | 2022-11-06 | OSP FO & Migrasi T-Cloud | MANADO | MANADO AREA |  | 2.1 EXPAND FTM PAKET-8 |  | 40 | 0 | 0 | Preparing | 2022-06-10 | 2022-11-20 | [5 empty] | 92874921 | 33061679 | 125936600 | 0 | 4500463950 |  |  |  |  | BANGTELINDO
12022150 | 0 | 105 | 01C11I01 | 019 | 72010123 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003316/HK.810/SSP-10000000/2022 | Pengadaan dan Pemasangan OSP FO & Migrasi T-Cloud TREG-4 Phase-2, Revitalisasi FTM dan Node-B Telkomsel TREG-6 Phase-2 | 2022-06-10 | 2022-11-06 | OSP FO & Migrasi T-Cloud | MANADO | MANADO AREA |  | 2.2 MIGRASI FTM FTM PAKET-8 |  | 35 | 0 | 0 | Preparing | 2022-06-10 | 2022-11-20 | [5 empty] | 269183561 | 206645844 | 475829405 | 0 | 4500463950 |  |  |  |  | BANGTELINDO
12022150 | 0 | 76 | 01C11I01 | 019 | 72030089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003316/HK.810/SSP-10000000/2022 | Pengadaan dan Pemasangan OSP FO & Migrasi T-Cloud TREG-4 Phase-2, Revitalisasi FTM dan Node-B Telkomsel TREG-6 Phase-2 | 2022-06-10 | 2022-11-06 | OSP FO & Migrasi T-Cloud | PALU | PALU AREA |  | 2.1 EXPAND FTM PAKET-9 |  | 40 | 0 | 0 | Preparing | 2022-06-10 | 2022-11-20 | [5 empty] | 99998769 | 38737215 | 138735984 | 0 | 4500463950 |  |  |  |  | BANGTELINDO
12022150 | 0 | 106 | 01C11I01 | 019 | 72030089 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL BROADBAND ACCESS DEPLOYMENT | ACCESS NODE DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003316/HK.810/SSP-10000000/2022 | Pengadaan dan Pemasangan OSP FO & Migrasi T-Cloud TREG-4 Phase-2, Revitalisasi FTM dan Node-B Telkomsel TREG-6 Phase-2 | 2022-06-10 | 2022-11-06 | OSP FO & Migrasi T-Cloud | PALU | PALU AREA |  | 2.2 MIGRASI FTM FTM PAKET-9 |  | 35 | 0 | 0 | Preparing | 2022-06-10 | 2022-11-20 | [5 empty] | 330199568 | 241812630 | 572012198 | 0 | 4500463950 |  |  |  |  | BANGTELINDO
G2022089 | 1 | 12 | 01E07P02 | 007 | 72040044 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | CANGADI |  | R7 PRE CGI PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.98/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 5147973 | 718764 | 5866737 | 5866737 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 13 | 01E07P02 | 007 | 72040044 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | CANGADI |  | R7 PRE CGI PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.107/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 10418111 | 1453479 | 11871590 | 11871590 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 26 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | ENREKANG |  | R7 PRE ENR PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.108/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 103875800 | 23922982 | 127798782 | 127798782 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 21 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | MAJENE |  | R7 PRE MAJ PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.104/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 5147973 | 843210 | 5991183 | 5991183 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 22 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | MAJENE |  | R7 PRE MAJ PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.109/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 24 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.110/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 46836541 | 7668002 | 54504543 | 54504543 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 23 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.105/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 3994222 | 601318 | 4595540 | 4595540 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 18 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | MASAMBA |  | R7 PRE MAS PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.102/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 5147973 | 718764 | 5866737 | 5866737 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 16 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.101/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 8579955 | 1633501 | 10213456 | 10213456 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 17 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.111/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 8990285 | 1233948 | 10224233 | 10224233 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 9 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.112/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 9142195 | 1444528 | 10586723 | 10586723 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 8 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.96/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 29050061 | 4977949 | 34028010 | 34028010 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 27 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | PINRANG |  | R7 PRE PIN PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.113/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 25 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | POLEWALI |  | R7 PRE PLW PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.106/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 301811 | 2017802 | 2017802 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 14 | 01E07P02 | 007 | 72040133 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | RANTEPAO |  | R7 PRE RTP PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.99/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 2278231 | 423953 | 2702184 | 2702184 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 10 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.97/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 12340517 | 2113127 | 14453644 | 14453644 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 11 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.114/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 62556295 | 12757395 | 75313690 | 75313690 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 15 | 01E07P02 | 007 | 72040159 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | SIDENRENG RAPPANG |  | R7 PRE SID PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.100/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 1715991 | 239588 | 1955579 | 1955579 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 19 | 01E07P02 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | SOROWAKO |  | R7 PRE SRK PT2 FEB 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.103/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 3431982 | 479176 | 3911158 | 3911158 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 20 | 01E07P02 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | SOROWAKO |  | R7 PRE SRK PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.115/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 4890673 | 655581 | 5546254 | 5546254 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 28 | 01E07P02 | 007 | 72040174 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | TANRUTEDONG |  | R7 PRE TTE PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.116/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 4941850 | 983229 | 5925079 | 5925079 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022089 | 1 | 29 | 01E07P02 | 007 | 72040186 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.003332/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-2 dan PT2 Tahap-3 22 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-10 | 2022-07-24 | PT2 | PARE-PARE | WATANSOPPENG |  | R7 PRE WTG PT2 MAR 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-22 | 2022-07-01 | TEL.117/LG.320/R7W-7D100000/2022 | 2022-07-13 | TEL.0012/LG.320/R7W-7D100000/2022 | 2022-07-13 | 13053381 | 2249536 | 15302917 | 15302917 | 4500464311 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022090 | 1 | 8 | 01E07R03 | 007 | 72010005 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | BAHU |  | R7 MDO BAH PT2 ODC-BAH-FAG |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.109/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 18410776 | 4154624 | 22565400 | 22565400 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 14 | 01E07R03 | 007 | 72010005 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | BAHU |  | R7 MDO BAH PT2 ODC-BAH-FAS |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.108/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 3106924 | 663516 | 3770440 | 3770440 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 11 | 01E07R03 | 007 | 72010008 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | BITUNG |  | R7 MDO BIT PT2 MADIDIR WERU |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.106/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 13230195 | 3682111 | 16912306 | 16912306 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 9 | 01E07R03 | 007 | 72010055 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | LANGOAN |  | R7 MDO LAN PT2 Meiyergri Tempone |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.105/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 2718345 | 325629 | 3043974 | 3043974 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 7 | 01E07R03 | 007 | 72010060 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | MANADO |  | R7 MDO MDO PT2 Nancy Wowor |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.104/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 2718345 | 325629 | 3043974 | 3043974 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 10 | 01E07R03 | 007 | 72010083 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | PANIKI |  | R7 MDO PIK PT2 LORONG KAIRAGI DUA |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.103/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 6557928 | 525597 | 7083525 | 7083525 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 15 | 01E07R03 | 007 | 72010083 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | MANADO | PANIKI |  | R7 MDO PIK PT2 PANIKI BAWAH |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.110/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 6456279 | 1007183 | 7463462 | 7463462 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 12 | 01E07R03 | 007 | 73020041 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT2 Yuyun Abbas |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | K.TEL.107/LG.320/R7W-7F100000/2022 | 2022-07-28 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 10184235 | 1835750 | 12019985 | 12019985 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 6 | 01E07R03 | 007 | 73020041 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT2 IDHAM ASWAD |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.102/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 20560458 | 3722278 | 24282736 | 24282736 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022090 | 1 | 13 | 01E07R03 | 007 | 73020041 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003433/HK.810/R7W-7F100000/2022 | Pengadaan Dan Pemasangan OSP FO PT-2 10 LOP Witel Sulut Malut Divisi Regional VII | 2022-06-13 | 2022-07-27 | OSP FO FTTH PT2 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT2 SRI ASTUTI GOSOLO |  | 100 | 100 | 100 | BAST-1 | 2022-06-13 | 2022-07-10 | 2022-06-13 | TEL.101/LG.320/R7W-7F100000/2022 | 2022-07-27 | TEL.0005/LG.320/R7W-7F100000/2022 | 2022-07-28 | 24741286 | 4513599 | 29254885 | 29254885 | 4500464639 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022091 | 0 | 6 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003533/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 5 LOP WITEL SULTENG | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | PALU | PALU A |  | R7 PAL PLA PAL270 UNTAD BAHASA |  | 0 | 0 | 0 | Preparing | [7 empty] | 13843972 | 3195675 | 17039647 | 0 | 4500465214 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022091 | 0 | 9 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003533/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 5 LOP WITEL SULTENG | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | PALU | PALU A |  | R7 PAL PLA SBU001 |  | 0 | 0 | 0 | Preparing | [7 empty] | 11695715 | 4295541 | 15991256 | 0 | 4500465214 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022091 | 0 | 8 | 01E07O02 | 007 | 72030061 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003533/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 5 LOP WITEL SULTENG | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | PALU | PARIGI |  | R7 PAL PGI PGI128 SUMBERSARI |  | 0 | 0 | 0 | Preparing | [7 empty] | 11268887 | 2816677 | 14085564 | 0 | 4500465214 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022091 | 0 | 7 | 01E07O02 | 007 | 72030084 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003533/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 5 LOP WITEL SULTENG | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | PALU | TOLI-TOLI |  | R7 PAL TOL TLI064 MALATUANG |  | 0 | 0 | 0 | Preparing | [7 empty] | 24295163 | 6148825 | 30443988 | 0 | 4500465214 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022091 | 0 | 10 | 01E07O02 | 007 | 72030084 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003533/HK.810/R7W-7C1H0000/2022 | FIMO NODE B 5 LOP WITEL SULTENG | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | PALU | TOLI-TOLI |  | R7 PAL TOL TLI074 BAOLAN BARU |  | 0 | 0 | 0 | Preparing | [7 empty] | 21105758 | 6643419 | 27749177 | 0 | 4500465214 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022092 | 2 | 7 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003565/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 2 LoP Witel Gorontalo | 2022-06-16 | 2022-07-30 | FIMO NODE-B 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL GTL037 TBG WONGKODITI |  | 100 | 100 | 100 | BAST-1 | 2022-06-16 | 2022-07-26 | 2022-06-16 | TEL.1166/LG.310/DR7-12700000/2022 | 2022-07-25 | TEL.0129/LG.320/DR7-10400000/2022 | 2022-07-25 | 25663217 | 7822911 | 33486128 | 33486128 | 4500465216 |  |  |  |  | TELKOM AKSES | 2022-08-15
G2022092 | 2 | 6 | 01E07V06 | 007 | 72020019 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.003565/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO Node B 2 LoP Witel Gorontalo | 2022-06-16 | 2022-07-30 | FIMO NODE-B 2022 | GORONTALO | KWANDANG |  | R7 GTO KWD ISM195 POSSO |  | 100 | 100 | 100 | BAST-1 | 2022-06-16 | 2022-07-26 | 2022-06-16 | TEL.1165/LG.310/DR7-12700000/2022 | 2022-07-25 | TEL.0129/LG.320/DR7-10400000/2022 | 2022-07-25 | 9381546 | 2584563 | 11966109 | 11966109 | 4500465216 |  |  |  |  | TELKOM AKSES | 2022-08-15
G2022093 | 0 | 6 | 01E07J04 | 007 | 72080001 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-07-08 | 2022-06-16 | TEL.397/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 8408200 | 1892279 | 10300479 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 7 | 01E07J04 | 007 | 72080163 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-07-02 | 2022-06-16 | TEL.398/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 13016420 | 3293873 | 16310293 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 8 | 01E07J04 | 007 | 72080164 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | MATTOANGIN |  | R7 MKS MAT PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-06-25 | 2022-06-16 | TEL.399/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 7238588 | 1537936 | 8776524 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 13 | 01E07J04 | 007 | 72080093 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | PANGKEP |  | R7 MKS PKN PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-06-23 | 2022-06-16 | TEL.404/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 6566664 | 1661305 | 8227969 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 9 | 01E07J04 | 007 | 72080167 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-06-24 | 2022-06-16 | TEL.400/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 86695082 | 20082789 | 106777871 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 12 | 01E07J04 | 007 | 72080165 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-06-24 | 2022-06-16 | TEL.403/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 13428677 | 2667542 | 16096219 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 10 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-06-23 | 2022-06-16 | TEL.401/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 23378462 | 5550005 | 28928467 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022093 | 0 | 11 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003577/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan PT-2 8 LOP Periode Januari 2022 Area Witel Makassar - PT. TELKOM AKSES | 2022-06-16 | 2022-08-14 | PT2 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP PT2 JAN 2022 |  | 100 | 90 | 0 | Siap UT | 2022-06-16 | 2022-06-23 | 2022-06-16 | TEL.402/LG310/R7W-7A1C0000/2022 | 2022-07-19 |  |  | 4540832 | 803831 | 5344663 | 0 | 4500464905 |  |  |  |  | TELKOM AKSES
G2022094 | 0 | 7 | 01E07J04 | 007 | 72080120 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003578/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 2 LoP Area Witel Makassar - PT. BAKTI SARANA PRATAMA | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | UJUNGPANDANG | TAKALAR |  | R7 MKS TKA SNS352 Desa Salajangki |  | 85 | 90 | 0 | Siap UT | 2022-06-16 | 2022-08-14 | 2022-07-01 | TEL.406/LG.310/R7W-7A150000/2022 | 2022-07-25 |  |  | 221921735 | 38947724 | 260869459 | 0 | 4500464858 |  |  |  |  | BAKTI SARANA PRATAMA
G2022094 | 0 | 6 | 01E07J04 | 007 | 72080166 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.003578/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 2 LoP Area Witel Makassar - PT. BAKTI SARANA PRATAMA | 2022-06-16 | 2022-08-14 | FIMO NODE-B 2022 | UJUNGPANDANG | TAMALANREA |  | R7 MKS TMA Bangkala Macinna |  | 85 | 90 | 0 | Siap UT | 2022-06-16 | 2022-08-14 | 2022-07-01 | TEL.405/LG.310/R7W-7A150000/2022 | 2022-07-25 |  |  | 135368765 | 34331504 | 169700269 | 0 | 4500464858 |  |  |  |  | BAKTI SARANA PRATAMA
G2022095 | 0 | 10 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003594/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Tahun 2022 5 LOP Area Witel Papua | 2022-06-17 | 2022-08-15 | HEM | JAYAPURA | ABEPURA |  | PERPUSTAKAAN RUMAH GUBERNUR |  | 100 | 90 | 0 | Siap UT | 2022-06-17 | 2022-07-14 | 2022-08-01 |  |  |  |  | 36240961 | 7474594 | 43715555 | 0 | 4500465527 |  |  |  |  | TELKOM AKSES
G2022095 | 0 | 6 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003594/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Tahun 2022 5 LOP Area Witel Papua | 2022-06-17 | 2022-08-15 | HEM | JAYAPURA | ABEPURA |  | POLRES KEEROM |  | 100 | 90 | 0 | Siap UT | 2022-06-17 | 2022-07-14 | 2022-08-01 |  |  |  |  | 17593957 | 5879423 | 23473380 | 0 | 4500465527 |  |  |  |  | TELKOM AKSES
G2022095 | 0 | 7 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003594/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Tahun 2022 5 LOP Area Witel Papua | 2022-06-17 | 2022-08-15 | HEM | JAYAPURA | ABEPURA |  | LOKA VETERINER JAYAPURA |  | 100 | 90 | 0 | Siap UT | 2022-06-17 | 2022-07-14 | 2022-08-01 |  |  |  |  | 15540568 | 5263744 | 20804312 | 0 | 4500465527 |  |  |  |  | TELKOM AKSES
G2022095 | 0 | 8 | 01E07L12 | 007 | 74030001 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003594/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Tahun 2022 5 LOP Area Witel Papua | 2022-06-17 | 2022-08-15 | HEM | JAYAPURA | ABEPURA |  | KEMENAG KABUPATEN KEEROM |  | 100 | 90 | 0 | Siap UT | 2022-06-17 | 2022-07-14 | 2022-08-01 |  |  |  |  | 101082542 | 43860865 | 144943407 | 0 | 4500465527 |  |  |  |  | TELKOM AKSES
G2022095 | 0 | 9 | 01E07L12 | 007 | 74030162 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003594/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan Lastmile HEM Untuk Pelanggan EGBIS Tahun 2022 5 LOP Area Witel Papua | 2022-06-17 | 2022-08-15 | HEM | JAYAPURA | JAYAPURA |  | MAKESDAM VIII TRIKORA |  | 100 | 90 | 0 | Siap UT | 2022-06-17 | 2022-07-14 | 2022-08-01 |  |  |  |  | 5072161 | 1405729 | 6477890 | 0 | 4500465527 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 122 | 01C11G01 | 019 | 74030166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | JAYAPURA | ABEWAENA |  | WRS025 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 133712654 | 216324648 | 350037302 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 125 | 01C11G01 | 019 | 74030166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | JAYAPURA | ABEWAENA |  | WRS041 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 290573688 | 387200648 | 677774336 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 124 | 01C11G01 | 019 | 74030166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | JAYAPURA | ABEWAENA |  | JAP262 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 931589577 | 1585258468 | 2516848045 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 123 | 01C11G01 | 019 | 74030166 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | JAYAPURA | ABEWAENA |  | WRS043 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 305552285 | 544540172 | 850092457 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 114 | 01C11G01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | KENDARI | BAU-BAU |  | BAU210 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 174937412 | 212076814 | 387014226 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 116 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | KENDARI | RAHA |  | RHA074 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 250314246 | 236693224 | 487007470 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 115 | 01C11G01 | 019 | 72050057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | KENDARI | RAHA |  | RHA004 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 1741905238 | 2290913128 | 4032818366 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 113 | 01C11G01 | 019 | 72010283 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | MANADO | TUTUYAN |  | COI227 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 472811369 | 570636430 | 1043447799 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 130 | 01C11G01 | 019 | 74040016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | MANOKWARI | WARMARE |  | MWR101 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 191793192 | 343994048 | 535787240 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 126 | 01C11G01 | 019 | 74050012 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | MERAUKE | MERAUKE |  | MRK819 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 492049268 | 736997096 | 1229046364 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 117 | 01C11G01 | 019 | 72030099 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | PALU | KOTARAYA |  | PGI013 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 224988402 | 283954804 | 508943206 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 118 | 01C11G01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | PALU | LUWUK |  | LWK083 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 129387732 | 146663134 | 276050866 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 119 | 01C11G01 | 019 | 72030139 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | PALU | TENTENA |  | PSO013 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 629690929 | 744414760 | 1374105689 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 120 | 01C11G01 | 019 | 72040193 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | PARE-PARE | BARRU |  | BAR035 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 9125701 | 6505652 | 15631353 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 121 | 01C11G01 | 019 | 72040119 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | PARE-PARE | PASANG KAYU |  | PSK024 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 165696312 | 198805714 | 364502026 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 129 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | SORONG | NABIRE |  | WRS020 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 705053151 | 1159562220 | 1864615371 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 128 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | SORONG | NABIRE |  | NAB018 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 742391232 | 1360942944 | 2103334176 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 127 | 01C11G01 | 019 | 74060040 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | SORONG | NABIRE |  | NAB062 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 9977827 | 9398324 | 19376151 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
T2022004 | 0 | 112 | 01C11G01 | 019 | 73020035 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO FIBER ACCESS PROJECT CONTROL | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003618/HK.810/TSC-B0000000/2022 | Surat Pesanan-15 (SP#15) Pengadaan dan Pemasangan OSP FO Node-B Telkomsel Tahap-3 | 2022-06-17 | 2022-12-13 | OSP FO | TERNATE | SOFIFI |  | TDE020 |  | 0 | 0 | 0 | Preparing | 2022-06-17 | 2022-12-27 | [5 empty] | 21433495 | 25448139 | 46881634 | 0 | 4500465221 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 6 | 01E07L12 | 007 | 74030162 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | JAYAPURA |  | Bhayangkara RS Dok 2 |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 81777156 | 24465276 | 106242432 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 10 | 01E07L12 | 007 | 74030162 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | JAYAPURA |  | Argapura |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 20696734 | 6584291 | 27281025 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 11 | 01E07L12 | 007 | 74030026 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | JAYAPURA B |  | Base-G Kayubatu |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 76754890 | 23273298 | 100028188 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 12 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | SENTANI |  | Griya Mandiri SNI |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 75700555 | 18844835 | 94545390 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 7 | 01E07L12 | 007 | 74030072 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | WAENA |  | Perumnas 2 |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 137635031 | 35221383 | 172856414 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 9 | 01E07L12 | 007 | 74030072 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | WAENA |  | JL Teratai Buper Waena |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 115032533 | 29263110 | 144295643 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022096 | 0 | 8 | 01E07L12 | 007 | 74030072 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003712/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan PT2 Maret Tahun 2022 7 LOP Area Witel Papua | 2022-06-20 | 2022-08-18 | PT2 | JAYAPURA | WAENA |  | Perum Kehutanan |  | 100 | 0 | 0 | Preparing | 2022-06-20 | 2022-07-18 | [5 empty] | 24452819 | 5546822 | 29999641 | 0 | 4500466148 |  |  |  |  | TELKOM AKSES
G2022097 | 1 | 17 | 01E07P12 | 007 | 72040275 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | AJANGALE |  | R7 PRE AJN PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.310/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 1715991 | 239588 | 1955579 | 1955579 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 18 | 01E07P12 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | ENREKANG |  | R7 PRE ENR PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.311/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 8579955 | 1322386 | 9902341 | 9902341 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 6 | 01E07P12 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.312/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 1715991 | 239588 | 1955579 | 1955579 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 7 | 01E07P12 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.313/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 37751802 | 5457605 | 43209407 | 43209407 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 9 | 01E07P12 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.314/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 70391784 | 16038547 | 86430331 | 86430331 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 8 | 01E07P12 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | PASANG KAYU |  | R7 PRE PKU PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.315/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 1715991 | 239588 | 1955579 | 1955579 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 10 | 01E07P12 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | PINRANG |  | R7 PRE PIN PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.316/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 7284400 | 1952084 | 9236484 | 9236484 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 11 | 01E07P12 | 007 | 72040133 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | RANTEPAO |  | R7 PRE RTP PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.317/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 7396459 | 1196980 | 8593439 | 8593439 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 12 | 01E07P12 | 007 | 72040135 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | RAPPANG |  | R7 PRE PRN PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.318/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 1715991 | 301811 | 2017802 | 2017802 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 13 | 01E07P12 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.319/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 5680468 | 770723 | 6451191 | 6451191 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 14 | 01E07P12 | 007 | 72040158 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | SIDRAP |  | R7 PRE SID PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.320/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 3431982 | 541399 | 3973381 | 3973381 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 15 | 01E07P12 | 007 | 72040161 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | SOROWAKO |  | R7 PRE SRK PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.321/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 1715991 | 239588 | 1955579 | 1955579 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022097 | 1 | 16 | 01E07P12 | 007 | 72040186 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | ACCESS OPERATION & MAINTENANCE QE | TELKOM REGIONAL VII | K.TEL.003733/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-4 13 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-20 | 2022-08-03 | PT2 | PARE-PARE | WATANSOPPENG |  | R7 PRE WTG PT2 APRIL 2022 |  | 100 | 100 | 100 | BAST-1 | 2022-06-20 | 2022-07-26 | 2022-07-01 | TEL.322/LG.320/R7W-7D510000/2022 | 2022-07-25 | TEL.0013/LG.320/R7W-7D100000/2022 | 2022-07-25 | 41289507 | 7177906 | 48467413 | 48467413 | 4500466291 |  |  |  |  | TELKOM AKSES | 2022-07-30
G2022098 | 0 | 8 | 01E07O02 | 007 | 72060027 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | LUWUK | LUWUK |  | TOILI 2 |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 100046931 | 20336464 | 120383395 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 10 | 01E07O02 | 007 | 72030159 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | AMPANA |  | LABUAN |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 2271844 | 361730 | 2633574 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 7 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | BUNGKU |  | JL. TRANS SULAWESI BUNGKU |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 17775304 | 4480727 | 22256031 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 6 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | PALU A |  | JL. GATOT SUBROTO |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 549813276 | 128611773 | 678425049 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 15 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | PALU A |  | JL. DAYO DARA |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 342422493 | 82893545 | 425316038 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 14 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | PALU A |  | JL. VETERAN |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 16994146 | 3389629 | 20383775 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 16 | 01E07O02 | 007 | 72030103 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | PALU A |  | JL. S. PARMAN |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 16268709 | 3351355 | 19620064 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 13 | 01E07O02 | 007 | 72030088 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | TAWAELI |  | JL. TRANS SULAWESI TWL-FH |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 37380789 | 9394523 | 46775312 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 11 | 01E07O02 | 007 | 72030139 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | TENTENA |  | JL. TRANS SULAWESI TENTENA |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 65635386 | 16560031 | 82195417 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 9 | 01E07O02 | 007 | 72030083 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | PALU | TOLAY |  | JL. TRANS SULAWESI |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 1861514 | 263499 | 2125013 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022098 | 0 | 12 | 01E07O02 | 007 | 72070016 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003779/HK.810/R7W-7C100000/2022 | FTTH PT 2 11 LOP TAHUN 2022 WITEL SULTENG | 2022-06-21 | 2022-08-19 | OSP FO FTTH PT2 2022 | POSO | POSO |  | JL. PULAU SABANG |  | 100 | 0 | 0 | Preparing | 2022-06-21 | 2022-06-29 | [5 empty] | 226073863 | 57211854 | 283285717 | 0 | 4500466388 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 13 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW916 DMT WAHYU FATUFIA |  | 100 | 50 | 0 | Mat. Delivery | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 7759855 | 2885085 | 10644940 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 12 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW917 COMBAT DESA BAHODOPI |  | 100 | 50 | 0 | Mat. Delivery | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 3473160 | 1653285 | 5126445 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 11 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW913 COMBAT PASAR MALAM BAHODOPI |  | 100 | 65 | 0 | Instalasi | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 32043303 | 9079243 | 41122546 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 10 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW123 COMBAT TUGU BAHOMAKMUR |  | 100 | 65 | 0 | Instalasi | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 5515739 | 1899969 | 7415708 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 9 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW914 DMT BAHOMAKMUR |  | 100 | 50 | 0 | Mat. Delivery | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 9720715 | 2783953 | 12504668 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 8 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW912 DMT KEUREA |  | 100 | 65 | 0 | Instalasi | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 27810673 | 7474441 | 35285114 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 7 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW122 DMT FATUFIA 2 |  | 100 | 65 | 0 | Instalasi | 2022-06-22 | 2022-07-04 | 2022-06-22 |  |  |  |  | 38714650 | 9765813 | 48480463 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
G2022099 | 1 | 6 | 01E07O02 | 007 | 72030012 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.003855/HK.810/R7W-7C100000/2022 | FIMO NODE B 8 LOP WITEL SULTENG | 2022-06-22 | 2022-08-20 | FIMO NODE-B 2022 | PALU | BUNGKU |  | R7 PAL BKU MRW915 COMBAT RUKO BAHODOPI |  | 100 | 50 | 0 | Mat. Delivery | 2022-06-22 | 2022-07-01 | 2022-06-22 |  |  |  |  | 6045177 | 2392365 | 8437542 | 0 | 4500466668 |  |  |  |  | TELKOM AKSES
12022162 | 0 | 74 | 01C11B01 | 019 | 73010104 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | AMBON | AMBON |  | ME-D7-AMB |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 838771440 | 110848644 | 949620084 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 101 | 01C11B01 | 019 | 73010057 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | AMBON | PASSO |  | ME-D7-PAO |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 96 | 01C11B01 | 019 | 74010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | BIAK | BIAK |  | ME-D7-BIA |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 116 | 01C11B01 | 019 | 72020004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | GORONTALO | GORONTALO |  | ME-D7-GTL |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 874993000 | 241076160 | 1116069160 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 131 | 01C11B01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | JAYAPURA | JAYAPURA |  | ME9-D7-JAP |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 3391711760 | 486489656 | 3878201416 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 20 | 01C11B01 | 019 | 74030043 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | JAYAPURA | KUALA KENCANA |  | ME-D7-KUK |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 257266340 | 26446874 | 283713214 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 95 | 01C11B01 | 019 | 72050009 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | KENDARI | BAU-BAU |  | ME-D7-BAU |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 22 | 01C11B01 | 019 | 72050025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | KENDARI | KENDARI |  | ME-D7-KDR |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 657196000 | 67673020 | 724869020 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 23 | 01C11B01 | 019 | 72050093 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | KENDARI | MANDONGA |  | ME-D7-MDG |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 600768800 | 61840520 | 662609320 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 108 | 01C11B01 | 019 | 72010002 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | AIR MADIDI |  | ME-D7-AMD |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 574097000 | 204968640 | 779065640 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 110 | 01C11B01 | 019 | 72010004 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | AMURANG |  | ME-D7-AM |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 151 | 01C11B01 | 019 | 72010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | BAHU |  | ME-D7-BAH |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 838771440 | 110848644 | 949620084 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 150 | 01C11B01 | 019 | 72010005 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | BAHU |  | ME-D7-BAH |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 21 | 01C11B01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | BITUNG |  | ME-D7-BT |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 257266340 | 26446874 | 283713214 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 115 | 01C11B01 | 019 | 72010008 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | BITUNG |  | ME-D7-BT |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 111 | 01C11B01 | 019 | 72010052 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | KOTAMOBAGU |  | ME-D7-KTG |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 112 | 01C11B01 | 019 | 72010055 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | LANGOAN |  | ME-D7-LGN |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 106 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | MANADO |  | ME-D7-MDO |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 104 | 01C11B01 | 019 | 72010060 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | MANADO |  | ME9-D7-MDO |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 5843461000 | 837300498 | 6680761498 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 107 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | PANIKI |  | ME-D7-PIK |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 105 | 01C11B01 | 019 | 72010083 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | PANIKI |  | ME9-D7-PIK |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 5814751000 | 833855298 | 6648606298 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 113 | 01C11B01 | 019 | 72010110 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | TOMOHON |  | ME-D7-TMH |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 114 | 01C11B01 | 019 | 72010112 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | MANADO | TONDANO |  | ME-D7-TDO |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 780000000 | 229677000 | 1009677000 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 117 | 01C11B01 | 019 | 72030102 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | PALU | LUWUK |  | ME-D7-LWK |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 874993000 | 241076160 | 1116069160 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 77 | 01C11B01 | 019 | 72030084 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | PALU | TOLI-TOLI |  | ME-D7-TLI |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 658025080 | 92755928 | 750781008 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 97 | 01C11B01 | 019 | 72040049 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | PARE-PARE | ENREKANG |  | ME-D7-ENR |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 98 | 01C11B01 | 019 | 72040078 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | PARE-PARE | MAJENE |  | ME-D7-MJN |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 129 | 01C11B01 | 019 | 72040109 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | PARE-PARE | PALOPO |  | ME-D7-PLP |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 657196000 | 67673020 | 724869020 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 102 | 01C11B01 | 019 | 72040128 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | PARE-PARE | PINRANG |  | ME-D7-PIN |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 130 | 01C11B01 | 019 | 72070016 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | POSO | POSO |  | ME-D7-PSO |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 658025080 | 92755928 | 750781008 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 100 | 01C11B01 | 019 | 74060039 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | SORONG | MANOKWARI |  | ME-D7-MWR |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 25 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | SORONG | SORONG |  | ME-D7-SRG |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 600768800 | 61840520 | 662609320 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 24 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | SORONG | SORONG |  | ME2-D7-SRG |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 600768800 | 61840520 | 662609320 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 132 | 01C11B01 | 019 | 74060025 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | SORONG | SORONG |  | ME2-D7-SRG |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 3610420580 | 508769698 | 4119190278 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 133 | 01C11B01 | 019 | 73020041 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | TERNATE | TERNATE |  | ME2-D7-TNT |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 174440000 | 153550600 | 327990600 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 78 | 01C11B01 | 019 | 72080001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | UJUNGPANDANG | ANTANG |  | ME-D7-ANT |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 658025080 | 92755928 | 750781008 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 99 | 01C11B01 | 019 | 72080080 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | UJUNGPANDANG | MAROS |  | ME-D7-MAR |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 76 | 01C11B01 | 019 | 72080164 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | UJUNGPANDANG | MATTOANGIN |  | ME-D7-MAT |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 658025080 | 92755928 | 750781008 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
12022162 | 0 | 103 | 01C11B01 | 019 | 72080115 | DIGITAL INFRASTRUCTURE DEVELOPMENT | BROADBAND NODE CLOUD&DEFA DEPLOYMENT | CORE NETWORK DEPLOYMENT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.003880/HK.810/SSP-10000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan Metro L3 Aggregation Platform Huawei | 2022-06-22 | 2022-10-19 | Metro L3 Aggregation | UJUNGPANDANG | SINJAI |  | ME-D7-SIN |  | 50 | 0 | 0 | Preparing | 2022-06-22 | 2022-10-19 | [5 empty] | 897254000 | 243747480 | 1141001480 | 0 | 4500466758 |  |  |  |  | HUAWEI TECH INVESTMENT
G2022100 | 0 | 7 | 01E07R03 | 007 | 73020009 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | JAILOLO |  | R7 MDO JLL TER151 - LOLORI JAILOLO |  | 20 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-13 |  |  |  |  | 160022921 | 32001043 | 192023964 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 11 | 01E07R03 | 007 | 73020013 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | LABUHA |  | R7 MDO LBH LBA027 |  | 60 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 74967605 | 21173369 | 96140974 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 9 | 01E07R03 | 007 | 73020013 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | LABUHA |  | R7 MDO LBH LBA052 |  | 90 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 509510386 | 108887140 | 618397526 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 13 | 01E07R03 | 007 | 73020013 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | LABUHA |  | R7 MDO LBH LBA003 - Pelabuhan Bacan |  | 50 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 3788025 | 2168613 | 5956638 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 12 | 01E07R03 | 007 | 73020013 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | LABUHA |  | R7 MDO LBH COI168 |  | 50 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 23244173 | 6042393 | 29286566 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 6 | 01E07R03 | 007 | 73020013 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | LABUHA |  | R7 MDO LBH LBA080 |  | 90 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 131271524 | 32989274 | 164260798 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 10 | 01E07R03 | 007 | 73020013 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | LABUHA |  | R7 MDO LBH LBA028 |  | 90 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-12 |  |  |  |  | 60379860 | 15319303 | 75699163 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 8 | 01E07R03 | 007 | 73020041 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | TERNATE |  | R7 MDO TNT TER035 - Protelindo Taduma |  | 50 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 17944861 | 5814953 | 23759814 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022100 | 0 | 14 | 01E07R03 | 007 | 73020041 | TELKOM REGIONAL VII | WITEL SULUT MALUKU UTARA (MENADO) | ACCESS MAINTENANCE & OPTIMA | TELKOM REGIONAL VII | K.TEL.003898/HK.810/R7W-7F100000/2022 | PENGADAAN DAN PEMASANGAN OSP FO NODE B 9 LOP WITEL SULUT MALUT DIVISI REGIONAL VII | 2022-06-23 | 2022-08-21 | OSP FO FTTH PT2 2022 | TERNATE | TERNATE |  | R7 MDO TNT TER137 - DMT Rua Ternate |  | 50 | 90 | 0 | Siap UT | 2022-06-23 | 2022-08-21 | 2022-07-11 |  |  |  |  | 8975559 | 3036181 | 12011740 | 0 | 4500466471 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022101 | 1 | 6 | 01E07S02 | 007 | 72050030 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003985/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan PT2 5 LoP Periode Januari Tahun 2022 Area Witel Sultra | 2022-06-24 | 2022-07-23 | PT2 | KENDARI | KOLAKA |  | R7 KDI KKA PT2 ODC-KKA-FQ |  | 100 | 100 | 100 | BAST-1 | 2022-06-24 | 2022-07-03 | 2022-07-01 | K.TEL.132/LG300/DR7-12800000/2022 | 2022-07-12 | TEL.0004/LG.320/R7W-7G100000/2022 | 2022-07-12 | 10140026 | 1994513 | 12134539 | 12134539 | 4500467464 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022101 | 1 | 9 | 01E07S02 | 007 | 72050030 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003985/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan PT2 5 LoP Periode Januari Tahun 2022 Area Witel Sultra | 2022-06-24 | 2022-07-23 | PT2 | KENDARI | KOLAKA |  | R7 KDI KKA PT2 ODC-KKA-FC |  | 100 | 100 | 100 | BAST-1 | 2022-06-24 | 2022-07-03 | 2022-07-01 | K.TEL.134/LG300/DR7-12800000/2022 | 2022-07-12 | TEL.0004/LG.320/R7W-7G100000/2022 | 2022-07-12 | 22636244 | 4392400 | 27028644 | 27028644 | 4500467464 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022101 | 1 | 8 | 01E07S02 | 007 | 72050030 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003985/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan PT2 5 LoP Periode Januari Tahun 2022 Area Witel Sultra | 2022-06-24 | 2022-07-23 | PT2 | KENDARI | KOLAKA |  | R7 KDI KKA PT2 ODC-KKA-FG |  | 100 | 100 | 100 | BAST-1 | 2022-06-24 | 2022-07-03 | 2022-07-01 | K.TEL.133/LG300/DR7-12800000/2022 | 2022-07-12 | TEL.0004/LG.320/R7W-7G100000/2022 | 2022-07-12 | 14628873 | 2982365 | 17611238 | 17611238 | 4500467464 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022101 | 1 | 10 | 01E07S02 | 007 | 72050050 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003985/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan PT2 5 LoP Periode Januari Tahun 2022 Area Witel Sultra | 2022-06-24 | 2022-07-23 | PT2 | KENDARI | POMALAA |  | R7 KDI PMA PT2 ADD SPL |  | 90 | 100 | 100 | BAST-1 | 2022-06-24 | 2022-07-03 | 2022-07-01 | K.TEL.136/LG300/DR7-12800000/2022 | 2022-07-12 | TEL.0004/LG.320/R7W-7G100000/2022 | 2022-07-12 | 1198122 | 150190 | 1348312 | 1348312 | 4500467464 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022101 | 1 | 7 | 01E07S02 | 007 | 72050050 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.003985/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan PT2 5 LoP Periode Januari Tahun 2022 Area Witel Sultra | 2022-06-24 | 2022-07-23 | PT2 | KENDARI | POMALAA |  | R7 KDI PMA PT2 ODC PMA FD |  | 100 | 100 | 100 | BAST-1 | 2022-06-24 | 2022-07-03 | 2022-07-01 | K.TEL.135/LG300/DR7-12800000/2022 | 2022-07-12 | TEL.0004/LG.320/R7W-7G100000/2022 | 2022-07-12 | 4199686 | 940180 | 5139866 | 5139866 | 4500467464 |  |  |  |  | TELKOM AKSES | 2022-07-22
G2022102 | 0 | 7 | 01E07J04 | 007 | 72080009 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004002/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 3 LoP 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-06-24 | 2022-08-22 | FIMO NODE-B 2022 | UJUNGPANDANG | BANTAENG |  | R7 MKS BTN BTN052 |  | 87 | 36 | 0 | Mat. Delivery | 2022-06-24 | 2022-08-13 | 2022-08-01 |  |  |  |  | 134780830 | 38130558 | 172911388 | 0 | 4500466583 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022102 | 0 | 6 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004002/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 3 LoP 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-06-24 | 2022-08-22 | FIMO NODE-B 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP SKG067 Deltacomsel Cenae Bola |  | 78 | 32 | 0 | Mat. Delivery | 2022-06-24 | 2022-08-17 | 2022-08-01 |  |  |  |  | 161588581 | 29295097 | 190883678 | 0 | 4500466583 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022102 | 0 | 8 | 01E07J04 | 007 | 72080199 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004002/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan FIMO NODE-B 3 LoP 2022 Area Witel Makassar - PT. CELEBES ANDHIKA PRATAMA | 2022-06-24 | 2022-08-22 | FIMO NODE-B 2022 | UJUNGPANDANG | WATAMPONE |  | R7 MKS WTP WTP181 TBG Ajalireng |  | 50 | 32 | 0 | Mat. Delivery | 2022-06-24 | 2022-08-17 | 2022-08-01 |  |  |  |  | 24591082 | 4608483 | 29199565 | 0 | 4500466583 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022103 | 2 | 6 | 01E07J04 | 007 | 72080036 | TELKOM REGIONAL VII | WITEL SULSEL (MAKASSAR) | ACCESS OPTIMATION | TELKOM REGIONAL VII | K.TEL.004204/HK.810/R7W-7A100000/2022 | Surat Pesanan Pengadaan dan Pemasangan OSP FIMO NODE-B 1 LoP Area Witel Makassar - PT. SIPAKALEBBI 2 | 2022-06-28 | 2022-08-26 | FIMO NODE-B 2022 | UJUNGPANDANG | BULUKUMBA |  | R7 MKS BLK BLK180 JOJJOLO |  | 95 | 100 | 100 | BAST-1 | 2022-06-28 | 2022-08-06 | 2022-06-30 | TEL.0395/LG.310/R7W-7A330000/2022 | 2022-07-18 | TEL.0007/LG.320/R7W-7A100000/2022 | 2022-07-18 | 222138516 | 48137086 | 270275602 | 270275602 | 4500467858 |  |  |  |  | SIPAKALEBBI 2 | 2022-07-29
G2022104 | 0 | 9 | 01E07S02 | 007 | 72050009 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU BAU182 DMT MCP Banabungi |  | 100 | 85 | 0 | Instalasi | 2022-06-28 | 2022-07-09 | 2022-07-01 |  |  |  |  | 19191963 | 5221480 | 24413443 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022104 | 0 | 10 | 01E07S02 | 007 | 72050025 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | KENDARI |  | R7 KDI KDR KDI270 Hotel Plaza Inn |  | 100 | 75 | 0 | Instalasi | 2022-06-28 | 2022-07-09 | 2022-07-01 |  |  |  |  | 10783420 | 1512672 | 12296092 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022104 | 0 | 12 | 01E07S02 | 007 | 72050025 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | KENDARI |  | R7 KDI KDR UNH097 |  | 100 | 95 | 0 | BAUT | 2022-06-28 | 2022-07-09 | 2022-07-01 | K.TEL.143/LG.310/R7W-7G100000/2022 | 2022-08-01 |  |  | 69049523 | 20214583 | 89264106 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022104 | 0 | 6 | 01E07S02 | 007 | 72050093 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | MANDONGA |  | R7 KDI MDG ADL003 Kasipute |  | 100 | 95 | 0 | BAUT | 2022-06-28 | 2022-07-09 | 2022-07-01 | K.TEL.146/LG.310/R7W-7G100000/2022 | 2022-08-01 |  |  | 2689355 | 3322794 | 6012149 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022104 | 0 | 11 | 01E07S02 | 007 | 72050050 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | POMALAA |  | R7 KDI PMA KKA256 LALONGGOLOSUA-BANDARA 2 |  | 100 | 0 | 0 | Preparing | 2022-06-28 | 2022-07-09 | [5 empty] | 73169179 | 19313016 | 92482195 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022104 | 0 | 7 | 01E07S02 | 007 | 72050050 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | POMALAA |  | R7 KDI PMA KKA257 COMBATANAIWOI |  | 100 | 95 | 0 | BAUT | 2022-06-28 | 2022-07-09 | 2022-07-01 | K.TEL.145/LG.310/R7W-7G100000/2022 | 2022-08-01 |  |  | 8771241 | 1344482 | 10115723 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022104 | 0 | 8 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004205/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 7 LoP Area Witel Sultra | 2022-06-28 | 2022-09-25 | FIMO NODE-B 2022 | KENDARI | UNAAHA |  | R7 KDI UNH KKA071 DMT Tunas Jaya |  | 100 | 95 | 0 | BAUT | 2022-06-28 | 2022-07-07 | 2022-07-01 | K.TEL.144/LG.310/R7W-7G100000/2022 | 2022-08-01 |  |  | 7582567 | 4029734 | 11612301 | 0 | 0000000000 |  |  |  |  | TELKOM AKSES
G2022105 | 0 | 6 | 01E07S02 | 007 | 72050025 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004206/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 5 LoP Area Witel Sultra | 2022-06-28 | 2022-08-26 | FIMO NODE-B 2022 | KENDARI | KENDARI |  | R7 KDI KDR ADL200 |  | 85 |  | 0 |  | 2022-06-28 | 2022-08-26 | [5 empty] | 345815465 | 60514696 | 406330161 | 0 | 0000000000 |  |  |  |  | INNANDA INDAH
G2022105 | 0 | 10 | 01E07S02 | 007 | 72050025 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004206/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 5 LoP Area Witel Sultra | 2022-06-28 | 2022-08-26 | FIMO NODE-B 2022 | KENDARI | KENDARI |  | R7 KDI KDR KDI324 TONDONGGEU |  | 95 |  | 0 |  | 2022-06-28 | 2022-08-26 | [5 empty] | 24753634 | 6165826 | 30919460 | 0 | 0000000000 |  |  |  |  | INNANDA INDAH
G2022105 | 0 | 9 | 01E07S02 | 007 | 72050030 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004206/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 5 LoP Area Witel Sultra | 2022-06-28 | 2022-08-26 | FIMO NODE-B 2022 | KENDARI | KOLAKA |  | R7 KDIKKA KKA145 COMBAT LORONG MISTIK |  | 85 |  | 0 |  | 2022-06-29 | 2022-08-26 | [5 empty] | 7620994 | 2291339 | 9912333 | 0 | 0000000000 |  |  |  |  | INNANDA INDAH
G2022105 | 0 | 8 | 01E07S02 | 007 | 72050093 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004206/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 5 LoP Area Witel Sultra | 2022-06-28 | 2022-08-26 | FIMO NODE-B 2022 | KENDARI | MANDONGA |  | R7 KDI MDG ADL286 |  | 95 |  | 0 |  | 2022-06-28 | 2022-08-26 | [5 empty] | 105540609 | 18854616 | 124395225 | 0 | 0000000000 |  |  |  |  | INNANDA INDAH
G2022105 | 0 | 7 | 01E07S02 | 007 | 72050072 | TELKOM REGIONAL VII | WITEL SULTRA (KENDARI) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004206/HK.810/R7W-7G100000/2022 | Pengadaan Pelaksanaan Pekerjaan OSP FIMO NODE-B 5 LoP Area Witel Sultra | 2022-06-28 | 2022-08-26 | FIMO NODE-B 2022 | KENDARI | UNAAHA |  | R7 KDI UNH KDI343 HELO |  | 85 |  | 0 |  | 2022-06-29 | 2022-08-26 | [5 empty] | 284575566 | 51867307 | 336442873 | 0 | 0000000000 |  |  |  |  | INNANDA INDAH
G2022106 | 0 | 11 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004279/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 4 LOP Area Witel Sultra | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 JL DEWI SARTIKA LAPULU |  | 90 | 0 | 0 | Preparing | 2022-06-29 | 2022-09-11 | [5 empty] | 289042195 | 50811719 | 339853914 | 0 | 4500468108 |  |  |  |  | INNANDA INDAH
G2022106 | 0 | 9 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004279/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 4 LOP Area Witel Sultra | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 RUSUNAWA BUNGKUTOKO |  | 88 | 0 | 0 | Preparing | 2022-06-29 | 2022-09-11 | [5 empty] | 679919768 | 156889877 | 836809645 | 0 | 4500468108 |  |  |  |  | INNANDA INDAH
G2022106 | 0 | 10 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004279/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 4 LOP Area Witel Sultra | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 LAPANGAN RANOMETO |  | 62 |  | 0 |  | 2022-06-29 | 2022-09-11 | [5 empty] | 691752518 | 189878839 | 881631357 | 0 | 4500468108 |  |  |  |  | INNANDA INDAH
G2022106 | 0 | 12 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004279/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 4 LOP Area Witel Sultra | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 ODC-UNH-FC CAMAT MOLAWE |  | 82 | 0 | 0 | Preparing | 2022-06-30 | 2022-09-11 | [5 empty] | 570634297 | 99546841 | 670181138 | 0 | 4500468108 |  |  |  |  | INNANDA INDAH
G2022107 | 0 | 6 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004280/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 1 LOP Area Witel Gorontalo | 2022-06-29 | 2022-08-27 | OSP FO FTTH PT3 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT3 POHUWATO TIMUR |  | 74 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 409593745 | 98680460 | 508274205 | 0 | 4500468059 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022108 | 0 | 7 | 01E07V01 | 007 | 73010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004281/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 3 LOP Area Witel Sulut Malut | 2022-06-29 | 2022-09-01 | FTTH BATCH-2 | AMBON | TOBELO |  | R7 MDO TOB PT3 KAMPUNG BARU |  | 50 | 80 | 0 | Instalasi | 2022-06-29 | 2022-09-01 | 2022-07-13 |  |  |  |  | 211712750 | 47220280 | 258933030 | 0 | 4500468102 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022108 | 0 | 8 | 01E07V01 | 007 | 73010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004281/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 3 LOP Area Witel Sulut Malut | 2022-06-29 | 2022-09-01 | FTTH BATCH-2 | AMBON | TOBELO |  | R7 MDO TOB PT3 WARI TOBELO |  | 50 | 50 | 0 | Mat. Delivery | 2022-06-29 | 2022-09-01 | 2022-07-26 |  |  |  |  | 388436476 | 84832444 | 473268920 | 0 | 4500468102 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022108 | 0 | 6 | 01E07V01 | 007 | 73010124 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004281/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 3 LOP Area Witel Sulut Malut | 2022-06-29 | 2022-09-01 | FTTH BATCH-2 | AMBON | TOBELO |  | R7 MDO TOB PT3 KEMAKMURAN TOBELO |  | 70 | 60 | 0 | Instalasi | 2022-06-29 | 2022-09-01 | 2022-07-26 |  |  |  |  | 445718329 | 91531286 | 537249615 | 0 | 4500468102 |  |  |  |  | SOLUSI AKSES MANDIRI
G2022109 | 0 | 12 | 01E07V01 | 007 | 74030043 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004282/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 5 LoP Area Witel Papua | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | JAYAPURA | KUALA KENCANA |  | R7 JYP KUK PT3 YSN KHATOLIK IGNASIUS SP3 |  | 55 |  | 0 |  | 2022-06-29 | 2022-09-11 | [5 empty] | 121727646 | 30929318 | 152656964 | 0 | 4500468073 |  |  |  |  | TRANSDATA SATKOMINDO
G2022109 | 0 | 11 | 01E07V01 | 007 | 74030072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004282/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 5 LoP Area Witel Papua | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | JAYAPURA | WAENA |  | R7 JYP WAE PT3 PERUMNAS 1 WAENA |  | 66 |  | 0 |  | 2022-06-29 | 2022-09-11 | [5 empty] | 441384588 | 128774287 | 570158875 | 0 | 4500468073 |  |  |  |  | TRANSDATA SATKOMINDO
G2022109 | 0 | 8 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004282/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 5 LoP Area Witel Papua | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 JL. RAYA MANDALA SERINGGU |  | 55 |  | 0 |  | 2022-06-29 | 2022-09-11 | [5 empty] | 164925582 | 41869920 | 206795502 | 0 | 4500468073 |  |  |  |  | TRANSDATA SATKOMINDO
G2022109 | 0 | 7 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004282/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 5 LoP Area Witel Papua | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 BUTI KPG |  | 55 |  | 0 |  | 2022-06-29 | 2022-09-11 | [5 empty] | 203761369 | 52321281 | 256082650 | 0 | 4500468073 |  |  |  |  | TRANSDATA SATKOMINDO
G2022109 | 0 | 9 | 01E07V01 | 007 | 74050012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004282/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 5 LoP Area Witel Papua | 2022-06-29 | 2022-09-11 | OSP FO FTTH PT3 2022 | MERAUKE | MERAUKE |  | R7 JYP MRK PT3 SERINGGU JAYA |  | 55 |  | 0 |  | 2022-06-29 | 2022-09-11 | [5 empty] | 145489604 | 40334121 | 185823725 | 0 | 4500468073 |  |  |  |  | TRANSDATA SATKOMINDO
G2022110 | 2 | 17 | 01E07V01 | 007 | 72030099 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004283/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 2 LoP Area Witel Sulteng (PT. PMP) | 2022-06-29 | 2022-08-12 | OSP FO FTTH PT3 2022 | PALU | KOTARAYA |  | R7 PAL KOR PT3 DESA ONGKA |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-12 | 2022-07-01 | TEL.1179/LG.310/DR7-12700000/2022 | 2022-08-04 | TEL.0128/LG.320/DR7-10400000/2022 | 2022-08-04 | 210514520 | 41635020 | 252149540 | 252149540 | 4500468077 |  |  |  |  | PAPUA MITRA PERKASA | 2022-08-11
G2022110 | 2 | 15 | 01E07V01 | 007 | 72030092 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004283/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 2 LoP Area Witel Sulteng (PT. PMP) | 2022-06-29 | 2022-08-12 | OSP FO FTTH PT3 2022 | PALU | PALU B |  | R7 PAL PLB PT3 JL. LAPATTA (FAD) |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-12 | 2022-07-01 | TEL.1180/LG.310/DR7-12700000/2022 | 2022-08-04 | TEL.0128/LG.320/DR7-10400000/2022 | 2022-08-04 | 265808972 | 52587800 | 318396772 | 318396772 | 4500468077 |  |  |  |  | PAPUA MITRA PERKASA | 2022-08-11
G2022111 | 0 | 18 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | LUWUK | LUWUK |  | R7 PAL LWU PT3 PULAU KALIMANTAN (FQ) |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 30073390 | 7959638 | 38033028 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 7 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | LUWUK | LUWUK |  | R7 PAL LWU PT3 TOILI 2 (FY) |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 27997010 | 4723082 | 32720092 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 19 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | LUWUK | LUWUK |  | R7 PAL LWU PT3 BUKIT HALIMUN (FH) |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 41222841 | 7433496 | 48656337 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 20 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | LUWUK | LUWUK |  | R7 PAL LWU PT3 MOILONG |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 986392835 | 174404324 | 1160797159 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 16 | 01E07V01 | 007 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | BUNGKU |  | R7 PAL BKU PT3 DESA LALAMPU |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-09-02 | [5 empty] | 417516255 | 77374775 | 494891030 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 12 | 01E07V01 | 007 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | BUNGKU |  | R7 PAL BKU PT3 BAHODOPI (FD) |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 99838286 | 27489756 | 127328042 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 10 | 01E07V01 | 007 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | KOLONODALE |  | R7 PAL KOL PT3 BETELEME |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 551225317 | 123698031 | 674923348 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 15 | 01E07V01 | 007 | 72030104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | KOLONODALE |  | R7 PAL KOL PT3 KOROLAMA |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 462922239 | 103375964 | 566298203 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 11 | 01E07V01 | 007 | 72030099 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | KOTARAYA |  | R7 PAL KOR PT3 BOLANO |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 287593657 | 78329026 | 365922683 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 17 | 01E07V01 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | PALU A |  | R7 PAL PLA PT3 LAYANA 2022 |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 517774868 | 244399797 | 762174665 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 8 | 01E07V01 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | PALU A |  | R7 PAL PLA PT3 UNTAD I BUMI ROVIGA 2 |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 309607549 | 57838984 | 367446533 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 9 | 01E07V01 | 007 | 72030092 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | PALU B |  | R7 PAL PLB PT3 BTN GREEN LANDO |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 236477329 | 110024364 | 346501693 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 14 | 01E07V01 | 007 | 72030061 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | PARIGI |  | R7 PAL PGI PT3 KEL MAESA (FK) |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 57366669 | 11472485 | 68839154 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 6 | 01E07V01 | 007 | 72030088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | TAWAELI |  | R7 PAL TWL PT3 TOAYA |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 379274231 | 85418629 | 464692860 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022111 | 0 | 13 | 01E07V01 | 007 | 72030084 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004285/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 15 LoP Area Witel Sulteng | 2022-06-29 | 2022-09-26 | OSP FTTH BATCH 2 | PALU | TOLI-TOLI |  | R7 PAL TOL PT3 JL. PELABUHAN (FE) |  | 95 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-02 | [5 empty] | 168262309 | 39162417 | 207424726 | 0 | 4500468089 |  |  |  |  | TELKOM AKSES
G2022112 | 2 | 7 | 01E07V01 | 007 | 72060027 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004286/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 2 LoP Area Witel Sulteng (PT. MES) | 2022-06-29 | 2022-08-29 | OSP FO FTTH PT3 2022 | LUWUK | LUWUK |  | R7 PAL LWU PT3 TOILI (FY) |  | 75 |  | 0 |  | 2022-06-29 | 2022-08-12 | [5 empty] | 600631852 | 105807679 | 706439531 | 0 | 4500468090 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022112 | 2 | 6 | 01E07V01 | 007 | 72030013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004286/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 2 LoP Area Witel Sulteng (PT. MES) | 2022-06-29 | 2022-08-29 | OSP FO FTTH PT3 2022 | PALU | BUOL |  | R7 PAL BUO PT3 DESA MOMONU 1 |  | 95 |  | 0 |  | 2022-06-29 | 2022-08-12 | [5 empty] | 192125909 | 36372417 | 228498326 | 0 | 4500468090 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022113 | 1 | 11 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004287/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-08-12 | FIMO NODE-B 2022 | PARE-PARE | MAJENE |  | R7 PRE MAJ MAJ013 Maliaya |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-11 | 2022-06-30 | TEL.336/LG.320/R7W-7D320000/2022 | 2022-08-01 | TEL.0003/LG.320/R7W-7D1G0000/2022 | 2022-08-01 | 10398816 | 2896884 | 13295700 | 13295700 | 4500467943 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-08-12
G2022113 | 1 | 10 | 01E07P02 | 007 | 72040086 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004287/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-08-12 | FIMO NODE-B 2022 | PARE-PARE | MAMASA |  | R7 PRE MMS COI270 Combat Tawalian |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-11 | 2022-06-29 | TEL.337/LG.320/R7W-7D320000/2022 | 2022-08-01 | TEL.0003/LG.320/R7W-7D1G0000/2022 | 2022-08-01 | 12656597 | 2912651 | 15569248 | 15569248 | 4500467943 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-08-12
G2022113 | 1 | 7 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004287/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-08-12 | FIMO NODE-B 2022 | PARE-PARE | POLEWALI |  | R7 PRE PLW PLW066 RLU Wonomulyo |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-11 | 2022-06-29 | TEL.338/LG.320/R7W-7D320000/2022 | 2022-08-01 | TEL.0003/LG.320/R7W-7D1G0000/2022 | 2022-08-01 | 2945571 | 1357706 | 4303277 | 4303277 | 4500467943 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-08-12
G2022113 | 1 | 8 | 01E07P02 | 007 | 72040195 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004287/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-08-12 | FIMO NODE-B 2022 | PARE-PARE | POLEWALI |  | R7 PRE PLW PLW008 Binuang |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-11 | 2022-06-30 | TEL.339/LG.320/R7W-7D320000/2022 | 2022-08-01 | TEL.0003/LG.320/R7W-7D1G0000/2022 | 2022-08-01 | 30531830 | 7385215 | 37917045 | 37917045 | 4500467943 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-08-12
G2022113 | 1 | 9 | 01E07P02 | 007 | 72040187 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004287/HK.810/R7W-7D1G0000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 5 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-08-12 | FIMO NODE-B 2022 | PARE-PARE | WONOMULYO |  | R7 PRE WON PLW009 Tapango |  | 95 | 100 | 100 | BAST-1 | 2022-06-29 | 2022-08-11 | 2022-06-29 | TEL.340/LG.320/R7W-7D320000/2022 | 2022-08-01 | TEL.0003/LG.320/R7W-7D1G0000/2022 | 2022-08-01 | 6137029 | 1997406 | 8134435 | 8134435 | 4500467943 |  |  |  |  | MAPPADECENG JAYA LESTARI | 2022-08-12
G2022114 | 0 | 16 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | ENREKANG |  | R7 PRE ENR MLE039 Gandasil |  | 50 | 53.509 | 0 | Instalasi | 2022-06-29 | 2022-09-26 | 2022-07-17 |  |  |  |  | 350129910 | 60866078 | 410995988 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 9 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | ENREKANG |  | R7 PRE ENR ENR045 DMT Isat Enrekang |  | 80 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-17 |  |  |  |  | 13615705 | 4461248 | 18076953 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 8 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | ENREKANG |  | R7 PRE ENR ENR031 Protelindo Batu Kede |  | 80 | 54.024 | 0 | Instalasi | 2022-06-29 | 2022-09-26 | 2022-07-17 |  |  |  |  | 248979261 | 42556352 | 291535613 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 17 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK MLE205 |  | 50 | 80 | 0 | Instalasi | 2022-06-29 | 2022-09-26 | 2022-07-17 |  |  |  |  | 10248531 | 2796827 | 13045358 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 14 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK MLE087 DMT Isat Sangalla |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-17 |  |  |  |  | 10918349 | 3069336 | 13987685 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 15 | 01E07P02 | 007 | 72040197 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK MLE123 DMT MM Kolam Makale |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-17 |  |  |  |  | 31378965 | 6266518 | 37645483 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 13 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP054 DMT Larompong Selatan |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-15 |  |  |  |  | 120015448 | 21695526 | 141710974 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 10 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP126 TBG Peta Sendana |  | 80 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-15 |  |  |  |  | 18972841 | 5258422 | 24231263 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 12 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP077 Protelindo Lanipa |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-15 |  |  |  |  | 27572740 | 8702526 | 36275266 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 11 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP118 Combat BTN Nyiur Palopo |  | 50 | 20 | 0 | Preparing | 2022-06-29 | 2022-09-26 | 2022-07-15 |  |  |  |  | 7596417 | 2065007 | 9661424 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022114 | 0 | 7 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004292/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP Fimo Node B 11 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-29 | 2022-09-26 | FIMO NODE-B 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PIN110 DMT Pasar Lanrisang |  | 80 |  | 0 |  | 2022-06-29 | 2022-09-26 | [5 empty] | 12641821 | 3261176 | 15902997 | 0 | 4500468112 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022115 | 0 | 8 | 01E07T02 | 007 | 74060035 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | BIAK |  | R7 SON BIA BIA021 DMT Nirmala Beach Biak |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 3158926 | 1931663 | 5090589 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 22 | 01E07T02 | 007 | 74060035 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | BIAK |  | R7 SON BIA BIA021 Dmt Nirmala Beach Biak |  | 66 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 64979455 | 17476816 | 82456271 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 9 | 01E07T02 | 007 | 74060037 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | BINTUINI |  | R7 SON BTI BTI903 |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 49287655 | 12318684 | 61606339 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 21 | 01E07T02 | 007 | 74060038 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | FAKFAK |  | R7 SON FFA FFK012 FAKFAKSELATAN(DMT) |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 6642847 | 3125663 | 9768510 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 18 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR MWR077 PANTAIANGREM |  | 60 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 31075780 | 11114036 | 42189816 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 11 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR MWR365 |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 13604681 | 5162519 | 18767200 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 19 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR MWR047 TELUKAROW |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 23562169 | 6007355 | 29569524 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 20 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR MWR045 GEREJATUAKWAWI |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 14075184 | 4867125 | 18942309 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 17 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR MWR130 MCPMESTNIMANOKWARI |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 3117269 | 1874363 | 4991632 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 12 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR MWR070 STPPMANOKWARI |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 4320233 | 2329663 | 6649896 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 23 | 01E07T02 | 007 | 74060039 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | MANOKWARI |  | R7 SON MWR RAS059 |  | 60 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 218783304 | 45119486 | 263902790 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 10 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | NABIRE |  | R7 SON NAB NAB203 |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 9388299 | 3217825 | 12606124 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 24 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | NABIRE |  | R7 SON NAB NAB031 |  | 50 |  | 0 |  | 2022-06-29 | 2022-08-27 | [5 empty] | 65369342 | 14678683 | 80048025 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 13 | 01E07T02 | 007 | 74060041 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | SERUI |  | R7 SON SRU SRU005 KANTORBUPATISERUI |  | 60 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 32799654 | 10051982 | 42851636 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 14 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | SORONG |  | R7 SON SON SON203 KAISEVO |  | 50 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 4278576 | 2272363 | 6550939 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 16 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | SORONG |  | R7 SON SON SON184 TBG Wiku Klawasi Sorong |  | 50 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 4278576 | 2272363 | 6550939 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 15 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | SORONG |  | R7 SON SON SON200 MOYOPERMAI |  | 65 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 34217711 | 10449982 | 44667693 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
G2022115 | 0 | 7 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004321/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 18 LOP AREA WITEL PAPUA BARAT | 2022-06-29 | 2022-08-27 | FIMO NODE-B 2022 | SORONG | SORONG |  | R7 SON SON SON432 Combat Mako Katapop |  | 50 | 0 | 0 | Preparing | 2022-06-29 | 2022-08-27 | [5 empty] | 2710283 | 1883456 | 4593739 | 0 | 4500468236 |  |  |  |  | TRANSDATA SATKOMINDO
T2022008 | 1 | 10 | 01C11G03 | 019 | 70000236 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004336/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-06-30 | 2022-11-26 | Radio IP | KANTOR DIVRE VII | IP RADIO SULAWESI |  | SS#2 : Upgrade Hardware Radio IP |  | 50 | 0 | 0 | Preparing | 2022-06-30 | 2022-12-10 | [5 empty] | 1623912825 | 199937810 | 1823850635 | 0 | 4500467836 |  |  |  |  | ERICSSON INDONESIA
T2022008 | 1 | 18 | 01C11G03 | 019 | 72080977 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004336/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform Ericsson | 2022-06-30 | 2022-11-26 | Radio IP | UJUNGPANDANG | SULSELBAR |  | SS#4 : BHP-ISR |  | 50 |  |  |  | 2022-06-30 | 2022-12-10 | [5 empty] | 0 | 204750000 | 204750000 | 0 | 4500467836 |  |  |  |  | ERICSSON INDONESIA
T2022009 | 1 | 15 | 01E-7C01 | 030 | 70000014 | SUBDIT CONSUMER FULFILLMENT | PERFORMANCE & SALES SUPPORT | OPEX & CAPEX MONITORING | SUBDIT CONSUMER FULFILLMENT | K.TEL.004346/HK.810/TSC-B0000000/2022 | Surat Pesanan-5 (SP#5) Pengadaan ONT Retail Dual Band Platform ZTE | 2022-06-30 | 2022-11-26 | ONT Retail | KANTOR DIVRE VII | KANTOR DIVRE VII |  |  |  | 90 | 100 | 100 | BAST-1 | 2022-07-20 | 2022-08-12 | 2022-08-01 | C.TEL1315/LG300/DR-7-12800000/2022 | 2022-08-11 | TEL.0091/LG.320/COP-F3000000/2022 | 2022-08-11 | 6594000000 | 0 | 6594000000 | 6594000000 | 4500468237 |  |  |  |  | ZTE INDONESIA | 2022-08-12
G2022116 | 0 | 15 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | BARRU |  | R7 PRE BAR BAR041 |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 23196442 | 4478025 | 27674467 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 14 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | BARRU |  | R7 PRE BAR BAR057 |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 4691275 | 1943757 | 6635032 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 16 | 01E07P02 | 007 | 72040193 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | BARRU |  | R7 PRE BAR BAR050 |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 2853711 | 1420503 | 4274214 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 13 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PRE046 TBG Lompoe |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 7652431 | 2779528 | 10431959 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 7 | 01E07P02 | 007 | 72040135 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | RAPPANG |  | SDR097 TBG Lakitta |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 31652577 | 8199569 | 39852146 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 11 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | SENGKANG |  | R7 PRE SKG SKG047 Protelindo Sabbangparu |  | 55 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 1082923393 | 233577725 | 1316501118 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 9 | 01E07P02 | 007 | 72040159 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | SIDENRENG RAPPANG |  | R7 PRE SID SDR068 DMT Padinyama Amparita |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 10534936 | 2907401 | 13442337 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 12 | 01E07P02 | 007 | 72040159 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | SIDENRENG RAPPANG |  | R7 PRE SID SDR035 DMT Isat Watangpulu_MW - 7 |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 13128913 | 2958398 | 16087311 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 8 | 01E07P02 | 007 | 72040174 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | TANRUTEDONG |  | R7 PRE TTE SDR107 MCR Pasar Tanru Tedong |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 2303587 | 1250478 | 3554065 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022116 | 0 | 10 | 01E07P02 | 007 | 72040186 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004353/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 10 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | WATANSOPPENG |  | R7 PRE WTG WTG033 Deltacomcel Mario Riwa |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-20 | [5 empty] | 7041274 | 1939316 | 8980590 | 0 | 4500468325 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022117 | 0 | 7 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004354/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MAS012 Baebunta Bajo |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-24 | [5 empty] | 243806362 | 42661252 | 286467614 | 0 | 4500468348 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022117 | 0 | 9 | 01E07P02 | 007 | 72040094 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004354/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | MASAMBA |  | R7 PRE MAS MAS011 Mappadecceng |  | 78 |  | 0 |  | 2022-06-30 | 2022-09-24 | [5 empty] | 762108482 | 145132760 | 907241242 | 0 | 4500468348 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022117 | 0 | 8 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004354/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP256 Pongko |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-24 | [5 empty] | 184149123 | 49413407 | 233562530 | 0 | 4500468348 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022117 | 0 | 10 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004354/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan OSP FIMO Node-B 4 LOP Tahun 2022 Area Witel Sulselbar | 2022-06-30 | 2022-09-27 | FIMO NODE-B 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PLP037 Rep. Bontosiring |  | 50 |  | 0 |  | 2022-06-30 | 2022-09-24 | [5 empty] | 354989950 | 61114428 | 416104378 | 0 | 4500468348 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022118 | 1 | 6 | 01E07O02 | 007 | 72070016 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004358/HK.810/R7W-7C100000/2022 | FIMO NODE B 1 LOP WITEL SULTENG | 2022-06-30 | 2022-07-29 | FIMO NODE-B 2022 | POSO | POSO |  | R7 PAL PSO PSO008_TUMORA |  | 100 | 100 | 100 | BAST-1 | 2022-07-01 | 2022-07-25 | 2022-07-30 | C.TEL.70/LG.000/WTL-7G310000/2022 | 2022-07-30 | TEL.0004/LG.320/R7W-7C100000/2022 | 2022-07-30 | 259015058 | 50159369 | 309174427 | 309174427 | 4500468110 |  |  |  |  | WENANG PERKASA ABADI | 2022-08-01
T2022010 | 2 | 75 | 01C11H01 | 019 | 74030001 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004359/HK.810/TSC-A0000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan DWDM Platform ZTE | 2022-06-30 | 2022-11-26 | DWDM | JAYAPURA | ABEPURA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-07-01 | 2022-11-26 | 2022-07-28 |  |  |  |  | 394763801 | 41139050 | 435902851 | 0 | 4500468273 |  |  |  |  | ZTE INDONESIA
T2022010 | 2 | 52 | 01C11H01 | 019 | 74030162 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004359/HK.810/TSC-A0000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan DWDM Platform ZTE | 2022-06-30 | 2022-11-26 | DWDM | JAYAPURA | JAYAPURA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-07-01 | 2022-11-26 | 2022-07-28 |  |  |  |  | 431910761 | 43925090 | 475835851 | 0 | 4500468273 |  |  |  |  | ZTE INDONESIA
T2022010 | 2 | 53 | 01C11H01 | 019 | 74030068 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004359/HK.810/TSC-A0000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan DWDM Platform ZTE | 2022-06-30 | 2022-11-26 | DWDM | JAYAPURA | TIMIKA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-07-01 | 2022-11-26 | 2022-07-28 |  |  |  |  | 440692020 | 38896380 | 479588400 | 0 | 4500468273 |  |  |  |  | ZTE INDONESIA
T2022010 | 2 | 74 | 01C11H01 | 019 | 74030179 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004359/HK.810/TSC-A0000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan DWDM Platform ZTE | 2022-06-30 | 2022-11-26 | DWDM | JAYAPURA | TTC JAYAPURA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-07-01 | 2022-11-26 | 2022-07-28 |  |  |  |  | 2316990336 | 207467832 | 2524458168 | 0 | 4500468273 |  |  |  |  | ZTE INDONESIA
T2022010 | 2 | 51 | 01C11H01 | 019 | 74030179 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004359/HK.810/TSC-A0000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan DWDM Platform ZTE | 2022-06-30 | 2022-11-26 | DWDM | JAYAPURA | TTC JAYAPURA |  |  |  | 20 | 90 | 0 | Siap UT | 2022-07-01 | 2022-11-26 | 2022-07-28 |  |  |  |  | 431910761 | 43925090 | 475835851 | 0 | 4500468273 |  |  |  |  | ZTE INDONESIA
T2022010 | 2 | 54 | 01C11H01 | 019 | 74030178 | DIGITAL INFRASTRUCTURE DEVELOPMENT | DIGITAL TRANSPORT DEPLOYMENT | BACKBONE SUBMARINE DEPLOYMENT AREA-1 | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004359/HK.810/TSC-A0000000/2022 | Surat Pesanan-1 (SP#1) Pengadaan dan Pemasangan DWDM Platform ZTE | 2022-06-30 | 2022-11-26 | DWDM | JAYAPURA | TTC TIMIKA |  | CLS Timika |  | 20 | 90 | 0 | Siap UT | 2022-07-01 | 2022-11-26 | 2022-07-28 |  |  |  |  | 440692020 | 38896380 | 479588400 | 0 | 4500468273 |  |  |  |  | ZTE INDONESIA
G2022119 | 0 | 11 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ODC-ABE-FP KALI ACAI |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 292300768 | 68668760 | 360969528 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 12 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 ODC-ABE-FU JALAN BARU |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 176037366 | 40279128 | 216316494 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 10 | 01E07V01 | 007 | 74030001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | ABEPURA |  | R7 JYP ABE PT3 WIGUNA FUTSAL |  | 85 | 0 | 0 | Preparing | 2022-06-30 | 2022-08-31 | [5 empty] | 693207743 | 186329465 | 879537208 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 15 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 ODC-JAP-FB ENTROP |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 201698776 | 55439302 | 257138078 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 14 | 01E07V01 | 007 | 74030025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | JAYAPURA A |  | R7 JYP JAP PT3 ODC-JAP-FAA PERUM PEMDA |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 135351911 | 34483723 | 169835634 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 13 | 01E07V01 | 007 | 74030043 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | KUALA KENCANA |  | R7 JYP KUK PT3 DISTRIBUSI ODC SP3 |  | 88 | 0 | 0 | Preparing | 2022-06-30 | 2022-08-31 | [5 empty] | 897481862 | 225169544 | 1122651406 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 18 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 BRIGIF TIMIKA |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 65097990 | 13942834 | 79040824 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 17 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 ODC-TIM-FT SMK YPPPGI |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 72152238 | 17474504 | 89626742 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 19 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 JALUR 1 KIRI SP2 |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 65153135 | 17260084 | 82413219 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022119 | 0 | 16 | 01E07V01 | 007 | 74030068 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004373/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 10 LoP Area Witel Papua | 2022-06-30 | 2022-09-17 | OSP FO FTTH PT3 2022 | JAYAPURA | TIMIKA |  | R7 JYP TIM PT3 ODC-TIM-FAE KELAPA DUA |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-31 | [5 empty] | 45080926 | 11520972 | 56601898 | 0 | 4500468173 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 8 | 01E07V01 | 007 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK PT3 MAKALE UTARA |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 757858566 | 143662630 | 901521196 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 14 | 01E07V01 | 007 | 72040082 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | MALILI |  | R7 PRE MLL PT3 NEW DS ODC-MLL-FA |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 409695437 | 86626844 | 496322281 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 10 | 01E07V01 | 007 | 72040086 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | MAMASA |  | R7 PRE MMS PT3 TANDUKALUA |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 424134554 | 93610244 | 517744798 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 7 | 01E07V01 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT3 ENDENG RANGAS |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 549959237 | 132204164 | 682163401 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 6 | 01E07V01 | 007 | 72040088 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT3 MAN 1 MAMUJU |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 662292225 | 149226608 | 811518833 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 12 | 01E07V01 | 007 | 72040195 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | POLEWALI |  | R7 PRE PLW PT3 NEW DS ODC-PLW-FAE |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 161480619 | 34894972 | 196375591 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 9 | 01E07V01 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | RANTEPAO |  | R7 PRE RTP PT3 SADAN |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 749670836 | 145343192 | 895014028 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 13 | 01E07V01 | 007 | 72040161 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | SOROWAKO |  | R7 PRE SRK PT3 NEW DS ODC-SRK-FB |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 209485536 | 46051721 | 255537257 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022120 | 0 | 11 | 01E07V01 | 007 | 72040187 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004374/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 9 LoP Area Witel Sulselbar | 2022-06-30 | 2022-10-07 | OSP FO FTTH PT3 2022 | PARE-PARE | WONOMULYO |  | R7 PRE WON PT3 ODC-WON-FAF |  | 100 | 0 | 0 | Preparing | 2022-06-30 | 2022-07-09 | [5 empty] | 329050802 | 78986231 | 408037033 | 0 | 4500468301 |  |  |  |  | TELKOM AKSES
G2022121 | 0 | 6 | 01E07V01 | 007 | 72040109 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004375/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 1 LoP Area Witel Sulselbar | 2022-06-30 | 2022-08-18 | OSP FO FTTH PT3 2022 | PARE-PARE | PALOPO |  | R7 PRE PT3 ODC-PLP-FAY |  | 78 |  | 0 |  | 2022-06-30 | 2022-08-14 | [5 empty] | 309470213 | 68550256 | 378020469 | 0 | 4500468462 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022122 | 0 | 8 | 01E07V01 | 007 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004376/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 3 LoP Area Witel Sulselbar | 2022-06-30 | 2022-08-28 | OSP FO FTTH PT3 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK PT3 NEW DS ODC-MAK-FAF |  | 82 | 82 | 0 | Instalasi | 2022-06-30 | 2022-08-28 | 2022-07-14 |  |  |  |  | 150271045 | 32154665 | 182425710 | 0 | 4500468459 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022122 | 0 | 9 | 01E07V01 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004376/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 3 LoP Area Witel Sulselbar | 2022-06-30 | 2022-08-28 | OSP FO FTTH PT3 2022 | PARE-PARE | RANTEPAO |  | R7 PRE RTP PT3 NEW DS ODC-RTP-FC |  | 50 | 74 | 0 | Instalasi | 2022-06-30 | 2022-08-28 | 2022-07-14 |  |  |  |  | 319376771 | 78659398 | 398036169 | 0 | 4500468459 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022122 | 0 | 7 | 01E07V01 | 007 | 72040160 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004376/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 3 LoP Area Witel Sulselbar | 2022-06-30 | 2022-08-28 | OSP FO FTTH PT3 2022 | PARE-PARE | SIWA |  | R7 PRE SIW PT3 NEW DS ODC-SIW-FAB |  | 82 | 82 | 0 | Instalasi | 2022-06-30 | 2022-08-28 | 2022-07-14 |  |  |  |  | 223958295 | 41998754 | 265957049 | 0 | 4500468459 |  |  |  |  | BAGAMAS PRIMA TEKNIK
T2022012 | 1 | 13 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004391/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-06-30 | 2022-12-26 | Radio IP | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#3 BHP ISR Bali Nusra |  | 50 | 20 | 0 | Preparing | 2022-07-21 | 2023-01-09 | 2022-07-28 |  |  |  |  | 0 | 240981630 | 240981630 | 0 | 4500467832 |  |  |  |  | NEC INDONESIA
T2022012 | 1 | 11 | 01C11G03 | 019 | 70000234 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004391/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-06-30 | 2022-12-26 | Radio IP | KANTOR DIVRE VII | IP RADIO_BALINUSRA |  | SS#1 Upgrade Hardware Bali Nusra |  | 50 | 20 | 0 | Preparing | 2022-07-21 | 2023-01-09 | 2022-07-28 |  |  |  |  | 2002613830 | 243934308 | 2246548138 | 0 | 4500467832 |  |  |  |  | NEC INDONESIA
T2022012 | 1 | 23 | 01C11G03 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004391/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-06-30 | 2022-12-26 | Radio IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#1 Upgrade Hardware Sumalpua |  | 50 | 20 | 0 | Preparing | 2022-07-21 | 2023-01-09 | 2022-07-28 |  |  |  |  | 2462767475 | 303355978 | 2766123453 | 0 | 4500467832 |  |  |  |  | NEC INDONESIA
T2022012 | 1 | 24 | 01C11G03 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004391/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-06-30 | 2022-12-26 | Radio IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#2 Redeploy Sumalpua |  | 50 | 20 | 0 | Preparing | 2022-07-21 | 2023-01-09 | 2022-07-28 |  |  |  |  | 632056739 | 338904476 | 970961215 | 0 | 4500467832 |  |  |  |  | NEC INDONESIA
T2022012 | 1 | 25 | 01C11G03 | 019 | 70000235 | DIGITAL INFRASTRUCTURE DEVELOPMENT | CNOP & OLO DEVELOPMENT | CNOP & OLO ORDER HANDLING CORE TRANS MGT | DIGITAL INFRASTRUCTURE DEVELOPMENT | K.TEL.004391/HK.810/TSC-B0200000/2022 | Surat Pesanan-3 (SP#3) Pengadaan dan Pemasangan Radio IP Backhaul Node-B Telkomsel Platform NEC | 2022-06-30 | 2022-12-26 | Radio IP | KANTOR DIVRE VII | IP RADIO_SULAMPUA |  | SS#3 BHP ISR Sumalpua |  | 50 | 20 | 0 | Preparing | 2022-07-21 | 2023-01-09 | 2022-07-28 |  |  |  |  | 0 | 291842863 | 291842863 | 0 | 4500467832 |  |  |  |  | NEC INDONESIA
G2022123 | 0 | 11 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 Jl. Bilinggata(Dulomo) |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1127/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 29716456 | 5264006 | 34980462 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 18 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL TAMAN BUAH - TALANGO |  | 74 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 800741384 | 191321724 | 992063108 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 20 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL PATTIMURA |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 117377377 | 28813400 | 146190777 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 19 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL JEND SUDIRMAN 105 |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 105434436 | 28950274 | 134384710 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 32 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 DRS ACHMAD NADJAMUDDIN 3 |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 104127275 | 24988316 | 129115591 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 31 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 SELAYAR DULALOWO |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 104334878 | 29495227 | 133830105 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 30 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL JEND POLISI A SUJARWO |  | 72 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 115714344 | 29339540 | 145053884 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 29 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 DONGGALA-HULONTHALANGI |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 130393717 | 33915244 | 164308961 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 28 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 TENILO-KOTA BARAT |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 38803780 | 11491505 | 50295285 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 27 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL BRIGJEN PIOLA ISA |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 80147906 | 19900537 | 100048443 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 26 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL SAMUDRA PASAI |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 163003944 | 40310852 | 203314796 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 25 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL BARITO BULANGO |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 117039977 | 29392453 | 146432430 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 24 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL PASAR MINGGU TINELO |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 145260105 | 38573460 | 183833565 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 23 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 MOUTONG-TILONGKABILA |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 146308220 | 33283529 | 179591749 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 22 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL MANGGA I 54-56 |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 88357526 | 22036296 | 110393822 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 21 | 01E07V01 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL PT3 JL DURIAN |  | 67 | 0 | 0 | Preparing | 2022-07-01 | 2022-08-31 | [5 empty] | 95568837 | 26494439 | 122063276 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 16 | 01E07V01 | 007 | 72020018 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | ISIMU |  | R7 GTO ISM PT3 Desa Tabongo-Dulupi |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1124/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 13729761 | 4011229 | 17740990 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 13 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT3 ODC-MRS-FAA |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1125/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 90824654 | 26823627 | 117648281 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 12 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT3 ODC-MRS-FAP (LEMITO) |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1123/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 28678653 | 7700401 | 36379054 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 15 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT3 ODC-MRS-FAN |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1129/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 10039642 | 2605246 | 12644888 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 14 | 01E07V01 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | MARISA |  | R7 GTO MRS PT3 PATUHU-RANDANGAN |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1126/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 211111847 | 52585023 | 263696870 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022123 | 0 | 17 | 01E07V01 | 007 | 72020038 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004399/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 22 LOP Area Witel Gorontalo | 2022-07-01 | 2022-09-28 | OSP FO FTTH PT3 2022 | GORONTALO | TELAGA |  | R7 GTO TLG PT3 Bulila |  | 67 | 90 | 0 | Siap UT | 2022-07-01 | 2022-08-31 | 2022-07-01 | TEL.1128/LG.310/DR7-12700000/2022 | 2022-08-12 |  |  | 33122493 | 6372359 | 39494852 | 0 | 4500468494 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 34 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 MOROSI INDAH PERMAI |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 87218800 | 14743888 | 101962688 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 35 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 JETTY MOROSI |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 637011033 | 137463245 | 774474278 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 36 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 JL. PATTIMURA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 238951763 | 52484505 | 291436268 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 22 | 01E07V01 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KOLAKA |  | R7 KDI KKA PT3 JL. MEKONGGA INDAH BYPASS |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 204383690 | 58243836 | 262627526 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 19 | 01E07V01 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KOLAKA |  | R7 KDI KKA PT3 JL. PAHLAWAN KOLAKA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 114139518 | 25084941 | 139224459 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 20 | 01E07V01 | 007 | 72050030 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KOLAKA |  | R7 KDI KKA PT3 JL. PRAMUKA KOLAKA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 80335921 | 17381039 | 97716960 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 25 | 01E07V01 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | LASUSUA |  | R7 KDI LSS PT3 RANTELIMBONG |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 301622966 | 52075599 | 353698565 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 29 | 01E07V01 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | LASUSUA |  | R7 KDI LSS PT3 DESA MALAMALA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 278423827 | 51164057 | 329587884 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 28 | 01E07V01 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | LASUSUA |  | R7 KDI LSS PT3 BTN GRIYA ELEGANT 2 |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 54185454 | 8929425 | 63114879 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 26 | 01E07V01 | 007 | 72050041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | LASUSUA |  | R7 KDI LSS PT3 PERDA LASUSUA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 11629621 | 2860085 | 14489706 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 33 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 SP2 JHONLIN |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 468524388 | 80098029 | 548622417 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 12 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 DESA RAROWATU UTARA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 490933870 | 85977556 | 576911426 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 11 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 MARGAHAYU POASIA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 104416952 | 20651242 | 125068194 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 32 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 RPH KENDARI FBF |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 172772959 | 30795841 | 203568800 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 24 | 01E07V01 | 007 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | POMALAA |  | R7 KDI PMA PT3 GREEN VILLE (HUKOHUKO) |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 89511789 | 19096490 | 108608279 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 23 | 01E07V01 | 007 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | POMALAA |  | R7 KDI PMA PT3 TOTOBO 1 |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 118345892 | 22194370 | 140540262 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 30 | 01E07V01 | 007 | 72050050 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | POMALAA |  | R7 KDI PMA PT3 DESA PUULEMO |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 211823769 | 41473731 | 253297500 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 15 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 POROS JEND SUDIRMAN FC |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 40068797 | 7721898 | 47790695 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 16 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 ANGGOPIU |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 12466210 | 3121953 | 15588163 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 27 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 POROS RATERATE LILINGATO |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 261722544 | 55538202 | 317260746 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 17 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 PUUWONUA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 80826594 | 15174173 | 96000767 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 14 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 POROS JEND SUDIRMAN FZ |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 313121249 | 65432134 | 378553383 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 13 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 POROS JEND SUDIRMAN |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 419031007 | 95811410 | 514842417 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 31 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 POROS GERBANG KOTA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 80346684 | 20548761 | 100895445 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022124 | 0 | 18 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004432/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 25 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 POROS JEND SUDIRMAN FL |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 11919682 | 2733068 | 14652750 | 0 | 4500468602 |  |  |  |  | TELKOM AKSES
G2022125 | 0 | 7 | 01E07V01 | 007 | 72040159 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004441/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan OSP FTTH Batch-2 1 LoP Area Witel Sulselbar | 2022-07-05 | 2022-09-02 | OSP FO FTTH PT3 2022 | PARE-PARE | SIDENRENG RAPPANG |  | R7 PRE SID PT3 NEW DS ODC-SID-FAS |  | 50 |  | 0 |  | 2022-07-05 | 2022-08-27 | [5 empty] | 701190799 | 144044902 | 845235701 | 0 | 4500468853 |  |  |  |  | EKSPANINDO PRIMA MULTIMEDIA
G2022126 | 0 | 18 | 01E07V01 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | DOBO |  | R7 AMB DOB PT3 KANTOR SEKRETARIAT RAPI |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 118617137 | 28535053 | 147152190 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 17 | 01E07V01 | 007 | 73010120 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | DOBO |  | R7 AMB DOB PT3 DESA WANGEL |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 188890332 | 43055904 | 231946236 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 13 | 01E07V01 | 007 | 73010046 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | NAMLEA |  | R7 AMB NML PT3 NEW ODC DESA SAWA |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-25 | [5 empty] | 831448065 | 172520796 | 1003968861 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 14 | 01E07V01 | 007 | 73010046 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | NAMLEA |  | R7 AMB NML PT3 SMA 1 NAMLEA |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 209885465 | 42514535 | 252400000 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 15 | 01E07V01 | 007 | 73010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | NAMROLE |  | R7 AMB NMR PT3 NEW ODC OKI BARU & OKI LAMA |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 955689873 | 186170597 | 1141860470 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 16 | 01E07V01 | 007 | 73010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | NAMROLE |  | R7 AMB NMR PT3 BANDARA UDARA NAMROLE |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 218534599 | 47656541 | 266191140 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 19 | 01E07V01 | 007 | 73010052 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | NAMROLE |  | R7 AMB NMR PT3 SWALAYAN GREEN NAMROLE |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 207373037 | 48048219 | 255421256 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 12 | 01E07V01 | 007 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | SAUMLAKI |  | R7 AMB SML PT3 BTN BOMAKI |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 395788221 | 76396984 | 472185205 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022126 | 0 | 11 | 01E07V01 | 007 | 73010103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004442/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 9 LOP Area Witel Maluku | 2022-07-05 | 2022-10-02 | OSP FO FTTH PT3 2022 | AMBON | SAUMLAKI |  | R7 AMB SML PT3 KANTOR RRI SAUMLAKI |  | 20 |  | 0 |  | 2022-07-05 | 2022-10-02 | [5 empty] | 501240967 | 108726129 | 609967096 | 0 | 4500468895 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 14 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | BIAK |  | R7 SON BIA PT3 GKI EDEN MANSOBEN SUPIORI |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 447229586 | 106614472 | 553844058 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 13 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | BIAK |  | R7 SON BIA PT3 SORIDO |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 118549543 | 30367388 | 148916931 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 12 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | BIAK |  | R7 SON BIA PT3 PASAR BOSNIK |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 162461082 | 59929761 | 222390843 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 10 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | BIAK |  | R7 SON BIA PT3 JL SISINGAMANGARAJA |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 256236296 | 62086562 | 318322858 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 15 | 01E07V01 | 007 | 74060035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | BIAK |  | R7 SON BIA PT3 WARYESI SUPIORI |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 197158361 | 41485279 | 238643640 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 16 | 01E07V01 | 007 | 74060039 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | MANOKWARI |  | R7 SON MWR PT3 SOGUN & MAKO BRIMOB |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 328692965 | 95704027 | 424396992 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 17 | 01E07V01 | 007 | 74060039 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | MANOKWARI |  | R7 SON MWR PT3 PERUM ARFAI INDAH PERMAI |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 140296359 | 36105239 | 176401598 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022127 | 0 | 11 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004443/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 8 LOP Area Witel Papua Barat | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 JL. WAIGEO |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 132354066 | 34184526 | 166538592 | 0 | 4500468884 |  |  |  |  | TRANSDATA SATKOMINDO
G2022128 | 2 | 21 | 01E07V01 | 007 | 74020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | FAKFAK |  | R7 SON FFA PT3 Jl. Kihajar Dewantara |  | 0 | 0 | 0 | Preparing | [7 empty] | 153204903 | 45501696 | 198706599 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 20 | 01E07V01 | 007 | 74020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | FAKFAK |  | R7 SON FFA PT3 Jl. MT Haryono |  | 0 | 0 | 0 | Preparing | [7 empty] | 173139469 | 47731746 | 220871215 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 9 | 01E07V01 | 007 | 74020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | FAKFAK |  | R7 SON FFA PT3 JL IMAM BONJOL |  | 0 | 0 | 0 | Preparing | [7 empty] | 212207542 | 59509862 | 271717404 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 22 | 01E07V01 | 007 | 74020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | FAKFAK |  | R7 SON FFA PT3 CAFE GALAXI |  | 0 | 0 | 0 | Preparing | [7 empty] | 106255874 | 31823716 | 138079590 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 23 | 01E07V01 | 007 | 74020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | FAKFAK |  | R7 SON FFA PT3 Kompleks Perumahan PU |  | 0 | 0 | 0 | Preparing | [7 empty] | 94009282 | 29701466 | 123710748 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 14 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN PT3 BANDARA |  | 0 | 0 | 0 | Preparing | [7 empty] | 223387256 | 63619431 | 287006687 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 24 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN PT3 Kompleks Kantor UPTD KKPD |  | 0 | 0 | 0 | Preparing | [7 empty] | 148078322 | 42296341 | 190374663 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 26 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN PT3 Jl. Utarom Kaimana 2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 143535165 | 37620539 | 181155704 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 27 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN PT3 Jl. Pedesaan Kaimana |  | 0 | 0 | 0 | Preparing | [7 empty] | 240689458 | 66966131 | 307655589 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 44 | 01E07V01 | 007 | 74020007 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | FAK-FAK | KAIMANA |  | R7 SON KIN PT3 Jl. Utarom Kaimana 1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 461619197 | 135208847 | 596828044 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 43 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 SP4 Bintuni 01 |  | 0 | 0 | 0 | Preparing | [7 empty] | 255629412 | 78440859 | 334070271 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 17 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 Taman Kota Bintuni |  | 0 | 0 | 0 | Preparing | [7 empty] | 137648329 | 34176074 | 171824403 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 12 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 JL RAYA KALI TUBI SP 4 |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-30 | [5 empty] | 84462113 | 27262559 | 111724672 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 18 | 01E07V01 | 007 | 74040002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT3 VERSAN NET |  | 0 | 0 | 0 | Preparing | [7 empty] | 63054879 | 18103645 | 81158524 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 46 | 01E07V01 | 007 | 74040016 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | MANOKWARI | WARMARE |  | R7 SON WMMR PT3 SP 2 Warmare |  | 0 | 0 | 0 | Preparing | [7 empty] | 382325681 | 110680952 | 493006633 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 30 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | NABIRE |  | R7 SON NAB PT3 JL JAYAPURA |  | 0 | 0 | 0 | Preparing | [7 empty] | 446601444 | 99622944 | 546224388 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 29 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | NABIRE |  | R7 SON NAB PT3 KALIBUMI |  | 0 | 0 | 0 | Preparing | [7 empty] | 413165553 | 91741679 | 504907232 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 28 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | NABIRE |  | R7 SON NAB PT3 WANGGAR |  | 0 | 0 | 0 | Preparing | [7 empty] | 439195497 | 93377610 | 532573107 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 15 | 01E07V01 | 007 | 74060040 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | NABIRE |  | R7 SON NAB PT3 KPR POLISI |  | 0 | 0 | 0 | Preparing | [7 empty] | 354371429 | 78761082 | 433132511 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 45 | 01E07V01 | 007 | 74060049 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | RAJA AMPAT |  | R7 SON RJA PT3 KANTOR STO RAJAAMPAT |  | 0 | 0 | 0 | Preparing | [7 empty] | 148974573 | 48113640 | 197088213 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 35 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 Jembatan Puri Perikanan |  | 35 | 100 | 100 | BAST-1 | 2022-07-05 | 2022-09-30 | 2022-07-05 | TEL.1168/LG.310/DR7-12700000/2022 | 2022-08-01 | TEL.0126/LG.320/DR7-10400000/2022 | 2022-08-02 | 33006967 | 10378269 | 43385236 | 43385236 | 4500468860 |  |  |  |  | TELKOM AKSES | 2022-08-08
G2022128 | 2 | 36 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 Pelabuhan Rakyat |  | 20 | 100 | 100 | BAST-1 | 2022-07-05 | 2022-09-30 | 2022-07-05 | TEL.1169/LG.310/DR7-12700000/2022 | 2022-08-02 | TEL.0126/LG.320/DR7-10400000/2022 | 2022-08-02 | 45450765 | 13711267 | 59162032 | 59162032 | 4500468860 |  |  |  |  | TELKOM AKSES | 2022-08-08
G2022128 | 2 | 11 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 ODC-SON-FUA JL TERONG |  | 0 | 0 | 0 | Preparing | [7 empty] | 188732677 | 39896439 | 228629116 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 37 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 RUFEI SORONG |  | 0 | 0 | 0 | Preparing | [7 empty] | 349053755 | 99612651 | 448666406 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 39 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 Wihara |  | 0 | 0 | 0 | Preparing | [7 empty] | 61554304 | 18611716 | 80166020 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 38 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 Kantor BMKG |  | 0 | 0 | 0 | Preparing | [7 empty] | 41787202 | 13904754 | 55691956 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 31 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 KM.9 |  | 0 | 0 | 0 | Preparing | [7 empty] | 394376122 | 102478034 | 496854156 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 34 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 PUTRA RECEIDENT MALIBELA |  | 0 | 0 | 0 | Preparing | [7 empty] | 92837085 | 26463828 | 119300913 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 33 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 PERUM KADAR MALIBELA |  | 0 | 0 | 0 | Preparing | [7 empty] | 88041129 | 25259313 | 113300442 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022128 | 2 | 32 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 JL JENDRAL SUDIRMAN |  | 20 | 100 | 100 | BAST-1 | 2022-07-05 | 2022-08-31 | 2022-07-05 | TEL.1167/LG.310/DR7-12700000/2022 | 2022-08-01 | TEL.0126/LG.320/DR7-10400000/2022 | 2022-08-02 | 63924645 | 19302361 | 83227006 | 83227006 | 4500468860 |  |  |  |  | TELKOM AKSES | 2022-08-08
G2022128 | 2 | 40 | 01E07V01 | 007 | 74060025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004444/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 31 LOP Area Witel Papua Barat | 2022-07-05 | 2022-11-01 | OSP FO FTTH PT3 2022 | SORONG | SORONG |  | R7 SON SON PT3 MASJID AL HIJRAH |  | 0 | 0 | 0 | Preparing | [7 empty] | 118260624 | 32135578 | 150396202 | 0 | 4500468860 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 11 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 JL GAJAH MADA BUSEL |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 419775804 | 112342120 | 532117924 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 14 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 MAWASANGKA TENGAH |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 334476337 | 79559736 | 414036073 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 19 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 BATAUGA |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 74145672 | 17399061 | 91544733 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 20 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 BTN CECERIA |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 36544742 | 6335518 | 42880260 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 24 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 PERUMAHAN TOPAZ 3 |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 161986022 | 30250671 | 192236693 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 25 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 ODC-BBU-FJ |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 30216172 | 5990404 | 36206576 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 26 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 JL. RAYA ROMBO EREKE |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 163540850 | 31184133 | 194724983 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 28 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 BTN GRIYA |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 46947791 | 10126347 | 57074138 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 29 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 BTN SRI AMALIA |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 25190406 | 4744573 | 29934979 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 15 | 01E07V01 | 007 | 72050009 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | BAU-BAU |  | R7 KDI BBU PT3 STO PASARWAJO |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 219630884 | 63733840 | 283364724 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 16 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 PURIRANO |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 300833826 | 73523019 | 374356845 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 13 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 AFIKA RESIDENCE TAHAP 2 |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 272158737 | 76914135 | 349072872 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 12 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 MANGGA DUA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-22 | [5 empty] | 371844246 | 98890170 | 470734416 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 18 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 GRAND ANDIKA 6&PRADANA 7 |  | 0 | 0 | 0 | Preparing | [7 empty] | 95968935 | 19836909 | 115805844 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 23 | 01E07V01 | 007 | 72050025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | KENDARI |  | R7 KDI KDR PT3 OSEMETUNDU B |  | 0 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-17 | [5 empty] | 282003052 | 59290472 | 341293524 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 31 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 JL. PALANGGA KONSEL |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 227571329 | 47702705 | 275274034 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 27 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 PERUMAHAN SWARNA DWIPA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 79774903 | 14664919 | 94439822 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 21 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 AMBAIPUA KONSEL |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 367673138 | 69889566 | 437562704 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 22 | 01E07V01 | 007 | 72050093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | MANDONGA |  | R7 KDI MDG PT3 ANAWAI & TUNGGALA DALAM |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 605467997 | 122732435 | 728200432 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022129 | 0 | 32 | 01E07V01 | 007 | 72050072 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004445/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 20 LOP Area Witel Sultra | 2022-07-05 | 2022-10-12 | OSP FO FTTH PT3 2022 | KENDARI | UNAAHA |  | R7 KDI UNH PT3 ANDOWIA |  | 100 | 0 | 0 | Preparing | 2022-07-05 | 2022-07-18 | [5 empty] | 249718927 | 54414616 | 304133543 | 0 | 4500468858 |  |  |  |  | TELKOM AKSES
G2022130 | 0 | 19 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 BATU LIKUPANG |  | 75 |  | 0 |  | 2022-07-05 | 2022-09-14 | [5 empty] | 157265586 | 30641350 | 187906936 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022130 | 0 | 17 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 TABANG |  | 70 |  | 0 |  | 2022-07-05 | 2022-09-15 | [5 empty] | 133454809 | 27699429 | 161154238 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022130 | 0 | 14 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 PUSAT MELONGUANE |  | 70 |  | 0 |  | 2022-07-05 | 2022-09-15 | [5 empty] | 192857257 | 44180469 | 237037726 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022130 | 0 | 16 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 KODIM TALAUD |  | 80 |  | 0 |  | 2022-07-05 | 2022-09-15 | [5 empty] | 40851487 | 7185251 | 48036738 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022130 | 0 | 15 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 RAINIS TALAUD |  | 65 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 478511467 | 92052538 | 570564005 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022130 | 0 | 11 | 01E07V01 | 007 | 72010064 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | MANADO BAHU |  | R7 MDO BAH PT3 MINANGA 2 |  | 75 |  | 0 |  | 2022-07-05 | 2022-09-09 | [5 empty] | 129127458 | 30978561 | 160106019 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022130 | 0 | 10 | 01E07V01 | 007 | 72010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004446/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 7 LOP Area Witel Sulut Malut | 2022-07-05 | 2022-09-17 | OSP FO FTTH PT3 2022 | MANADO | TAHUNA |  | R7 MDO THN PT3 TAHUNA PANTAI |  | 20 |  | 0 |  | 2022-07-05 | 2022-09-17 | [5 empty] | 278551600 | 54827981 | 333379581 | 0 | 4500468857 |  |  |  |  | TRANSDATA SATKOMINDO
G2022131 | 2 | 28 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 JLN BARU THR |  | 95 | 100 | 100 | BAST-1 | 2022-07-07 | 2022-08-02 | 2022-07-06 | TEL.1093/LG.310/DR7-12700000/2025 | 2022-07-26 | TEL.0121/LG.320/DR7-10400000/2022 | 2022-07-27 | 34175461 | 6341137 | 40516598 | 40516598 | 4500469049 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022131 | 2 | 23 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 ODC-ABO-FAR GALUNGGUNG |  | 95 | 100 | 100 | BAST-1 | 2022-07-07 | 2022-08-02 | 2022-07-06 | TEL.1092/LG.310/DR7-12700000/2024 | 2022-07-26 | TEL.0121/LG.320/DR7-10400000/2022 | 2022-07-27 | 55557491 | 14540777 | 70098268 | 70098268 | 4500469049 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022131 | 2 | 20 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 SERI |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 548511999 | 117052508 | 665564507 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 14 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 ABO PT3 NEW ODC AMAHUSU |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 178742722 | 59109920 | 237852642 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 16 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 PERUMAHAN AIRMAR |  | 95 | 100 | 100 | BAST-1 | 2022-07-07 | 2022-08-02 | 2022-07-06 | TEL.1091/LG.310/DR7-12700000/2023 | 2022-07-26 | TEL.0121/LG.320/DR7-10400000/2022 | 2022-07-27 | 114581232 | 30031135 | 144612367 | 144612367 | 4500469049 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022131 | 2 | 17 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 KAPAHA |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 77579845 | 20212149 | 97791994 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 22 | 01E07V01 | 007 | 73010104 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | AMBON |  | R7 AMB ABO PT3 FARMASI ATAS |  | 90 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 164371439 | 37886583 | 202258022 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 24 | 01E07V01 | 007 | 73010013 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | BULA |  | R7 AMB BUL PT3 TERMINAL PASAR BULA |  | 93 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 134398098 | 29390886 | 163788984 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 25 | 01E07V01 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | MASOHI |  | R7 AMB MSH PT3 KAIRATU |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 640527200 | 130312919 | 770840119 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 27 | 01E07V01 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | MASOHI |  | R7 AMB MSH PT3 KAMPUS SAID PERINTAH |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 108426447 | 26654113 | 135080560 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 30 | 01E07V01 | 007 | 73010042 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | MASOHI |  | R7 AMB MSH PT3 KANTOR PENGADILAN |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 16435800 | 3576601 | 20012401 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 8 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 TRANSIT PASSO |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 237349936 | 48875241 | 286225177 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 10 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 PERUMAHAN LATERI INDAH |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 341772411 | 90712322 | 432484733 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 12 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 WAYAME |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 492668906 | 141486004 | 634154910 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 31 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 HATU |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 115275591 | 28497412 | 143773003 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 15 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 INA KAKA |  | 93 | 100 | 100 | BAST-1 | 2022-07-07 | 2022-08-02 | 2022-07-06 | TEL.1090/LG.310/DR7-12700000/2022 | 2022-07-27 | TEL.0121/LG.320/DR7-10400000/2022 | 2022-07-27 | 125232230 | 27525757 | 152757987 | 152757987 | 4500469049 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022131 | 2 | 29 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 HALONG BARU |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 90142677 | 16983314 | 107125991 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 19 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 HALONG ATAS |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 228079935 | 55643998 | 283723933 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 18 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 PERUM TENTARA WAIHERU |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 82202931 | 19546420 | 101749351 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 32 | 01E07V01 | 007 | 73010057 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PASSO |  | R7 AMB PAO PT3 BATU GONG |  | 95 | 100 | 100 | BAST-1 | 2022-07-07 | 2022-08-02 | 2022-07-06 | TEL.1094/LG.310/DR7-12700000/2026 | 2022-07-27 | TEL.0121/LG.320/DR7-10400000/2022 | 2022-07-27 | 30491952 | 5525913 | 36017865 | 36017865 | 4500469049 |  |  |  |  | TELKOM AKSES | 2022-07-29
G2022131 | 2 | 11 | 01E07V01 | 007 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PIRU |  | R7 AMB PIR PT3 KANTOR BUPATI SBB |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 759683607 | 185033250 | 944716857 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 13 | 01E07V01 | 007 | 73010059 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | PIRU |  | R7 AMB PIR PT3 WAESALA |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 332435995 | 81325722 | 413761717 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 21 | 01E07V01 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | TUAL |  | R7 AMB TUA PT3 BTN MAHKOTA |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 46427547 | 13126374 | 59553921 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022131 | 2 | 26 | 01E07V01 | 007 | 73010119 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004462/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 24 LOP Area Witel Maluku | 2022-07-06 | 2022-10-13 | OSP FO FTTH PT3 2022 | AMBON | TUAL |  | R7 AMB TUA PT3 PERUM EVAV RESIDENCE |  | 95 | 0 | 0 | Preparing | 2022-07-07 | 2022-08-02 | [5 empty] | 81626626 | 18495199 | 100121825 | 0 | 4500469049 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 8 | 01E07O02 | 007 | 72030124 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | BUNTA |  | R7 PAL BUT OLO BAKTI POI BUNTA |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 5938843 | 2916276 | 8855119 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 14 | 01E07O02 | 007 | 72030013 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | BUOL |  | R7 PAL BUO OLO BAKTI POI BUOL |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 5938843 | 2916276 | 8855119 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 16 | 01E07O02 | 007 | 72030017 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | DONGGALA |  | R7 PAL DGL OLO BAKTI POI DONGGALA |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 3814545 | 2321776 | 6136321 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 12 | 01E07O02 | 007 | 72030099 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | KOTARAYA |  | R7 PAL KOR OLO BAKTI POI KOTARAYA |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 4876694 | 2619026 | 7495720 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 10 | 01E07O02 | 007 | 72030050 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | MOUTONG |  | R7 PAL MOT OLO BAKTI POI MOUTONG |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 3814545 | 2321776 | 6136321 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 15 | 01E07O02 | 007 | 72030092 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | PALU B |  | R7 PAL PLB OLO BAKTI POI PALU B |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 3814545 | 2321776 | 6136321 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 13 | 01E07O02 | 007 | 72030061 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | PARIGI |  | R7 PAL PGI OLO BAKTI POI PARIGI |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 5772132 | 2908186 | 8680318 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 9 | 01E07O02 | 007 | 72030081 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | TINOMBO |  | R7 PAL TNB OLO BAKTI POI TINOMBO |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 5938843 | 2916276 | 8855119 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022132 | 0 | 11 | 01E07O02 | 007 | 72030084 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004528/HK.810/R7W-7C1H0000/2022 | LASTMILE OLO JUNI 2022 9 LOP WITEL SULTENG | 2022-07-08 | 2022-09-05 | OLO | PALU | TOLI-TOLI |  | R7 PAL TLI OLO BAKTI POI TOLI-TOLI |  | 100 | 0 | 0 | Preparing | 2022-07-08 | 2022-07-17 | [5 empty] | 4364669 | 2491801 | 6856470 | 0 | 4500469636 |  |  |  |  | TELKOM AKSES
G2022133 | 0 | 7 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004542/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-2 Lokasi Bontomarannu Area Witel Makassar | 2022-07-08 | 2022-08-21 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT3 BONTOMARANU |  | 60 |  | 0 |  | 2022-07-08 | 2022-08-21 | [5 empty] | 539506643 | 94506807 | 634013450 | 0 | 4500469594 |  |  |  |  | MANDOR KAWAT
G2022134 | 0 | 6 | 01E07V01 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004543/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 1 LoP Area Witel Makassar | 2022-07-08 | 2022-08-21 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT3 NUANSA INDAH RESIDENCE |  | 66 | 82 | 0 | Instalasi | 2022-07-08 | 2022-08-21 | 2022-07-15 |  |  |  |  | 63447024 | 14277058 | 77724082 | 0 | 4500469541 |  |  |  |  | BAGAMAS PRIMA TEKNIK
G2022135 | 0 | 6 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004544/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 3 LOP Area Witel Sulut Malut | 2022-07-08 | 2022-09-05 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 WEROT |  | 50 | 0 | 0 | Preparing | 2022-07-08 | 2022-09-05 | [5 empty] | 51789393 | 11466191 | 63255584 | 0 | 4500469539 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022135 | 0 | 7 | 01E07V01 | 007 | 72010045 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004544/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 3 LOP Area Witel Sulut Malut | 2022-07-08 | 2022-09-05 | OSP FO FTTH PT3 2022 | MANADO | KAUDITAN |  | R7 MDO KAU PT3 PRM CITRA KAUDITAN PERMAI |  | 50 | 0 | 0 | Preparing | 2022-07-08 | 2022-09-05 | [5 empty] | 27628224 | 5052917 | 32681141 | 0 | 4500469539 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022135 | 0 | 9 | 01E07V01 | 007 | 72010127 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004544/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 3 LOP Area Witel Sulut Malut | 2022-07-08 | 2022-09-05 | OSP FO FTTH PT3 2022 | MANADO | LANGOWAN |  | R7 MDO LAN PT3 TARERAN |  | 50 | 0 | 0 | Preparing | 2022-07-08 | 2022-09-05 | [5 empty] | 213874815 | 55031067 | 268905882 | 0 | 4500469539 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022136 | 0 | 9 | 01E07V01 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004545/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-2 1 LoP Area Witel Makassar | 2022-07-08 | 2022-08-21 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT3 ODC-SUD-FAT |  | 70 | 0 | 0 | Preparing | 2022-07-08 | 2022-08-19 | [5 empty] | 237936069 | 45207572 | 283143641 | 0 | 4500469543 |  |  |  |  | LAMUNA INDOTIMUR
G2022137 | 0 | 19 | 01E07P02 | 007 | 72040275 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | AJANGALE |  | R7 PRE AJN PT2 MEI 2022 |  | 85 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-16 | [5 empty] | 3431982 | 479176 | 3911158 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 20 | 01E07P02 | 007 | 72040044 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | CANGADI |  | R7 PRE CGI PT2 MEI 2022 |  | 85 | 0 | 0 | Preparing | 2022-08-01 | 2022-08-16 | [5 empty] | 2278231 | 299507 | 2577738 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 9 | 01E07P02 | 007 | 72040049 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | ENREKANG |  | R7 PRE ENR PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3431982 | 479176 | 3911158 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 14 | 01E07P02 | 007 | 72040078 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | MAJENE |  | R7 PRE MAJ PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3431982 | 479176 | 3911158 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 13 | 01E07P02 | 007 | 72040086 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | MAMASA |  | R7 PRE MMS PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3431982 | 479176 | 3911158 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 15 | 01E07P02 | 007 | 72040088 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | MAMUJU |  | R7 PRE MAM PT2 MEI 2022 22 |  | 0 | 0 | 0 | Preparing | [7 empty] | 13220141 | 3198165 | 16418306 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 16 | 01E07P02 | 007 | 72040109 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | PALOPO |  | R7 PRE PLP PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5680468 | 770723 | 6451191 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 11 | 01E07P02 | 007 | 72040117 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | PARE-PARE |  | R7 PRE PRE PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5147973 | 780987 | 5928960 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 12 | 01E07P02 | 007 | 72040119 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | PASANG KAYU |  | R7 PRE PKA PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 4478727 | 979607 | 5458334 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 10 | 01E07P02 | 007 | 72040128 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | PINRANG |  | R7 PRE PIN PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 10172576 | 1866053 | 12038629 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 18 | 01E07P02 | 007 | 72040194 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | SENGKANG |  | R7 PRE SKG PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3431982 | 479176 | 3911158 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 8 | 01E07P02 | 007 | 72040158 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | SIDRAP |  | R7 PRE SID PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 7396459 | 1010311 | 8406770 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 17 | 01E07P02 | 007 | 72040160 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | SIWA |  | R7 PRE SIW PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 87467454 | 21956750 | 109424204 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022137 | 0 | 21 | 01E07P02 | 007 | 72040186 | TELKOM REGIONAL VII | WITEL SULSEL BARAT (PARE PARE) | OPTIMA & DAMAN | TELKOM REGIONAL VII | K.TEL.004546/HK.810/R7W-7D100000/2022 | Pengadaan Pekerjaan PT2 Tahap-5 14 LOP Tahun 2022 Area Witel Sulselbar | 2022-07-09 | 2022-08-22 | OSP FO FTTH PT2 2022 | PARE-PARE | WATANSOPPENG |  | R7 PRE WTG PT2 MEI 2022 |  | 0 | 0 | 0 | Preparing | [7 empty] | 3431982 | 479176 | 3911158 | 0 | 4500469698 |  |  |  |  | TELKOM AKSES
G2022138 | 0 | 14 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | SENTANI |  | R7 JAP SNI JAP256 TBG Gunung Sentani |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 32203867 | 11457191 | 43661058 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 13 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | SENTANI |  | R7 JAP SNI JAP489 Mcr Btn Palomo Grand |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 15909920 | 6179035 | 22088955 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 15 | 01E07L12 | 007 | 74030063 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | SENTANI |  | R7 JAP SNI JAP634 Kwadeware |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 31868232 | 9726999 | 41595231 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 8 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JAP TIM TIM148 TBG KAMORO JAYA |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 246786203 | 66804036 | 313590239 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 9 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JAP TIM TIM323 TIM323 |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 391405219 | 114768675 | 506173894 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 7 | 01E07L12 | 007 | 74030068 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | TIMIKA |  | R7 JAP TIM TIM165 TBG Pisang Pasar Sentral |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 178555253 | 44819846 | 223375099 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 12 | 01E07L12 | 007 | 74030072 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | JAYAPURA | WAENA |  | R7 JAP WAE JAP638 UNCEN |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 19250846 | 6147703 | 25398549 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 11 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | R7 JAP MRK MRK140 Dmt waning gap |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 17476712 | 4456066 | 21932778 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022138 | 0 | 10 | 01E07L12 | 007 | 74050012 | TELKOM REGIONAL VII | WITEL PAPUA (JAYAPURA) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004547/HK.810/R7W-7B100000/2022 | Pengadaan Pekerjaan FIMO Node B 9 LoP Area Witel Papua | 2022-07-11 | 2022-09-08 | FIMO NODE-B 2022 | MERAUKE | MERAUKE |  | R7 JAP MRK MRK125 TBG KAMUNDU TBG KAMUNDU |  | 20 |  | 0 |  | 2022-07-11 | 2022-09-08 | [5 empty] | 20070614 | 4792984 | 24863598 | 0 | 4500469759 |  |  |  |  | TRANSDATA SATKOMINDO
G2022139 | 0 | 7 | 01E07O02 | 007 | 72030061 | TELKOM REGIONAL VII | WITEL SULTENG (PALU) | ACCESS AREA | TELKOM REGIONAL VII | K.TEL.004554/HK.810/R7W-7C100000/2022 | FIMO NODE B 1 LOP WITEL SULTENG | 2022-07-11 | 2022-08-24 | FIMO NODE-B 2022 | PALU | PARIGI |  | R7 PAL PGI PGI176 Siendeng |  | 0 | 0 | 0 | Preparing | [7 empty] | 402342241 | 75417301 | 477759542 | 0 | 4500469772 |  |  |  |  | MITRATAMA ENERGI SELEBES
G2022140 | 0 | 9 | 01E07V01 | 007 | 72080167 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004560/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 Lokasi Laqava Area Witel Makassar | 2022-07-11 | 2022-08-19 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUDIANG |  | R7 MKS SUD PT3 LAQAVA |  | 65 | 0 | 0 | Preparing | 2022-07-11 | 2022-08-19 | [5 empty] | 103931839 | 21756323 | 125688162 | 0 | 4500469884 |  |  |  |  | BAKTI SARANA PRATAMA
G2022141 | 0 | 10 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD FE CITRA REGENCY 2 RAJAWALI1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 108335526 | 33481244 | 141816770 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 12 | 01E07V01 | 007 | 72010045 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | KAUDITAN |  | R7 MDO KAU FE TANJUNG MERAH_1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 308209369 | 78949111 | 387158480 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 32 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN FE WATULANEY KAYUROYA_1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 556634873 | 535227726 | 1091862599 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 13 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN FE TANGARI TONDANO_1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 442730085 | 110603887 | 553333972 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 19 | 01E07V01 | 007 | 72030012 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | PALU | BUNGKU |  | R7 PAL BKU FE DESA LALAMPU |  | 100 | 0 | 0 | Preparing | 2022-07-11 | 2022-07-28 | [5 empty] | 177364882 | 55578935 | 232943817 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 20 | 01E07V01 | 007 | 72030102 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | PALU | LUWUK |  | R7 PAL LWU FE MOILONG |  | 100 | 0 | 0 | Preparing | 2022-07-11 | 2022-07-28 | [5 empty] | 785752062 | 133569764 | 919321826 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 17 | 01E07V01 | 007 | 72030103 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | PALU | PALU A |  | R7 PAL PLA FE UNTAD I BUMI ROVIGA 2 |  | 100 | 0 | 0 | Preparing | 2022-07-11 | 2022-07-28 | [5 empty] | 697901404 | 462962434 | 1160863838 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 24 | 01E07V01 | 007 | 72040197 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | PARE-PARE | MAKALE |  | R7 PRE MAK FE MAKALE UTARA |  | 100 | 0 | 0 | Preparing | 2022-07-11 | 2022-07-30 | [5 empty] | 664866417 | 139658752 | 804525169 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 23 | 01E07V01 | 007 | 72040133 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | PARE-PARE | RANTEPAO |  | R7 PRE RTP FE SADAN |  | 100 | 0 | 0 | Preparing | 2022-07-11 | 2022-07-30 | [5 empty] | 366631111 | 103140188 | 469771299 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022141 | 0 | 15 | 01E07V01 | 007 | 72080115 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004561/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan Feeder Branching Batch 2 Tahun 2022 Witel Sulteng, Sulutmalut, Makassar dan Sulselbar | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SINJAI |  | R7 MKS SIN FE SINJAI INNER 1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 181877243 | 122482791 | 304360034 | 0 | 4500469883 |  |  |  |  | TELKOM AKSES
G2022142 | 0 | 9 | 01E07V01 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004562/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FTTH Batch-2 Lokasi Pannampu Area Witel Makassar | 2022-07-11 | 2022-08-24 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT3 PANNAMPU |  | 95 | 50 | 0 | Mat. Delivery | 2022-07-11 | 2022-08-15 | 2022-07-11 |  |  |  |  | 82420844 | 20416655 | 102837499 | 0 | 4500469785 |  |  |  |  | KOPKAR SIPORENNU
G2022143 | 0 | 40 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 Fellyndri Hedwige Tumbol |  | 0 | 0 | 0 | Preparing | [7 empty] | 8938225 | 1893018 | 10831243 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 26 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 CITRA REGENCY 2 RAJAWALI1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 205049264 | 38220205 | 243269469 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 41 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 Rudi Setiawan |  | 0 | 0 | 0 | Preparing | [7 empty] | 32443947 | 5609816 | 38053763 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 39 | 01E07V01 | 007 | 72010002 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | AIR MADIDI |  | R7 MDO AMD PT3 Ferdynand M Sumalenda |  | 0 | 0 | 0 | Preparing | [7 empty] | 11793470 | 2668199 | 14461669 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 34 | 01E07V01 | 007 | 72010004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | AMURANG |  | R7 MDO AMR PT3 OLGA UMBOH |  | 0 | 0 | 0 | Preparing | [7 empty] | 9297071 | 1826602 | 11123673 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 33 | 01E07V01 | 007 | 72010258 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | BEO |  | R7 MDO BEO PT3 TAROHAN |  | 0 | 0 | 0 | Preparing | [7 empty] | 393475218 | 88318809 | 481794027 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 43 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | BITUNG |  | R7 MDO BIT PT3 SARI KELAPA BITUNG |  | 0 | 0 | 0 | Preparing | [7 empty] | 9197134 | 1765775 | 10962909 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 46 | 01E07V01 | 007 | 72010008 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | BITUNG |  | R7 MDO BIT PT3 DUA SAUDARA |  | 0 | 0 | 0 | Preparing | [7 empty] | 223302879 | 56341794 | 279644673 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 31 | 01E07V01 | 007 | 72010045 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | KAUDITAN |  | R7 MDO KAU PT3 TANJUNG MERAH_1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 300098920 | 56277016 | 356375936 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 36 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 FRILLY VALENCIA |  | 0 | 0 | 0 | Preparing | [7 empty] | 14366238 | 3233644 | 17599882 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 27 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 GRAND MERIDIAN |  | 0 | 0 | 0 | Preparing | [7 empty] | 37234213 | 18148473 | 55382686 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 37 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 Dharsono Nainggolan |  | 0 | 0 | 0 | Preparing | [7 empty] | 10181237 | 2055835 | 12237072 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 35 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 MARCELO ENRIQUE LEVINSON |  | 0 | 0 | 0 | Preparing | [7 empty] | 18860000 | 4649118 | 23509118 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 45 | 01E07V01 | 007 | 72010060 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO |  | R7 MDO MDO PT3 PERUM SAWANGAN PERMAI C |  | 0 | 0 | 0 | Preparing | [7 empty] | 226810638 | 53221675 | 280032313 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 29 | 01E07V01 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH PT3 GOLDEN PEAK |  | 0 | 0 | 0 | Preparing | [7 empty] | 203530556 | 62249006 | 265779562 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 28 | 01E07V01 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH PT3 Glory Hill & Diamond Hill |  | 0 | 0 | 0 | Preparing | [7 empty] | 185434541 | 60721275 | 246155816 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 42 | 01E07V01 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH PT3 Rudy Alexander Pelealu |  | 0 | 0 | 0 | Preparing | [7 empty] | 21917357 | 4679671 | 26597028 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 44 | 01E07V01 | 007 | 72010132 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | MANADO - BAHU |  | R7 MDO BAH PT3 PERUM SAWANGAN PERMAI B |  | 0 | 0 | 0 | Preparing | [7 empty] | 171805762 | 45618408 | 217424170 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 30 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 PURI MANADO PERMAI |  | 0 | 0 | 0 | Preparing | [7 empty] | 96834661 | 17925931 | 114760592 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 38 | 01E07V01 | 007 | 72010083 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | PANIKI |  | R7 MDO PIK PT3 Roland Muhammad |  | 0 | 0 | 0 | Preparing | [7 empty] | 9423316 | 1824416 | 11247732 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 24 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 TONSARU_2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 463930955 | 84773488 | 548704443 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 25 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 WATULANEY KAYUROYA_1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 227709383 | 47854510 | 275563893 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 32 | 01E07V01 | 007 | 72010112 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | MANADO | TONDANO |  | R7 MDO TDN PT3 TANGARI TONDANO_1 |  | 0 | 0 | 0 | Preparing | [7 empty] | 59754535 | 12942115 | 72696650 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 16 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI PT3 WEDA 2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 434827292 | 83083057 | 517910349 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 15 | 01E07V01 | 007 | 73020035 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | SOFIFI |  | R7 MDO SFI PT3 LELILEF 2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 605090342 | 166260196 | 771350538 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 18 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 TABONA2 |  | 0 | 0 | 0 | Preparing | [7 empty] | 77723569 | 21058799 | 98782368 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 19 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 TANAH TINGGI |  | 0 | 0 | 0 | Preparing | [7 empty] | 153686165 | 34724622 | 188410787 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 17 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 JATI METRO |  | 0 | 0 | 0 | Preparing | [7 empty] | 135975851 | 29985789 | 165961640 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 20 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 GANG KAYU BUA |  | 0 | 0 | 0 | Preparing | [7 empty] | 97237038 | 21566250 | 118803288 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 21 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 GAMAYOU |  | 0 | 0 | 0 | Preparing | [7 empty] | 86979235 | 20715449 | 107694684 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 23 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 MALIARO 9 |  | 0 | 0 | 0 | Preparing | [7 empty] | 18344953 | 3176385 | 21521338 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022143 | 0 | 22 | 01E07V01 | 007 | 73020041 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004563/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 32 LOP Area Witel Sulut Malut | 2022-07-11 | 2022-11-07 | OSP FO FTTH PT3 2022 | TERNATE | TERNATE |  | R7 MDO TNT PT3 MARIKURUBU |  | 0 | 0 | 0 | Preparing | [7 empty] | 31790002 | 5911529 | 37701531 | 0 | 4500469868 |  |  |  |  | TELKOM AKSES
G2022144 | 0 | 8 | 01E07V01 | 007 | 72080091 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004564/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 3 LoP Area Witel Makassar | 2022-07-11 | 2022-09-08 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | PANAKUKANG |  | R7 MKS PNK PT3 GRAHA LESTARI MAKASSAR |  | 70 |  | 0 |  | 2022-07-11 | 2022-09-06 | [5 empty] | 103887337 | 21208849 | 125096186 | 0 | 4500469869 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022144 | 0 | 9 | 01E07V01 | 007 | 72080093 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004564/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 3 LoP Area Witel Makassar | 2022-07-11 | 2022-09-08 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | PANGKEP |  | R7 MKS PKN PT3 PERUMAHAN RISKITA - NAYLA |  | 50 |  | 0 |  | 2022-07-11 | 2022-09-06 | [5 empty] | 280348309 | 54230440 | 334578749 | 0 | 4500469869 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022144 | 0 | 10 | 01E07V01 | 007 | 72080165 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004564/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan OSP FTTH BATCH-2 3 LoP Area Witel Makassar | 2022-07-11 | 2022-09-08 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | SUNGGUMINASA |  | R7 MKS SUG PT3 DESA HIJAU |  | 50 |  | 0 |  | 2022-07-11 | 2022-09-06 | [5 empty] | 59230546 | 14411193 | 73641739 | 0 | 4500469869 |  |  |  |  | CELEBES ANDHIKA PRATAMA
G2022145 | 0 | 43 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 belakang bandara |  | 0 | 0 | 0 | Preparing | [7 empty] | 12650409 | 3600373 | 16250782 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 27 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Jl. Kristina Tiahahu |  | 0 | 0 | 0 | Preparing | [7 empty] | 10865940 | 2641883 | 13507823 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 41 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Gereja katolik St. Fransiskus Xaverius Kiat |  | 0 | 0 | 0 | Preparing | [7 empty] | 19907902 | 6332614 | 26240516 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 42 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Kampung dulanpokpok |  | 0 | 0 | 0 | Preparing | [7 empty] | 60133852 | 17428128 | 77561980 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 39 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 GKI Siloam Danaweria |  | 0 | 0 | 0 | Preparing | [7 empty] | 31649404 | 9082014 | 40731418 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 40 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Jl. Sakartemin |  | 0 | 0 | 0 | Preparing | [7 empty] | 14833865 | 4187174 | 19021039 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 38 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Pasar Togartupin |  | 0 | 0 | 0 | Preparing | [7 empty] | 13963667 | 3961060 | 17924727 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 37 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Jl. JP Matondang |  | 0 | 0 | 0 | Preparing | [7 empty] | 23523842 | 6704405 | 30228247 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 36 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FCA / 044 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5443447 | 1712661 | 7156108 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 35 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FCA / 061 |  | 0 | 0 | 0 | Preparing | [7 empty] | 6473775 | 1587617 | 8061392 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 34 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FCA / 017 |  | 0 | 0 | 0 | Preparing | [7 empty] | 16401862 | 3828447 | 20230309 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 33 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FCA / 006 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1917869 | 461361 | 2379230 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 32 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FCA / 003 |  | 0 | 0 | 0 | Preparing | [7 empty] | 11989451 | 3050547 | 15039998 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 31 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FGA / 067 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1917869 | 461361 | 2379230 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 30 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FGA / 047 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1917869 | 461361 | 2379230 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 29 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 ODP-FFA-FGA / 013 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1917869 | 461361 | 2379230 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 28 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Masjid Al kautsar |  | 0 | 0 | 0 | Preparing | [7 empty] | 58488078 | 16483071 | 74971149 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 44 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA PT2 Bank Papua |  | 0 | 0 | 0 | Preparing | [7 empty] | 19422517 | 5489635 | 24912152 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 20 | 01E07T02 | 007 | 74040002 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | MANOKWARI | BINTUNI |  | R7 SON BTI PT2 Polres Teluk Bintuni |  | 0 | 0 | 0 | Preparing | [7 empty] | 10009498 | 2201061 | 12210559 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 26 | 01E07T02 | 007 | 74040010 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | MANOKWARI | RANSIKI |  | R7 SON RSK PT2 JL MANOWARI-BINTUNI 01 |  | 0 | 0 | 0 | Preparing | [7 empty] | 2493097 | 447625 | 2940722 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 48 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Taman JK |  | 0 | 0 | 0 | Preparing | [7 empty] | 18514736 | 5741831 | 24256567 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 47 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Jl. Pedesaan |  | 0 | 0 | 0 | Preparing | [7 empty] | 32617561 | 9828786 | 42446347 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 46 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Kedai Tembakau |  | 0 | 0 | 0 | Preparing | [7 empty] | 60515954 | 18111137 | 78627091 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 51 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Kios Sarah |  | 0 | 0 | 0 | Preparing | [7 empty] | 37013124 | 10921858 | 47934982 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 52 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 YONIF 756 |  | 0 | 0 | 0 | Preparing | [7 empty] | 18254462 | 5033069 | 23287531 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 49 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Jl. Perumahan DPR |  | 0 | 0 | 0 | Preparing | [7 empty] | 21385659 | 6258451 | 27644110 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 50 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Jl. Batu Putih Krooy |  | 0 | 0 | 0 | Preparing | [7 empty] | 47029088 | 13842822 | 60871910 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 53 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Jl. Lingkar simora |  | 0 | 0 | 0 | Preparing | [7 empty] | 65795886 | 18194058 | 83989944 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 54 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 ODP-KIN-FB/062 |  | 0 | 0 | 0 | Preparing | [7 empty] | 1917869 | 461361 | 2379230 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 55 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 ODP-KIN-FB/063 |  | 0 | 0 | 0 | Preparing | [7 empty] | 5267432 | 1614477 | 6881909 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 56 | 01E07T02 | 007 | 74060078 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | KAIMANA |  | R7 SON KIN PT2 Puncak Sceep45 |  | 0 | 0 | 0 | Preparing | [7 empty] | 16693447 | 3988222 | 20681669 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 15 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 JL ENAROTALI GIRIMULYO |  | 0 | 0 | 0 | Preparing | [7 empty] | 2493097 | 447625 | 2940722 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 14 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. A Gobay Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 33691964 | 7509340 | 41201304 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 13 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. Merdeka Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 25088225 | 5653927 | 30742152 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 12 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. Dr. Sutomo Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 33466863 | 7565075 | 41031938 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 11 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Masjid Nurul Bahri Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 28078787 | 5811207 | 33889994 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 8 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. Poros samabusa |  | 0 | 0 | 0 | Preparing | [7 empty] | 22693132 | 5879362 | 28572494 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 9 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. Dr. Sam Ratulangi |  | 0 | 0 | 0 | Preparing | [7 empty] | 19150669 | 4386618 | 23537287 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 16 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 JL. SAM RATULANGI Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 2493097 | 447625 | 2940722 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 17 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 jl. medan Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 2493097 | 447625 | 2940722 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 18 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. Medy Tonapa Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 27564711 | 6019505 | 33584216 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 19 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Bakso mamak danar Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 25195348 | 6848721 | 32044069 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 10 | 01E07T02 | 007 | 74060040 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | NABIRE |  | R7 SON NAB PT2 Jl. Yan mamoribo Nabire |  | 0 | 0 | 0 | Preparing | [7 empty] | 39209098 | 8966523 | 48175621 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 24 | 01E07T02 | 007 | 74060049 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | RAJA AMPAT |  | R7 SON RJA PT2 DEPAN KANTOR SAMSAT |  | 0 | 0 | 0 | Preparing | [7 empty] | 14451386 | 3467620 | 17919006 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 25 | 01E07T02 | 007 | 74060049 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | RAJA AMPAT |  | R7 SON RJA PT2 KOMP.POLRES RAJA AMPAT |  | 0 | 0 | 0 | Preparing | [7 empty] | 11513202 | 3071435 | 14584637 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 22 | 01E07T02 | 007 | 74060049 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | RAJA AMPAT |  | R7 SON RJA PT2 GKI Alfa Omega Waisai |  | 0 | 0 | 0 | Preparing | [7 empty] | 46290167 | 12565130 | 58855297 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 23 | 01E07T02 | 007 | 74060049 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | RAJA AMPAT |  | R7 SON RJA PT2 SMAN 1 RAJA AMPAT |  | 0 | 0 | 0 | Preparing | [7 empty] | 29719644 | 6826654 | 36546298 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 45 | 01E07T02 | 007 | 74060025 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | SORONG |  | R7 SON SON PT2 WIFI ID Sorong |  | 0 | 0 | 0 | Preparing | [7 empty] | 9327081 | 2084373 | 11411454 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022145 | 0 | 21 | 01E07T02 | 007 | 74060027 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004645/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN PT2 Q2 TAHUN 2022 AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | OSP FO FTTH PT2 2022 | SORONG | TEMINABUAN |  | R7 SON TMB PT2 LAPAS TEMINABUAN SESNA |  | 0 | 0 | 0 | Preparing | [7 empty] | 3791891 | 926141 | 4718032 | 0 | 4500470565 |  |  |  |  | TELKOM AKSES
G2022146 | 0 | 7 | 01E07T02 | 007 | 74020026 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004646/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 2 LOP AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | FAK-FAK | FAK-FAK |  | R7 SON FFA FFK004 Werba ex Fakfak 3 |  | 20 | 0 | 0 | Preparing | 2022-07-13 | 2022-09-10 | [5 empty] | 659746530 | 138292588 | 798039118 | 0 | 4500470534 |  |  |  |  | TRANSDATA SATKOMINDO
G2022146 | 0 | 9 | 01E07T02 | 007 | 74040005 | TELKOM REGIONAL VII | WITEL PAPUA BARAT (SORONG) | ACCESS OPTIMA & MAINTENANCE | TELKOM REGIONAL VII | K.TEL.004646/HK.810/R7W-7H100000/2022 | PENGADAAN DAN PELAKSANAAN PEKERJAAN FIMO NODE B 2 LOP AREA WITEL PAPUA BARAT | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | MANOKWARI | MANOKWARI |  | R7 SON MWR BTW005 DMTKAMPUNGURI |  | 20 | 0 | 0 | Preparing | 2022-07-13 | 2022-09-10 | [5 empty] | 457651508 | 95687095 | 553338603 | 0 | 4500470534 |  |  |  |  | TRANSDATA SATKOMINDO
G2022147 | 0 | 8 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004648/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO NODE-B 2 LOP Area Witel Gorontalo | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | GORONTALO | MARISA |  | R7 GTO MRS MRA011 Dudewulo |  | 20 | 0 | 0 | Preparing | 2022-07-13 | 2022-09-10 | [5 empty] | 303330543 | 95414910 | 398745453 | 0 | 4500470387 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022147 | 0 | 7 | 01E07V06 | 007 | 72020025 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004648/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan FIMO NODE-B 2 LOP Area Witel Gorontalo | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | GORONTALO | MARISA |  | R7 GTO MRS BOA065 |  | 20 | 0 | 0 | Preparing | 2022-07-13 | 2022-09-10 | [5 empty] | 116410480 | 36307125 | 152717605 | 0 | 4500470387 |  |  |  |  | TECHNOLOGY KARYA MANDIRI
G2022148 | 0 | 9 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004649/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 3 LoP Area Witel Gorontalo | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | GORONTALO | GORONTALO |  | RT GTO GTL SWW026 PST MCP Talomopatu |  | 55 | 0 | 0 | Preparing | 2022-07-13 | 2022-09-08 | [5 empty] | 32693676 | 7583337 | 40277013 | 0 | 4500470404 |  |  |  |  | TELKOM AKSES
G2022148 | 0 | 8 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004649/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 3 LoP Area Witel Gorontalo | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL GTO189 MC Muttathohirin |  | 60 | 0 | 0 | Preparing | 2022-07-13 | 2022-08-31 | [5 empty] | 148945113 | 52660049 | 201605162 | 0 | 4500470404 |  |  |  |  | TELKOM AKSES
G2022148 | 0 | 7 | 01E07V06 | 007 | 72020004 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ENTERPRISE, OLO & WIFI DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004649/HK.810/DR7-10400000/2022 | Pengadaan dan Pemasangan Pekerjaan FIMO NODE-B 3 LoP Area Witel Gorontalo | 2022-07-13 | 2022-09-10 | FIMO NODE-B 2022 | GORONTALO | GORONTALO |  | R7 GTO GTL SWW002 Bilungala |  | 55 | 0 | 0 | Preparing | 2022-07-13 | 2022-09-06 | [5 empty] | 7277811 | 3215481 | 10493292 | 0 | 4500470404 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 16 | 01E07V01 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT3 NEW DS ODC-ANT-FS |  | 60 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-29 | [5 empty] | 163662843 | 29678803 | 193341646 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 18 | 01E07V01 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT3 BARUGA - TANAH DATAR |  | 55 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-18 | [5 empty] | 80765316 | 26880383 | 107645699 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 17 | 01E07V01 | 007 | 72080001 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | ANTANG |  | R7 MKS ANT PT3 Baruga Cluster BaliThai |  | 55 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-25 | [5 empty] | 290300945 | 88317986 | 378618931 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES
G2022149 | 0 | 22 | 01E07V01 | 007 | 72080163 | TELKOM REGIONAL VII | PLANNING, ENGINEERING & DEPLOYMENT | ACCESS NEW FTTH & MODERNIZATION DEPLOYMENT | TELKOM REGIONAL VII | K.TEL.004650/HK.810/DR7-10400000/2022 | Pengadaan Pekerjaan OSP FTTH Batch 2 13 LOP Area Witel Sulsel | 2022-07-13 | 2022-11-09 | OSP FO FTTH PT3 2022 | UJUNGPANDANG | BALAIKOTA |  | R7 MKS BAL PT3 Cendrawasih (4) |  | 55 | 0 | 0 | Preparing | 2022-07-15 | 2022-08-25 | [5 empty] | 141690345 | 31850194 | 173540539 | 0 | 4500470548 |  |  |  |  | TELKOM AKSES